## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | f990e097-fc29-47b7-9a03-e7c82400a82a |  | checklist | Linings Walls |  |  |  |  | Yes | Linings Walls | 345c52cd-dc70-427a-9e95-fe399ae00a73
checkpoint-status | 563da3b3-4035-4cc7-9ec6-21e0f1b9a6ee |  | checkpoint | Work area ready and Envision Eighty20 approval to progress
checkpoint-status | b5c96a8e-1abc-4954-8233-7cde39c63aae |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | 5106dfc2-d82c-4b03-9d80-8eaecabed9dd |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status | 0f046dd7-ebfc-4322-94a0-8bcba5f8b011 |  | checkpoint | No gaps between the joints
checkpoint-status | 89e38b9a-c62d-46d4-ab5a-5803066a5250 |  | checkpoint | All screws installed to correct depth
checkpoint-status | dd11da18-446f-435d-9f04-ea78d145cc59 |  | checkpoint | All service penetrations and cut out and not overcut
checkpoint-status | f2805cbc-cefc-4812-af73-5f839a1055f0 |  | checkpoint | Correct lining used as per spec GBTL60
checkpoint-status | 872717a7-c07c-4e9f-9208-d42eb540aaf3 |  | checkpoint | Correct screw spacings accurately marked on board and around perimeter
checkpoint-status | f3bed9cb-66f7-4ed6-a8a0-5ecd3d6ed542 |  | checkpoint | All joints to be back blocked on firewalls including around services
checkpoint-status | 80f6912a-896e-42f9-93b4-8d6707bf52cb |  | checkpoint | Fixings to layers 41mm x 6g gib grabber screws@300crs
checkpoint-status | 756dc48d-8fe0-42cb-98ce-a190d9d2ce73 |  | checkpoint | Correct lining used as per spec GNT134
checkpoint-status | 22c084d1-6010-4745-a0aa-0c17bd8fcda7 |  | checkpoint | Correct screw spacings accurately marked on board and around perimeter
checkpoint-status | 654078b9-d6cc-45f7-8ed2-6c1576f11970 |  | checkpoint | Acoustic sealant between inner and outer layer
checkpoint-status | 6500a355-3e52-4094-bdef-181f3be81757 |  | checkpoint | Fixings to inner layer 51mm x 7g gib grabber high thread screws @800crs
checkpoint-status | c9ba8ca1-c351-474b-a1f3-8257833c7707 |  | checkpoint | Fixings to outer layer 63mm x 8g gib grabber self tapping screws @800crs
checkpoint-status | ee4ba481-083f-413e-afd6-0cba358beb4d |  | checkpoint | Correct lining used as per spec JHETGR60-E
checkpoint-status | 801b8a9e-71b1-430a-8ba8-9fb021a8d9d8 |  | checkpoint | Correct screw spacings accurately marked on board and around perimeter
checkpoint-status | 8f5563b2-f64a-45e2-b536-faa4dedda15c |  | checkpoint | Fixings to layers 41mm x 6g gib grabber screws@300crs
checkpoint-status | 983aa0e7-6914-402a-8a08-a27ae357d605 |  | checkpoint | Area left clean and tidy
checklist-flat | a3314122-30ab-4681-beb4-38b9b4a039eb |  | checklist | Linings Ceilings |  |  |  |  | Yes | Linings Ceilings | 59f81a31-5deb-4a25-bc96-148e222a7a00
checkpoint-status | 4820adca-3644-40f7-9870-eab69be636c4 |  | checkpoint | Work area ready and Envision Eighty20 approval to progress
checkpoint-status | 75d20105-72a7-41da-b612-e536047b75e0 |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | 1ce60964-2744-4df5-be60-b3ad3e7687df |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status | 40e677e2-b472-45e6-9f61-80462745128f |  | checkpoint | Correct linings used as per RCP
checkpoint-status | 19b180d0-e273-4388-a1e0-70766aee2758 |  | checkpoint | No gaps between joints
checkpoint-status | 9f984ecd-1945-47bd-abb7-b830af447e0b |  | checkpoint | All screws installed to correct depth
checkpoint-status | 2ba6fd3a-35e6-42af-9d3c-1a8b7a27c913 |  | checkpoint | All service penetrations cut out and not overcut
checkpoint-status | 9a726e9a-c692-4d0c-b095-82b30d34021f |  | checkpoint | All butt joints to be back blocked
checkpoint-status | 200910ce-849f-4e8c-a39a-b79ee1cb95c8 |  | checkpoint | Where ceiling sheets are back blocked ensure there is no clashes with recessed lights
checkpoint-status | ab06f087-1a4b-44d4-a3d9-4c3e169daa20 |  | checkpoint | Area left clean and tidy
checklist-flat | d3ef38c7-9f38-47cd-8953-ac1eac96532c |  | checklist | Photos |  |  |  |  | Yes | Photos | 8804b7ea-2c0c-4c77-8f8c-963f707e4d20
checkpoint-no-status | 07f3a41c-5bae-4b85-addd-1aded74fc9a0 |  | checkpoint | Attach Images Here
checklist-flat | 94090563-5c20-4b6b-bb41-a6168f8897d4 |  | checklist | Variation # |  |  |  |  | Yes | Variation # | 8b9cb1b0-fd95-4986-be70-d29b854c4799
checkpoint-status | 42df5fec-093f-40af-a7c0-7ddd05a9f1f4 |  | checkpoint | Variation completed with photos of work
text | 50824351-b5d5-5a3b-99f2-64c71f58ac29 |  | textbox | Details (Level/Unit/Area)
text | 6628b37d-ba2b-53f3-9720-e829ecb6a4f3 |  | textbox | Hours/Minutes
checklist-flat | 484415fb-426c-4b04-b953-59d95b14d83a |  | checklist | Stopping |  |  |  |  | Yes | Stopping | b3831547-6c70-47a3-967a-8386ece64068
checkpoint-status | d74d4dd6-8292-48f3-a2b3-b383be4d66e1 |  | checkpoint | Work area ready and approval to progress / postline passed
checkpoint-status | 8a27da69-d0db-4c02-a8cf-cc380965285c |  | checkpoint | Correct firestopping product applied (if required)
checkpoint-status | a645267f-3fc2-45c8-b462-63a53526069e |  | checkpoint | Correct stopping product and applied correctly to Level 4 finish
checkpoint-status | 727afb88-666a-47ed-87b5-b9fbb2114735 |  | checkpoint | Square stopping, coving, slimlines and joints checked and acceptable
checkpoint-status | fcef8bfd-3efe-4fed-a67b-b08b8d411f21 |  | checkpoint | Adequate drying time between applications & no visible bubbling
checkpoint-status | 6e9b2e58-444d-4183-ab8b-095a5879c0aa |  | checkpoint | All sanding completed as required and checked with light
checkpoint-status | f77bce4e-8a34-4029-af60-9601811c7967 |  | checkpoint | Stopping completed, checked and Supervisor sign off
checkpoint-status | 64fd693d-321f-401c-8394-fcedda9116c1 |  | checkpoint | Light check after sealer coat completed
checkpoint-status | 83741319-8a28-420c-a680-eaa288fc565c |  | checkpoint | Handover from B&B to painters
checkpoint-status | 11255fa9-9f0f-42d1-8c9d-39e2d4b6382f |  | checkpoint | Area left clean and tidy