## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | a958b9d6-345b-49f3-bc29-bdc7b0972b86 |  | checklist | Linings Ceilings |  |  |  |  | Yes | Linings Ceilings | 12640225-6c2a-44ce-a16c-b46870b724d5
checkpoint-status | 9243b262-68b1-4a0f-ba30-012e8fe08602 |  | checkpoint | Work area ready and BROSNAN approval to progress
checkpoint-status | dd3afd7f-9ccf-4628-86c8-8d06c68d2e4f |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | be7c836e-c2b6-4f4f-b627-8d22fe26990c |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status | 58fc56fd-1de8-4872-b0c3-e7d396963765 |  | checkpoint | No gaps between joints
checkpoint-status | 2930c1df-c784-4930-bd53-96085b12f4d1 |  | checkpoint | All screws installed to correct depth
checkpoint-status | 15fdfc22-3843-469a-8885-f3808be7b32c |  | checkpoint | All service penetrations and cut out and not overcut
checkpoint-status | daedb797-cb92-498f-a779-b19a9ddcb1c3 |  | checkpoint | All butt joints to be back blocked
checkpoint-status | e8b4c3ca-2a13-40a4-9e2a-90280e2ac89c |  | checkpoint | Where ceilings sheets are back blocked ensure there is no clashes with recessed lights
checklist-flat | d8519402-9b27-418e-987e-2d8eaa82cf6d |  | checklist | Ceiling Frame |  |  |  |  | Yes | Ceiling Frame | 14aeb7fb-8890-470f-ac71-d6ffb1198152
checkpoint-status | 327f15ec-53e9-4fd1-84b6-3dd56577321b |  | checkpoint | Has previous trades QA been completed
checkpoint-status | 20427255-e543-439d-8cb7-21751a241c49 |  | checkpoint | Has all ceiling types been identified and ceilings heights confirmed
checkpoint-status | dbcd0a2a-4397-4984-a628-b21444b54bfc |  | checkpoint | Has ceiling been installed as per manufacturer's specification - ie: correct centres
checkpoint-status | 5cd4bd0d-3c9f-4208-a69e-7dc5238ebccb |  | checkpoint | Is firestopping complete where applicable
checkpoint-status | f19915d2-c1a5-49d2-86bf-870e24ff8c41 |  | checkpoint | Are all ceiling hangers installed correctly
checkpoint-status | 931e32d6-fdc0-4cf5-a4e0-1015684f3bc4 |  | checkpoint | Check no clashes between rondo and services (ie light positions, etc)
checkpoint-status | 0f382390-faa8-490c-934f-bd53e691bf04 |  | checkpoint | Check all hatch/grilles locations are correct
checkpoint-status | 40e4f78f-f891-4438-9a0c-ecf555b41039 |  | checkpoint | Check all opening sizes of hatches/grilles
checkpoint-status | d478bb47-4d9e-4a21-bfdb-1c81e1af7d1a |  | checkpoint | Ceiling complete as per seismic design
checkpoint-status | 52163193-0e21-4b3a-9501-830cbcfd7feb |  | checkpoint | Ceiling braces in correct location and built correctly
checkpoint-status | 98bbb045-57d2-48f4-a9a5-1f42bb6d937b |  | checkpoint | Correct seismic clearances from framing to services
checkpoint-status | c7146dd0-83ff-4b70-a524-b7c328839bf4 |  | checkpoint | Seismic gap in correct location and built correctly
checkpoint-status | feca9180-b141-4681-a6ff-b6fea7b747e0 |  | checkpoint | Expansion gap in correct location and built correctly
checklist-flat | 134b5ebf-06df-47eb-b448-09baaa71d9ff |  | checklist | Steel Stud |  |  |  |  | Yes | Steel Stud | 1843ba61-c4c3-4ca1-b1ec-59cac92ef89d
checkpoint-status | ccb05b28-ca53-45ed-8f7f-22f68e203ce7 |  | checkpoint | Work area ready and BROSNAN approval to progress
checkpoint-status | fe751e09-a868-4bac-808f-d5860de644d2 |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | dea355e6-89d5-45e9-bf94-eb4029d5d27d |  | checkpoint | Set out is correct & signed off
checkpoint-status | ff1363be-10b6-4692-9faf-ad850448f0f7 |  | checkpoint | Dimensions / locations of walls checked and correct
checkpoint-status | 33029d50-eea8-46a0-aa8a-3a0e23ada31e |  | checkpoint | DPC to underneath to bottom plates and where framing meets concrete
checkpoint-status | cff1691f-d872-49b8-8d20-ddf7bc881ca9 |  | checkpoint | All frames are square & plumb
checkpoint-status | 670730ea-0fea-47ad-840f-d4af1ec5dd55 |  | checkpoint | Deflection head track installed correctly, no gaps to double layer gib strips on firewalls
checkpoint-status | 551f748e-1b07-4a20-8a25-4018cb0606fb |  | checkpoint | Nogging track is installed and in correct location as per SRP manual
checkpoint-status | dc2d65ee-13d9-4003-9ecc-528bc53b45c7 |  | checkpoint | Steel studs are correct size installed at correct centres
checkpoint-status | d73b61a9-6c84-409b-9cd0-a18ded2fc043 |  | checkpoint | Studs to be "free" at deflection head, staple, punch in the top track.
checkpoint-status | b269775d-b52c-4f65-804c-ee33a87549ce |  | checkpoint | Intersections of walls/corners/T juctions/etc framed as per SRP technical manual
checkpoint-status | 6856b246-db99-49f3-8c69-27e8032944d2 |  | checkpoint | Door & window openings are in correct location and correct size
checkpoint-status | 1da6c8c3-a823-4bf0-ae3b-8f78365163dd |  | checkpoint | Door framing constructed correctly for door type
checkpoint-status | f939cdbb-c6ba-4d91-a7ae-759ed1f32f7e |  | checkpoint | Wall Strapping installed correctly ie; straight, plumb and square
checkpoint-status | 1d44377b-893f-4d20-b5e0-80dda6d663e9 |  | checkpoint | Anchors installed at maximum 1200 centres on walls strapping
checkpoint-status | b19bcc03-bec8-4f29-b6c1-fe69cee75e7f |  | checkpoint | Wall Strapping is installed to depth at minimum 50mm
checklist-flat | 525ea471-dd3c-4b1d-b1da-4f9cdb2174ea |  | checklist | Linings Walls |  |  |  |  | Yes | Linings Walls | 6c4edb69-5177-4d0b-8b62-c48a241780db
checkpoint-status | cffa89db-b19e-4036-ac5e-4fd9d3ccdbba |  | checkpoint | Work area ready and BROSNAN approval to progress
checkpoint-status | eeb789eb-eed6-40d2-929e-28bfba7a3c4a |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | c469c5e8-d151-43a7-b0ac-3bad9ec5848e |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status | ba6cd329-556a-489f-9dcd-4bf606e37aac |  | checkpoint | No gaps between joints
checkpoint-status | 6de119ff-65c9-4c80-ac5d-cd9d3d639d44 |  | checkpoint | All screws installed to correct depth
checkpoint-status | 2dfe7de1-a8fa-418e-8835-49c9d35c54bd |  | checkpoint | All service penetrations and cut out and not overcut
checkpoint-status | d2d95227-c4ce-4336-b63f-8919bccd6647 |  | checkpoint | Correct lining used as per spec GBQSA 45
checkpoint-status | 4364c557-56b2-4199-a67b-623c27905621 |  | checkpoint | Ceminseal linings - screws, screws spacing
checkpoint-status | 84a5d986-df02-427f-8708-c4af3608f679 |  | checkpoint | Acoustic sealant between inner layer and outer layer
checkpoint-status | c0a24785-4b00-4431-8f31-6fa7d6d96a2d |  | checkpoint | All joints to be back blocked on firewalls including around services
checkpoint-status | 7848c822-7606-4f04-8b35-eb234397c335 |  | checkpoint | Fixings to inner layer 25mm x 6g gib grabber screws @300crs
checkpoint-status | 94119f4e-af5f-4c71-bc9f-e353932a7379 |  | checkpoint | Fixings to outer layer 41mm x 6g gib grabber screws @300crs
checkpoint-status | 0937f56e-eaa7-45b1-8390-f2ea7367d2ba |  | checkpoint | Area left clean & tidy
checklist-flat | d3ef38c7-9f38-47cd-8953-ac1eac96532c |  | checklist | Photos |  |  |  |  | Yes | Photos | bcfbeff8-ee9a-4731-8620-7e221b2220b4
checkpoint-no-status | 07f3a41c-5bae-4b85-addd-1aded74fc9a0 |  | checkpoint | Attach Images Here
checklist-flat | 816387dc-fe4c-44e6-bd22-b56dc6db6be0 |  | checklist | Set Out |  |  |  |  | Yes | Set Out | ceab099c-89b8-4427-b65a-5fa5db4a0d92
checkpoint-status | c3eb8986-2e33-4bfa-9a91-7862c885d177 |  | checkpoint | Work area clear and ready to start
checkpoint-status | daeedf4b-dad7-46c4-97d1-c31fc2b905f8 |  | checkpoint | Check latest plans and revisons
checkpoint-status | b1c3c995-49a6-479e-afa1-1fed5f49b6fe |  | checkpoint | Do bathrooms meets council requirements (accessibles etc)
checkpoint-status | 7d1f885c-5f21-422e-82b0-01d60b2a1d31 |  | checkpoint | Grid lines located and checked for square
checkpoint-status | 6437b354-ddd6-43c9-9d7b-f3bf235551f5 |  | checkpoint | Check all wall types and linings have been allowed for
checkpoint-status | 34dfc91c-4240-413b-96b8-065add7a8282 |  | checkpoint | Has a 16mm step been allowed for at the entry door
checkpoint-status | fbc23f86-1448-4420-b56c-b55114373a4e |  | checkpoint | Have strapping walls been squared off internals
checkpoint-status | 3b98541a-90aa-40f2-9c8e-71da3be33d39 |  | checkpoint | Does corridor wall fly past pre cast panels
checkpoint-status | 401c850b-46d9-4b4c-aebf-9c9f6c1099ca |  | checkpoint | Are entryways minimum 1m wide
checkpoint-status | ff4fe7e3-7743-43aa-bc2a-3ccda8df1d3b |  | checkpoint | Is corridor wall square with apartment walls?
checkpoint-status | 7972c9aa-2bf3-4a32-990e-ab426e326177 |  | checkpoint | Are apartment hallways parallel
checkpoint-status | aec1140f-037d-4534-93cd-78ab206f9203 |  | checkpoint | Check marks for existing walls are square
checkpoint-status | 042f0d28-c296-4b69-ae1b-e5fc67f545e5 |  | checkpoint | Area left clean and tidy
checklist-flat | 529af293-ee07-4dcf-a89b-3544903d69c8 |  | checklist | Variation # |  |  |  |  | Yes | Variation # | f417cba4-aceb-4027-ae28-8d55809b566e
checkpoint-status | 5acc395a-d689-4cf5-b317-52808b928766 |  | checkpoint | Variation completed with photos of work
text | 50824351-b5d5-5a3b-99f2-64c71f58ac29 |  | textbox | Details (Level/Unit/Area)
text | 6628b37d-ba2b-53f3-9720-e829ecb6a4f3 |  | textbox | Hours/Minutes
checklist-flat | c3ba0f99-77cd-4559-9503-61cf922e57c9 |  | checklist | Stopping |  |  |  |  | Yes | Stopping | fd3e7317-6d42-41bb-9f99-671537f890f6
checkpoint-status | 36133909-72ee-4b45-b09a-dd2a42ada54a |  | checkpoint | Work area ready and approval to progress / postline passed
checkpoint-status | 4a350c9f-ee17-4220-adb3-9155c77fde95 |  | checkpoint | Correct firestopping product applied (if required)
checkpoint-status | 4cda4e4c-72fe-48a6-9456-5e3fad2e171c |  | checkpoint | Correct stopping product and applied correctly to Level 4 finish
checkpoint-status | 170f4378-3a94-4d87-b962-3628c8745dc4 |  | checkpoint | Square stopping, coving, slimlines and joints checked and acceptable
checkpoint-status | 7b4ff715-933d-4569-b719-889d65590080 |  | checkpoint | Adequate drying time between applications & no visible bubbling
checkpoint-status | 8b090bac-c222-4ab7-bb8f-24dcdda61128 |  | checkpoint | All sanding completed as required and checked with light
checkpoint-status | e0ef465b-9524-4808-b4b2-0f7955a3953b |  | checkpoint | Stopping completed, checked and Supervisor sign off
checkpoint-status | 5b85ef29-28ac-4d57-a384-a67cd113b27e |  | checkpoint | Light check after sealer coat completed
checkpoint-status | 2fc87910-982b-4c5d-9401-f57cdc435336 |  | checkpoint | Handover from B&B to MR Decorating
checkpoint-status | 854a0fff-907f-47e6-bc85-e0eae2817229 |  | checkpoint | Area left clean & tidy