## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 9efddc52-c150-4fb1-85f3-5a3fe43152c4 |  | checklist | Precheck 4 |  |  |  |  | Yes | Precheck 4 | 01527fd8-52f0-431c-af60-257cf83627d1
checkpoint-status | cc117b28-435b-4c6f-92d8-80f323ade33f |  | checkpoint | Work area ready and approval to progress/posline passed
checklist-flat | cf0c22a9-b52c-4f1f-85fa-07c9b4de754e |  | checklist | Room 115 |  |  |  |  | Yes | Remedial - Room 115 | 02c29998-5827-4cb2-87ad-b4530f32723a
checkpoint-status | bfbd4008-dd0d-4c92-ae6d-98cf0aac1ed2 |  | checkpoint | Hanger not straight
checkpoint-status | 097d8ea5-1236-4439-acb5-0b8523edafce |  | checkpoint | Fix connection not complete
checkpoint-status | b580c66f-84ef-4ca0-b557-faf357f2c5ba |  | checkpoint | Wardrobe FC require fixings
checkpoint-status | 3d33f724-4d11-4215-89c7-ed16ae9f4f01 |  | checkpoint | Add TCR where is cut
checklist-flat | 723aa73b-502e-4198-95e4-70bc2d1bcca6 |  | checklist | Room 108 |  |  |  |  | Yes | Remedial - Room 108 | 0e62a84d-9dbe-426d-bc39-65370743244c
checkpoint-status | 0f0fe06a-1c43-466c-a078-8f9955963e3b |  | checkpoint | Add L bracket on bulkhead bracing
checkpoint-status | 754a4882-d1fe-46ca-8c24-672331d998a2 |  | checkpoint | FC 75mm of wall x2
checklist-flat | 730ff0f1-34fe-4111-8f90-f44bab698554 |  | checklist | Insulation |  |  |  |  | Yes | Insulation | 0fbb56b3-f8a0-4eb3-a104-484eda9b5862
checkpoint-status | e170c32f-6738-481d-a11f-ee5c8d24b1de |  | checkpoint | Area checked for correct insulation used for all wall/ceilings types
checkpoint-status | de90911a-3d94-4433-9669-515f49902b53 |  | checkpoint | Has insulation installed correctly with no gaps to insulation
checkpoint-status | 83f49dea-1088-4f3a-a4b1-77dbda767407 |  | checkpoint | Has insulation been installed correct around services (ie pipes and plugs)
checklist-flat | d3ef38c7-9f38-47cd-8953-ac1eac96532c |  | checklist | Photos |  |  |  |  | Yes | Photos | 16d3d4af-f2a1-442a-b9db-d53f0160c27b
checkpoint-no-status | 07f3a41c-5bae-4b85-addd-1aded74fc9a0 |  | checkpoint | Attach Images Here
checklist-flat | 4616bfd8-6a17-414d-9e22-975edab442da |  | checklist | Linings |  |  |  |  | Yes | Linings | 175cbc11-b15e-4ac9-ba03-ab5ed06f8422
checkpoint-status | b781391c-b334-4a31-9299-2c2e7c39cd20 |  | checkpoint | Latest consented drawing available, checked and referenced - Ref drawing number
checkpoint-status | 4c03cafb-9315-45bb-8da5-d2cfe290649c |  | checkpoint | Correct lining used as per wall type and specifications
checkpoint-status | 1d1db6cd-26b5-4e5f-9e11-3a4bda861f5d |  | checkpoint | Correct screws used for wall type and specifications
checkpoint-status | bb83bb8d-5eac-4ec2-bc53-9e6264598548 |  | checkpoint | Gaps and joints acceptable
checkpoint-status | a01a3a5f-829a-408c-9330-9d2372758019 |  | checkpoint | All screws installed to correct depth and at correct centres/spacing as per specifications
checkpoint-status | 72c15334-afd6-4200-b00c-973a925b9a07 |  | checkpoint | No overcut service penetrations
checkpoint-status | c51be0ae-6ec7-4561-8ab6-4da43a474f5a |  | checkpoint | Acoustic sealant installed correctly as per gib specification for wall type
checkpoint-status | b6900baf-f1df-4bfc-b09a-41f63d3e8e50 |  | checkpoint | Lining completed, checked and supervisor sign off
checkpoint-status | 4be486d6-3fcf-49b5-90d8-dbf0dcb10f20 |  | checkpoint | Area left clean and tidy
checklist-flat | 2bf2f279-f6ae-4df6-9b07-7fc9935d5202 |  | checklist | Precheck |  |  |  |  | Yes | Precheck | 1b63af37-d3b6-4d53-95eb-ba1c835f1702
checkpoint-status | b7cb31b7-5416-4cee-949d-ac21047aee05 |  | checkpoint | Have previous QA been completed
checkpoint-status | 62e8ab7e-405c-44d7-9741-b77b470e5578 |  | checkpoint | Have all insulation wall/ceiling types been identified
checklist-flat | 376e409f-c0e3-4aa2-b967-8e67135c85f1 |  | checklist | Remaining Walls |  |  |  |  | Yes | Remaining Walls | 1db02ccc-cd44-4d27-8ce4-2374e7876b9c
checkpoint-status | 910645e0-0a53-46ee-8adf-378fbc38551a |  | checkpoint | Work area ready and approval to progress
checkpoint-status | 05d21803-7430-458a-939d-e8a9ab436581 |  | checkpoint | Latest entered drawings available, checked and referenced
checkpoint-status | 9551aad6-fe92-483a-9cfe-910c56dc9e83 |  | checkpoint | Set out is correct and signed off
checkpoint-status | 6666fd0c-ee4b-45fa-869f-79a7b6b2642d |  | checkpoint | Dimensions/locations of walls checked and correct
checkpoint-status | afa396cc-936b-45db-8e3b-1c8e6339b943 |  | checkpoint | All frames are square and plumb
checkpoint-status | 28180c9a-2f2f-43d2-9a33-6caedf4e2952 |  | checkpoint | Deflection head track installed and correct
checkpoint-status | 857d35c9-b643-4873-b5a8-aa07c9e53ed8 |  | checkpoint | Nogging track is installed and in correct location
checkpoint-status | 7887696c-8d22-4fa8-bb1e-9efa97304e91 |  | checkpoint | Steel stud are correct size installed at correct centres
checkpoint-status | ed157e3a-4894-43f8-a514-f6d5bac0bebb |  | checkpoint | Door and windows openings are in correct location and correct size
checkpoint-status | b3d0c7a1-1c0e-4fbd-a47e-a489c492ff63 |  | checkpoint | Door timbers installed correctly plumb and square
checkpoint-status | edee344a-2eb1-445a-8d80-681387104cb1 |  | checkpoint | Are all 1st round gib linings installed in correct locations as per marked plans
checkpoint-status | ce87d5fa-ef20-4cd5-8119-32a4dfa6a8be |  | checkpoint | All steel stud and wall strapping completed completed correctly, checked and supervisor sign off
checkpoint-status | 796857e4-b88b-4f8c-897d-ab364a8fdceb |  | checkpoint | Area left clean and tidy
checklist-flat | 9f224fe1-f1ee-40ec-83cb-42301d7ee59e |  | checklist | Precheck 3 |  |  |  |  | Yes | Precheck 3 | 472f7df8-dd6f-4fc6-8bd1-f16763789fc6
checkpoint-status | c4d14e2c-1dea-47d6-934e-2f1c38fde203 |  | checkpoint | Work area ready and approval to progress
checkpoint-status | 3fb11bed-15ab-4701-bc2f-e785fa6b15d0 |  | checkpoint | Latest consented drawing available, checked and referenced - Ref drawing number
checklist-flat | 84b4ccc8-c095-4ef0-932f-9ce6b6790cc2 |  | checklist | Stopping |  |  |  |  | Yes | Stopping | 48afbc0d-e6c0-4138-b29d-e8eeac5c4f6c
checkpoint-status | 2cba0acd-a98d-4623-b63c-29542614aca1 |  | checkpoint | Correct stopping product applied correctly to level 4 finish
checkpoint-status | 3710b37f-6809-48d6-8759-d052b585e191 |  | checkpoint | Square stopping, coving, slimlines and joints checked and acceptable
checkpoint-status | cfdab7b9-c8cd-41d3-8c41-cec56d3ed757 |  | checkpoint | Adequate drying time between applications and no visible bubbling
checkpoint-status | 5c3ee4e2-9b7c-4f5d-ba24-378104d7c193 |  | checkpoint | All sanding completed as required
checkpoint-status | df4d7a58-2e89-4673-b278-014ffe1f6ff7 |  | checkpoint | Stopping completed, checked and supervisor sign off
checkpoint-status | 37639d46-f690-4af5-9db3-52a8600b0e47 |  | checkpoint | Area left clean and tidy
checklist-flat | 6d121f81-0b69-40ce-b0dc-928d61d76717 |  | checklist | Room 109 |  |  |  |  | Yes | Remedial - Room 109 | 4d8b1ff0-0a3d-44a0-be1c-ecea5fbd5714
checkpoint-status | 7eed9a30-2d00-4c70-896d-d34d692f7898 |  | checkpoint | L bracket added to bulkhead
checkpoint-status | 51244e62-0642-4521-bbf6-6b0b90bcb3a5 |  | checkpoint | Change fixed ceiling side and follow screw required
checklist-flat | fde3ad76-957b-4d4f-b4ee-a7768799fdef |  | checklist | Precheck 2 |  |  |  |  | Yes | Precheck 2 | 698fa2e4-5706-4a07-93a8-6f47491b5888
checkpoint-status | a670075d-ac73-4619-9354-a3d8ada563e1 |  | checkpoint | Has previous trades QA been completed
checkpoint-status | d0b436ec-bec8-46d3-ae56-1e59ee788d05 |  | checkpoint | Has all ceiling types been identified
checkpoint-status | c66ec3d2-db6f-48bc-9c54-e47aa2d0d225 |  | checkpoint | Has ceiling been installed as per manufacturer's specification
checkpoint-status | 43c6c84e-8bde-40e0-b5ee-a40f2aa65463 |  | checkpoint | Correct firestopping product applied (if required)
checklist-flat | acf2d37d-c35e-4949-9361-1a2d20b2288d |  | checklist | Room 106 |  |  |  |  | Yes | Remedial - Room 106 | 6a3983a8-d546-4a08-84da-6eeacab6eefa
checkpoint-status | 02e8d1c3-6c4f-46aa-b728-30cf623adfb6 |  | checkpoint | TCR spliced correctly
checkpoint-status | 3b1333b5-8f3a-4d27-babc-4073033ef310 |  | checkpoint | Add bulkhead bracing at 600centres and L brackets
checklist-flat | 3a44ec38-580a-4d00-9f59-0b02424d8b76 |  | checklist | Ceiling linings |  |  |  |  | Yes | Ceiling linings | 6bfd7d9f-5f2b-4b64-a5df-a872a8e24a51
checkpoint-status | 223fd455-703f-404e-b13a-d08d7e617439 |  | checkpoint | Ceiling bathrooms have been lined correctly
checkpoint-status | 29768c5f-2629-4289-bb59-5aec89c7fa21 |  | checkpoint | Latest consented drawing available, checked and referenced - Ref drawing number
checkpoint-status | 5db587ff-6158-4723-90f0-0b4a18038d82 |  | checkpoint | Correct lining used as per ceiling type and specifications
checkpoint-status | 6a50d91d-b08a-450b-b9a9-d259029a4ace |  | checkpoint | Correct screws used
checkpoint-status | 875617f8-d718-4f3f-9307-ee0aebfca32c |  | checkpoint | Gaps and joints acceptable
checkpoint-status | a3ab7dc3-632f-4d2d-89f6-d47d6efbbd87 |  | checkpoint | All screws installed to correct depth and at correct centres/spacing as per specifications
checkpoint-status | dc2d9ffa-8ae0-42b9-810e-165ffd7b5646 |  | checkpoint | No overcut service penetrations
checkpoint-status | f4e8779b-d11d-4835-92a7-621194798185 |  | checkpoint | Lining completed, checked and supervisor sign off
checkpoint-status | 722ad54e-31ea-4777-8aca-f9d474b37413 |  | checkpoint | Area left clean and tidy
checklist-flat | 5bc69d7c-73dc-4b37-8112-b7c373018360 |  | checklist | Room 110 |  |  |  |  | Yes | Remedial - Room 110 | 73aa2e92-ecdc-4c18-a269-7f5205903965
checkpoint-status | fe18bfda-be5d-45be-83b4-3de22bf5bcc9 |  | checkpoint | Change fixed connection side and fixing
checkpoint-status | 01b64d21-1628-42da-8d30-b08530b7d1d4 |  | checkpoint | Wall wardrobe FC require extra fixing
checkpoint-status | 81aa0dc2-da74-45cd-8287-560373610058 |  | checkpoint | Suspension wire not straight
checkpoint-status | 615be746-51a7-48cf-94f2-28b4e2a28b47 |  | checkpoint | L bracket to bulkhead
checklist-flat | b203525a-905d-45bf-8d8c-c6cc36ef801f |  | checklist | Grindlines |  |  |  |  | Yes | Grindlines | 77cbd38b-cfb8-4b40-a32e-92e68b87d385
checkpoint-status | 82596c81-46fd-4927-a737-e1c9b71b72ee |  | checkpoint | Work are clear to work
checkpoint-status | 608fc79a-07be-430d-a698-5b750cb295ab |  | checkpoint | Check latest plan revision prior to start. Have specific plans been used alongside floor set out plans
checkpoint-status | 2667a855-97b9-4dfd-98cf-d36c795c5e2a |  | checkpoint | Locate and check datum grid lines for square
checkpoint-status | 1fb05133-de5f-421a-8a9e-5fbfe604e6b7 |  | checkpoint | Check all wall types are correct and wall linings have been allowed for
checkpoint-status | 1b7e6612-b9fd-4e6d-8c42-241590c04bfe |  | checkpoint | All rooms measure correct and square
checkpoint-status | 394f6fbc-9919-45fb-94e2-599ea223e044 |  | checkpoint | Check all showers recess dimensions to fit shower tray and make sure it is square.
checklist-flat | fb13686f-f853-4e79-8fe6-3a9120f01b6a |  | checklist | Room 107 |  |  |  |  | Yes | Remedial - Room 107 | 7e85bfa5-bf8e-425d-bbb4-4356f822d1a1
checkpoint-status | 2daa3309-6c9a-46e0-944a-a6b54fd88eb7 |  | checkpoint | L brackets on bulkheads
checkpoint-status | 5ac5cf58-3407-496b-b79f-d302be056399 |  | checkpoint | Add TCR on lower sction of bulkhead by window
checklist-flat | 1c92bde7-a7dd-4e41-af07-84f052280bb7 |  | checklist | Room 101 |  |  |  |  | Yes | Remedial - Room 101 | 93518c52-97c1-4eb9-a6a9-1679b3d18f7b
checkpoint-status | bcb0eaef-3f21-4ac9-a2bb-fb8dedf947bc |  | checkpoint | Check hangers are straight with TCR
checkpoint-status | 3124ddc4-60c7-4220-84c0-2654fc7c85e7 |  | checkpoint | Install additional hanger by window where TCR is cut
checkpoint-status | 520989dd-64fd-4243-a109-80e6aec36c67 |  | checkpoint | TCR spliced correctly (check all)
checkpoint-status | e4253e06-11b9-44af-828e-d6bdcbc3c8aa |  | checkpoint | Bulkhead L brackets installed
checkpoint-status | 0b922593-47c6-468a-bd15-b89c01c08d06 |  | checkpoint | Add 10g screw to each wardrobe FC
checklist-flat | bed0ffb2-ca30-483e-b6ca-234bf8e49ae9 |  | checklist | Room 111 |  |  |  |  | Yes | Remedial - Room 111 | 9e89e41a-fef1-4103-aa92-74c02690afc2
checkpoint-status | 4ef22bb1-badc-4ea0-aa8a-788f22be41dc |  | checkpoint | Change fixed connection side and add fixings
checkpoint-status | e639e94d-672e-45dd-8618-da4c0dcea6c6 |  | checkpoint | Hanger not straight with TCR
checkpoint-status | 4b1a2930-7fce-46e9-aa4d-cd1e8d9cf6f2 |  | checkpoint | Wardrobe FC require extra fixing
checkpoint-status | f61a7b5a-98b2-40e0-b7cf-fe1de6518f53 |  | checkpoint | L bracket to bulkhead
checklist-flat | 68cd4926-2940-4690-b33b-a2df9a399a2e |  | checklist | Room 104 |  |  |  |  | Yes | Remedial - Room 104 | a451afe4-6a7a-42bd-945f-aa374ca388cc
checkpoint-status | c97b84b3-70ff-440f-92f8-dfc563588d01 |  | checkpoint | L brackets for bulkhead
checklist-flat | 9d4a8305-06f6-4e83-99c8-5588cc6e9d18 |  | checklist | Entertainment walls |  |  |  |  | Yes | Entertainment walls | b9612ce4-f0cf-411a-9016-c8b196e2dc81
checkpoint-status | 59bf8bc8-5938-4553-8798-3fca53e214ab |  | checkpoint | Work area ready and approval to progress
checkpoint-status | b51f27ef-01ea-4c67-9843-f8c0b61bf94b |  | checkpoint | Latest entered drawings available, checked and referenced
checkpoint-status | 0c38254b-0947-4281-a4ea-cbb0af1be149 |  | checkpoint | Set out is correct and signed off
checkpoint-status | bad2ffbc-5177-4797-91ae-84910005c4c6 |  | checkpoint | Dimensions/locations of walls checked and correct
checkpoint-status | 06f820c4-266a-4242-aaa3-30aad3b9c29b |  | checkpoint | All frames are square and plumb
checkpoint-status | 72a287e3-9a5b-46a3-ba44-de3cb2fed859 |  | checkpoint | Deflection head track installed and correct
checkpoint-status | 94d307fe-3ec7-4fd7-b92b-77b3ac2a58c9 |  | checkpoint | Nogging track is installed and in correct location
checkpoint-status | c49ad639-f56a-4501-8ec0-0328eda09c4a |  | checkpoint | Steel stud are correct size installed at correct centres
checkpoint-status | 109a4820-0239-4946-bb48-43ac90db359a |  | checkpoint | Door and windows openings are in correct location and correct size
checkpoint-status | 796cafd6-7956-444e-9fac-e60ca20976ae |  | checkpoint | Door timbers installed correctly plumb and square
checkpoint-status | 79ccf253-167b-43fc-80db-d4782975fea4 |  | checkpoint | Are all 1st round gib linings installed in correct locations as per marked plans
checkpoint-status | 7e24d398-81c0-41be-a5b1-73f8639deb35 |  | checkpoint | All steel stud and wall strapping completed completed correctly, checked and supervisor sign off
checkpoint-status | 679c4cb2-f45d-41cd-ba36-10381da78a3c |  | checkpoint | Area left clean and tidy
checklist-flat | 91fbde05-1085-413e-a4c3-7bd91ba712e7 |  | checklist | Variation # |  |  |  |  | Yes | Variation # | bda54089-bdae-4c01-9cc3-76a97e5395e1
checkpoint-status | 8b8a9676-2d8e-4fe1-9e88-e656a66089f0 |  | checkpoint | Variation completed with photos of work
text | 50824351-b5d5-5a3b-99f2-64c71f58ac29 |  | textbox | Details (Level/Unit/Area)
text | 6628b37d-ba2b-53f3-9720-e829ecb6a4f3 |  | textbox | Hours/Minutes
checklist-flat | 5898ff02-1575-47c7-8b68-f61128c91b67 |  | checklist | Room 114 |  |  |  |  | Yes | Remedial - Room 114 | bdb6e441-b0b8-4a08-b82b-b16c4358f871
checkpoint-status | 87672e0a-1775-4744-84a6-834b41833e1d |  | checkpoint | Change fixed side connection
checkpoint-status | c91cd1d0-0f2e-482b-af1d-fc1ff827d0a5 |  | checkpoint | Add fixing to FC in wardrobe
checkpoint-status | 11a3c10f-0ff0-42a9-a256-575dcf3dece1 |  | checkpoint | L bracket to bulkhead
checklist-flat | a8423b9c-c6c8-4972-af80-151c40f2261f |  | checklist | Room 105 |  |  |  |  | Yes | Remedial - Room 105 | ca7e3822-c19e-4afc-9450-7c97679b5847
checkpoint-status | 0b70dd33-f721-4cb3-a6ad-1f428badf12f |  | checkpoint | TCR spliced correctly
checkpoint-status | 7895cc2f-bf4b-4dbb-87ac-a2938dcea519 |  | checkpoint | L brackets for bulkheads
checkpoint-status | e042d12c-b50a-4bc6-8ab4-f196483db871 |  | checkpoint | Remove screws for Hvac ceiling to float
checkpoint-status | e6a01f04-dc14-44e2-873f-dd3a36798ec4 |  | checkpoint | Add screws to wardrobe FCs
checklist-flat | b80accb6-f300-49dd-89a1-83ab354243dc |  | checklist | Room 102 |  |  |  |  | Yes | Remedial - Room 102 | cb528a27-e653-4e1f-9f71-5b23e12c63f4
checkpoint-status | dac30198-d10f-4148-ab52-eb4c24ca1b85 |  | checkpoint | TCRs spliced correctly
checkpoint-status | a1208679-3c0a-4ea7-9d97-ea4c6405f710 |  | checkpoint | L brackets for ceiling bracings
checklist-flat | e2a1bb4f-826f-4e58-b9a0-ee1c4f0d1d36 |  | checklist | Room 113 |  |  |  |  | Yes | Remedial - Room 113 | d8a0137d-2a1b-4e1b-8437-d26adb02b119
checkpoint-status | 1bd0eafe-78ea-4ecf-acb0-b2b134764c05 |  | checkpoint | Finish ceiling grids
checkpoint-status | 2dc47724-3e76-4fbc-9fad-66b980e84fd0 |  | checkpoint | L bracket installed to bulkhead
checkpoint-status | a3c74604-4cf3-41f9-98a6-b4f3d2b0d65d |  | checkpoint | Wardrobe FC fixed x2 each side
checkpoint-status | 02fca1c4-b685-420d-a289-d19c746df1bd |  | checkpoint | Fix connection side completed
checklist-flat | afa92525-621b-468c-a798-3b4b73be8bc4 |  | checklist | Room 116 |  |  |  |  | Yes | Remedial - Room 116 | dc01952e-897e-4f65-9a40-b1ac23e1b548
checkpoint-status | e8c4d08d-e016-437b-8cf8-1c2e6507d45a |  | checkpoint | Fixed connection changed
checkpoint-status | 35ae82a8-3454-4f59-8b40-05831595a7fb |  | checkpoint | Wardrobe FC require extra fixing
checkpoint-status | 0cb4e8db-f522-4a21-a828-3bc782e5225b |  | checkpoint | FC required 75mm off wall
checkpoint-status | 139e1b40-21d4-4d63-a966-ab1d3cdde32b |  | checkpoint | Suspension wire 200mm off wall
checklist-flat | 598ae966-2199-49a8-8afe-fbea8f5fd20a |  | checklist | Ceiling Frame |  |  |  |  | Yes | Ceiling Frame | e14711c7-c9ce-4f82-9196-7ed788a5cac0
checkpoint-status | e2500b41-d2e8-4a71-a810-67a2ee2e9cbc |  | checkpoint | Has all ceiling types been identified
checkpoint-status | 250c622d-c125-4070-8ff3-ebfc40d4f9fc |  | checkpoint | Has ceiling been installed as per manufacturer's specification
checkpoint-status | 002da5d4-1e23-4516-afae-de7875077487 |  | checkpoint | Correct fire stopping product applied (if required)
checkpoint-status | abb0fa8f-a667-483a-b218-c1f7536c7fcf |  | checkpoint | Ceiling complete as per seismic design
checkpoint-status | c2db2992-c42c-4552-b3b8-c986372fb2cd |  | checkpoint | Is fixing for curtain details correct
checkpoint-status | 20958d44-99a1-41c2-bc06-577ba9fc40b1 |  | checkpoint | Are all ceiling fixings/nogs installed correct (if applicable)
checkpoint-status | 5da5cac7-879e-4dc4-ac68-b2c19a3002a9 |  | checkpoint | Check no clashes between rondo and services (ie light positions, etc)
checkpoint-status | 45bf9c47-5045-4858-91be-41e470b8680d |  | checkpoint | Check hatch locations are correct
checkpoint-status | 2bcb2766-6533-484a-b8a1-f596c4ab35c7 |  | checkpoint | Check opening size of hatches/grilles
checklist-flat | d76f5475-ae4d-4152-a77f-3a120b782667 |  | checklist | Room 103 |  |  |  |  | Yes | Remedial - Room 103 | e6a994ca-0c68-4431-a543-1697c886bc41
checkpoint-status | 2b8e3092-1063-41c1-847c-2623bcd4586b |  | checkpoint | Remove screws for floating end
checkpoint-status | c03f7614-3568-48b8-a181-0c92137739b5 |  | checkpoint | TCR spliced correctly
checkpoint-status | 2ae30fc0-9eaa-48da-8da8-88e9d282a3e4 |  | checkpoint | L brackets to bulkheads
checklist-flat | 45068f21-dea2-48c1-8162-b37e8f229679 |  | checklist | Room 112 |  |  |  |  | Yes | Remedial - Room 112 | fa5c28d4-2d34-4446-bdc9-2269d2ea60f3
checkpoint-status | eec9e75b-8064-4084-943b-62c70d0e68c5 |  | checkpoint | Change fixed connection side and add fixings
checkpoint-status | 8fd5ca12-42e5-4faf-9c95-c7fac718f03e |  | checkpoint | Wardrobe FC fixed both side x2
checkpoint-status | 2979bd1c-9ba5-4877-94be-b04eb6d47c99 |  | checkpoint | L bracket installed to bulkheads
checkpoint-status | da926547-8761-47da-a8d9-04ecfbda20a5 |  | checkpoint | TCR splice connection done incorrectly