## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | bfbaaad3-694e-425c-a69e-11a92de0b151 |  | checklist | Steel Stud and Wall Bracing Checklist |  |  |  |  | Yes | Steel Stud and Wall Bracing Checklist | 25e8902d-8a97-45af-bf62-af32fef352de
checkpoint-status | a1ad4742-16ba-4423-95cb-e0fd89ed4b00 |  | checkpoint | Work area ready and approval to progress
checkpoint-status | 3adc303c-6603-4e7a-8cf4-9490b80a557e |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | fc5053b0-1dcb-45c9-9021-5b095ea699d5 |  | checkpoint | Set out is correct & signed off
checkpoint-status | 84b93cd1-b4dc-4698-9529-3b9b480a3a5d |  | checkpoint | Dimensions / locations of walls checked and correct
checkpoint-status | 3f89014d-78af-4df2-8825-b171585edaea |  | checkpoint | All frames are square & plumb
checkpoint-status | 9970efea-00de-47f7-bc43-2a3dae9bc049 |  | checkpoint | Deflection head track installed and correct
checkpoint-status | 267d11dc-9bcf-4509-ad8d-37ca9d8ba12c |  | checkpoint | Trackloks installed and in the correct locations
checkpoint-status | 1fe8b9e0-a71f-421f-97d9-17155e97845a |  | checkpoint | Nogging track is installed and in correct location
checkpoint-status | 5ebfab2f-db6c-4acb-9eb8-ad81ff8e6402 |  | checkpoint | Steel studs are correct size installed at correct centres
checkpoint-status | 9555e335-8d28-4fc2-a7c8-c637ee4f5b38 |  | checkpoint | Studs are fixed at bottom track but nothing in deflection head track
checkpoint-status | f177be7a-7792-48e9-aaf0-863ed2307293 |  | checkpoint | Strapping brackets installed with Thermal Break at correct centres
checkpoint-status | 98c0fda2-563b-4d9d-a791-3695d0cdc553 |  | checkpoint | Door & window openings are in correct location and correct size
checkpoint-status | 96cc9303-160a-45d2-9d02-3ebd1173dcc8 |  | checkpoint | All Steel Stud and Wall Strapping completed correctly, checked & Supervisor sign off
checkpoint-status | cb18a7a6-3eeb-4f6e-aad8-1624aa375ab6 |  | checkpoint | Area left clean & tidy
checklist-flat | fffaebaa-6dbe-4ca4-b53d-d21c191734fe |  | checklist | Lining Checklist |  |  |  |  | Yes | Lining Checklist | 82517ed5-f9e7-4951-b16d-2a5c0df62a04
checkpoint-status | fe117608-fb27-4d9c-9010-c92069ebaf9e |  | checkpoint | Work area ready and approval to progress
checkpoint-status | 34e88cc7-4527-4f7e-8f00-df2850937331 |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | 2a40f149-3f16-4d3c-afe2-c7f5ebfa759e |  | checkpoint | Correct lining used as per spec
checkpoint-status | 83919d3b-5ed8-47a0-b60c-0db36b66d786 |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status | 144176fe-8703-4f2c-88ed-26549c527f24 |  | checkpoint | Gaps and joints acceptable
checkpoint-status | c1055a26-a296-4fc4-8873-9fa4f41b7e4c |  | checkpoint | All screws installed to correct depth
checkpoint-status | 3d4a5bf4-2a98-49df-a90f-2b5f3aab69d5 |  | checkpoint | No overcut service penetrations
checkpoint-status | f1c8e3c9-d1d5-486c-891b-91902d0873c4 |  | checkpoint | Correct sealant used
checkpoint-status | 0c80d613-f4b8-462e-a069-262fe1b48f7d |  | checkpoint | Lining completed, checked and Supervisor sign off
checkpoint-status | 79ab27f0-10f4-431c-9a19-596155d5e7a3 |  | checkpoint | Area left clean & tidy
checklist-flat | cc75b5c1-dfde-4384-b107-5a606751a5bd |  | checklist | Fire Rating Details and Beams |  |  |  |  | Yes | Fire Rating Checklist | 8aaaf70b-7cc9-4f95-aeea-f5017439ecc0
checkpoint-status | 99f94925-0dba-4b93-a317-f8d38ace4559 |  | checkpoint | Check fire rated bulkhead details is complete
checkpoint-status | c49a5b25-f548-4004-8c2d-3222c8cff162 |  | checkpoint | Ensure screws are at 300mm center of the bulkhead
checkpoint-status | 4af59eb9-84cd-497e-b24a-510954b83dad |  | checkpoint | Ensure there are screws fixed all around the beams
checkpoint-status | 70fbeac1-e265-4fda-9b51-545ce4f7c020 |  | checkpoint | Ensure beams are encased with fireline GIB
checkpoint-status | 50692678-8876-4e32-8893-6d4f6bee9b45 |  | checkpoint | Make sure all screws in the main room and bathroom are covered with plaster
checkpoint-status | cf9c92cc-2c57-4a99-ad0e-c7c46148a3f1 |  | checkpoint | Ensure all external GIB is taped and covered with plaster
checkpoint-status | c2807123-f2ff-4c0a-841c-a08255a5a451 |  | checkpoint | Ensure all external GIB (90 degree angle) is taped and covered with plaster
checkpoint-status | d0d4cdfc-596c-40e3-ba83-7b257dd07ede |  | checkpoint | Ensure all the flat joints are taped and plastered
checklist-flat | 862e27b8-0baf-4bee-b3af-56eee946f2f7 |  | checklist | Set Out Checklist |  |  |  |  | Yes | Set Out Checklist | c750d778-2f3c-44a1-a59d-50c877a5397e
checkpoint-status | e99c7fd8-5521-4d8a-840e-3c1ddd976049 |  | checkpoint | Work area clear to work
checkpoint-status | 05beff42-ffbc-4e0b-930a-0c6dd8b5edf6 |  | checkpoint | Check latest plan revision prior to start
checkpoint-status | 2d39d609-7066-4ef3-9f5a-0b2808724ae2 |  | checkpoint | All bathrooms meet council requirements
checkpoint-status | 3a3ec9d8-c032-4343-9507-0e3d79f1cf8c |  | checkpoint | Locate and check datum grid lines for square
checkpoint-status | ac872adf-2245-4f97-86fb-c205967f0b7b |  | checkpoint | Check all wall types are correct and wall lining have been allowed for
checkpoint-status | e24e48a0-1f18-4e11-8eca-56a0b5de2873 |  | checkpoint | All rooms measure correct and square
checkpoint-status | 920c0dad-67b2-440c-bf24-982d44abbcbf |  | checkpoint | All bracings has been correctly marked
checkpoint-status | 6e5865f0-ab5f-4351-87a4-c8a78a81d92c |  | checkpoint | Has pre line been QA'd by South Base?
checkpoint-status | 4f4b7d71-942a-4f79-9f58-ca4bd11bb622 |  | checkpoint | Have specific plans been used along side floor set out plans?
checklist-flat | 48f77bd3-2de5-4c47-907b-3758d54b7b3f |  | checklist | Variation # |  |  |  |  | Yes | Variation # | cc460df4-ed52-4505-902b-4aefbb31ae2e
checkpoint-status | 7698fb0d-351c-404b-bee9-73cd0c6b2180 |  | checkpoint | Variation completed with photos of work
text | 50824351-b5d5-5a3b-99f2-64c71f58ac29 |  | textbox | Details (Level/Unit/Area)
text | 6628b37d-ba2b-53f3-9720-e829ecb6a4f3 |  | textbox | Hours/Minutes
checklist-flat | cf546931-b45f-4928-83c7-97288c51fd72 |  | checklist | Stopping Checklist |  |  |  |  | Yes | Stopping Checklist | daaa9902-c58c-4b91-b57b-c10bc526c9bd
checkpoint-status | e449e761-6595-4f4c-8c8c-c7e3da68b924 |  | checkpoint | Work area ready and approval to progress / postline passed
checkpoint-status | 8ba60d4b-e85d-430e-9994-505c5c5c6f60 |  | checkpoint | Correct fire stopping product applied (if required)
checkpoint-status | f5b70b0f-4357-4291-9270-982c7d218ef0 |  | checkpoint | Correct stopping product and applied correctly to Level 4 finish
checkpoint-status | 74fb5eaf-ce00-447c-9cca-d7ec4fb44d9c |  | checkpoint | Square stopping, coving, slimlines and joints checked and acceptable
checkpoint-status | 7514b0f8-fa71-40bf-a206-309371896fc6 |  | checkpoint | Adequate drying time between applications & no visible bubbling
checkpoint-status | 208a3bb6-36fe-461e-86d0-9d896b04a301 |  | checkpoint | All sanding completed as required
checkpoint-status | b9607ae4-e56d-420a-ad8b-6621ce3f777f |  | checkpoint | Stopping completed, checked and Supervisor sign off
checkpoint-status | 6035099b-60eb-4d06-87b6-7697088eefa6 |  | checkpoint | Area left clean & tidy
checklist-flat | d3ef38c7-9f38-47cd-8953-ac1eac96532c |  | checklist | Photos |  |  |  |  | Yes | Photos | ed28059d-5130-4331-8177-a1c619dff193
checkpoint-no-status | 07f3a41c-5bae-4b85-addd-1aded74fc9a0 |  | checkpoint | Attach Images Here