## ITP
|  |  | Inspection and Test Plan - Bored Pile Construction | [7 empty] | Document # 1145-C200-FUL-QAC-ITP-0016
[11 empty] | Revision: 00 | Date: 24/11/2022
Client: | MRPV |  | Construction Process: | Bored Pile Construction |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Craigieburn Road Upgrade |  | Specifications: | Project Specification 3050 VicRoads Specifications Section 606 (Jul 2017), 610 (Feb 2020), 611 (Nov 2018) |  | Name: | Jonathon Rock | Name: | Mustafa Kamel |  | Name: | Babak Rudd
Contract No: | CONS-1145 |  | Structure / Component: |  |  | Position: | Project Engineer | Position: | Project Engineer |  | Position: | Quality Manager
|  |  | Location: |  |  | Date : | 2022-11-09 | Date : | 2022-11-09 |  | Date : | 2022-11-24
Lot No: | ITP-016-AX-LOT-XXX |  | Lot Details: |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works/ Design and Submissions
1.1 | Induction |  | Prior to Commencing | All personnel on site have been inducted to the CRG site | Site Induction Register | Document review | Site induction signed. | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Work pack briefing |  | Prior to Commencing | All personnel on site have been briefed on the relevant work park relating to scope of works. | WP | Document Review | Work pack signed. | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.3 | Safety measures are in place, Safe Work Method Statement (SWMS) undertaken |  | Prior to commencing | As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work. | Health and Safety Co-Ordination Plan | Document Review | SWMS(s) signed | HP* | Site Engineer | N/A |  | N/A
1.4 | Check that current revision drawings are being used |  | Prior to Commencing | Issued For Construction (IFC) and latest available revision used | Project Drawings / Drawing Register | Document review | This ITP Signed | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.5 | Confirm understanding of current Environment Management Plan (CEMP) related to the work area and that all prescribed environmental controls are in place |  | Prior to Commencing | All personnel on site have been inducted and briefed on the requirements of the CEMP. All environmental measures including sediment and erosion control to be implemented as per current CEMP. | CEMP | Document review & Site inspection | This ITP Signed | IP | Site Engineer | N/A |  | N/A
1.6 | Excavation Permit issued |  | Prior to Commencing Work | Current Excavation Permit signed and specific for the area where works will be executed. | Excavation Permit | Document review & Site inspection | Excavation Permit # | HP* | Site Engineer | N/A |  | N/A
1.7 | Traffic Management (When required) |  | Prior to Commencing Work | Approved WTMP and MOA | WTMP | Document review & Site inspection | Superintendents Correspondence | AP | Site Engineer |  |  | N/A
1.8 | Mix design |  | No less than 4 weeks prior to commencement of activity | The concrete mix design details shall be submitted for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Concrete shall not be placed until the mix design has been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes. Concrete mix designs shall remain valid for 12 months from the date of registration, unless constituent materials and material proportions cease to comply with the specified requirements. | VicRoads Spec. Cl.610.07(b) | Document review | Approved Mix Design Allocated registration number on the Register of VicRoads approved concrete mixes. | HP | Project Engineer & Superintendent |  |  | N/A
1.9 | Steel Reinforcement |  | Prior to commencing works and no more than 14 days after contract award | Steel reinforcement shall comply with the requirements of Section 611. Unless otherwise shown on drawings, bars shall be grade 500N. Allowances should be made when preparing the steel reinforcement schedule to achieve the specified tolerances on member dimensions, concrete cover and location of steel reinforcement Manufacturer of steel reinforcement materials must be in possession of a current certificate of approval, issued by the Australian Certification Authority for Reinforcing Steel (ACRS). Evidence of compliance with this clause shall be submitted to the superintendent within 14 days of award of the contract. | VicRoads Spec. Cl.611.03(a) Cl.611.04 Cl611.05(a) | Document Review | Submitted Product Details | HP* | Project Engineer | N/A |  | N/A
1.10 | Quality Procedure for pile construction |  | No less than 4 weeks prior to commencement of activity | A quality procedure for the construction of the piles shall be submitted to the Superintendent not less than 4 weeks prior to the commencement of the piling works. Piling works shall not take place until the quality procedure has been reviewed and approved by the Superintendent. Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials, and the method of placement of concrete under water has been reviewed by the Superintendent. The Contractor shall submit the procedure for placing concrete in bored piles, under water and in dry bores, for review by the Superintendent at least four weeks prior to concreting. Concrete shall not be placed in bored piles, under water or in a dry bore until the proposed method of placement of concrete has been approved by the Superintendent. | VicRoads Spec. Cl.606.03(a) Cl.606.06(a) Cl.610.18(c) | Document review | Approval of Quality Procedure for piles construction Procedure for placing concrete reviewed | HP | Project Engineer & Superintendent |  |  | N/A
2 | Boring
2.1 | Survey set-out |  | Prior to Commencing | Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks required for the works. The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. | Project Spec. Cl.1190.06 Latest IFC Drawings | Site Inspection | This ITP Signed, Survey Records | SCP | Site Engineer & Surveyor | N/A |  | N/A
2.1 | Protection of Adjacent Piles |  | Prior to Commencing | No pile shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15MPa | VicRoads Spec. Cl.606.04 | Visual Inspection | This ITP Signed, Bored Pile Checklist | IP | Site Engineer | N/A |  | N/A
2.1 | Excavation levels |  | Each pile | Check the toe levels conform to the drawing. | Latest IFC Drawings | Document review | Bored Pile Checklist CRG-FH-CL-0006 | IP | Site Engineer | N/A |  | N/A
2.1 | Inspection of Pile Excavation |  | Each Pile, a minimum of 48 hrs notice given to the Superintendent for arrangement of the inspection of the pile excavation | The temporary casing (where used) shall not be removed, nor shall reinforcement and/or concrete be placed until the pile walls and base have been inspected by the Superintendent and that the inspection has confirmed that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions. | VicRoads Spec. Cl.606.05 | Site Inspection | Pile walls and base inspected by Superintendent This ITP signed off | HP | Site Engineer & Superintendent |  |  | N/A
2.1 | Check reinforcement cages |  | Each pile | Steel Reinforcement shall be securely held during placing and compacting of concrete. Steel reinforcements shall be made of concrete blocks of a strength similar to the structure, strong enough to withstand the imposed loads without movement of the steel reinforcement. No other materials to be used as supports. Spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained. Reinforcement as per drawings and specification. | VicRoads Spec. Cl.606.06(a) Cl.611.03(a) Cl.611.04 Cl.611.10 Project Specification | Site Inspection | Bored Pile Checklist CRU-FH-CL-0006 | IP | Site Engineer | N/A |  | N/A
2.1 | Pre – pour checklist |  | Each pile | Bored Pile Checklist completed and signed. | Work Pack | Site Inspection | Bored Pile Checklist CRG-FH-CL-0006 | HP* | Site Engineer | N/A |  | N/A
3 | Placing and Finishing Concrete
3.1 | Carry out sampling of concrete |  | As per table 610.161 | Slump flow: 550-800mm spread T500 time: Achieve a spread of 500 mm within 1 to 5 seconds Passing ability ≤ 10 mm. Observations as per Table 610.131 of VicRoads Spec. - Three cylinders taken from the same sample used to test. 1 cylinder crushed at 7 days. 2 cylinders crushed at 28 days - Number of samples taken shall be as per Table 610.161 | VicRoads Spec. Cl.610.13(b) Cl.610.16(b) Cl.610.16(n) Table 610.131 Table 610.161 | Site Inspection Site Sampling | Concrete Pour Record CRG-FH-CL-0003 and Bored Pile Checklist CRG-FH-CL-0006 completed | IP | Site Engineer | N/A |  | N/A
3.2 | Place Concrete |  | Each Concrete pour | Piles shall be concreted within 24 hours of completion of the pile excavation. Discharge time between truckloads for the same cast to be <45 mins. All concrete to be placed within 60 minutes from batch or as specified in the approved VR mix. Each batch (truckload) of concrete delivered to site shall be visually inspected to ensure consistency of concrete supply, and the estimated slump shall be recorded on the identification certificate for the batch. Piles places in the dry shall be constructed to a minimum of 300mm above pile cut-off level to allow breaking back of contaminated concrete at the top of the pile. | VicRoads Spec. Cl.610.16(b) Cl.610.16( c) Cl.610.13(f) CL.606.06(a) | Site Inspection | Concrete Pour Record Bored Pile Checklist Concrete dockets | IP | Site Engineer | N/A |  | N/A
4 | Testing Requirements
4.1 | Pile Testing |  | Representative Sample determined in consultation with the Superintendent. | Unless dispensation is granted, a representative sample of piles shall be tested by a consultant prequalified to VicRoads as per the requirements of Section 606.07 including: (A) Integrity Testing - First 6 piles constructed, then 1 in 3 remaining. (B) Static Load Testing (C ) Dynamic Load Testing - 1 in 10 Piles with a pile depth within 2m. Results including raw data are to be provided to the superintendent per the timeframes requested but no less than 48 hours after collection of results. | Project Spec. Cl.3050.07 VicRoads Spec. Cl.606.07 | Test report | Test reports provided to Superintendent This ITP signed off | HP | Site Engineer / Superintendent |  |  | N/A
4.2 | Concrete Test Results |  | Each sample | Minimum 7 day strength (26MPa) achieved as per table 610.051 Minimum 28 strength (40MPa) achieved Strength average of tested cylinders | VicRoads Spec. Cl.610.05 Table 610.051 | Test report | Compressive Strength (MPa) Test report This ITP signed off | TP | Site Engineer | N/A |  | N/A
4.3 | Tolerance Check & As Built survey |  | Each pile | Check Tolerances & Survey Pile positions: (a) pile head shall finish within 75 mm of the specified plan position; (b) variation from the vertical or the specified batter/rake shall not be more than 1 in 100; (c) where piling excavation has developed a curve or out of verticality, the offset from the theoretical straight pile line shall not exceed 150 mm over a length of 15 metres or proportionally for greater or shorter lengths. Mark all details correctly on as-builts Pile head position & verticality | VicRoads Spec. Cl.606.08 | Site Inspection/ Document review | Survey report | SCP | Site Engineer & Surveyor | N/A |  | N/A
Notes
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Work Completed On:
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
[5 empty] | WP | Witness Point |  | An inspection which must be witnessed by the Superintendent