## ITP007 - Unbound Pavements
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-016-AX-LOT-XXX - Desc | itp |  |  |  |  | ITP 0016 - Bored Pile Construction
section | Lot Information
checkpoint | 1.0 Lot Information
textbox | Lot Created On
textbox | Lot Opened On
textbox | Work Commenced On
dropdown | Lot Type | CIL - Civil Lot, DRL - Drainage Lot, EAL - Earthworks Lot, ELL - Electrical Lot, UTL - Utility Lot, STL - Structural Lot
textbox | From and To Chainage
dropdown | Construction Element | FOUN - Foundation
dropdown | Activity | BORP - Bored Pile
dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
textbox | Engineer Responsible
textbox | comments
section | 1 - Preliminary Works / Design and Submissions
checkpoint | 1.1 - Induction
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: All personnel on site have been inducted to the CRG site
label | - - - - - - - - -
label | Reference Documents: Site Induction Register
label | - - - - - - - - -
label | Inspection / Test Method: Document review
label | - - - - - - - - -
label | Record of conformity: Site induction signed.
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: Site Engineer / Site Foreman
checkpoint | 1.2 - Work pack briefing
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: All personnel on site have been briefed on the relevant work park relating to scope of works.
label | - - - - - - - - -
label | Reference Documents: WP
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of conformity: Work pack signed.
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: Site Engineer / Site Foreman
checkpoint | 1.3 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
label | Frequency: Prior to commencing
label | - - - - - - - - -
label | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | - - - - - - - - -
label | Reference Documents: Health and Safety Co-Ordination Plan
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of conformity: SWMS(s) signed
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint | 1.4 - Check that current revision drawings are being used
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | - - - - - - - - -
label | Reference Documents: Project Drawings / Drawing Register
label | - - - - - - - - -
label | Inspection / Test Method: Document review
label | - - - - - - - - -
label | Record of conformity: This ITP Signed
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: Site Engineer / Site Foreman
checkpoint | 1.5 - Confirm understanding of current Environment Management Plan (CEMP) related to the work area and that all prescribed environmental controls are in place
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: All personnel on site have been inducted and briefed on the requirements of the CEMP. All environmental measures including sediment and erosion control to be implemented as per current CEMP.
label | - - - - - - - - -
label | Reference Documents: CEMP
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of conformity: This ITP Signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint | 1.6 - Excavation Permit issued
label | Frequency: Prior to Commencing Work
label | - - - - - - - - -
label | Acceptance Criteria: Current Excavation Permit signed and specific for the area where works will be executed.
label | - - - - - - - - -
label | Reference Documents: Excavation Permit
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of conformity: Excavation Permit #
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint | 1.7 - Traffic Management (When required)
label | Frequency: Prior to Commencing Work
label | - - - - - - - - -
label | Acceptance Criteria: Approved WTMP and MOA
label | - - - - - - - - -
label | Reference Documents: WTMP
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of conformity: Superintendents Correspondence
label | - - - - - - - - -
label | AP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint | 1.8 - Mix design
label | Frequency: No less than 4 weeks prior to commencement of activity
label | - - - - - - - - -
label | Acceptance Criteria: The concrete mix design details shall be submitted for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Concrete shall not be placed until the mix design has been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
label | Concrete mix designs shall remain valid for 12 months from the date of registration, unless constituent materials and material proportions cease to comply with the specified requirements.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec. Cl.610.07(b)
label | - - - - - - - - -
label | Inspection / Test Method: Document review
label | - - - - - - - - -
label | Record of conformity: Approved Mix Design
label | Allocated registration number on the Register of VicRoads approved concrete mixes.
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Project Engineer & Superintendent
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.9 - Steel Reinforcement
label | Frequency: Prior to commencing works and no more than 14 days after contract award
label | - - - - - - - - -
label | Acceptance Criteria: Steel reinforcement shall comply with the requirements of Section 611. Unless otherwise shown on drawings, bars shall be grade 500N. Allowances should be made when preparing the steel reinforcement schedule to achieve the specified tolerances on member dimensions, concrete cover and location of steel reinforcement
label | Manufacturer of steel reinforcement materials must be in possession of a current certificate of approval, issued by the Australian Certification Authority for Reinforcing Steel (ACRS). Evidence of compliance with this clause shall be submitted to the superintendent within 14 days of award of the contract.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec.
label | Cl.611.03(a)
label | Cl.611.04
label | Cl611.05(a)
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of conformity: Submitted Product Details
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: Project Engineer
checkpoint | 1.10 - Quality Procedure for pile construction
label | Frequency: No less than 4 weeks prior to commencement of activity
label | - - - - - - - - -
label | Acceptance Criteria: A quality procedure for the construction of the piles shall be submitted to the Superintendent not less than 4 weeks prior to the commencement of the piling works. Piling works shall not take place until the quality procedure has been reviewed and approved by the Superintendent.
label | Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials, and the method of placement of concrete under water has been reviewed by the Superintendent.
label | The Contractor shall submit the procedure for placing concrete in bored piles, under water and in dry bores, for review by the Superintendent at least four weeks prior to concreting.
label | Concrete shall not be placed in bored piles, under water or in a dry bore until the proposed method of placement of concrete has been approved by the Superintendent.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec.
label | Cl.606.03(a)
label | Cl.606.06(a)
label | Cl.610.18(c)
label | - - - - - - - - -
label | Inspection / Test Method: Document review
label | - - - - - - - - -
label | Record of conformity: Approval of Quality Procedure for piles construction
label | Procedure for placing concrete reviewed
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Project Engineer & Superintendent
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Boring
checkpoint | 2.1 - Survey set-out
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks required for the works. The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity.
label | - - - - - - - - -
label | Reference Documents: Project Spec. Cl.1190.06
label | Latest IFC Drawings
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: This ITP Signed, Survey Records
label | - - - - - - - - -
label | SCP
label | - - - - - - - - -
label | Responsibility: Site Engineer & Surveyor
checkpoint | 2.2 - Protection of Adjacent Piles
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: No pile shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15MPa
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec. Cl.606.04
label | - - - - - - - - -
label | Inspection / Test Method: Visual Inspection
label | - - - - - - - - -
label | Record of conformity: This ITP Signed, Bored Pile Checklist
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint | 2.3 - Excavation levels
label | Frequency: Each pile
label | - - - - - - - - -
label | Acceptance Criteria: Check the toe levels conform to the drawing.
label | - - - - - - - - -
label | Reference Documents: Latest IFC Drawings
label | - - - - - - - - -
label | Inspection / Test Method: Document review
label | - - - - - - - - -
label | Record of conformity: Bored Pile Checklist CRG-FH-CL-0006
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint | 2.4 - Inspection of Pile Excavation
label | Frequency: Each Pile, a minimum of 48 hrs notice given to the Superintendent for arrangement of the inspection of the pile excavation
label | - - - - - - - - -
label | Acceptance Criteria: The temporary casing (where used) shall not be removed, nor shall reinforcement and/or concrete be placed until the pile walls and base have been inspected by the Superintendent and that the inspection has confirmed that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec. Cl.606.05
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Pile walls and base inspected by Superintendent, This ITP signed off
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Site Engineer & Superintendent
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Check reinforcement cages
label | Frequency: Each pile
label | - - - - - - - - -
label | Acceptance Criteria: Steel Reinforcement shall be securely held during placing and compacting of concrete. Steel reinforcements shall be made of concrete blocks of a strength similar to the structure, strong enough to withstand the imposed loads without movement of the steel reinforcement. No other materials to be used as supports.
label | Spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained.
label | Reinforcement as per drawings and specification.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec.
label | Cl.606.06(a)
label | Cl.611.03(a)
label | Cl.611.04
label | Cl.611.10
label | Project Specification
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Bored Pile Checklist CRU-FH-CL-0006
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint | 2.6 - Pre – pour checklist
label | Frequency: Each pile
label | - - - - - - - - -
label | Acceptance Criteria: Bored Pile Checklist completed and signed.
label | - - - - - - - - -
label | Reference Documents: Work Pack
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Bored Pile Checklist CRG-FH-CL-0006
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: Site Engineer
section | 3 - Placing and Finishing Concrete
checkpoint | 3.1 - Carry out sampling of concrete
label | Frequency: As per table 610.161
label | - - - - - - - - -
label | Acceptance Criteria: Slump flow: 550-800mm spread
label | T500 time: Achieve a spread of 500 mm within 1 to 5 seconds
label | Passing ability ≤ 10 mm.
label | Observations as per Table 610.131 of VicRoads Spec.
label | – Three cylinders taken from the same sample used to test. 1 cylinder crushed at 7 days. 2 cylinders crushed at 28 days
label | – Number of samples taken shall be as per Table 610.161
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec.
label | Cl.610.13(b)
label | Cl.610.16(b)
label | Cl.610.16(n)
label | Table 610.131
label | Table 610.161
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection, Site Sampling
label | - - - - - - - - -
label | Record of conformity: Concrete Pour Record CRG-FH-CL-0003 and Bored Pile Checklist CRG-FH-CL-0006 completed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint | 3.2 - Place Concrete
label | Frequency: Each Concrete pour
label | - - - - - - - - -
label | Acceptance Criteria: Piles shall be concreted within 24 hours of completion of the pile excavation.
label | Discharge time between truckloads for the same cast to be <45 mins.
label | All concrete to be placed within 60 minutes from batch or as specified in the approved VR mix.
label | Each batch (truckload) of concrete delivered to site shall be visually inspected to ensure consistency of concrete supply, and the estimated slump shall be recorded on the identification certificate for the batch.
label | Piles places in the dry shall be constructed to a minimum of 300mm above pile cut-off level to allow breaking back of contaminated concrete at the top of the pile.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec.
label | Cl.610.16(b)
label | Cl.610.16(c)
label | Cl.610.13(f)
label | CL.606.06(a)
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Concrete Pour Record, Bored Pile Checklist, Concrete dockets
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
section | 4 - Testing Requirements
checkpoint | 4.1 - Pile Testing
label | Frequency: Representative Sample determined in consultation with the Superintendent.
label | - - - - - - - - -
label | Acceptance Criteria: Unless dispensation is granted, a representative sample of piles shall be tested by a consultant prequalified to VicRoads as per the requirements of Section 606.07 including:
label | (A) Integrity Testing - First 6 piles constructed, then 1 in 3 remaining.
label | (B) Static Load Testing
label | (C) Dynamic Load Testing - 1 in 10 Piles with a pile depth within 2m.
label | Results including raw data are to be provided to the superintendent per the timeframes requested but no less than 48 hours after collection of results.
label | - - - - - - - - -
label | Reference Documents: Project Spec. Cl.3050.07
label | VicRoads Spec. Cl.606.07
label | - - - - - - - - -
label | Inspection / Test Method: Test report
label | - - - - - - - - -
label | Record of conformity: Test reports provided to Superintendent, This ITP signed off
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Site Engineer / Superintendent
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Concrete Test Results
label | Frequency: Each sample
label | - - - - - - - - -
label | Acceptance Criteria: Minimum 7 day strength (26MPa) achieved as per table 610.051
label | Minimum 28 strength (40MPa) achieved
label | Strength average of tested cylinders
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec. Cl.610.05
label | Table 610.051
label | - - - - - - - - -
label | Inspection / Test Method: Test report
label | - - - - - - - - -
label | Record of conformity: Compressive Strength (MPa) Test report, This ITP signed off
label | - - - - - - - - -
label | TP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint | 4.3 - Tolerance Check & As Built survey
label | Frequency: Each pile
label | - - - - - - - - -
label | Acceptance Criteria: Check Tolerances & Survey Pile positions:
label | (a) pile head shall finish within 75 mm of the specified plan position;
label | (b) variation from the vertical or the specified batter/rake shall not be more than 1 in 100;
label | (c) where piling excavation has developed a curve or out of verticality, the offset from the theoretical straight pile line shall not exceed 150 mm over a length of 15 metres or proportionally for greater or shorter lengths.
label | Mark all details correctly on as-builts
label | Pile head position & verticality
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec. Cl.606.08
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection/ Document review
label | - - - - - - - - -
label | Record of conformity: Survey report
label | - - - - - - - - -
label | SCP
label | - - - - - - - - -
label | Responsibility: Site Engineer & Surveyor
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
textbox | Work Completed On:
section | Lot Verification
checkpoint | Lot Verification.
dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
textbox | Other:
dropdown | Lot Status | OUTSTANDING, CLOSED
textbox | Lot Closed On
textbox | comments