## Master List Templates
Id | Type | Name | Values | Prompting Name
8a4bfb74-04d2-47d1-9d9c-4e0e45c8e71f | checklist | Documents |  | Documents
d27e664b-b8db-4dae-8ce3-cc3995597fdf | section | Details
9483f8e0-de31-4f34-b59b-8778c5e33994 | checkpoint | Document attached
71311430-12af-4de5-b2e1-320343a3d7c5 | checklist | Test ITP | itp | Test ITP
20380797-825e-43d5-b636-1e28953acadd | section | Preliminary Works
107e3d9c-f945-48ad-a893-382139576ad3 | checkpoint | 3.1 Pre-construction Photos
955645e1-125c-52ac-a36d-9f7aaf64fd68 | note | Inspection Point: Quality Control Activity - Photos of worksite including vehicle access points.
de815be8-ff5b-5bbf-8fcf-b6a74f875d15 | note | ○ Photos of any existing defects/damage.
f629ba35-c6c9-5e84-afb6-f12afe19ba50 | note | Acceptance Criteria - Coverage of whole site
b343e756-6236-534e-a04c-adde741f9cf9 | note | Verifying Document - Photos saved
487d2c77-26c6-574d-9f8c-69197b900e60 | note | Reference: Contract Specs/Standards - D1.4
aa7dcc23-975c-5d3e-90f1-e46ecef13a8e | note | Inspection Point/Signature & Date - PM
441f8f47-9e59-4e93-af48-52ea9db74b4f | checkpoint | 3.2 Verify Construction Drawings
5979cb19-48d2-5a0f-8a4a-18a2495e019b | note | Inspection Point: Quality Control Activity - Verify Construction Drawings that are in the site folder are the latest revision.
77adfc3c-637c-5532-a2de-de99b4eb0801 | note | Acceptance Criteria - Latest drawings approved
2e7272cf-1b67-5992-8aea-1c720473b1e1 | note | Verifying Document - Drawings Register
91384230-7de8-55b8-b9f0-cf3094b4e632 | note | Reference: Contract Specs/Standards -
53f92b21-b0f6-50b0-9a66-65c339b74caa | note | Inspection Point/Signature & Date - PM
92a4d361-6a90-4261-aacc-b17a70c5ba02 | checkpoint | 3.3 Road Authority Notifications
a5905a4b-3c67-5ea9-9f5c-3f49ad93a559 | note | Inspection Point: Quality Control Activity - Corridor access Permit.
0158a33e-7ce3-58a8-babd-2c00a85ada9b | note | ○ Block by block Temporary Traffic Management Plans.
c980e384-1324-5a31-ad80-c5f42c7f2909 | note | Acceptance Criteria - Permit & Traffic Plan approved
670802ca-5daf-518d-ba40-b11f61b8bba8 | note | Verifying Document - Work Access Permit & TMP
ae04fd1d-8285-5e71-9dc0-6c451b22a24a | note | Reference: Contract Specs/Standards - C1.09, D1.4
afbe1801-0461-5ff9-9968-d71d709c4667 | note | Inspection Point/Signature & Date - PM
d39f31d1-9f41-49b3-8e2e-f1d32ae48a60 | checkpoint | 3.4 Management Plan
dacc70c9-2410-5db2-bd45-66d975547e52 | note | Inspection Point: Quality Control Activity - H&S Plan
c98cf114-7fba-5cd7-9f75-05f14d1dc0c4 | note | ○ Environmental Plan
ff8ca60d-7b07-570e-837e-2ea6f5924d22 | note | ○ Quality Assurances
6ad36c2d-187f-596a-87f1-b024ccfeeffd | note | Acceptance Criteria - Plans & Safety Measures in place
d5f70aa4-3aed-5da0-b07e-f5410907778d | note | Verifying Document - H&S Plan, Method Statement
79d6f9d4-a271-5202-907c-58e7835bcb83 | note | Reference: Contract Specs/Standards - D1.3
7f636cf1-81e6-5b8d-8b3a-e415c151f5d7 | note | Inspection Point/Signature & Date - PM, CR
5d595464-2779-423b-add8-0d8127f9cada | checkpoint | 3.5 Public Notification
3a84e0b1-0335-5dc4-bb53-a8236469f1e8 | note | Inspection Point: Quality Control Activity - Notice of works to properties in the construction zone in each block
111ac031-f06c-52e2-8d36-657040eef63d | note | ○ Notification to Rubbish collection contractor.
6425c7b3-a4a7-5fc9-b4d2-348fb03ae6aa | note | ○ Project Signage
1fb132d3-92db-5038-aa91-124209dd7f89 | note | Acceptance Criteria - 48 hours prior notification
6a28c857-a4f5-59ec-8a55-c083caf0c3a7 | note | Verifying Document - Letter to residents
c926fb82-add6-5d96-9893-e1996f955a14 | note | Reference: Contract Specs/Standards - D1.10
bdbcb526-3a1e-5e5d-86ef-0a808ab8369e | note | Inspection Point/Signature & Date - PM
83d17dff-2396-439e-955c-8f1f727f65ed | checkpoint | 3.6 Shutdown/Isolation
6ea865c2-ca78-5854-8fa3-2264bf699993 | note | Inspection Point: Quality Control Activity - Shutdown/Isolation process verified in each block closure
1555c1d5-29de-5a42-a7d4-8b3739287984 | note | Acceptance Criteria - Shutdown process verified
cd7f89f3-8fdf-5085-8c83-7bb9094c8b0a | note | Verifying Document - Notification letters
ef26b893-83e8-5557-854d-c80eb7263938 | note | Reference: Contract Specs/Standards - C1.16, D2.7.8
28d7be85-39af-58e3-9302-9376a974da67 | note | Inspection Point/Signature & Date - PS
d167c212-b415-420c-a15c-45c677294de6 | checkpoint | 3.7 Construction Set Out
742868c8-23f0-5452-9b92-ba186649d8d7 | note | Inspection Point: Quality Control Activity - Correctly mark out the position of the new pipelines for construction.
9e97b2cc-ba1a-5815-b8f9-fbfc1eb1d305 | note | Acceptance Criteria - Construction Plans checked
5b2e22e1-e5ff-5dc0-99bf-61f23b16df05 | note | Verifying Document - Construction Plans
62386f7d-45bf-5fb2-8ee5-5645b5fb6848 | note | Reference: Contract Specs/Standards - D2.7.1
d58502cb-242d-55dc-b860-3551207f6eba | note | Inspection Point/Signature & Date - PS, CR
a5600e25-383f-46d4-8512-0c264c1e449f | checkpoint | 3.8 Pre-Excavation Permits
dae1eccc-c23e-53c5-a82d-0efd94bccfeb | note | Inspection Point: Quality Control Activity - Permit to excavate for the location has been endorsed by an authorised person.
4086823b-a3b0-5514-bed4-f7f9e3b60915 | note | ○ Existing service plans & locates
c1e5fd2a-aef6-51bf-8cd0-bb993a96c4c9 | note | ○ Close approach permits
e9ebe2eb-6bb3-5920-af4f-3e5f51dc6ced | note | ○ Notifiable works
c0184131-3963-58e5-89ee-4c85ee5a746b | note | Acceptance Criteria - Permit to excavate endorsed
ef5bff12-f195-5b6f-aa81-cb8850c90580 | note | Verifying Document - Ground Disturbance Permit
64acb508-1d91-553b-8bd2-2bec3032ca97 | note | Reference: Contract Specs/Standards - D1.7
7835cccc-5334-5c60-a2d5-886aa9e0b519 | note | Inspection Point/Signature & Date - PS
02c8290d-79fe-4b01-a4f8-43e9d4c6e881 | signoff | HOLD POINT
abbb431d-e004-44ec-b738-fab1868140b8 | section | Incoming Goods Inspections
2aa07f2e-4aed-4158-88a0-e6abf1872ee1 | checkpoint | 4.1 Pipe & Fitting Inspections
335e2b85-3765-5d7c-823f-1a30f4f4c2cd | note | Inspection Point: Quality Control Activity - Visual check of materials delivered:
3c2f6b16-25d4-518b-a78c-50cd0381e2b9 | note | ○ Correct Material & dimensions
38ce9bbf-d35b-56d0-9094-6888dbbe0772 | note | ○ Condition & Quantity
e0aca729-1137-5fa6-a9c4-e65d8d4be14e | note | ○ Free of defects – surface abrasion, ovality, not kinked or crushed
c7813b84-576f-505d-b003-53fb30070daf | note | ○ Batch/serial numbers present
e60eb730-8b8d-5bbe-9001-2c575dd38607 | note | Acceptance Criteria - Correct material & no defects
775a2f60-1a0d-5a61-a840-33859f5f5380 | note | Verifying Document - Packing Slips
5523d66d-7eb8-57b7-8130-17f63b83eb86 | note | Reference: Contract Specs/Standards - D2.4,D3.3, D4.3, D5.3, D8.3
4815886f-d85b-584d-a8bf-54bb43596b4d | note | Inspection Point/Signature & Date - PS
18a89c7a-07fc-4278-9ab2-46bbdeed02f3 | checkpoint | 4.2 Pipe & Fitting Storage
736fc6ca-0587-58a7-aa66-1e6006900b05 | note | Inspection Point: Quality Control Activity - Stored as per manufacturers specifications including maximum height limits and safely chocked in place.
88679b02-09b0-5f6d-85d2-86abe8c910f1 | note | ○ All pipes are end capped.
ace5e548-9b68-55f8-acb6-13682245a6d3 | note | ○ No scoring of pipe more than 10% of thickness.
0f1df64d-4495-5578-a941-f201cb9bd702 | note | ○ No damage to epoxy coating on Ductile fittings.
1dbf0fff-4157-5283-af1b-f1fa245cb0fd | note | Acceptance Criteria - Stored as per manufacturer
c2c2afc7-5301-5e5c-ba67-ba552d116bc1 | note | Verifying Document - Manufacturer’s Storage Instructions
99bbba7a-beec-5223-939d-15034191d36d | note | Reference: Contract Specs/Standards -
1dbd7e86-bf3c-5e32-8b08-073e38069992 | note | Inspection Point/Signature & Date - PS, CR
6b2618a5-8d30-4b91-a333-0dfd3ca9cf5f | signoff | HOLD POINT
1f6a3545-531a-431b-8950-db0056c6a96e | section | Construction Inspections
5b9fc0f7-1004-4407-be8c-24b464b7f09e | checkpoint | 5.1 Trench Excavation
02e391fc-3a18-522d-9c19-e2a03e270cfb | note | Inspection Point: Quality Control Activity - Trench width to be sufficient to safely lay the pipe (including shoring if required) and compact the side support of the new pipe. Bedding details below;
a6f490ee-48df-5ce7-ad7c-e1ea3aa3e379 | note | ○ Sufficient room to enable the pipe, joint, bed, haunch or surround shown in the drawings to be accommodated.
eec54b15-5ecd-5436-96af-7f3f1ec2feb7 | note | ○ Trench depth to enable pipe to be laid with the designed cover as shown on construction plans.
8fd021a9-e8d2-5b4c-8b4b-5843892fc6d1 | note | ○ If trench bottom to be suitable to compact pipe bedding as support pipe.
fc3f41ae-94b6-572c-ac89-2a9ef6fb22bf | note | Acceptance Criteria - Trench dimensions correct
e3b19d68-be79-52b1-b552-b4069f08f057 | note | Verifying Document - Daily Site Diary
84a404dc-63b4-5583-b4db-f3add2e91694 | note | Reference: Contract Specs/Standards - D2.6, D2.7
5aa888e2-14d6-582f-9a52-d9c849c2397e | note | Inspection Point/Signature & Date - PS
27edf7a6-5c6f-40e4-b0c0-9ab61a806878 | checkpoint | 5.2 Encountered Services
da1255de-facf-5b78-9de0-40b88d5693d6 | note | Inspection Point: Quality Control Activity - Block by block ensure existing live services are not unnecessarily damaged by works.
5fc0b366-4852-5bfe-a581-cba57122ba03 | note | ○ Repair any services that are temporarily removed during construction.
c6c5167f-c5f2-5998-b8d3-01f5f3e9341c | note | ○ Record any services found.
0631e0d3-22a9-5d7c-8b37-c6cbd46c7c91 | note | Acceptance Criteria - Existing services not damaged
81f412b2-a38d-50f2-a598-84775c34f384 | note | Verifying Document - Encountered Services Record
90c9acea-6aa9-5d0a-b22b-e74a722eebd8 | note | Reference: Contract Specs/Standards - D1.7, D2.7.7
7d0df532-6775-5e02-87ef-5933b5113c19 | note | Inspection Point/Signature & Date - PS
0bb6eb81-7e4a-451f-830e-1b4ed2ca3ea2 | checkpoint | 5.3 Pipe Installation
e9a5264d-e34d-57c2-b251-70577ea28002 | note | Inspection Point: Quality Control Activity - Interior of each pipe visually inspected to ensure free of debris.
4de7eba6-7a52-508a-8f6f-3da7ba17c6ad | note | ○ Re-cap end of pipe after installation.
9fcd0740-534d-500d-8189-e0970be0fe0f | note | ○ Check pipe installed at correct depth.
97372ff6-7a61-5b54-b317-dc368cef403b | note | ○ Ensure all collars are free from contamination in McDougall St berm
d141a6e9-ce08-571e-8cfd-8a4080f2f31b | note | Acceptance Criteria - Pipes free of debris & correctly installed
6c48859f-43ee-519f-b185-e2757b35f5ef | note | Verifying Document - Daily Site Diary
d6e34e20-3287-5bb8-accf-914843f1e5ed | note | Reference: Contract Specs/Standards - D2.5, D2.7, D8.4.2
c344ad27-9a7c-5088-8578-ce9de1f06115 | note | Inspection Point/Signature & Date - PS
315ca360-db4e-4b0f-b047-bcd13a88803d | checkpoint | 5.4 Concrete Pre-Pour Inspection
a0c3ca9d-7c53-5f00-a910-1efc9d53070f | note | Inspection Point: Quality Control Activity - Check dimensions of formwork match details in the Construction Drawings.
63a3685f-631f-50f2-b45b-5b550dd42985 | note | ○ Check pipe fitting joints are clear of concrete pour.
23788df5-5f26-5f32-a93c-2b6f87bf050f | note | ○ Thrust blocks to be poured against good solid natural ground.
2e389bbc-ca69-56cc-991e-0c7ae5298cfb | note | Acceptance Criteria - Thrust blocks against solid ground
4630ea02-6452-5ef8-9df0-b7baf484a9ae | note | Verifying Document - Daily Site Diary & Photos
2a52135d-b44a-5d64-8c2f-594fcb8d9444 | note | Reference: Contract Specs/Standards - D5.1, D5.3.2, D5.7
270f8374-94d2-5ff4-afe3-a9f4d98bb457 | note | Inspection Point/Signature & Date - PS, CR
02e5fe15-a3d0-4117-9c59-df286de87b71 | checkpoint | 5.5 Hydrant Depth
c166f8ac-68a4-56d5-a714-45a77c232876 | note | Inspection Point: Quality Control Activity - Confirm depth requirements have been met;
2f2ace55-1dbf-557c-880b-7b6a3dd25264 | note | ○ Hydrant outlet: 200mm min. to 400mm max.
285e10aa-95d7-51d9-ab64-3b2072cdb2d5 | note | Acceptance Criteria - Hydrant depth verified
9803aeb2-9d90-54ba-9e49-df36b5629658 | note | Verifying Document - Daily Site Diary
f8c94654-15c9-51e9-8452-342e59ecae6e | note | Reference: Contract Specs/Standards - D5.5
cc256614-c42e-5f6e-a39f-f68a89b87155 | note | Inspection Point/Signature & Date - PS
a0e3fce6-d131-4d47-b2fa-1afd64dedf22 | checkpoint | 5.6 Compaction Testing
ba0f25db-c515-54bf-af10-241ef05a2184 | note | Inspection Point: Quality Control Activity - Confirm trenches in paved areas are compacted to standard block by block.
49e7f8fd-7c6b-5d23-b61b-854926d2d227 | note | Acceptance Criteria - Compaction confirmed
22f4308c-0c3d-5079-b554-738af731d09f | note | Verifying Document - Clegg Record Sheet
ea3ff20d-d289-5332-88c3-7d7ac37a937a | note | Reference: Contract Specs/Standards - D2.7.10
bb591b35-fe0b-530a-8cb7-36e77516390e | note | Inspection Point/Signature & Date - PS
cdecfdb6-ad87-453e-b692-8fb65eb5cbe7 | checkpoint | 5.7 Watermain Pressure Testing
1da5f833-284a-5b18-99a9-331354fad608 | note | Inspection Point: Quality Control Activity - Hydrostatic pressure test on new pipeline and fittings block by block.
2f9a2668-68c2-5f33-8c5e-ec33a157d16e | note | Acceptance Criteria - Pressure test passed
36849462-809a-58b1-a71f-40568e648c95 | note | Verifying Document - Pressure Test Record Sheet
a57df2e3-9168-58b3-8e23-04a24658c806 | note | Reference: Contract Specs/Standards - D2.9.1, AS/NSZ 2566.2:2002 Section 6
2d130f10-37f0-55a1-8d72-a460b1f28c32 | note | Inspection Point/Signature & Date - PS, CR
a1e1175c-838a-44d4-97e2-105d86a88295 | checkpoint | 5.8 Watermain Sterilization
ce10429c-a3e0-5c3c-b478-43bc65ee371b | note | Inspection Point: Quality Control Activity - Flushing and sterilizing full length of new pipeline and fittings block by block.
14828d25-390c-5376-8cc6-48d3ee750694 | note | Acceptance Criteria - Sterilization completed
72845af4-3a77-57b0-bfd3-8c8b00ad194a | note | Verifying Document - Sterilization Record Sheet
c67f69b9-5827-576d-aa4b-e05ef53cf735 | note | Reference: Contract Specs/Standards - D2.9.1, AS/NSZ 2566.2:2002 Section 6
99631707-3d31-5b31-aff4-efb8e8c21979 | note | Inspection Point/Signature & Date - PS, CR
ddf7462a-b76e-41eb-a36d-0de8b8dd2a87 | checkpoint | 5.9 As-built Information
517e67db-4033-58c1-a6ca-d3362f98ca30 | note | Inspection Point: Quality Control Activity - Capture data for all new construction work.
ba450391-5c8a-5c55-b1c4-c22f0833b96c | note | Acceptance Criteria - Redline mark-up plan submitted
3eb797e2-7275-5590-8fac-676aa04c793f | note | Verifying Document - Redline Mark-up Plan
b2cc15a1-1e88-5f06-9c50-d2d2827d97a5 | note | Reference: Contract Specs/Standards - C1.22
3c06f156-3b4e-51b2-91ab-48d5a7624304 | note | Inspection Point/Signature & Date - PM
6fda002d-0146-4403-8542-79c60a61f794 | signoff | HOLD POINT
8b2fb51e-3dea-4864-85cf-ea6c1f2099ae | section | Final Inspection and Handover
e1185f06-97ee-41c3-ba68-9fa87ec8f197 | checkpoint | 6.1 Final Inspection of Works
937e6486-743d-5157-8e7e-d97207a69798 | note | Inspection Point: Quality Control Activity - Work is inspected by the authorised person and complies with the nominated specification/standards
17149ea4-e39d-5a08-9b34-a5a55b8544b8 | note | Acceptance Criteria - Work inspected & complies with standards
69020570-efe6-5843-a2ad-9a102698555a | note | Verifying Document - Practical Completion Certificate
b28f2ad8-0f63-5340-9f55-310a0e29c35a | note | Reference: Contract Specs/Standards -
5422ff6f-c5f8-5de4-8a22-f168bf4f557c | note | Inspection Point/Signature & Date - PM
aca660fb-dc8b-43a6-b666-e84980ea511b | signoff | HOLD POINT

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
79e9d5bd-2944-4856-a658-ae302210f3d6 | checklist | QMD07 ITP-001 - Installation WWMH F20525 | itp | QMD07 ITP-001 - Installation WWMH F20525
71c3efb1-2dc4-47b3-b654-daa52b196e99 | section | ITP-001 - Installation WWMH F20525
82dbb01e-03ec-4157-81ce-a936b70453f2 | checkpoint | 1 - Manhole base Preparation (Pre-cast or in-situ)
766f760c-e3e4-51bb-9b39-ced7c8060c97 | note | Controlled By : (Position) - CR
62583a7e-eed3-5255-8f12-f5899fb23741 | note | Accept / Reject Criteria - Clean and dry base
138802b0-9b2d-591b-bd7d-b4ab015ccbde | note | ○ Correct bedding material and compaction
cd63ca5c-32dc-592c-94a9-ed8803a7007c | note | ○ Reinforcement and formwork inspected
ae4e38a2-d811-5333-a70d-aa41fd8f3e26 | note | ○ Waterproofing components in place
f1d47e60-e659-5d9e-bf89-39b393407867 | note | Spec. Ref, Procedure Or Method Statement - Project Drawings, D18 Construction Methodology
eb766024-0326-5018-a9c2-2a31e3248118 | note | Frequency Of Inspection OR Test - Prior to placing concrete or setting precast base
e28d7cfe-31fe-5461-87b7-14e775975c3e | note | HOLD POINT - I
1940a1af-207d-4e05-8157-7b8a89438ce4 | checkpoint | 2 - Manhole Cyclinder Installation
a07bfda7-4558-5de2-af8a-9629d967b966 | note | Controlled By : (Position) - FM
4dad8a70-230b-5e41-892d-c3d99e897c6b | note | Accept / Reject Criteria - Correct alignment and verticality
569beb3e-305d-5eb5-8810-cc6bf07082cb | note | ○ Joints sealed with approved material
0ef53783-6ff1-5c0b-8eda-26c27e2abe6f | note | ○ Steps/lifting holes sealed
a584545f-d488-58e1-8fa6-0ad9aecfe9f3 | note | ○ Wall thickness and type verified
b3f2dba9-58e8-5251-b4f9-ae6e8b53c6c2 | note | Spec. Ref, Procedure Or Method Statement - D18 – Precast Installations, Manufacturer specs NZS 3109
45e0db3b-e5b9-583e-9fda-9df39f9b087a | note | Frequency Of Inspection OR Test - Prior to backfilling
d4b13136-8675-5070-96b3-c840ff237207 | note | HOLD POINT - H
cba97589-9f5f-42de-b508-3a178f7f8263 | signoff | HOLD POINT
bad69d38-a745-47cf-8405-95c1195dfeda | checkpoint | 3 - Pipe protrusions into manhole
2c4192e3-7029-53ab-af08-690d12b40aed | note | Controlled By : (Position) - FM
eeba2cf2-4060-50ad-9ffc-2f5366ad255f | note | Accept / Reject Criteria - Flexible joint within 1metre of the manhole
b86fce06-ade6-5764-9980-25438145b715 | note | Spec. Ref, Procedure Or Method Statement - D18.3 INSTALLATION
4d990c16-385e-597a-8cfb-520f5a217d03 | note | Frequency Of Inspection OR Test - Prior to pouring corbels
7272c824-806f-5c66-b267-beb70a4cc244 | note | HOLD POINT - H
fe24e278-252c-4b33-be3b-534debeb9eb0 | signoff | HOLD POINT
022dec69-0ac2-4399-8438-2eefd26dbb2b | checkpoint | 4 - Internal Benching and Channeling
13130bf0-e2e3-5d79-8862-787080cac9d1 | note | Controlled By : (Position) - PM
22e92e7f-496e-53fc-9071-ce77dd3c1d54 | note | Accept / Reject Criteria - Smooth trowelled finish
71d5568d-13d1-5d66-9bcc-831e291444b6 | note | ○ Accurate channel fall to spec
d607f8b5-9f18-5fd1-b5ae-ca3ecc22370a | note | ○ Benching slope toward channel
ce9e3b49-a3ab-5b47-8f98-98975a55a775 | note | ○ No honeycombing or cracks
3775db1d-d6df-5a38-a676-c1854cac5910 | note | Spec. Ref, Procedure Or Method Statement - D18.3 - AS/NZS 3500 - Formed finish F3 as specified in NZS 3114
1d447972-2e28-5540-8f79-2e480fcc70b1 | note | Frequency Of Inspection OR Test - After completion of benching/invert
1e16eda9-8b78-5af2-bb98-2bf971815de7 | note | HOLD POINT - H
9707f6cf-295c-4bdf-8207-73eca8ee5dbe | signoff | HOLD POINT
d20b8225-1bbd-4df5-af75-6935f744a61f | checkpoint | 5 - Manhole Cover and Frame Installation
4569a535-fc8a-5b1d-9c9c-f8120a242378 | note | Controlled By : (Position) - PM
8f9b4876-874d-52c0-9e29-3a70ffaf8fb9 | note | Accept / Reject Criteria - Infiltration check
506a0c44-cbdd-59aa-951b-5e990a27fa91 | note | ○ Visual condition check
ade79895-4742-5270-946c-ad62d2a166b9 | note | ○ Manhole dimensions
fcc682a5-e157-5777-bf82-53763cb4372c | note | ○ Functional access features
67f7e23a-e119-5ae5-aa23-802c5ac460d4 | note | Spec. Ref, Procedure Or Method Statement - D15.2 MATERIALS Maestro DIMHMCFHS MH cover
7235d5df-2103-569b-ab0c-ab508e3ddccd | note | Frequency Of Inspection OR Test - Before handover or commissioning
2e35f744-6503-5f3f-be88-e0b3c54889bf | note | HOLD POINT - H
706e462e-f690-4997-9601-8a0fc6977c7e | signoff | HOLD POINT
2cf88039-0f15-420c-9075-e25b3eaecbdd | checklist | QMD07 ITP-002 - Installation WWMH F20538 | itp | QMD07 ITP-002 - Installation WWMH F20538
032c00f4-32b7-4f77-a6f8-94227d191c4a | section | ITP-002 - Installation WWMH F20538
75bace4e-5863-422d-bcac-98797d86412e | checkpoint | 1 - Manhole base Preparation (Pre-cast or in-situ)
638ddae0-af59-5d07-813d-03fb1f9eb548 | note | Controlled By : (Position) - CR
3998f9be-efe1-5834-a3fc-58019542697f | note | Accept / Reject Criteria - Clean and dry base
9804c8de-e71e-559e-b30b-c5469d7faa11 | note | ○ Correct bedding material and compaction
1b8ecb07-161d-5cd1-a398-6f8cb95b8d6b | note | ○ Reinforcement and formwork inspected
0c15d2a6-fc8b-5b9b-9f44-97fd27ba9f8f | note | ○ Waterproofing components in place
2d707fb9-5ba3-5514-930b-18ba1e82117c | note | Spec. Ref, Procedure Or Method Statement - Project Drawings, D18 Construction Methodology
7815174b-68ce-5b5f-a479-fe2304164184 | note | Frequency Of Inspection OR Test - Prior to placing concrete or setting precast base
a9a97f76-14be-5b24-9fec-d34793b5218e | note | HOLD POINT - I
8f4b7d9a-9221-427a-88c9-6602a285144d | checkpoint | 2 - Manhole Cyclinder Installation
0be7872d-852a-5765-89bd-d5a9e361175b | note | Controlled By : (Position) - FM
9d9a5ee3-56f5-5641-96de-e13be910e3e3 | note | Accept / Reject Criteria - Correct alignment and verticality
41762b21-f0d4-5a86-8650-b8d1dc17a83b | note | ○ Joints sealed with approved material
7cb1369e-cf16-5b67-9a09-c8bbf0add464 | note | ○ Steps/lifting holes sealed
e1b2e81d-ebcc-5ac5-943b-e0fc123147c4 | note | ○ Wall thickness and type verified
0078dbc4-26d4-52ea-a40b-bde6e680d6ba | note | Spec. Ref, Procedure Or Method Statement - D18 – Precast Installations, Manufacturer specs NZS 3109
f928efe6-0473-5cd7-8bde-7ac34c779223 | note | Frequency Of Inspection OR Test - Prior to backfilling
8303cec6-2d85-5776-853d-7cac4ac7d35a | note | HOLD POINT - H
061e655f-b0d5-451c-a801-8ab6aef2c53e | signoff | HOLD POINT
d4e6de70-8260-44bf-8d90-c3bb368fb482 | checkpoint | 3 - Pipe protrusions into manhole
56b67ad3-1512-51a1-8516-aed27543dc0e | note | Controlled By : (Position) - FM
e00cb306-7e3a-5c4d-84b5-8e688df9f15f | note | Accept / Reject Criteria - Flexible joint within 1metre of the manhole
4bdf34b4-7b5c-5b49-af99-ba46f4966ecb | note | Spec. Ref, Procedure Or Method Statement - D18.3 INSTALLATION
65dd8079-b6de-5186-8c42-0bcb598a29d7 | note | Frequency Of Inspection OR Test - Prior to pouring corbels
63615336-35b2-5527-bcad-4dba3a1b48cf | note | HOLD POINT - H
542031a3-8c79-4e40-9b64-b6cea47cb621 | signoff | HOLD POINT
6fa4b21b-797a-4627-b405-48fbc9a5ec0a | checkpoint | 4 - Internal Benching and Channeling
f9470084-2a16-5f27-a965-3190697883fd | note | Controlled By : (Position) - PM
e8b307bd-363a-5f79-895c-42b41a9bd555 | note | Accept / Reject Criteria - Smooth trowelled finish
e8a387e4-f72b-5760-a9f1-59d8b9d3ba17 | note | ○ Accurate channel fall to spec
995c515a-94bc-53ec-81df-2bd4ecd6c26f | note | ○ Benching slope toward channel
5db0a269-a20c-586b-bc4d-7ada82cf812b | note | ○ No honeycombing or cracks
ad934f7c-9375-5a13-b3fe-19b801dfa7be | note | Spec. Ref, Procedure Or Method Statement - D18.3 - AS/NZS 3500 - Formed finish F3 as specified in NZS 3114
641d2cad-2717-56f4-ba35-b1ae5d6103ee | note | Frequency Of Inspection OR Test - After completion of benching/invert
74266671-0b08-5a15-ad2e-fd150aa62a5a | note | HOLD POINT - H
6dd52273-b209-475b-b195-80a73d518645 | signoff | HOLD POINT
fd0f4af6-996a-477d-b5fc-5da8c9c1e4de | checkpoint | 5 - Manhole Cover and Frame Installation
359e0009-df11-5d59-9cab-28b8a7f864f3 | note | Controlled By : (Position) - PM
e7a0ac04-d384-51d8-93c5-db9187629226 | note | Accept / Reject Criteria - Infiltration check
79d23a83-8aed-512e-b9d8-8ab252965ef4 | note | ○ Visual condition check
241caa15-ea7c-51b7-91b6-683f70e6c7f6 | note | ○ Manhole dimensions
8ab4d603-fa5c-5cc8-b227-c66887f0e48d | note | ○ Functional access features
69476f33-960b-550e-9bcb-908256fd28a2 | note | Spec. Ref, Procedure Or Method Statement - D15.2 MATERIALS Maestro DIMHMCFHS MH cover
2274abd2-0a3e-5766-a59b-23e227a732f4 | note | Frequency Of Inspection OR Test - Before handover or commissioning
d6a2d329-f902-53b6-83a8-a3b176f15743 | note | HOLD POINT - H
8cd206f6-aeee-46e1-8d24-b0eee2d00d67 | signoff | HOLD POINT
c8c5fc1a-e65d-4dea-8f69-28f840b30bdf | checklist | QMD07 ITP-003 - Installation SWMH S21358 | itp | QMD07 ITP-003 - Installation SWMH S21358
86348736-e869-4791-9b44-a4888c23744d | section | ITP-003 - Installation SWMH S21358
ceb89dfc-c5c9-461f-9066-926ccf14ba47 | checkpoint | 1 - Manhole base Preparation (Pre-cast or in-situ)
c51baf2e-b1e1-5ab0-a314-2ea5422c5ad4 | note | Controlled By : (Position) - CR
27338d7c-d2e0-5c7b-b269-0c9336708a5e | note | Accept / Reject Criteria - Clean and dry base
b6437805-5815-581b-8f7a-4e3e759ca41c | note | ○ Correct bedding material and compaction
95424d85-5084-5019-8767-70a06df7953b | note | ○ Reinforcement and formwork inspected
927b69fc-e30d-5d01-b734-88c0553bffc4 | note | ○ Waterproofing components in place
e390fdb3-0834-5907-b10e-7f0d6adc83cb | note | Spec. Ref, Procedure Or Method Statement - Project Drawings, D18 Construction Methodology
77eb6e62-cf28-5079-82a2-6b1b5d144a83 | note | Frequency Of Inspection OR Test - Prior to placing concrete or setting precast base
bc7f405a-d6c4-553a-b867-dbbe069f1ca2 | note | HOLD POINT - I
91419e1d-cf02-483e-af56-47359be0146c | checkpoint | 2 - Manhole Cyclinder Installation
da375ee6-4286-56f7-a43d-54f534c93425 | note | Controlled By : (Position) - FM
000b21fe-f337-5ccf-a044-5c6d6ff53d65 | note | Accept / Reject Criteria - Correct alignment and verticality
c2233d36-8069-51d8-81f5-bfbe3a2f6e25 | note | ○ Joints sealed with approved material
4221bd58-1dc9-5561-b16f-6c9a11b9c64f | note | ○ Steps/lifting holes sealed
a071565a-efcf-5c2c-a544-4965430a3a1a | note | ○ Wall thickness and type verified
d51c71f8-92a9-5a56-b736-a3d6b1e28c0e | note | Spec. Ref, Procedure Or Method Statement - D18 – Precast Installations, Manufacturer specs NZS 3109
ed4e04d3-8172-58bf-a57d-7b2fae7cb267 | note | Frequency Of Inspection OR Test - Prior to backfilling
0566d108-048b-5c0d-9302-e374eb62f3b9 | note | HOLD POINT - H
ac2e04e3-232e-4eaa-8dfa-baf3a83fa5f4 | signoff | HOLD POINT
454466c7-f13f-4a29-9f6b-03c3827aec4f | checkpoint | 3 - Pipe protrusions into manhole
665fc073-acd0-5dd4-9b65-d5ec86fb7710 | note | Controlled By : (Position) - FM
a7969ad2-d036-53a5-b492-e3e58170cbfd | note | Accept / Reject Criteria - Flexible joint within 1metre of the manhole
b7204a07-9d5e-5600-8c53-d1c634f85980 | note | Spec. Ref, Procedure Or Method Statement - D18.3 INSTALLATION
55424d39-18ea-5512-ad0d-f57d58a96dcf | note | Frequency Of Inspection OR Test - Prior to pouring corbels
c9677aae-ac57-5184-89d6-14e001060107 | note | HOLD POINT - H
b7967b3a-a40a-477e-8489-24aad3bfc812 | signoff | HOLD POINT
aa5ded48-4dce-4618-b26e-06ea0a3c393e | checkpoint | 4 - Internal Benching and Channeling
05eb10a1-6330-5086-8100-3d205d75c2b0 | note | Controlled By : (Position) - PM
7b3c44b6-9dd7-58c2-841f-25ade2b4cdfe | note | Accept / Reject Criteria - Smooth trowelled finish
03a9a86b-dd23-574a-a37e-fa3cc894b3ff | note | ○ Accurate channel fall to spec
8e32fd5a-6c93-5ebb-9df2-9529a06cbe8d | note | ○ Benching slope toward channel
5f0a3991-371c-509d-b3ee-cbdcf6cbfaac | note | ○ No honeycombing or cracks
f92946ce-f53f-5e2f-8751-267bbb7da5fa | note | Spec. Ref, Procedure Or Method Statement - D18.3 - AS/NZS 3500 - Formed finish F3 as specified in NZS 3114
3ad9af25-d9d5-5383-8e9c-c839afc94bc5 | note | Frequency Of Inspection OR Test - After completion of benching/invert
7465240d-e365-5fea-9553-872735e145c8 | note | HOLD POINT - H
96f1da6c-aaec-4a30-ab7f-ba56402376f2 | signoff | HOLD POINT
9e53d52d-6c79-4a95-9002-35ebc41a52af | checkpoint | 5 - Manhole Cover and Frame Installation
f2dfbf25-64ec-5fcd-9e4c-5a36a20ffa5a | note | Controlled By : (Position) - PM
ec8d76d5-0846-5d54-9677-4ef27b39ae25 | note | Accept / Reject Criteria - Infiltration check
651b2e67-fc91-5c58-a42d-a48711c315d6 | note | ○ Visual condition check
c7177211-911a-53f2-9b9a-2332cf646a10 | note | ○ Manhole dimensions
7cf96106-c7e9-5650-9d61-7c175e02b296 | note | ○ Functional access features
6c0ad284-b5e6-52d4-8bd6-5c36e4d4c863 | note | Spec. Ref, Procedure Or Method Statement - D15.2 MATERIALS Maestro DIMHMCFHS MH cover
be8f7feb-9192-5123-b0bb-139eb12b2b38 | note | Frequency Of Inspection OR Test - Before handover or commissioning
019f381b-6df5-5fe2-8c13-ce4af17b2362 | note | HOLD POINT - H
bafc9631-dac7-41d5-a481-f409632cfd9a | signoff | HOLD POINT
f894a851-43a2-405b-9e1a-9c1533c81cda | checklist | QMD07 ITP-004 - Installation SWMH S21359 | itp | QMD07 ITP-004 - Installation SWMH S21359
5ae557a6-40bd-4490-b7d0-e1c2a0b7e1b2 | section | ITP-004 - Installation SWMH S21359
4e6d2606-8318-4529-987c-e7abfbc7c18b | checkpoint | 1 - Manhole base Preparation (Pre-cast or in-situ)
f7095f06-bf6d-505e-8a03-075bcb6e2cea | note | Controlled By : (Position) - CR
d7bee61b-ebca-5c2e-905a-d9cc189c04ed | note | Accept / Reject Criteria - Clean and dry base
cd6f166d-a1c7-5767-afd3-4b5feab03ad9 | note | ○ Correct bedding material and compaction
b2050c96-6801-53eb-b0c8-f46209047488 | note | ○ Reinforcement and formwork inspected
7f2797f0-e64b-5f2a-9ad9-cdf378d02d0a | note | ○ Waterproofing components in place
8b66ad15-509e-5d19-b7a2-3db904ffa010 | note | Spec. Ref, Procedure Or Method Statement - Project Drawings, D18 Construction Methodology
8f626e8a-a137-5305-8d16-6208bccd8b8b | note | Frequency Of Inspection OR Test - Prior to placing concrete or setting precast base
29259242-1dea-5e6f-be90-cd1321e06955 | note | HOLD POINT - I
d7b3ed24-254e-46a4-b4a6-8fabcafcaa7d | checkpoint | 2 - Manhole Cyclinder Installation
d729e783-f33c-5781-80c2-644f6df53d41 | note | Controlled By : (Position) - FM
66430dda-8119-54cf-9c7a-75926566aa47 | note | Accept / Reject Criteria - Correct alignment and verticality
bcd979cb-4e93-5f86-9d6b-59d4e8ffe201 | note | ○ Joints sealed with approved material
74985713-821d-54ae-9693-1ea4fc53e60a | note | ○ Steps/lifting holes sealed
a7ffb72d-b4f9-54ea-ac3f-98c313700318 | note | ○ Wall thickness and type verified
9fee9966-7965-5ea8-abfc-2c51172b9921 | note | Spec. Ref, Procedure Or Method Statement - D18 – Precast Installations, Manufacturer specs NZS 3109
0ec34219-8b5a-5239-b24f-3a9acb9d6bf2 | note | Frequency Of Inspection OR Test - Prior to backfilling
fb830e02-6b39-5ff9-8ecc-81a0660d2e9c | note | HOLD POINT - H
08cf7ddb-fba4-42ed-ba26-c08d875d267c | signoff | HOLD POINT
7c1f59fe-80af-4a32-8369-194c34c5fb82 | checkpoint | 3 - Pipe protrusions into manhole
80eb8ef0-0a4d-5737-834c-3b6085a4109c | note | Controlled By : (Position) - FM
a2bae06a-30bc-50b2-9509-3c16fe700b7e | note | Accept / Reject Criteria - Flexible joint within 1metre of the manhole
43b6e345-586c-5d44-908c-796df108c8d7 | note | Spec. Ref, Procedure Or Method Statement - D18.3 INSTALLATION
586e818d-d327-5590-8268-65d38f7d1bff | note | Frequency Of Inspection OR Test - Prior to pouring corbels
95bba6df-658b-5a73-ba00-68244dfcf119 | note | HOLD POINT - H
2c311121-a6e2-41e1-b6a7-c0d7fc0ed7a6 | signoff | HOLD POINT
6ba78cc0-a624-4caf-9485-f32c427ac957 | checkpoint | 4 - Internal Benching and Channeling
62e3be51-5275-5bbe-8746-7544aa4ddf1e | note | Controlled By : (Position) - PM
f4e87113-80f0-5912-aade-28ab48e087d2 | note | Accept / Reject Criteria - Smooth trowelled finish
88a4b1fb-1222-5f3b-a278-02e275b80bf9 | note | ○ Accurate channel fall to spec
53904532-e7fb-509d-8ca3-8de1811b3591 | note | ○ Benching slope toward channel
1826f8cb-7039-5e48-b827-03d1156956bd | note | ○ No honeycombing or cracks
d1323441-3d47-5d87-bdb4-2c2c1937dcaf | note | Spec. Ref, Procedure Or Method Statement - D18.3 - AS/NZS 3500 - Formed finish F3 as specified in NZS 3114
614651be-eeee-54af-8700-487717388551 | note | Frequency Of Inspection OR Test - After completion of benching/invert
dfcae449-5745-5ff8-8f1b-6801b91a05ca | note | HOLD POINT - H
a41f7d93-e501-40c0-a34d-2ac4dbb318e1 | signoff | HOLD POINT
b7d02337-997c-4167-a780-30a882e5b947 | checkpoint | 5 - Manhole Cover and Frame Installation
ec2760c1-581c-5988-abe6-1bdac8624812 | note | Controlled By : (Position) - PM
63e6527f-4865-5542-9598-8bf9d7196016 | note | Accept / Reject Criteria - Infiltration check
abbb571f-220c-5634-94cd-b7ccf537a5c1 | note | ○ Visual condition check
d7fcd23f-6833-559d-81a3-8535edb06b72 | note | ○ Manhole dimensions
eb824c79-0057-5dd2-a412-956fcf864c4d | note | ○ Functional access features
4f843702-c2b8-5f1b-a0c5-9a8ca922ff52 | note | Spec. Ref, Procedure Or Method Statement - D15.2 MATERIALS Maestro DIMHMCFHS MH cover
8f92a0fa-aed7-557a-9b00-d9213f3093c4 | note | Frequency Of Inspection OR Test - Before handover or commissioning
c713ad4b-fc6b-50c1-aedb-2345fc111084 | note | HOLD POINT - H
71fd92e4-5f8d-4d9e-9860-d05afde5413d | signoff | HOLD POINT
cdbf17ce-15ec-4a0f-aa7a-b2c6d7fe0475 | checklist | QMD07 ITP-005 - Installation Water main and Structures | itp | QMD07 ITP-005 - Installation Water main and Structures
4799f4b3-4273-403f-a1d2-c4420f242c9b | section | ITP-005 - Installation Water main and Structures
0e7bab3c-2b22-45e0-8074-c48f2be83acf | checkpoint | 1 - Excavation
801448b6-d1dc-5110-be2a-27d3bd646a6a | note | Controlled By : (Position) - FM
c17bdc80-a843-5a0f-a156-64c4b2239db5 | note | Accept / Reject Criteria - Excavation depth, bedding material, trench width
a2e7b808-1613-5d84-b66f-927e45b58e6e | note | Spec. Ref, Procedure Or Method Statement - D2 Buried Pipelines NZS 4404, AS/NZS 2566.2
63fa1a56-f489-56bb-bdf8-373e87708a77 | note | Frequency Of Inspection OR Test - As works progress
c803eda0-2330-5d99-8f95-b595b8dd4c97 | note | HOLD POINT - S
55f345e5-fb82-45bd-93a7-e34254bca038 | checkpoint | 2 - Pipe material delivery and storage
7156ec64-4728-57d7-89b6-4e956a6f86a5 | note | Controlled By : (Position) - FM/CR
5b456097-44e2-5d2c-af94-ea183be28823 | note | Accept / Reject Criteria - Inspection for damage, conformity with specs
5f6700f2-b17f-5de6-9cfb-b1f4c6f3cedd | note | Spec. Ref, Procedure Or Method Statement - D1.24
66923be8-d86b-52e3-b93f-a5945dcb169a | note | Frequency Of Inspection OR Test - Upon arrival
acb80ec6-dba0-5655-82ce-cd5782477f46 | note | HOLD POINT - I
dcc79881-b1a8-424f-ae5f-f067fa47e417 | checkpoint | 3 - Pipe laying (PE/ductile iron)
8a8466db-f892-5c80-a92f-a28757ebf677 | note | Controlled By : (Position) - FM
80b536c0-ad87-521a-a679-dcf6386b163d | note | Accept / Reject Criteria - Alignment, gradient, jointing method
e16c9eff-5f88-5379-bfe4-9fec7f620f4c | note | Spec. Ref, Procedure Or Method Statement - D2, AS/NZS 2566.2
96516771-9a7a-5305-b87a-e4d7a4085367 | note | Frequency Of Inspection OR Test - As works progress
95b480f9-3ee0-59c7-8884-f0dac97ec346 | note | HOLD POINT - S
a3c25c33-a83e-4836-b370-f19f2e69b344 | checkpoint | 4 - Valve and fitting installation
6f48d0df-c45b-5d09-aea8-3d5d61744206 | note | Controlled By : (Position) - FM
829cc025-f4c0-5b5d-8366-642a15f51a16 | note | Accept / Reject Criteria - Correct location, bedding, supports
493ac102-6c16-5358-859f-3de11ef5e337 | note | Spec. Ref, Procedure Or Method Statement - D5, AS/NZS 2280
96c26baf-78ae-58a6-8a55-740fb1635694 | note | Frequency Of Inspection OR Test - After completion of each valve and fitting installed
10e2f0ca-e79a-52c4-8e85-447c7464d354 | note | HOLD POINT - H
b7b230bb-e0f3-47fb-9a08-ddb5824131ca | signoff | HOLD POINT
352f8cea-b48b-4611-a2d8-a48b0953eb99 | checkpoint | 5 - Thrust blocks / anchor blocks
f3a248f1-03ff-5b45-aa09-bfdf4eee596a | note | Controlled By : (Position) - FM
e8dc3f9f-5dd6-5916-b12a-f9bb2a337a0b | note | Accept / Reject Criteria - Dimensions, concrete strength, curing
961ffaa6-5618-54ac-ab5c-8eafae18fb91 | note | Spec. Ref, Procedure Or Method Statement - D5.7, NZS 4404
c4f7c5d9-9488-5fc3-9e6c-9ebba9bb18f3 | note | Frequency Of Inspection OR Test - After completion of each thrust block
bd72b518-0aa0-5a36-b58f-18b27f680d82 | note | HOLD POINT - H
dac1886e-048a-49c2-8372-c43f832e29ab | signoff | HOLD POINT
0928c06d-fbe2-4800-97fb-cf9ecdc68265 | checkpoint | 6 - Pipe bedding and backfilling
ae9310a1-2548-5444-888b-54ddb13fc6e1 | note | Controlled By : (Position) - FM
a7569e9b-986b-56c0-9895-c0b8fb30a22b | note | Accept / Reject Criteria - Correct layer thickness, compaction testing
9844bbf9-11f2-5455-a1ee-6e10b0d3851c | note | Spec. Ref, Procedure Or Method Statement - D2.7, AS/NZS 2566.2
dc56a9b2-ef5a-5dd1-8ff8-6733aa1f6b14 | note | Frequency Of Inspection OR Test - As works progress
c49c3c3c-1416-54d4-a76e-133d02e19825 | note | HOLD POINT - S
375bd98e-2697-4910-83fb-088e5a53372e | checkpoint | 7 - Lateral Installation
7e5fd2d3-1d3e-5794-b600-28da93f30c4e | note | Controlled By : (Position) - FM
7f13931e-09f3-51c0-bcd9-6ce75eee45e0 | note | Accept / Reject Criteria - Alignment, jointing method
3afe73c9-bd4e-5bbd-a570-b72fae6dbdc0 | note | Spec. Ref, Procedure Or Method Statement - D8, AS/NZS 2566.2
002dd793-1ab3-5216-9aa1-2a6416810873 | note | Frequency Of Inspection OR Test - As works progress
7813b28e-3719-5b2e-85d3-31b0e3509e3f | note | HOLD POINT - S
1de14061-0335-426d-aa12-e6108f83592b | checkpoint | 8 - Hydrostatic pressure testing
22176050-b6ff-5b88-b3f1-008a400c5539 | note | Controlled By : (Position) - PM/CR
d05b0035-9ecf-5ae9-bc7d-8eedaf3215a9 | note | Accept / Reject Criteria - M7 Pressure rebound test
92248b2e-a7e9-509e-ad91-af58d8520bac | note | Spec. Ref, Procedure Or Method Statement - D2.9, AS/NZS 2566.2
87d44817-a58a-561f-85fb-dc286353215a | note | Frequency Of Inspection OR Test - Prior to comission
f2a34fc6-37af-50dd-8cc3-f3ba98caaba1 | note | HOLD POINT - I
5cbe70c8-297c-4034-96e4-87e4d531e073 | checkpoint | 9 - Disinfection and flushing
fa2162ab-1bf6-5569-9b4a-868171a5c17c | note | Controlled By : (Position) - PM/CR
2d651a3b-3d6e-5351-843e-c69a86455f2f | note | Accept / Reject Criteria - Chlorination to 50 mg/L, 24 hr retention, residual test
becc7c79-a4ac-53b0-88e6-01503078b1bf | note | Spec. Ref, Procedure Or Method Statement - D2.9, AS/NZS 4020, MoH Drinking Water Standards
aa2ae0d7-bf12-5d04-a963-021cc22ab1e5 | note | Frequency Of Inspection OR Test - Prior to comission
a0d5aa3d-ed87-5481-8c58-eaa54ca310f4 | note | HOLD POINT - I
303925bf-e324-41f0-94d3-6d87073b8508 | checkpoint | 10 - Final connections and commissioning
f4af8e09-97b1-5b39-9cfe-fa0d7632b22a | note | Controlled By : (Position) - FM
887b80e7-006a-5a87-9a16-877faa223988 | note | Accept / Reject Criteria - Visual inspection, isolation checks, flow direction
ecaa5393-461d-5749-b353-54c3695b306c | note | Spec. Ref, Procedure Or Method Statement - D2, NZS 4404
8d588590-fa4e-5bd2-bdd9-8d57bbe733a7 | note | Frequency Of Inspection OR Test - As works progress
50a469d8-b3a3-5c54-b533-f717e24f7771 | note | HOLD POINT - H
a5a3b535-dd57-4459-a4e0-53880c202926 | signoff | HOLD POINT
78cfced9-49e7-421d-a759-65f3bf0c473b | checklist | QMD07 ITP-006 - Installation Foulsewer main F13717 | itp | QMD07 ITP-006 - Installation Foulsewer main F13717
48f3caa7-9546-4d06-8ebc-a7ee4e17b8e8 | section | ITP-006 - Installation Foulsewer main F13717
c1237603-07b4-4454-a34b-b9e110a23b63 | checkpoint | 1 - Excavation
b7c68eb0-9545-586b-b12e-746a8b446b38 | note | Controlled By : (Position) - FM
5f760f80-232e-5f86-aba2-6d8cf35f2e6d | note | Accept / Reject Criteria - Excavation depth, bedding material, trench width
7ad833d6-579b-5cc6-84f3-400dd3101c34 | note | Spec. Ref, Procedure Or Method Statement - D2 Buried Pipelines NZS 4404, AS/NZS 2566.2
78276483-e490-5798-89bc-849e21e5baeb | note | Frequency Of Inspection OR Test - As works progress
f756b0ad-c44e-5dad-91ec-73c695db66bd | note | HOLD POINT - S
096038a7-aa82-46b8-887c-2fa3523b5db5 | checkpoint | 2 - Pipe material delivery and storage
078c3277-a900-517b-9567-152019cbd202 | note | Controlled By : (Position) - FM/CR
cb3485c2-86af-57a2-bca1-c9cbf940dc03 | note | Accept / Reject Criteria - Inspection for damage, conformity with specs
8bffe1bc-84e1-5834-8ba3-e4edff64743a | note | Spec. Ref, Procedure Or Method Statement - D1.24
ba92fc92-e1ff-5e39-938e-f509d2a2a295 | note | Frequency Of Inspection OR Test - Upon arrival
1fdf6777-d9f4-534e-ac63-ef4feb73f922 | note | HOLD POINT - I
9ebf3058-6edf-41f6-9521-2c07d8ac62c4 | checkpoint | 3 - Pipe laying (uPVC)
e57a26e7-d321-504d-bd74-472aa66cb249 | note | Controlled By : (Position) - FM
f31011de-3d50-5339-9427-eb06c59da31f | note | Accept / Reject Criteria - Alignment, gradient, jointing method
b79323a2-cedc-56ab-b47c-2333224682a0 | note | Spec. Ref, Procedure Or Method Statement - D2.7 - AS/NZS 2566.2
36ee25e5-5895-5896-aee2-aaff1777cf82 | note | Frequency Of Inspection OR Test - As works progress
502d1dea-2489-565a-974e-807bee806a93 | note | HOLD POINT - S
6cebf68d-d920-40ab-8505-2db77f8d7b5e | checkpoint | 4 - Compaction of backfill material
df3205aa-b240-56cf-a0dd-5cd48ceaa608 | note | Controlled By : (Position) - FM
c04497ef-ac0a-5ddd-b5d6-a0c0017fb97e | note | Accept / Reject Criteria - Correct aggregates, 200mm layer depth, Plateau test, clegg readings, NDM testing
f656d1a3-f9c6-5423-9cff-a3db7c313809 | note | Spec. Ref, Procedure Or Method Statement - D2.7.7 - AS/NZS 2566.2
e1e6ca3f-90ab-5174-8b43-81d635aadbaf | note | Frequency Of Inspection OR Test - 200mm layers
578a471c-2964-5932-a69d-b70afbd90527 | note | ○ Clegg result every 6m
96d3ceea-a27c-5dd7-b1da-7f901bd0f4ea | note | ○ NDM result every 120m
1370beae-9052-5a61-913a-cdf7a8cdc3c2 | note | HOLD POINT - S
33e289bd-9fa0-4d62-97fb-2c3c05108e06 | checkpoint | 5 - Lateral Installation
8c2cf874-78a4-5c2a-ad40-3c8180b4100b | note | Controlled By : (Position) - FM
c3893eda-45a2-5d69-8c41-41d7707a64d8 | note | Accept / Reject Criteria - Alignment, gradient, jointing method, concrete around junctions and bends as required
232377e1-5918-5c17-a44f-b67ee057091d | note | Spec. Ref, Procedure Or Method Statement - D4 - AS/NZS 2566.2
22fc1d8e-4c59-5880-9232-e9c8f214ca7f | note | Frequency Of Inspection OR Test - As works progress
e7fd41cf-09fb-5f2d-9596-0bccf6c97076 | note | HOLD POINT - S
ee297e69-9fe0-473c-8b77-783bcc42368c | checkpoint | 6 - Foul Sewer main pressure testing
6c6744bc-833c-52a1-8b79-3f02665d0261 | note | Controlled By : (Position) - FM/CR
ae752ea8-f823-52b6-a1eb-e454fb7a387a | note | Accept / Reject Criteria - Leakage testing including laterals
f7ac3c8b-fd95-5ab0-9d10-7d303b83235f | note | Spec. Ref, Procedure Or Method Statement - D2.9 - AS/NZS 2566.2
d3bbf263-11d7-5b3c-bde6-5487c89340a0 | note | Frequency Of Inspection OR Test - After completion of main and lateral installation
4c47be51-e52f-56e0-845b-de004b45c3a1 | note | HOLD POINT - I
d9dee524-53c4-4eb6-b876-f6d23af17f2c | checkpoint | 7 - Pipe bedding and backfilling
6ec6fe8c-0920-5e26-8057-4ba25bbf22a6 | note | Controlled By : (Position) - FM
c7aba561-ef1d-5e82-9859-128ceac38875 | note | Accept / Reject Criteria - Correct layer thickness, compaction testing
2f8d8da4-36b2-5a61-be65-8ab7c272c41a | note | Spec. Ref, Procedure Or Method Statement - D2.7 - AS/NZS 2566.2
ff65d1cc-b8cb-502b-a7fc-f3c6cb4bdb66 | note | Frequency Of Inspection OR Test - As works progress
430bb02d-1a5d-5fbe-a209-c49a558a16c0 | note | HOLD POINT - S
b0d5a23e-00de-4e68-8b8a-d2852a26f6aa | checkpoint | 8 - Cleaning and CCTV new main
efc3edf6-8e2e-59f5-8796-544002f608b2 | note | Controlled By : (Position) - PM
2d6532eb-a1c0-5431-8503-d9c67d298740 | note | Accept / Reject Criteria - No debris or defects
3a039636-1223-5469-8a70-b4528dbf6449 | note | Spec. Ref, Procedure Or Method Statement - D2.9 - AS/NZS 2566.2
32c68e37-d6c4-53f5-bd09-dcfcf45f0d16 | note | Frequency Of Inspection OR Test - Prior to comission
995ed1a9-e0d3-5892-b6af-22e67fbca302 | note | HOLD POINT - I
fa8800f3-cf8a-4679-84a4-b87e29ca2141 | checklist | QMD07 ITP-007 - Installation Foulsewer main F13725 | itp | QMD07 ITP-007 - Installation Foulsewer main F13725
1d88f00c-c458-427c-bdf5-956a5005da40 | section | ITP-007 - Installation Foulsewer main F13725
f9f113a0-f3f1-4fae-9c4e-53c8dc621b3f | checkpoint | 1 - Excavation
d1982159-6a5b-5fb9-ad51-6fa62d06896c | note | Controlled By : (Position) - FM
a9b75f1c-8d1f-5966-b0d0-810b0c585797 | note | Accept / Reject Criteria - Excavation depth, bedding material, trench width
2695e576-c4a3-5f5d-8526-a84a6ca06bde | note | Spec. Ref, Procedure Or Method Statement - D2 Buried Pipelines NZS 4404, AS/NZS 2566.2
38e5cfad-edc3-5bd8-a842-70bec279ffbf | note | Frequency Of Inspection OR Test - As works progress
a0830f5b-7d62-545a-a382-12e290744805 | note | HOLD POINT - S
447d14d5-a114-47c8-8744-f9aee2cd27a3 | checkpoint | 2 - Pipe material delivery and storage
2f464e5f-82c4-58fc-a6f7-b4b7d05e7560 | note | Controlled By : (Position) - FM/CR
45f1510a-5ed0-5ffa-be14-6bd05ebc20b5 | note | Accept / Reject Criteria - Inspection for damage, conformity with specs
a5c69461-70a4-5c12-901d-2bbb9d2c2c64 | note | Spec. Ref, Procedure Or Method Statement - D1.24
a77e1c00-edee-5517-9ae0-23d0e1472700 | note | Frequency Of Inspection OR Test - Upon arrival
e38b1e2d-e3ea-54ad-abdd-fc7b9ff69f8a | note | HOLD POINT - I
8215d845-2992-4734-a27c-be7a5630c0c6 | checkpoint | 3 - Pipe laying (uPVC)
19316985-2369-5451-9abc-93932a681678 | note | Controlled By : (Position) - FM
ff7b9031-39db-5845-bbf2-4123b42e5e86 | note | Accept / Reject Criteria - Alignment, gradient, jointing method
cbed2146-73ad-5ecb-aeef-8c0af3f937d8 | note | Spec. Ref, Procedure Or Method Statement - D2.7 - AS/NZS 2566.2
80fa40b1-4bc3-5823-8211-5e15aa3782d2 | note | Frequency Of Inspection OR Test - As works progress
a159ade6-f6a2-599b-a64e-670d048d8f2b | note | HOLD POINT - S
50b81f73-3d61-4f8a-92a0-af0381d0ccf7 | checkpoint | 4 - Compaction of backfill material
49b7b7eb-2a8d-575b-80c7-5a6ce001fa6f | note | Controlled By : (Position) - FM
32f8fc59-e974-5855-8388-ea7705c2eac7 | note | Accept / Reject Criteria - Correct aggregates, 200mm layer depth, Plateau test, clegg readings, NDM testing
a70e27cb-a82c-5688-bcec-be5fee2f822c | note | Spec. Ref, Procedure Or Method Statement - D2.7.7 - AS/NZS 2566.2
bc46cdde-1135-5a80-bc2a-2ce7e8d394a4 | note | Frequency Of Inspection OR Test - 200mm layers
cac55182-80ef-5a7c-928c-2975ffe27084 | note | ○ Clegg result every 6m
28a57b9c-f7f5-5cad-b904-d25282a3cd83 | note | ○ NDM result every 120m
9ec9657a-4a39-5809-80d6-933e418f98b7 | note | HOLD POINT - S
860ede68-8435-4f12-bd34-197abce55376 | checkpoint | 5 - Lateral Installation
c1c902a5-045b-5345-bc3e-d1d01cebb0f8 | note | Controlled By : (Position) - FM
ee2740bf-ae44-5eb8-9521-de1ce139221d | note | Accept / Reject Criteria - Alignment, gradient, jointing method, concrete around junctions and bends as required
659b0868-58e9-5672-8ef8-5909e9f74454 | note | Spec. Ref, Procedure Or Method Statement - D4 - AS/NZS 2566.2
cffee6a2-60a8-51a9-ad4b-1120fafa97a5 | note | Frequency Of Inspection OR Test - As works progress
9cd06579-0619-579b-9580-ded0e3d002b8 | note | HOLD POINT - S
fbe925d3-21f8-4ddc-a691-bd84a9c1a171 | checkpoint | 6 - Foul Sewer main pressure testing
228382b7-0f9b-5d02-bf1e-d02b29628930 | note | Controlled By : (Position) - FM/CR
82b8f962-ad85-5165-9612-bc2aab506e4e | note | Accept / Reject Criteria - Leakage testing including laterals
22d6c52c-3246-557a-9b10-1e70ef9c873a | note | Spec. Ref, Procedure Or Method Statement - D2.9 - AS/NZS 2566.2
a9f1082a-e67d-5e7b-93c9-c57f87b7dc66 | note | Frequency Of Inspection OR Test - After completion of main and lateral installation
efb04786-5a11-5a5c-a79c-f239656bb28a | note | HOLD POINT - I
0d4d4b8a-4b63-48e6-8a78-bb4a055f49fb | checkpoint | 7 - Pipe bedding and backfilling
056433a7-ec76-58bc-8aa8-40ee24024968 | note | Controlled By : (Position) - FM
1225423f-5441-59ae-82ab-d38ce43292cc | note | Accept / Reject Criteria - Correct layer thickness, compaction testing
b6d03dc8-bd50-5ef9-b67a-9317d6ff2ca9 | note | Spec. Ref, Procedure Or Method Statement - D2.7 - AS/NZS 2566.2
a09b9cd9-a8c1-5033-9264-76715d024193 | note | Frequency Of Inspection OR Test - As works progress
2d6c8b2a-b046-59d8-8380-781802e11a49 | note | HOLD POINT - S
73a9e837-a459-402f-8f1d-ef22e65cb47a | checkpoint | 8 - Cleaning and CCTV new main
ae37dc59-1c5a-5193-a81f-b57c7f3796b4 | note | Controlled By : (Position) - PM
b56da38a-1ae7-580b-af44-e51159156707 | note | Accept / Reject Criteria - No debris or defects
33b6147b-c974-524a-a633-e521eb083e78 | note | Spec. Ref, Procedure Or Method Statement - D2.9 - AS/NZS 2566.2
37c7cb20-db83-5ef3-9244-2ceb85197a96 | note | Frequency Of Inspection OR Test - Prior to comission
5298e1ff-e1a3-5962-a705-2195c152af00 | note | HOLD POINT - I
b3f3a3f0-01df-4f7d-8f75-8a6db601eaa0 | checklist | QMD07 ITP-008 - Installation Stormwater main S13459 | itp | QMD07 ITP-008 - Installation Stormwater main S13459
3d22bfe3-fa1a-4915-ab28-c29406ba6036 | section | ITP-008 - Installation Stormwater main S13459
fc0e209a-33db-4ca7-8c3c-8b98a67655ea | checkpoint | 1 - Excavation
6f0636e8-2c6a-59f8-bbad-7a04ce39c1a7 | note | Controlled By : (Position) - FM
3efc8fd5-b331-57e4-a1ce-9a85ee84ea92 | note | Accept / Reject Criteria - Excavation depth, bedding material, trench width
fa88c9fd-f48b-51df-b6df-a83c0bf0bf03 | note | Spec. Ref, Procedure Or Method Statement - D2 Buried Pipelines NZS 4404, AS/NZS 2566.2
0b16bc44-3e7a-538f-b670-4c5d9851f199 | note | Frequency Of Inspection OR Test - As works progress
d0cccf27-74df-5166-8c09-018e1293e0e0 | note | HOLD POINT - S
19139cea-b6d0-4593-974f-1a5468b84539 | checkpoint | 2 - Pipe material delivery and storage
a219f6ed-d12b-55f3-9ff2-4eb18e9e0611 | note | Controlled By : (Position) - FM/CR
5deab325-365f-53fa-a139-f6fd21e9dd9a | note | Accept / Reject Criteria - Inspection for damage, conformity with specs
8e926ade-58d5-5bf8-90c3-770f6c43f993 | note | Spec. Ref, Procedure Or Method Statement - D1.24
35246fb2-c783-5f3c-9673-1b0bea1032a3 | note | Frequency Of Inspection OR Test - Upon arrival
af00527b-57e9-5640-867c-a668d170fbde | note | HOLD POINT - I
5c2a1a79-4701-4537-98a7-9ca1bba3b2c8 | checkpoint | 3 - Pipe laying (uPVC)
b513c83a-5228-5b99-8cff-ecbd984bc91e | note | Controlled By : (Position) - FM
f118305b-d97c-59e2-8518-9454c764165b | note | Accept / Reject Criteria - Alignment, gradient, jointing method
cfd9fe1a-24be-56f8-ac75-042016e1af44 | note | Spec. Ref, Procedure Or Method Statement - D2.7 - AS/NZS 2566.2
3042b30d-cb4f-5f87-92de-c1d8168d1c84 | note | Frequency Of Inspection OR Test - As works progress
83667c5b-91c4-5e19-ba04-5e82e986bb71 | note | HOLD POINT - S
526ca38d-ecaa-4b1b-999d-9b688fc765d0 | checkpoint | 4 - Compaction of backfill material
ea9baa38-96d0-56e3-ba84-9fee62db1f23 | note | Controlled By : (Position) - FM
7bf9be77-4350-5a43-a5f3-dfde7deaeace | note | Accept / Reject Criteria - Correct aggregates, 200mm layer depth, Plateau test, clegg readings, NDM testing
ffdff1bc-0633-514e-83d8-c20e14376b56 | note | Spec. Ref, Procedure Or Method Statement - D2.7.7 - AS/NZS 2566.2
f953e855-dd02-5cee-8bdc-6f04c74fab11 | note | Frequency Of Inspection OR Test - 200mm layers
7f610c08-405c-59e7-b52e-8dc7c0c5211f | note | ○ Clegg result every 6m
8cf1ea57-879f-5dbe-99df-3273fb2c29bd | note | ○ NDM result every 120m
4838643c-d965-5d97-9cfe-6e32956c90c6 | note | HOLD POINT - S
831ea854-911f-456d-8a4c-bb7fbb24abb0 | checkpoint | 5 - Lateral Installation
84742182-4d9c-50bf-b5b2-3911502261d0 | note | Controlled By : (Position) - FM
cb404f45-71d2-57d7-8004-35ac1c73047f | note | Accept / Reject Criteria - Alignment, gradient, jointing method, concrete around junctions and bends as required
d816070c-810f-5b71-9e1a-f97151057d3b | note | Spec. Ref, Procedure Or Method Statement - D4 - AS/NZS 2566.2
053fdf72-b40d-572a-a9bc-8bef3659f1b4 | note | Frequency Of Inspection OR Test - As works progress
7feffed6-7e1e-5755-bad0-080c2748028f | note | HOLD POINT - S
3151551c-ff0c-469e-adde-2a22860306af | checkpoint | 6 - Pipe bedding and backfilling
97d09dcd-cb45-564e-8f38-bd8e53227d96 | note | Controlled By : (Position) - FM
fa24f8a7-2c14-5e63-9688-355da211b75a | note | Accept / Reject Criteria - Correct layer thickness, compaction testing
5c51423b-4913-5daf-8723-abafd6bf1bb2 | note | Spec. Ref, Procedure Or Method Statement - D2.7 - AS/NZS 2566.2
76a986ff-236b-56cb-a43f-c5de9bb62904 | note | Frequency Of Inspection OR Test - As works progress
c03b5ce8-f0dd-5d90-a044-53f98e2f76ec | note | HOLD POINT - S
a30b6fbf-662d-46df-af84-e1a3b4ee032a | checkpoint | 7 - Cleaning and CCTV new main
06e8a11f-6049-56e5-affa-bbe9757437a7 | note | Controlled By : (Position) - PM
861c3e92-2a9a-5aff-ad78-5e149ec4f72e | note | Accept / Reject Criteria - No debris or defects
bbed4035-f39d-5a3a-881f-24668aadcff4 | note | Spec. Ref, Procedure Or Method Statement - D2.9 - AS/NZS 2566.2
0e2ad07f-4693-52e9-9200-281d28742964 | note | Frequency Of Inspection OR Test - Prior to comission
668ef7ae-82d7-5f3c-bedd-c62fc0809be6 | note | HOLD POINT - I
53e6b0eb-7fca-4b2d-8efa-9e2408ba39ac | checklist | QMD07 ITP-009 - Installation Stormwater main S13440 | itp | QMD07 ITP-009 - Installation Stormwater main S13440
31eda1c9-136b-4eb0-9e55-31df5b7aa269 | section | ITP-009 - Installation Stormwater main S13440
cb178419-e8a9-43d3-b312-efd9c50d71db | checkpoint | 1 - Excavation
907793b3-6805-508b-867d-6e5398ddca25 | note | Controlled By : (Position) - FM
2da6db67-71ec-5bf6-8946-8e499435694a | note | Accept / Reject Criteria - Excavation depth, bedding material, trench width
0e30cb2e-4649-5803-9a4d-898e1895b326 | note | Spec. Ref, Procedure Or Method Statement - D2 Buried Pipelines NZS 4404, AS/NZS 2566.2
b63d6de3-b8b9-5e6a-80ff-7e49e3630793 | note | Frequency Of Inspection OR Test - As works progress
7e50d420-ce6b-54c9-8da5-3999a608db2f | note | HOLD POINT - S
60fb496a-a95a-44e0-bb6a-f41578f5cfad | checkpoint | 2 - Pipe material delivery and storage
e424a678-0613-5e59-8cbc-6d17d82d4104 | note | Controlled By : (Position) - FM/CR
04e1abb9-5ac1-5915-83fb-b4ed355c1b86 | note | Accept / Reject Criteria - Inspection for damage, conformity with specs
7ce913cd-2c27-559e-bda2-9bf1b5af0edf | note | Spec. Ref, Procedure Or Method Statement - D1.24
01796ae7-7ffc-5555-a074-74e878f0072f | note | Frequency Of Inspection OR Test - Upon arrival
fa0e494e-42e0-5f07-b742-be0131c09705 | note | HOLD POINT - I
d7e8a030-2d0b-4c9d-b64f-2e6d361fad88 | checkpoint | 3 - Pipe laying (uPVC)
fe4e1008-7e3b-51c1-aa86-a85a0f641063 | note | Controlled By : (Position) - FM
55c13b21-8529-54a2-8baf-620e88200a36 | note | Accept / Reject Criteria - Alignment, gradient, jointing method
c0f3accc-bb51-5988-b62c-50844d929873 | note | Spec. Ref, Procedure Or Method Statement - D2.7 - AS/NZS 2566.2
0eccfff7-1cd5-5bed-862b-d1268242b812 | note | Frequency Of Inspection OR Test - As works progress
16e1c8a9-790d-5e07-aa76-fe06f61792cf | note | HOLD POINT - S
4e21aaec-9bc4-41c6-9c22-46f1fd7b8eda | checkpoint | 4 - Compaction of backfill material
4a575613-26bb-574f-836c-06740c3471d7 | note | Controlled By : (Position) - FM
8708264a-df0b-5fea-a597-36c67d937a7d | note | Accept / Reject Criteria - Correct aggregates, 200mm layer depth, Plateau test, clegg readings, NDM testing
a3eb8edd-49f4-52e5-a590-38ea4449af55 | note | Spec. Ref, Procedure Or Method Statement - D2.7.7 - AS/NZS 2566.2
cb42f088-6299-5456-a69c-b5676ba31f74 | note | Frequency Of Inspection OR Test - 200mm layers
204874f1-8a43-5296-b7c2-08ad7a4fb20e | note | ○ Clegg result every 6m
f02c7d88-1fd0-5935-86ad-a9a74771ae95 | note | ○ NDM result every 120m
a9bbd57d-1c69-53dd-a71f-de863cbaeebc | note | HOLD POINT - S
6ca26698-5bc0-40a7-a919-2217fb4e10d3 | checkpoint | 5 - Lateral Installation
6b8d80ec-f18f-5735-ae81-bf06a2df52d7 | note | Controlled By : (Position) - FM
1ed1c96d-965e-5f53-8a1e-f0bbe4d1b825 | note | Accept / Reject Criteria - Alignment, gradient, jointing method, concrete around junctions and bends as required
1daaaca6-2c5f-5dff-9046-0e1ff0e43bc5 | note | Spec. Ref, Procedure Or Method Statement - D4 - AS/NZS 2566.2
6991a1c8-cfd9-5a49-b1d4-79c825ba0f9b | note | Frequency Of Inspection OR Test - As works progress
1a4190fa-2681-55b7-8b82-314cdf79c8b3 | note | HOLD POINT - S
dd3d1596-2237-4413-b2e9-e8eeef38019d | checkpoint | 6 - Pipe bedding and backfilling
9e108d1c-b2aa-5887-96c3-5ddce7ea018f | note | Controlled By : (Position) - FM
144a0200-0453-5acd-9387-283743cb4313 | note | Accept / Reject Criteria - Correct layer thickness, compaction testing
35c5a029-9d08-5f95-946e-0a28cc8e7c0d | note | Spec. Ref, Procedure Or Method Statement - D2.7 - AS/NZS 2566.2
0ac1bef1-1835-5ae3-82f6-6108a0eda1f6 | note | Frequency Of Inspection OR Test - As works progress
36c00480-8002-5e4c-89c5-9c3d74073045 | note | HOLD POINT - S
9a785096-bc58-461f-835e-7b67d3257dc0 | checkpoint | 7 - Cleaning and CCTV new main
bac8174b-29fe-525d-b62f-be924ce9e84f | note | Controlled By : (Position) - PM
5d4fe0b2-a268-51b8-9466-3acdd6baabaa | note | Accept / Reject Criteria - No debris or defects
7b2bc2bf-4ed7-53a2-9b5e-7c307500ddfd | note | Spec. Ref, Procedure Or Method Statement - D2.9 - AS/NZS 2566.2
95a660fa-a87f-5962-8378-bcf144ef7240 | note | Frequency Of Inspection OR Test - Prior to comission
152467e9-3ce3-5cee-89da-9f94fd5cd345 | note | HOLD POINT - I
264ada50-1bab-490f-94ad-1fb461f696b7 | checklist | QMD07 ITP-010 - Asphalt Reinstatement | itp | QMD07 ITP-010 - Asphalt Reinstatement
bf805b79-498d-4a7d-9ca4-dbb390973f46 | section | ITP-010 - Asphalt Reinstatement
228b0f14-d04b-43aa-936e-cb9124d0787b | checkpoint | 1 - Saw cutting of existing pavement
38ff2223-4a8f-5689-86f4-54d103961bb0 | note | Controlled By : (Position) - PM/CR
289401c4-2576-5652-9ba4-d6764b30ccf3 | note | Accept / Reject Criteria - Edge alignment, depth, and cleanliness
2b0ed49b-99e4-5370-ae83-e694cb11e5ee | note | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA P40
27ce2991-1c68-5fac-a6ef-457c875ca3b8 | note | Frequency Of Inspection OR Test - Prior to reinstatement
da105e09-3963-5a7d-9c75-51e8c1bf23ff | note | HOLD POINT - S
dc8a1960-6655-4473-ae4c-3aee4640e851 | checkpoint | 2 - Placement and compaction of basecourse
d66359ad-371f-5466-87c1-74bce4908a4a | note | Controlled By : (Position) - PM/CR
4d306ca8-a53c-5c82-855a-ea5163f83bf9 | note | Accept / Reject Criteria - Layer thickness and compaction testing, preparation tolerance -/+5mm
8e8eebfa-4f11-52c6-8a17-0c8d8a2f3972 | note | Spec. Ref, Procedure Or Method Statement - D2.7.7.2 - NZTA B/2
a9124458-564d-5250-8371-94d8c66457ed | note | Frequency Of Inspection OR Test - As works progress
e42aa9aa-fc88-56d0-b484-7578b8a54993 | note | HOLD POINT - I
bc0a71b6-628b-46f2-8ab2-15d903429943 | checkpoint | 3 - Tack coating edges and base
09fcb62f-c959-5a0b-8905-2f9dd1d95dc5 | note | Controlled By : (Position) - SUB
bf7e0f50-1414-5c8f-b70f-c503c5713748 | note | Accept / Reject Criteria - Uniform application, coverage check
093562a8-de9e-5605-89d6-e3a3c3f66280 | note | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA P42 – Tack Coat Application
89df90ea-2d03-5e09-89b9-6638687ffd56 | note | Frequency Of Inspection OR Test - As works progress
ca86ae87-6943-5fed-9dfa-ad29469b2ba6 | note | HOLD POINT - S
da4e0f39-4095-4606-8849-e3b0933adaf1 | checkpoint | 4 - Placement of asphalt (AC mix)
0be7feb1-f3df-592a-889c-847c9e2fb8c4 | note | Controlled By : (Position) - SUB
2eeeb293-80a9-59f6-85dc-afbf9eae39bb | note | Accept / Reject Criteria - Correct temperature and spread rate
b332a8e6-b16b-53c9-aa9d-24e9922bd806 | note | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA M/10 – Asphalt Mix Requirements
8cace986-41c2-5cad-a57b-0851c19cbd4c | note | Frequency Of Inspection OR Test - As works progress
a55bf43f-d864-5fca-aead-977f44786682 | note | HOLD POINT - S
02df7df2-8689-4cbd-9b3b-167a9bf0a8eb | checkpoint | 5 - Compaction of asphalt layers
db1a5c28-0410-5dbd-a718-a460b15988d9 | note | Controlled By : (Position) - SUB
afc088c6-b58d-5e54-ac5e-0ebb139dff7d | note | Accept / Reject Criteria - Rolling pattern, compaction
eea8f53d-2c30-53e2-9053-d1680b0c4119 | note | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA M/10, B2 – Asphalt Compaction
e14e5ca9-f214-591d-8378-ff84331cb5e8 | note | Frequency Of Inspection OR Test - As works progress
0983b0e5-b88a-54e7-b571-6a3051c3fb55 | note | HOLD POINT - S
e8de432a-2438-4e4c-8641-e41d9a2bb5a8 | checkpoint | 6 - Joint sealing and finish
127dd293-9269-505b-815b-1648b656bf60 | note | Controlled By : (Position) - SUB
a102c797-a683-5691-81c6-444542f91099 | note | Accept / Reject Criteria - Seam bonding and surface appearance
f34b2ade-b44b-5889-8a29-713ebccb3948 | note | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA P40 – Joints and Finish
3a6f6945-2426-5f17-8d5b-15383cec7468 | note | Frequency Of Inspection OR Test - Post Paving
81ac3a99-4709-5eda-b6d8-b2e79d11834c | note | HOLD POINT - S
429762ab-cfd3-4e08-a0ee-ea5c4eb4eb3a | checkpoint | 7 - Final inspection and sign-off
d8a83cf5-6b8d-5c3a-9a3c-ca37c64c49ab | note | Controlled By : (Position) - PM/CR
c0a8ae80-c1f1-55e6-b33b-34c07cb6e1de | note | Accept / Reject Criteria - All specs met, records submitted
05573a9c-412a-5888-af1c-5401f8bc5bae | note | Spec. Ref, Procedure Or Method Statement - Contract Conditions
6cf0a60a-4e82-5615-b51a-a45031e41bbd | note | Frequency Of Inspection OR Test - Final Walk over
89ecbdd4-c2ad-5d2e-b3cd-1fced943567b | note | HOLD POINT - I