## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | QMD07 ITP001 - Installation SWMH 1 | itp
section | SWMH 1
checkpoint | 1 - Manhole base Preparation (Pre-cast or in-situ)
label | Controlled By : (Position) - CR
label | Accept / Reject Criteria - Clean and dry base
label | — Correct bedding material and compaction
label | — Reinforcement and formwork inspected
label | — Waterproofing components in place
label | Spec. Ref, Procedure Or Method Statement - Project Drawings, D18 Construction Methodology
label | Frequency Of Inspection OR Test - Prior to placing concrete or setting precast base
label | HOLD POINT - I
checkpoint | 2 - Manhole Cyclinder Installation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct alignment and verticality
label | — Joints sealed with approved material
label | — Steps/lifting holes sealed
label | — Wall thickness and type verified
label | Spec. Ref, Procedure Or Method Statement - D18 – Precast Installations, Manufacturer specs NZS 3109
label | Frequency Of Inspection OR Test - Prior to backfilling
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 3 - Pipe protrusions into manhole
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Flexible joint within 1metre of the manhole
label | Spec. Ref, Procedure Or Method Statement - D18.3 INSTALLATION
label | Frequency Of Inspection OR Test - Prior to pouring corbels
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 4 - Internal Benching and Channeling
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - Smooth trowelled finish
label | — Accurate channel fall to spec
label | — Benching slope toward channel
label | — No honeycombing or cracks
label | Spec. Ref, Procedure Or Method Statement - D18.3 - AS/NZS 3500 - Formed finish F3 as specified in NZS 3114
label | Frequency Of Inspection OR Test - After completion of benching/invert
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 5 - Manhole Cover and Frame Installation
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - Infiltration check
label | — Visual condition check
label | — Manhole dimensions
label | — Functional access features
label | Spec. Ref, Procedure Or Method Statement - D15.2 MATERIALS Maestro DIMHMCFHS MH cover
label | Frequency Of Inspection OR Test - Before handover or commissioning
label | HOLD POINT - H
holdpoint | HOLD POINT
checklist | QMD07 ITP002 - Replace and Install SWMH S22736 | itp
section | SWMH S22736
checkpoint | 1 - Manhole base Preparation (Pre-cast or in-situ)
label | Controlled By : (Position) - CR
label | Accept / Reject Criteria - Clean and dry base
label | — Correct bedding material and compaction
label | — Reinforcement and formwork inspected
label | — Waterproofing components in place
label | Spec. Ref, Procedure Or Method Statement - Project Drawings, D18 Construction Methodology
label | Frequency Of Inspection OR Test - Prior to placing concrete or setting precast base
label | HOLD POINT - I
checkpoint | 2 - Manhole Cyclinder Installation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct alignment and verticality
label | — Joints sealed with approved material
label | — Steps/lifting holes sealed
label | — Wall thickness and type verified
label | Spec. Ref, Procedure Or Method Statement - D18 – Precast Installations, Manufacturer specs NZS 3109
label | Frequency Of Inspection OR Test - Prior to backfilling
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 3 - Pipe protrusions into manhole
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Flexible joint within 1metre of the manhole
label | Spec. Ref, Procedure Or Method Statement - D18.3 INSTALLATION
label | Frequency Of Inspection OR Test - Prior to pouring corbels
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 4 - Internal Benching and Channeling
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - Smooth trowelled finish
label | — Accurate channel fall to spec
label | — Benching slope toward channel
label | — No honeycombing or cracks
label | Spec. Ref, Procedure Or Method Statement - D18.3 - AS/NZS 3500 - Formed finish F3 as specified in NZS 3114
label | Frequency Of Inspection OR Test - After completion of benching/invert
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 5 - Manhole Cover and Frame Installation
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - Infiltration check
label | — Visual condition check
label | — Manhole dimensions
label | — Functional access features
label | Spec. Ref, Procedure Or Method Statement - D15.2 MATERIALS Maestro DIMHMCFHS MH cover
label | Frequency Of Inspection OR Test - Before handover or commissioning
label | HOLD POINT - H
holdpoint | HOLD POINT
checklist | QMD07 ITP003 - Replace and Install SWMH S22735 | itp
section | SWMH S22735
checkpoint | 1 - Manhole base Preparation (Pre-cast or in-situ)
label | Controlled By : (Position) - CR
label | Accept / Reject Criteria - Clean and dry base
label | — Correct bedding material and compaction
label | — Reinforcement and formwork inspected
label | — Waterproofing components in place
label | Spec. Ref, Procedure Or Method Statement - Project Drawings, D18 Construction Methodology
label | Frequency Of Inspection OR Test - Prior to placing concrete or setting precast base
label | HOLD POINT - I
checkpoint | 2 - Manhole Cyclinder Installation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct alignment and verticality
label | — Joints sealed with approved material
label | — Steps/lifting holes sealed
label | — Wall thickness and type verified
label | Spec. Ref, Procedure Or Method Statement - D18 – Precast Installations, Manufacturer specs NZS 3109
label | Frequency Of Inspection OR Test - Prior to backfilling
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 3 - Pipe protrusions into manhole
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Flexible joint within 1metre of the manhole
label | Spec. Ref, Procedure Or Method Statement - D18.3 INSTALLATION
label | Frequency Of Inspection OR Test - Prior to pouring corbels
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 4 - Internal Benching and Channeling
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - Smooth trowelled finish
label | — Accurate channel fall to spec
label | — Benching slope toward channel
label | — No honeycombing or cracks
label | Spec. Ref, Procedure Or Method Statement - D18.3 - AS/NZS 3500 - Formed finish F3 as specified in NZS 3114
label | Frequency Of Inspection OR Test - After completion of benching/invert
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 5 - Manhole Cover and Frame Installation
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - Infiltration check
label | — Visual condition check
label | — Manhole dimensions
label | — Functional access features
label | Spec. Ref, Procedure Or Method Statement - D15.2 MATERIALS Maestro DIMHMCFHS MH cover
label | Frequency Of Inspection OR Test - Before handover or commissioning
label | HOLD POINT - H
holdpoint | HOLD POINT
checklist | QMD07 ITP004 - Installation Stormwater main 450Ø CH 0m-112m | itp
section | S13459
checkpoint | 1 - Excavation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Excavation depth, bedding material, trench width
label | Spec. Ref, Procedure Or Method Statement - D2 Buried Pipelines, NZS 4404, AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 2 - Pipe material delivery and storage
label | Controlled By : (Position) - FM/CR
label | Accept / Reject Criteria - Inspection for damage, conformity with specs
label | Spec. Ref, Procedure Or Method Statement - D1.24
label | Frequency Of Inspection OR Test - Upon arrival
label | HOLD POINT - I
checkpoint | 3 - Compaction of backfill material
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct aggregates, 200mm layer depth, Plateau test, clegg readings, NDM testing
label | Spec. Ref, Procedure Or Method Statement - D2.7.7 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - 200mm layers
label | ○ Clegg result every 6m
label | ○ NDM result every 120m
label | HOLD POINT - S
checkpoint | 4 - Lateral Installation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Alignment, gradient, jointing method, concrete around junctions and bends as required
label | Spec. Ref, Procedure Or Method Statement - D4 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 5 - Pipe bedding and backfilling
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct layer thickness, compaction testing
label | Spec. Ref, Procedure Or Method Statement - D2.7 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 6 - Cleaning and CCTV new main
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - No debris or defects
label | Spec. Ref, Procedure Or Method Statement - D2.9 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - Prior to comission
label | HOLD POINT - I
checklist | QMD07 ITP005 - Installation Stormwater main 450Ø CH 112m-230m | itp
section | S13459
checkpoint | 1 - Excavation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Excavation depth, bedding material, trench width
label | Spec. Ref, Procedure Or Method Statement - D2 Buried Pipelines, NZS 4404, AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 2 - Pipe material delivery and storage
label | Controlled By : (Position) - FM/CR
label | Accept / Reject Criteria - Inspection for damage, conformity with specs
label | Spec. Ref, Procedure Or Method Statement - D1.24
label | Frequency Of Inspection OR Test - Upon arrival
label | HOLD POINT - I
checkpoint | 3 - Compaction of backfill material
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct aggregates, 200mm layer depth, Plateau test, clegg readings, NDM testing
label | Spec. Ref, Procedure Or Method Statement - D2.7.7 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - 200mm layers
label | ○ Clegg result every 6m
label | ○ NDM result every 120m
label | HOLD POINT - S
checkpoint | 4 - Lateral Installation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Alignment, gradient, jointing method, concrete around junctions and bends as required
label | Spec. Ref, Procedure Or Method Statement - D4 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 5 - Pipe bedding and backfilling
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct layer thickness, compaction testing
label | Spec. Ref, Procedure Or Method Statement - D2.7 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 6 - Cleaning and CCTV new main
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - No debris or defects
label | Spec. Ref, Procedure Or Method Statement - D2.9 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - Prior to comission
label | HOLD POINT - I
checklist | QMD07 ITP006 - Installation Stormwater main 300Ø CH 230m-243 | itp
section | S13459
checkpoint | 1 - Excavation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Excavation depth, bedding material, trench width
label | Spec. Ref, Procedure Or Method Statement - D2 Buried Pipelines, NZS 4404, AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 2 - Pipe material delivery and storage
label | Controlled By : (Position) - FM/CR
label | Accept / Reject Criteria - Inspection for damage, conformity with specs
label | Spec. Ref, Procedure Or Method Statement - D1.24
label | Frequency Of Inspection OR Test - Upon arrival
label | HOLD POINT - I
checkpoint | 3 - Compaction of backfill material
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct aggregates, 200mm layer depth, Plateau test, clegg readings, NDM testing
label | Spec. Ref, Procedure Or Method Statement - D2.7.7 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - 200mm layers
label | ○ Clegg result every 6m
label | ○ NDM result every 120m
label | HOLD POINT - S
checkpoint | 4 - Lateral Installation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Alignment, gradient, jointing method, concrete around junctions and bends as required
label | Spec. Ref, Procedure Or Method Statement - D4 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 5 - Pipe bedding and backfilling
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct layer thickness, compaction testing
label | Spec. Ref, Procedure Or Method Statement - D2.7 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 6 - Cleaning and CCTV new main
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - No debris or defects
label | Spec. Ref, Procedure Or Method Statement - D2.9 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - Prior to comission
label | HOLD POINT - I
checklist | QMD07 ITP007 - Asphalt Reinstatement 1 | itp
section | Asphalt Reinstatement 1
checkpoint | 1 - Saw cutting of existing pavement
label | Controlled By : (Position) - PM/CR
label | Accept / Reject Criteria - Edge alignment, depth, and cleanliness
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA P40
label | Frequency Of Inspection OR Test - Prior to reinstatement
label | HOLD POINT - S
checkpoint | 2 - Placement and compaction of basecourse
label | Controlled By : (Position) - PM/CR
label | Accept / Reject Criteria - Layer thickness and compaction testing, preparation tolerance -/+5mm
label | Spec. Ref, Procedure Or Method Statement - D2.7.7.2 - NZTA B/2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - I
checkpoint | 3 - Tack coating edges and base
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Uniform application, coverage check
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA P42 – Tack Coat Application
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 4 - Placement of asphalt (AC mix)
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Correct temperature and spread rate
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA M/10 – Asphalt Mix Requirements
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 5 - Compaction of asphalt layers
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Rolling pattern, compaction
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA M/10, B2 – Asphalt Compaction
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 6 - Joint sealing and finish
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Seam bonding and surface appearance
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA P40 – Joints and Finish
label | Frequency Of Inspection OR Test - Post Paving
label | HOLD POINT - S
checkpoint | 7 - Final inspection and sign-off
label | Controlled By : (Position) - PM/CR
label | Accept / Reject Criteria - All specs met, records submitted
label | Spec. Ref, Procedure Or Method Statement - Contract Conditions
label | Frequency Of Inspection OR Test - Final Walk over
label | HOLD POINT - I
checklist | QMD07 ITP008 - Asphalt Reinstatement 2 | itp
section | Asphalt Reinstatement 2
checkpoint | 1 - Saw cutting of existing pavement
label | Controlled By : (Position) - PM/CR
label | Accept / Reject Criteria - Edge alignment, depth, and cleanliness
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA P40
label | Frequency Of Inspection OR Test - Prior to reinstatement
label | HOLD POINT - S
checkpoint | 2 - Placement and compaction of basecourse
label | Controlled By : (Position) - PM/CR
label | Accept / Reject Criteria - Layer thickness and compaction testing, preparation tolerance -/+5mm
label | Spec. Ref, Procedure Or Method Statement - D2.7.7.2 - NZTA B/2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - I
checkpoint | 3 - Tack coating edges and base
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Uniform application, coverage check
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA P42 – Tack Coat Application
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 4 - Placement of asphalt (AC mix)
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Correct temperature and spread rate
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA M/10 – Asphalt Mix Requirements
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 5 - Compaction of asphalt layers
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Rolling pattern, compaction
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA M/10, B2 – Asphalt Compaction
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 6 - Joint sealing and finish
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Seam bonding and surface appearance
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA P40 – Joints and Finish
label | Frequency Of Inspection OR Test - Post Paving
label | HOLD POINT - S
checkpoint | 7 - Final inspection and sign-off
label | Controlled By : (Position) - PM/CR
label | Accept / Reject Criteria - All specs met, records submitted
label | Spec. Ref, Procedure Or Method Statement - Contract Conditions
label | Frequency Of Inspection OR Test - Final Walk over
label | HOLD POINT - I
checklist | QMD07 ITP009 - Asphalt Reinstatement 3 | itp
section | Asphalt Reinstatement 3
checkpoint | 1 - Saw cutting of existing pavement
label | Controlled By : (Position) - PM/CR
label | Accept / Reject Criteria - Edge alignment, depth, and cleanliness
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA P40
label | Frequency Of Inspection OR Test - Prior to reinstatement
label | HOLD POINT - S
checkpoint | 2 - Placement and compaction of basecourse
label | Controlled By : (Position) - PM/CR
label | Accept / Reject Criteria - Layer thickness and compaction testing, preparation tolerance -/+5mm
label | Spec. Ref, Procedure Or Method Statement - D2.7.7.2 - NZTA B/2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - I
checkpoint | 3 - Tack coating edges and base
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Uniform application, coverage check
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA P42 – Tack Coat Application
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 4 - Placement of asphalt (AC mix)
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Correct temperature and spread rate
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA M/10 – Asphalt Mix Requirements
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 5 - Compaction of asphalt layers
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Rolling pattern, compaction
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA M/10, B2 – Asphalt Compaction
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 6 - Joint sealing and finish
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Seam bonding and surface appearance
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA P40 – Joints and Finish
label | Frequency Of Inspection OR Test - Post Paving
label | HOLD POINT - S
checkpoint | 7 - Final inspection and sign-off
label | Controlled By : (Position) - PM/CR
label | Accept / Reject Criteria - All specs met, records submitted
label | Spec. Ref, Procedure Or Method Statement - Contract Conditions
label | Frequency Of Inspection OR Test - Final Walk over
label | HOLD POINT - I
checklist | QMD07 ITP010 - Asphalt Reinstatement 4 | itp
section | Asphalt Reinstatement 4
checkpoint | 1 - Saw cutting of existing pavement
label | Controlled By : (Position) - PM/CR
label | Accept / Reject Criteria - Edge alignment, depth, and cleanliness
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA P40
label | Frequency Of Inspection OR Test - Prior to reinstatement
label | HOLD POINT - S
checkpoint | 2 - Placement and compaction of basecourse
label | Controlled By : (Position) - PM/CR
label | Accept / Reject Criteria - Layer thickness and compaction testing, preparation tolerance -/+5mm
label | Spec. Ref, Procedure Or Method Statement - D2.7.7.2 - NZTA B/2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - I
checkpoint | 3 - Tack coating edges and base
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Uniform application, coverage check
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA P42 – Tack Coat Application
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 4 - Placement of asphalt (AC mix)
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Correct temperature and spread rate
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA M/10 – Asphalt Mix Requirements
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 5 - Compaction of asphalt layers
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Rolling pattern, compaction
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA M/10, B2 – Asphalt Compaction
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 6 - Joint sealing and finish
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Seam bonding and surface appearance
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA P40 – Joints and Finish
label | Frequency Of Inspection OR Test - Post Paving
label | HOLD POINT - S
checkpoint | 7 - Final inspection and sign-off
label | Controlled By : (Position) - PM/CR
label | Accept / Reject Criteria - All specs met, records submitted
label | Spec. Ref, Procedure Or Method Statement - Contract Conditions
label | Frequency Of Inspection OR Test - Final Walk over
label | HOLD POINT - I