## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Add Bespoke Task |  | Bespoke Task | c50d11ae-0e5a-449f-ad82-65c014528368
| checkpoint | Scope Description (from Bravada SOW) and item numbers
13672680-43c2-5fbf-9b90-beacfc406d47 | textbox | Enter SOW description
13ab94a7-67c1-51f9-a096-4cf077f00eef | button | Warrantable Works | Yes, No
d3294e6f-2eca-5338-a20b-3853ecfd380f | textbox | Notes Relating To Works Performed
| checkpoint | Area completed - photos attached below
| checklist | Bentonite - Anchor Boxouts |  | Bentonite - Anchor Boxouts | b267b441-e833-4b4a-a376-9303d4634422
| checkpoint | Scope Description (from Bravada SOW) and item numbers
4c7b06d1-d1ea-5c6d-a5d1-27a5c87ce0f3 | textbox | Enter SOW description
| checkpoint | Substrate suitable for application
5bebbfb0-05d0-5a69-949b-d6834b903d01 | textbox | If inspection failed, please provide reasons and recommended course of action.
633aefe1-b73b-5d0b-8b89-9cc4d79069df | button | Membrane, Bentoseal & waterstop installed? | Yes,No
| checkpoint | Area completed - photos attached below
cdacfa9c-3605-582f-8a4d-e9c5cf09be11 | textbox | If inspection failed, please provide reasons and recommended course of action.
d9ca658c-1ec6-5f7f-bc81-676b3bb3b8d5 | button | Manufacturer Inspection Requested? | Yes,No,N/A
| checkpoint | Manufacturer Inspection
f6327ac1-07db-5699-8ffc-5bcc1ca3d4a1 | note | Attach Manufacturer's Signature Below
99fdc77b-061b-5ba9-acd9-bf763e25edc5 | note | Attach Manufacturer's Report Below
| checklist | Bentonite - Capping Beam Waterstop |  | Bentonite - Capping Beam Waterstop | 3a8fa130-4869-4d44-9abe-087c08e61805
| checkpoint | Scope Description (from Bravada SOW) and item numbers
e23c3863-5178-5ef0-ad5e-3bf35def1a22 | textbox | Enter SOW description
| checkpoint | Substrate suitable for application
23250503-46af-5100-995d-48175c071220 | textbox | If inspection failed, please provide reasons and recommended course of action.
9526201f-c069-50b5-b930-8305dfda774f | button | Waterstop installed? | Yes,No
| checkpoint | Area completed - photos attached below
264e20c9-a1c8-595c-9822-d0e92d9bc7b9 | textbox | If inspection failed, please provide reasons and recommended course of action.
72b8eb06-db21-52b7-a865-f85a23c652c3 | button | Manufacturer Inspection Requested? | Yes,No
| checkpoint | Manufacturer Inspection
dad277c9-d7e5-5c26-b3e4-2e10203f4d9e | note | Attach Manufacturer's Signature Below
b1b1f226-bb63-5700-a32c-d3e6cc8cc48e | note | Attach Manufacturer's Report Below
| checklist | Bentonite - Dewatering Wells |  | Bentonite - Dewatering Wells | f81fd71b-e80e-42c0-96bb-b0096019f1ac
| checkpoint | Scope Description (from Bravada SOW) and item numbers
0ab407d1-7b97-54ff-81f8-3b5c463ef208 | textbox | Enter SOW description
| checkpoint | Substrate suitable for application
6d4507dd-d2e4-5c66-928a-96aaa67453fb | textbox | If inspection failed, please provide reasons and recommended course of action.
cf43e0b8-3d1c-54c9-8aab-512f4b2429ed | button | PureGold Chips Installed | Yes,No
6133f56e-e57f-5f70-a6be-ac93ac5523d2 | button | Builder installed Concrete Grout | Yes,No
af11c48a-9d7a-5d77-931f-f4dd154f6403 | button | Membrane Installed? | Yes,No
8943eb3b-e178-564d-8b8d-cef65d68f9d6 | button | Waterstop installed? | Yes,No
| checkpoint | Area completed - photos attached below
5e8f4f8f-9a1f-55c9-a683-b9b02ef24e41 | textbox | If inspection failed, please provide reasons and recommended course of action.
a73effa1-314b-588f-9ee1-3e4367fad00b | button | Manufacturer Inspection Requested? | Yes,No
| checkpoint | Manufacturer Inspection
a0cff7dd-2884-5e76-985c-b8774bc9f2ee | note | Attach Manufacturer's Signature Below
ae57e7b4-63c9-5dfe-b86d-57e577aa690f | note | Attach Manufacturer's Report Below
| checklist | Bentonite - PT Slab Wall Junction Termination |  | Bentonite - PT Slab Wall Junction Termination | ea8c1777-27ed-4a1e-b9e6-ae6ace5bfeba
| checkpoint | Scope Description (from Bravada SOW) and item numbers
6e9b8646-de21-5c24-a017-0e8699a25264 | textbox | Enter SOW description
| checkpoint | Substrate suitable for application
3b67dcc4-9a39-5907-ac8b-74d2cbda5775 | textbox | If inspection failed, please provide reasons and recommended course of action.
c51b238e-dfd7-5fbc-9adf-d83e8b440214 | button | Waterstop installed? | Yes,No
832a0be4-b411-5c18-9129-8720ecfc9641 | button | Termination bar installed? | Yes,No,N/A
81a30ed1-03b8-50b2-a5e0-722254503313 | button | Bentoseal installed? | Yes,No,N/A
e14c8e6a-0491-5c98-b58b-adaff04ccf20 | button | Cetinject installed? | Yes,No,N/A
| checkpoint | Area completed - photos attached below
638a3856-62d4-565a-922a-bccd5eb7306d | textbox | If inspection failed, please provide reasons and recommended course of action.
16c4889d-8a80-536e-a26c-f9ec2c68b755 | button | Manufacturer Inspection Requested? | Yes,No
| checkpoint | Manufacturer Inspection
2e25e2b2-e694-5ea4-ac53-cb1b90e4444c | note | Attach Manufacturer's Signature Below
8b26d37f-d643-5bf4-9a87-249265c641bd | note | Attach Manufacturer's Report Below
| checklist | Bentonite - Shotcrete Wall Membrane |  | Bentonite - Shotcrete Wall Membrane | 65d2e8c0-4d6c-42b9-a510-c899b16d5314
| checkpoint | Scope Description (from Bravada SOW) and item numbers
807d2ddf-a8d1-5253-873a-e38c63d2b0cc | textbox | Enter SOW description
| checkpoint | Substrate suitable for application
78c21440-9a7d-5d84-8045-c3b311d261be | textbox | If inspection failed, please provide reasons and recommended course of action.
24f3f366-f752-53a1-8078-b0ceb637d9dd | dropdown | Join Coverage | 50mm,75mm,100mm,50-100mm
0d786c86-b748-52e6-8c29-ac1f4c1d18e9 | button | Capping Beam Part Of Installation? | Yes,No
83694976-b33f-5b98-add1-f6d1f1aa1f62 | button | Capping Beam Waterstop Installed? | Yes,No
dd3b011a-78e7-5d5a-91fe-216f6c67278c | dropdown | Waterstop Type | RX-102,Akwaswell,Both
51feb509-2db7-58f9-a8b6-b56c072757c3 | button | Waterstop to drop join installed ? | Yes,No,N/A
878f19cd-4085-5ce7-96b3-252333dabe34 | button | Detailing of penetrations | Yes,No,N/A
ecd894a8-f68e-5a9f-9439-f31c9813ee8c | button | Membrane Installed? | Yes,No
035a9248-f827-56a5-a190-8f9eaf316940 | dropdown | Minimum lap required | 150mm,200mm
| checkpoint | Starter bars detailed
| checkpoint | Area completed - photos attached below
87910686-9f5b-5520-b8b3-e943aa335846 | textbox | If inspection failed, please provide reasons and recommended course of action.
7401e2a9-8cd3-51b4-910e-2711d8c42e57 | note | Attach Manufacturer's Report Below
| checklist | Bentonite - Strip/Pad Footings (Hydrostatic) |  | Bentonite - Strip/Pad Footings (Hydrostatic) | 3ec7a42a-9583-44ec-b25f-1235e42b57c1
| checkpoint | Scope Description (from Bravada SOW) and item numbers
a72017de-09cc-558c-9848-3090ee7c6b03 | textbox | Enter SOW description
| checkpoint | Substrate suitable for application
8be87338-cf3c-53c0-8b5e-a8885f5c87f1 | textbox | If inspection failed, please provide reasons and recommended course of action.
| checkpoint | Dewatered
bd97c8b7-135a-516b-a629-d099864cc249 | textbox | Notes on dewatering for Project Manager
747122e0-130c-5c21-9236-96e67e9488d6 | button | Granules to perimeter? | Yes,No
baba0ae6-9ad7-5398-aeed-7748abe49194 | button | Membrane Installed? | Yes,No
70e62807-d2b7-5479-82ee-9dd7e5b64d21 | dropdown | Minimum lap required | 150mm,200mm
| checkpoint | Area completed - photos attached below
bc1fc3d0-b08f-56a6-8ddb-ee52ccdb1121 | textbox | If inspection failed, please provide reasons and recommended course of action.
1e97c4f9-929d-5525-b280-6b243abb1281 | button | Manufacturer Inspection Requested? | Yes,No
| checkpoint | Manufacturer Inspection
16fdeee3-0e28-56c0-971a-423fd5a8ca12 | note | Attach Manufacturer's Signature Below
1c7cfd90-92b9-5587-8337-5633bfc56b7b | note | Attach Manufacturer's Report Below
| checklist | Bentonite - Underslab Membrane (Hydrostatic) |  | Bentonite - Underslab Membrane (Hydrostatic) | 5eda08c9-8f42-43d7-9ccb-abb3a480eca6
| checkpoint | Scope Description (from Bravada SOW) and item numbers
5d5c04d0-14ea-522b-abe0-45f5d383735b | textbox | Enter SOW description
| checkpoint | Substrate suitable for application
6aba74f9-1db9-566b-b339-506b39844fc1 | textbox | If inspection failed, please provide reasons and recommended course of action.
| checkpoint | Dewatered
38afa2f2-5a98-5107-8f44-525b4c96aa5e | textbox | Notes on dewatering for Project Manager
794f576b-e7b3-5d29-b91d-4bf6f7c79c3f | button | Membrane Installed? | Yes,No
83adaa0f-6c64-51fa-b614-080faf889333 | dropdown | Minimum lap required | 150mm,200mm
2a326046-c308-51e1-a8ea-c7f3bf5db829 | button | Waterstop to pile caps | Yes,No,N/A
47d7a6f5-48d7-5bdb-a7d0-661bfb4507c0 | button | Detailing of penetrations | Yes,No,N/A
| checkpoint | Area completed - photos attached below
3caee4dd-9670-5b01-bb32-d9f387d18ba3 | textbox | If inspection failed, please provide reasons and recommended course of action.
8e025066-9b65-526a-ac21-7da10d4a7a0b | button | Manufacturer Inspection Requested? | Yes,No
| checkpoint | Manufacturer Inspection
6ca13afd-657b-5c44-8c89-4f681f7d1233 | note | Attach Manufacturer's Signature Below
b3f7b342-3283-58f8-8cb7-e50c838e9369 | note | Attach Manufacturer's Report Below
| checklist | Bentonite - Underslab Membrane (Non-Hydrostatic) |  | Bentonite - Underslab Membrane (Non-Hydrostatic) | aedfb01e-3ea8-4b7e-9c65-e41e1ab56650
| checkpoint | Scope Description (from Bravada SOW) and item numbers
7823b74b-8933-5ce1-a21a-13ad01b57af3 | textbox | Enter SOW description
| checkpoint | Substrate suitable for application
b8f966f9-1efe-51f3-abc2-552aba65dd42 | textbox | If inspection failed, please provide reasons and recommended course of action.
| checkpoint | Dewatered
8139d3f3-3584-5f66-9e97-83ada1188a62 | textbox | Notes on dewatering for Project Manager
ce95436f-afcc-517b-9c6c-21a7e0b7af0b | button | Membrane Installed? | Yes,No
5217f3c5-0cf4-5496-a86a-f92684865cc7 | dropdown | Minimum lap required | 150mm,200mm
54a3c460-388c-504e-83d0-ed0975adc95e | button | Detailing to pile caps | Yes,No,N/A
c5f11fdf-ebbf-51a2-b449-efc2a70e5347 | button | Detailing of penetrations | Yes,No,N/A
| checkpoint | Area completed - photos attached below
08aac69c-8776-5f4d-a24b-bdd889b6711d | textbox | If inspection failed, please provide reasons and recommended course of action.
6bc2cf39-7fae-5676-ab4e-7df9adfc7448 | button | Manufacturer Inspection Requested? | Yes,No
| checkpoint | Manufacturer Inspection
c4f5574f-956c-54cf-9bec-a80d74fd143c | note | Attach Manufacturer's Signature Below
0c24de3e-7588-52a5-97be-34c708663ed9 | note | Attach Manufacturer's Report Below
| checklist | Bentonite - Wall / Slab Junction |  | Bentonite - Wall / Slab Junction | 1006e06c-7ddb-4aeb-b28a-6d934b13b919
| checkpoint | Scope Description (from Bravada SOW) and item numbers
562f5c13-adff-5175-9e62-6f21a6474c7e | textbox | Enter SOW description
| checkpoint | Substrate suitable for application
1c05c36c-d15d-5824-807b-de561507c110 | textbox | If inspection failed, please provide reasons and recommended course of action.
c8788c95-e324-5600-9fc8-9312d51f8e2c | dropdown | Slab Thickness | <450mm,>=450mm
f087d916-e39a-5776-a62c-45e29d1e2adf | dropdown | No. of waterstops to install | 1,2
335b2842-0c56-5efe-93d1-5306e4c233d2 | button | Waterstop installed? | Yes,No
e8896aac-b439-5954-bbac-f0a42010875d | button | Granules to junction? | Yes,No
2790ebeb-4606-50ac-a01c-5661f74bb770 | button | Akwaswell to lowest 2 laps? | Yes,No
| checkpoint | Area completed - photos attached below
42e19aeb-2fc1-5b41-8860-cac511e1adab | textbox | If inspection failed, please provide reasons and recommended course of action.
4b8febfa-0d9f-50ae-aecf-3c867808cd69 | button | Manufacturer Inspection Requested? | Yes,No
| checkpoint | Manufacturer Inspection
9069bf98-9d35-5444-b547-68b747bb4460 | note | Attach Manufacturer's Signature Below
33fa6737-9fdc-5e78-9072-2c635bc8eba7 | note | Attach Manufacturer's Report Below
| checklist | Bituthene 6000EIM Installation |  | Bituthene 6000EIM Installation | d4a30be0-a604-4c28-892c-46e2742f1f6b
| checkpoint | Scope Description (from Bravada SOW) and item numbers
df1ae2d3-4833-5aa9-aca0-57d38b324a9f | textbox | Enter SOW description
| checkpoint | Attach TDS for application
| checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
| checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
| checkpoint | Substrate free from pooling or ponding water - Moisture gauge photo attached below
be745d8d-664f-54ff-85b5-652312ae3ab8 | note | If any of these checkpoints fail please provide information and required action by builder
bac745dc-012c-5c2e-9d1a-9059a9f532c4 | textbox | Add Comment
| checkpoint | Installation of Bituthene Type C primer as required?
| checkpoint | Record (Photo) batch number and date of manufacture of primer
| checkpoint | Curing time for primer (Minimum 2 hours)
| checkpoint | Installation of base sheet
| checkpoint | Record (Photo) batch number and date of manufacture of Bituthene 6000EIM base sheet
| checkpoint | Installation of top sheet
| checkpoint | Record (Photo) batch number and date of manufacture of Bituthene 6000EIM top sheet
| checkpoint | Installation of Bituthene LM Mastic to perimeters
| checkpoint | Record (Photo) batch number and date of manufacture of top sheet
| checkpoint | Area completed to manufacturer's specification - photos attached below
| checklist | Butynol Installation (External) |  | Butynol Installation (External) | bdc104a5-2b2d-4540-9879-d430dd4cfd27
| checkpoint | Scope Description (from Bravada SOW) and item numbers
6dc99cdc-faa2-52aa-8cd3-cb0c8627fa46 | textbox | Enter SOW description
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Substrate clear of dust, debris and contaminants (Attach photos below)
| checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
| checkpoint | Substrate free from pooling or ponding water? (Attach moisture gauge photo)
3fbdef10-c6bd-523b-8f6a-85d7e4cab951 | button | Adequate fall in substrate? | Yes,No
aa19ec6e-c043-5a97-9554-70401fcd702f | note | If any of these checkpoints fail please provide information and required action by builder
92b06a76-965b-5411-9401-bfde9807db56 | textbox | Add Comment
cb1aac0d-a5f8-5d9d-b84d-2f7a80554648 | button | Installation of primer as required? | Yes,No
| checkpoint | Substrate free from surface water? (Attach moisture gauge photo)
6fc854fb-1aa3-5fbf-81ca-e9297e4a1a78 | button | Installation of sheet membrane to manufacturer's specification (min. 50mm overlaps) ? | Yes,No
288bf048-1697-5794-adb2-1e62ed9e7b37 | button | Installation of sheet membrane to perimeters, incl. compatible sealant as required? | Yes,No
| checkpoint | Area completed to manufacturer's specification? - photos attached below
62c5d79a-aa16-565e-8c87-e672785f64c9 | note | Attach Client Signature Below
| checklist | Butynol Installation (Internal) |  | Butynol Installation (Internal) | 99c6c49c-7f20-441c-95fc-a8b44639114f
| checkpoint | Scope Description (from Bravada SOW) and item numbers
fdba740c-3ad2-5562-850c-784b8e575e13 | textbox | Enter SOW description
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Substrate clear of dust, debris and contaminants (Attach photos below)
a517516d-30cb-51b8-a5ef-d63dba2ffd22 | note | If substrate failed please provide information and required action by builder
23b10c1e-05d3-52b0-9d8e-713fdede3c77 | textbox | Add Comment
bc50826f-6f40-5792-ae0c-1757b1e5505e | button | Installation of sheet membrane to manufacturer's specification (min. 50mm overlaps) ? | Yes,No
8a4dd41e-3630-54e0-a416-332b2b7dc709 | button | Installation of sheet membrane to perimeters, incl. compatible sealant as required? | Yes,No
| checkpoint | Area completed to manufacturer's specification? - photos attached below
8820a6f5-5957-58f1-824d-bd9131145a91 | note | Attach Client Signature Below
| checklist | Colphene Uni NG Capping Beam |  | Colphene Uni NG Capping Beam | bbaaa3c9-2dd4-457a-bc5d-7991fff4e7aa
| section | Details
| checkpoint | Scope Description (from Bravada SOW) and item numbers
06ff0b37-30b8-577d-bb82-87ac598bd2e7 | textbox | SOW description entered
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Substrate Acceptance
a12bd4d4-5d6b-597a-860c-99bb3b4d328e | button | Blinding installed to acceptable surface uniformity (photos attached below) | Yes,No
be3d776e-49af-5e40-a45a-29ee535dad39 | button | Pile tops prepared to acceptable surface uniformity (photos attached below) | Yes,No
7d263282-62c2-55e3-986c-1012bfdc777f | button | Substrate free from pooling or ponding water (photos attached below) | Yes,No
| checkpoint | Colphene Uni NG Around Pile
61c2314c-6343-5124-99e0-f48a73cd604b | button | Colphene Uni NG installed tightly around pile (photos attached below) | Yes,No
| checkpoint | Epoxy Fillet
a3e6a893-5067-55ee-b9c5-5a38b6889f57 | button | Epoxy fillet of Alsan EPM installed to junction of pile over Colphene Uni NG (photos attached below) | Yes,No
| checkpoint | Junction Reinforcement
e264beef-20af-5e0c-9a63-88e4dec8d392 | button | Reinforcement strip of Colphene Uni NG fully torched to corner junction of capping beam. Half width of reinforcement will sit inside formwork, half width outside formwork. (photos attached below) | Yes,No
f324846b-0f3a-542f-b0da-cac481e92fa1 | dropdown | Reinforcement width of Colphene Uni NG | 200mm,300mm,400mm,500mm,Greater than 500mm
| checkpoint | Flashing Over Pile
1eb5db36-6661-5c66-87dd-652b9ec461e0 | button | Alsan Flashing with Alsan reinforcement over pile and lapped onto membrane around pile (photos attached below) | Yes,No
0c32ce42-4d9b-5d6f-8d3b-c22eedc7820c | dropdown | Lap size of flashing Colphene Uni NG | 50mm,100mm,150mm,200mm
| checkpoint | Torching to Side of Capping Beam
bb54d6be-ec6d-50d8-ac9a-7412d730ecec | button | Concrete of acceptable surface uniformity to install fully torched membrane (photos attached below) | Yes,No
cdc70829-f523-5705-8fdb-11d55ce0e0b9 | button | Colphene Uni NG fully torched to side of capping beam (Record batch and install photos) | Yes,No
574920c1-30c2-5a65-84f8-9f8565519861 | button | Sopradrain 20 drainage cell installed to side of capping beam (Record batch and install photos) | Yes,No
| checkpoint | Gasket Installation
c2a3a312-cb07-512a-a9b0-3df0f5ef0374 | dropdown | Gasket responsibility | Bravada,Client,N/A
3bb6bce6-5290-53f9-8dc6-d9a882ac4633 | button | If Bravada responsibility, is gasket installed to manufacturer's specification? (Record batch and install photos) | Yes,No
| checkpoint | Area completed to manufacturer's specification? - photos attached below
| checklist | Concrete Injection |  | Concrete Injection | 1c93b074-31f8-487a-a0f8-dc71b397c0ec
| checkpoint | Investigate location and document.
9a197116-df9e-57ab-a7a4-e76e31ee9891 | button | Is injection required? | Yes,No
| checkpoint | Record product, batch number and TDS.
110aa801-923e-574b-97ae-cf7de0625723 | textbox | Drill, insert and record packers as required.
69ef3c13-d9c7-5b04-9d4f-3000318dd71a | textbox | Record results of injection including (but not limited to) quantity of material injected per packer and relevant observations. Include sketch/markup if required.
20888a7d-ea3d-50d8-a967-a7a3ddd6328e | button | Injection completed as per manufacturer's specification | Yes,No
| checklist | Control Joints |  | Control Joints | cffd06c6-c223-4455-8515-b588af1b68a6
| checkpoint | Scope Description (from Bravada SOW) and item numbers
79301476-5a91-51f2-87a7-f1c5fe195d99 | textbox | Enter SOW description
| checkpoint | Channel cut to sufficient width
af095250-1167-5223-8e7c-413956204204 | textbox | Enter width
| checkpoint | Polyurethane caulk applied to channel
| checklist | Dermafil (Concrete Lid) |  | Dermafil (Concrete Lid) | 58e94a7f-a013-44ce-ad52-f08fb15444a8
| checkpoint | Scope Description (from Bravada SOW) and item numbers
cca6913e-fb5b-55c6-93d6-29493708f733 | textbox | Enter SOW description
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Substrate Acceptance (as per manufacturer's technical data sheet and method statement)
a86744d1-63ac-5c78-95e5-67bbc2baf2ad | button | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below | Yes,No
48dc42fc-4175-5212-8dcd-385f9f69f2e4 | button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
8d29f25e-117b-5056-80fd-e6cb2a896c33 | button | Substrate free from pooling or ponding water | Yes,No
7d4e00a7-a4df-55b6-91d2-8f1096746d7e | button | Moisture content is 4% or less (Moisture gauge photo attached below) | Yes,No
b317272a-d287-5054-8966-8b0b8e4990ee | button | Adequate fall in substrate | Yes,No
| checkpoint | Priming
0aec156f-1625-50fa-8e47-81183cc345f7 | note | Record batch numbers
a6339416-d7b0-59ed-8279-06d758703004 | button | Dermaprimer installed to manufacturer's specification - photos attached below | Yes,No
3058dc84-bdd9-58b3-91c5-cd489c662a50 | button | Primer given adequate time to cure as per manufacturers specification | Yes,No
75b90a27-fd14-5418-bf98-42379c758493 | button | Area completed and suitable for membrane application - photos attached below | Yes,No
| checkpoint | Dermafil Installation
56cbf7c5-501e-51e6-946f-c16b8956151f | note | Record batch numbers
910b7b5f-e194-5442-8061-3ec7493db1eb | button | Substrate clear of dust, debris and contaminants - photos attached below | Yes,No
b5ad3662-d35d-5e5c-a6d6-6dfd162a35ee | button | Installation of base layer membrane (min. 100mm overlaps) - photos attached below | Yes,No
7fce1b43-16af-57af-b3df-10edbe109ff9 | button | Termination pressure bar installed where required - photos attached below | Yes,No
| checkpoint | ILD Testing
9b78a4c4-0334-5b26-bdb4-95cb762b598a | button | ILD test requested | Yes,No
acba65c0-0eda-50c7-9874-00414504f247 | button | ILD test performed | Yes,No
b01e44e0-617f-59ac-a998-3bd4c2cbbc35 | textbox | Any rectifications performed
55574ec3-34dc-52de-b15b-134f6c2e5f13 | button | ILD test report issued | Yes,No
| checkpoint | Protection
0f632de3-d252-5a89-baec-0a4aaefc45ec | button | Casali Protector installed - photos attached below | Yes,No
| checkpoint | Area completed to manufacturer's specification - photos attached below
55e980be-0b47-5561-ae4e-c5822f9f0160 | note | Attach Client Signature Below
| checklist | EnduroFlex Insulated Roof PVC Installation |  | EnduroFlex Insulated Roof PVC Installation | 2210723c-99c2-4285-a0c4-075fa721d0cd
| checkpoint | Scope Description (from Bravada SOW) and item numbers
881d1cae-d465-5f42-99b5-c62de4e35740 | textbox | SOW description entered
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Substrate Acceptance
278edb56-039c-5940-979a-cfa10c435f3b | button | Substrate washed / cleaned & assessed for surface uniformity (photos attached below) | Yes,No
f715a8d0-c638-566a-a9b7-7aba7c05d91f | button | Substrate temperature is not less than 10*C and no greater then 35*C | Yes,No
cb9e7e4a-9e3f-58f9-bf7c-baf04c8ca1df | button | Substrate free from pooling or ponding water (Moisture gauge photo attached below) | Yes,No
7215b73f-1b90-508c-a305-3e2ca46533c0 | button | Adequate fall in substrate? | Yes,No
| checkpoint | Vapour barrier installation
d7cd42bc-baaf-570d-bd79-bc3122a4a101 | dropdown | Vapour barrier type | Fully Adhered, Loose Laid
2aed48ab-bca9-5d23-a262-ee19fcd423a8 | button | Primer installed to manufacturer's specification (Record batch and install photos) | Yes,No
eb9c509b-5af2-57df-a6af-a17b75addd3a | button | Vapour barrier installed to manufacturer's specification (Record batch and install photos) | Yes,No
| checkpoint | Insulation Installation
2fccffb6-fdf2-581e-b14f-21baddeaa725 | button | Vapour barrier free of pooling water? | Yes,No
9f5d89dc-0f29-583b-b8c8-5a1553499613 | dropdown | Insulation installation method | Foam Adhesive,Mechanically Fixed
b08cb857-13c7-55af-a92c-04bf6477f4ac | button | Insulation installed to fall? | Yes,No,N/A
| checkpoint | Membrane Installation
c35f5365-0ea1-5db7-9ecd-09687a82d044 | button | Installation of fully adhered base sheet membrane to manufacturer's specification (Record batch and install photos) | Yes,No
0abee5f7-a2e4-5210-862a-458efe9fd112 | dropdown | Cap sheet installation method | Fully Adhered,Torched
79e00b46-624f-5fed-817f-5e3a11fa3c38 | dropdown | Cap sheet type | Unexposed,UV-Stable,Anti-Root
8cdeef0f-5fde-50f1-b505-79d1a0671e1e | button | Installation of cap sheet membrane to manufacturer's specification (Record batch and install photos) | Yes,No
34462895-fc66-59a0-8a44-90a3a6fc8009 | button | Termination pressure bar installed to manufacturer's specification (Record batch and install photos) | Yes,No
| checkpoint | Area completed to manufacturer's specification? - photos attached below
| checklist | Eradix (Backfilled Downturns) |  | Eradix (Backfilled Downturns) | a8b29387-84b7-46c2-bbbe-8fbd702ba49f
| checkpoint | Scope Description (from Bravada SOW) and item numbers
262c072e-f20f-5553-9cfb-2832106a2cdb | textbox | Enter SOW description
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Diaphragm Wall Preparation
519e7f42-7aff-5d66-bfac-4ee097eb6d59 | button | Transition compound to D-Wall installed as per manufacturer's specification | Yes,No
| checkpoint | Substrate Acceptance (as per manufacturer's technical data sheet and method statement)
d97923e7-6cab-5e9d-9541-1d9c871d0016 | button | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below | Yes,No
bc8b2226-32ce-518f-be88-1e7ec09585b6 | button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
9f33d685-58a1-5224-955e-7b585d71c83b | button | Moisture content is 4% or less (Moisture gauge photo attached below) | Yes,No
| checkpoint | Priming
78b46b01-8cf2-51ab-8dec-13fd61cad1b1 | note | Record batch numbers
32653558-0436-5349-8b1e-2c20587246c3 | button | Dermaprimer installed to manufacturer's specification - photos attached below | Yes,No
9bbdf920-c6c6-57df-89ee-5e21c4ffde90 | button | Primer given adequate time to cure as per manufacturers specification | Yes,No
68497c8a-5ed4-5ddd-ae17-a04269f0cd5f | button | Area completed and suitable for membrane application - photos attached below | Yes,No
| checkpoint | Eradix Installation
1ef6aeef-dee7-59c1-af9f-273284ed7e05 | note | Record batch numbers
782f94c7-ea0b-5de6-9f53-572ffbf98a81 | button | Substrate clear of dust, debris and contaminants - photos attached below | Yes,No
cbb5c353-e48c-5701-a2c7-40590c4dd837 | button | Installation of base layer membrane (min. 100mm overlaps) - photos attached below | Yes,No
8e99c39c-cfae-5c88-9dfa-47d024b8963c | button | Termination pressure bar installed where required- photos attached below | Yes,No
| checkpoint | ILD Testing
87e9195e-2365-5249-9e37-597b36c83d9b | button | ILD test requested | Yes,No
e65c5adc-621e-5390-8ab7-6d4e8af6951e | button | ILD test performed | Yes,No
f7293006-b20d-59ee-ae8f-4c3286f2eec7 | textbox | Any rectifications performed
97a50da0-40f1-5c24-8d28-9e731d18d90c | button | ILD test report issued | Yes,No
| checkpoint | Protection
562202d8-9c34-59e8-a26f-0cd03bf785a2 | button | Casali Protector installed - photos attached below | Yes,No
| checkpoint | Area completed to manufacturer's specification - photos attached below
f196104a-7cba-5767-baba-3ed0a421acd5 | note | Attach Client Signature Below
| checklist | External (Exposed) |  | External (Exposed) | 585469a7-a333-48af-b705-fe416932a98b
| checkpoint | Scope Description (from Bravada SOW) and item numbers
d28a7764-9542-5c8d-8808-0e24012aec8b | textbox | Enter SOW description
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
| checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
| checkpoint | Substrate free from pooling or ponding water - Moisture gauge photo attached below
7fc11175-5e68-592f-9a08-ddd5f7eeb7b4 | button | Adequate fall in substrate? | Yes,No
f8ed1ef4-afc4-5601-b139-1a2c67988105 | note | If any of these checkpoints fail please provide information and required action by builder
d4446a5c-1929-51f9-8a74-0f234ccca01e | textbox | Add Comment
b462a3d0-8373-5ab9-b9ee-895a55df48a1 | button | Installation of primer as required? | Yes,No
| checkpoint | Record (Photo) batch number and date of manufacture of primer
819686ac-ab1b-5a68-b684-df1d9012436a | dropdown | Curing time for primer (hours) | 6,12,18,24
| checkpoint | Substrate free from surface water - Moisture gauge photo attached below
b85b128d-cae0-51c9-b535-a234c792ad07 | button | Installation of fillets/bandage to junctions as required? | Yes,No
462de1b6-b119-54de-b736-6f75a46a778e | button | Installation of base coat within rquired maximum curing time of primer? | Yes,No
| checkpoint | Record (Photo) batch number and date of manufacture of base coat
ef7a5954-54f7-5ac7-a69b-dbf5d57377b1 | button | Base coat installed to minimum film thickness? | Yes,No
672970c9-996a-5f5b-b80e-25f723705934 | button | Installation of UV-stable top coat? | Yes,No,N/A
| checkpoint | Record (Photo) batch number and date of manufacture of top coat
00c50874-66dd-5c4e-967d-a5f62f45e2f7 | button | Top coat installed to minimum film thickness? | Yes,No,N/A
b5bce0d6-63a2-572c-8c9e-5d0fd89efc84 | button | Broadcast of 30/60 quartz if trafficable? | Yes,No,N/A
| checkpoint | Area completed to manufacturer's specification - photos attached below
| checklist | External (Non-Exposed) |  | External (Non-Exposed) | c7b76de3-a0fe-4057-bf94-d02d1c31c42e
| checkpoint | Scope Description (from Bravada SOW) and item numbers
9cdafd14-ff00-581f-9a62-264cb7467b95 | textbox | Enter SOW description
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
| checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
| checkpoint | Substrate free from surface - Moisture gauge photo attached below
f69bc01b-d28c-5cf3-bf2b-d2bfd6e82ea8 | button | Adequate fall in substrate? | Yes,No
ea6f2f7f-cbe2-58a4-adb7-ca59ef80f519 | note | If any of these checkpoints fail please provide information and required action by builder
1d896c19-a0af-57e8-b214-9b996aa22dcd | textbox | Add Comment
52802da8-9083-5d85-ba05-041f077fa2f9 | button | Installation of primer as required? | Yes,No
| checkpoint | Record (Photo) batch number and date of manufacture of primer
| checkpoint | Substrate free from surface water - photos attached below
e1c88a62-4a13-50dd-b783-4c96f2098cee | button | Installation of fillets/bandage to junctions as required? | Yes,No
b5951553-87e0-54f4-9f34-73e201e58912 | button | Installation of base coat? | Yes,No
d153b2ad-a9e1-5bc5-b847-1804c9ff3a64 | button | Base coat installed to minimum film thickness? | Yes,No
| checkpoint | Record (Photo) batch number and date of manufacture of base coat
| checkpoint | Area completed to manufacturer's specification - photos attached below
89035656-ffd3-5a98-a77b-32aa6515b923 | note | Attach Client Signature Below
| checklist | Fatra Insulated Roof PVC Installation |  | Fatra Insulated Roof PVC Installation | e052db65-509a-42f5-96c1-2524a94d0b80
| section | Details
| checkpoint | Scope Description (from Bravada SOW) and item numbers
26f95d6f-0861-5c39-ac7b-1c74563d2b30 | textbox | SOW description entered
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Substrate Acceptance
2daac989-4a0f-58eb-9a1b-e0e016dc8088 | button | Substrate washed / cleaned & assessed for surface uniformity (photos attached below) | Yes,No
52bc80ea-2d0e-5077-b873-b9e71aa6487c | button | Substrate temperature is not less than 10*C and no greater then 35*C | Yes,No
4a8d3bfd-b839-5004-aa31-2d61173a79f3 | button | Substrate free from pooling or ponding water (Moisture gauge photo attached below) | Yes,No
d2ae3e64-ad5e-5893-883d-337ef982c3f6 | button | Adequate fall in substrate? | Yes,No
| checkpoint | Vapour barrier installation
8c5ae038-c04e-5ff3-8d25-102118b809f1 | button | Primer installed to manufacturer's specification (Record batch and install photos) | Yes,No
3cc24bb8-7bac-5028-b2eb-972751ee0b6a | button | Vapour barrier installed to manufacturer's specification (Record batch and install photos) | Yes,No
| checkpoint | Insulation Installation
478e1ea9-1759-5dc7-a899-1b3f3d45f263 | button | Vapour barrier free of pooling water? | Yes,No
b618520a-1fe2-55ed-a70d-7d00f249c8b6 | button | Foam adhesive applied to manufacturer's specification? | Yes,No
af682ba3-4d7e-5b97-8483-0a3f81de0509 | button | Insulation installed to fall? | Yes,No,N/A
| checkpoint | Membrane Installation
9aff8715-a3d5-5b5f-85c7-1689cd892eb6 | button | Installation of fleece-backed sheet membrane to floors with minimum 50mm overlaps? (Record batch and install photos) | Yes,No
1ff5fb4b-ef93-5d04-8e10-642cff9f2756 | button | Installation of termination profiles via to perimeter upstands & wall / floor junctions as per manufacturer's specifications as required? | Yes,No
760cd153-0792-56d5-8f92-c84e2fbcaf59 | button | Installation of sheet membrane to perimeters, incl. compatible sealant as required (profiles welded)? | Yes,No
| checkpoint | Area completed to manufacturer's specification? - photos attached below
| checklist | Fatra Underslab |  | Fatra Underslab | 59626d8e-e598-4e98-951f-20afc306cf90
| section | Details
| checkpoint | Scope Description (from Bravada SOW) and item numbers
4fd8b23c-5741-5f5a-8704-f5a91ce4d594 | textbox | Enter SOW description and attach TDS
| checkpoint | Substrate Preparation
4b5b5cd9-0259-52fa-a7b8-c0b1d6f73cd1 | textbox | Substrate assessed for surface uniformity - photos attached below
e6b3c568-a5af-51d3-b875-079311fc92b7 | textbox | Substrate free from pooling, ponding of flowing water
| checkpoint | Membrane installation
92849ad1-40bc-59f2-9c9d-5cdc9755ac29 | textbox | Record (Photo) batch number and date of manufacture of all materials
ca3955f1-df65-53a9-b959-1f4408899297 | textbox | Install Fatratex geotextile fabric
590592b9-ffa7-57aa-81b7-5777b400422c | textbox | Install Fatrafol 803V PVC membrane
e488ba1b-661a-52cb-a21a-f76542fb31b3 | textbox | Install Fatrafol 803V reinforcement PVC membrane to slab/wall junction
7bc2f05c-1e96-5b06-a3a3-8944722701c5 | textbox | Install FatraArmour protection board
| checkpoint | Area completed to manufacturer's specification - photos attached below
| checklist | Fatra Walls |  | Fatra Walls | c040c331-bbbc-483e-95ee-2a145cd6d486
| section | Details
| checkpoint | Scope Description (from Bravada SOW) and item numbers
c3b5fd87-b2f2-5d8b-8fc1-240ef1d37e35 | textbox | Enter SOW description and attach TDS
| checkpoint | Substrate Preparation
8f1ad69f-ba66-51c0-879f-ed5ccafaa855 | textbox | Substrate assessed for surface uniformity - photos attached below
| checkpoint | Membrane installation
8082483a-a102-54ae-bafd-dcda9a7d872e | textbox | Record (Photo) batch number and date of manufacture of all materials
1da0891b-7d73-5c3b-a894-cf603f1bf7a9 | textbox | Install Fatrafol 803V PVC membrane
250ffe27-e5ce-56c3-92f8-5a65f09c39be | button | Install FatraArmour protection board | Yes/No
aebc3b83-6170-57ef-af09-3cd8e39854b9 | button | Install Coreflute protection board | Yes/No
0fcd76f5-d7ed-5e13-986e-6f1d7ebcb2f3 | textbox | Install PVC termination profile
| checkpoint | Area completed to manufacturer's specification - photos attached below
| checklist | Floor Coatings |  | Floor Coatings | 99d711c5-ecff-4d6c-bda1-d3de3a725025
| checkpoint | Scope Description (from Bravada SOW) and item numbers
3f26cada-e56b-584c-8dcb-1536b6470f73 | textbox | Enter SOW description
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Substrate to be cleaned, mechanically grinded & assessed for surface uniformity - photos attached below
| checkpoint | Substrate temperature is not less then 5*C and no greater then 35*C
| checkpoint | Substrate free from pooling or ponding water - Moisture gauge photo attached below
ce8a85ac-a492-5a15-b7aa-33aad1d29bc9 | button | Adequate fall in substrate? | Yes,No
fb6c15f0-f9a3-5405-bbf7-2db45d72213d | note | If any of these checkpoints fail please provide information and required action by builder
703ec741-71ab-5a4e-8496-b721de9b1c95 | textbox | Add Comment
39022404-8c57-5cc7-9f41-4c816e758b86 | button | Installation of epoxy primer? | Yes,No
| checkpoint | Record (Photo) batch number and date of manufacture of primer
| checkpoint | Substrate free from surface water?
5e2aad06-60aa-51a4-927d-654f2d161d0e | button | Construction joints marked for mirroring after application? | Yes,No,N/A
4819f37d-f025-5486-8628-cbeb76111e21 | button | Installation of base coat? | Yes,No
| checkpoint | Record (Photo) batch number and date of manufacture of base coat
8bc5e7d6-77f3-5cc2-89cb-1eb88d579c2f | button | Broadcast of non-slip application if required | Yes,No,N/A
f170ef3f-2982-5fbc-80c8-244ca6a4d027 | button | Installation of top coat (UV stable if required)? | Yes,No,N/A
| checkpoint | Record (Photo) batch number and date of manufacture of top coat
c6d4c1e6-ac84-5fd8-8604-3c12d9b7d7c4 | button | Chase out onstruction joints and caulk? | Yes,No,N/A
| checkpoint | Area completed to manufacturer's specification - photos attached below
ce4d57fa-7f27-5142-a0f3-3aef7126876e | note | Add Comment
ac965013-4f0e-5fe8-9a78-e6cd4885b163 | note | Attach Client Signature Below
| checklist | Handover |  | Handover | aa9bb1f3-2b04-4200-bd6b-f139e83df835
| checkpoint | Scope Description (from Bravada SOW) and item numbers
3b38f2ae-4fbf-5eba-a72e-17576cf2ec03 | textbox | SOW description entered
f5e5e7e0-7d19-555d-897d-aa0b47fcdb62 | note | Bravada and Client Representative name/(s) and signature/(s) attached below
| checklist | ILD Testing |  | ILD Testing | 31a98a89-a627-4ebc-a506-40f38981d51e
| checkpoint | Scope Description (from Bravada SOW) and item numbers
18316e6c-f288-5b53-add2-59f9e7bc75b3 | textbox | SOW description entered
947c8c9c-3d16-53a4-8bc9-171e68c683c5 | button | ILD Test Requested? | Yes,No
32bb3202-947f-5d37-bf1c-7737096492c0 | button | ILD Test Performed | Yes,No
| checkpoint | ILD Test
a7d46359-d914-5d09-9434-ad143437f7b3 | note | ILD technician signature attached below
fb9ff672-0620-5cc0-bcd4-758d7e8b0e77 | note | ILD report attached below
| checklist | Internal |  | Internal | 11a11c00-8ca7-4ab0-95eb-ce2ccb0ce838
| checkpoint-no-value | Scope
4d51a533-c9f0-5d5b-966d-16fdf1d86c7c | note | Scope Description (from Bravada SOW) and item numbers
cc61a791-9f38-5a38-8ab5-99d3200b2187 | textbox | Enter SOW description
| checkpoint | Substrate clear of dust, debris and contaminants (Attach photos below)
869b5318-907b-5380-b944-718ac7f08b0d | button | Adequate fall in substrate? | Yes,No
fc96a2dc-836e-5291-ac2d-b1baf2c92e90 | note | If any of these checkpoints fail please provide information and required action by builder
3012f7c6-7b7c-5b5d-9402-e7fb5dfe735f | textbox | Add Comment
fb24a488-9153-5589-a9f1-9368b9cb9cef | button | Installation of tape or caulk to junctions. | Yes,No
2a591944-09dd-5fa6-a55a-6ea10e0f1196 | button | Penetrations correctly detailed? | Yes,No
010a0299-59e6-5c50-b7ad-4cf1ad1f966a | button | Waterstop correctly detailed? | Yes,No,N/A
7e9fae6e-5532-50b1-a341-60ebb4c31574 | button | Installation of liquid membrane to manufacturer's specification? | Yes,No
8076184d-8423-5402-8e43-2a0e396b2c72 | button | Installation of liquid membrane to perimeters, incl. compatible sealant as required? | Yes,No
| checkpoint | Area completed to manufacturer's specification? - attach photos below
| checkpoint | Record (Photo) batch number and date of manufacture of membrane
b24b58c1-87d2-56e3-918f-64a45620d7d3 | note | Attach Client Signature Below
| checklist | Leak Remediation |  | Leak Remediation | c8121bcc-88d1-4e3a-99f3-e68035525780
| checkpoint | Locate and identify source of leak
2481d615-6d87-538a-98d8-a8984a3f0ad1 | textbox | Enter description and location of leak
b9b68fd3-0d9c-515c-b2bb-288da4254e7b | button | Can Bravada offer a solution to the leak? | Yes,No
| checkpoint | Methodology to resolve leak
204b828a-c3b7-54e5-9a1f-5f3898b920f5 | textbox | Enter methodology
f71cd974-cad2-5ad6-a5a4-11413ef3903f | note | Attach TDS for any products used
| checkpoint | Provide photos of completed remediation
f644056f-7d91-5260-b27f-5744125dcc8f | button | Is ILD testing required? | Yes,No
450135f3-e303-5541-bf94-8f2695e05a18 | button | If ILD testing is required, did it pass? | Yes,No,N/A
38db331b-8adf-5cb1-bed3-1b061e92e7d0 | button | Has the leak been remediated? | Yes,No
| checklist | MataCryl Trafficable |  | MataCryl Trafficable | 4d01149f-08f1-4e83-93c3-e2e59a4694a9
| section | Details
| checkpoint | Scope Description (from Bravada SOW) and item numbers
38cab569-f797-59d2-a049-f646b6e97043 | textbox | Enter SOW description
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Preliminary Substrate Assessment for Potential Rectification
f41d6911-96e6-577d-a0a7-3bc6758a5b91 | button | Adequate fall in substrate? | Yes,No,N/A
2fb105ca-3ae1-5199-8670-340d33612898 | textbox | Provide description, photos and plan identifying any areas where the client is required to repair/remediate the substrate
| checkpoint | Substrate Assessment for Acceptance, and Adhesion Testing
6f113128-51af-5511-afe9-b111a1405d48 | button | Substrate deemed acceptable for membrane application as per VicRoads specification 691 | Yes,No
| checkpoint | Substrate Preparation
c8000910-8c67-5b7b-8c2a-a032b00cc875 | button | Substrate to be washed/cleaned | Yes,No
9057495b-9b53-5c2c-ba18-2cad305afcf9 | textbox | If any damage has occurred since initial assessment and/or rectification please identify and alert builder.
44d93ac6-2650-5282-858a-ada13a24f8de | button | Substrate ready for membrane application. | Yes,No
| checkpoint | Matacryl Primer H Application
b2e763ad-ba95-5878-9ceb-d191ec72b4d9 | button | Substrate free from surface water | Yes,No
c4407f4d-94f2-5785-90e4-6c9c1fafe4e7 | button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
2e23fcae-2653-52a0-9b3b-b20cf00e106a | button | Moisture content > 7% | Yes,No
dfb596f3-5d9a-5cdc-a8d6-ed6591ff52ae | textbox | Record (Photo) batch number and date of manufacture of primer
09b6bf38-9d29-5890-8c21-128961194399 | textbox | Record date/time, temperature and % catalyst at time of mixing primer
dd1c3c2f-d81d-5557-8f40-c94e88b66aab | button | Substrate free from surface water - record moisture reading | Yes,No
78849dc7-9782-5f12-8217-7915df27cfee | button | Primer installed before pot life expiry? | Yes,No
dafb7bc2-5c48-585f-9c09-6238793b147a | textbox | Record date and time of primer installation
0047e4db-c33f-50cc-a488-27d2d58cd341 | button | Quartz aggregate broadcast into primer | Yes,No
2b996476-a1fd-528d-8c26-d21078ddf33e | textbox | Record date and time of quartz broadcast
| checkpoint | Matacryl Manual Base Coat Application
368ed5cd-c4a2-5018-bda3-6b671be97c16 | button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
2e758321-1bdd-514b-95d9-202a9e3702f9 | textbox | Record (Photo) batch number and date of manufacture of MataCryl Manual
2f0ba8f8-7f37-58c8-ba58-3e124f427971 | textbox | Record date/time, temperature and % catalyst at time of mixing MataCryl Manual
729a8143-5e4a-5026-a183-f590e573f797 | button | MataCryl Manual installed before pot life expiry? | Yes,No
c47a9f01-191c-5a16-8384-4ca01a01d005 | button | MataCryl Thix installed to upturns before pot life expiry? | Yes,No
9c80f2c8-47e3-58ff-bea7-93c26122775d | textbox | Record date and time of MataCryl Manual installation
| checkpoint | Matacryl WL (Wearing Layer) First Top Coat Application
1cf936e9-0f91-590f-bdd9-fc996ce92fe5 | button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
e5b60403-f58a-5aa5-8667-982b9c9f69cc | textbox | Record (Photo) batch number and date of manufacture of MataCryl WL
efbb8808-ae77-5500-a1ba-f93dab1eefc9 | textbox | Record date/time, temperature and % catalyst at time of mixing MataCryl WL
9d2a4f39-2829-5fb2-a71a-9a7dc7e6f4e0 | button | MataCryl WL installed before pot life expiry? | Yes,No
e8b9541a-975f-5a87-ab76-a8fe6fe4eec1 | textbox | Record date and time of MataCryl WL installation
6d5ae0fd-b8c2-5833-be4b-b89312d071dd | button | Quartz aggregate broadcast into primer | Yes,No
d6105bab-218a-515f-849d-db54237fc03b | textbox | Record date and time of quartz broadcast
| checkpoint | Matacryl WL (Wearing Layer) Second Top Coat Application
dde7f578-1156-5dcc-b3f2-a431c0e4af3e | button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
1fa3c3c4-f5ce-5867-97a6-7b2de1276155 | textbox | Record (Photo) batch number and date of manufacture of MataCryl WL
b1943c27-30de-5334-b646-cb3b2c7a11e0 | textbox | Record date/time, temperature and % catalyst at time of mixing MataCryl WL
80604813-719d-5f55-a9d6-41532438344e | button | MataCryl WL installed before pot life expiry? | Yes,No
961a91c7-443d-5cbb-b2d9-6dbb76882ba8 | textbox | Record date and time of MataCryl WL installation
c0c55c1a-ad57-569d-8d12-725b9f986e1d | note | Attach Client Signature Below
| checklist | Park and Ride - Busway Sarnafil Installation |  | Park and Ride - Busway Sarnafil Installation | 68e4b566-6fb4-4be7-a7a4-e78e41fda697
| checkpoint | Scope Description (from Bravada SOW) and item numbers
ffb449bb-c4e6-5a2c-9ed3-33b7ebd2a759 | textbox | SOW description entered
| checkpoint | Attach TDS for application
| checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
| checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
| checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
| checkpoint | Adequate fall in substrate?
c2216853-72c7-508f-9a28-586c18591746 | note | If any of these checkpoints fail information and required action by builder provided in comments below
| checkpoint | Saw cuts (15mm deep x 5 mm wide) at Watertite membrane junctions able to accept Type 5 profile?
| checkpoint | Installation of Type 6 profile for junction with Watertite membrane?
| checkpoint | Installation of Type 8 profile on upturn?
| checkpoint | Adhesive installed to manufacturer's specification?
| checkpoint | Record (Photo) batch number and date of manufacture of adhesive
| checkpoint | Installation of sheet membrane to floor areas (min. 50mm overlaps)?
| checkpoint | Column bases (24) detailed to manufacturers specification?
| checkpoint | Installation of Type 5 profile to junction?
| checkpoint | Installation of sheet membrane to perimeters, incl. compatible sealant as required (profiles welded)?
| checkpoint | Area completed to manufacturer's specification? - photos attached below
| checklist | Park and Ride - Green Roof Sarnafil Installation |  | Park and Ride - Green Roof Sarnafil Installation | 178e36ce-5946-4c49-93dc-0311066813cb
| checkpoint | Scope Description (from Bravada SOW) and item numbers
409a702c-466b-51c7-a905-7d1741649b69 | textbox | SOW description entered
| checkpoint | Attach TDS for application
| checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
| checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
| checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
| checkpoint | Adequate fall in substrate?
93913b53-55f0-5427-8614-f5f3c1a5340c | note | If any of these checkpoints fail information and required action by builder provided in comments below
| checkpoint | Saw cuts (15mm deep x 5 mm wide) at Watertite membrane junctions able to accept Type 5 profile?
| checkpoint | Installation of Type 6 profile for junction with Watertite membrane?
| checkpoint | Installation of Type 8 profile on upturn?
| checkpoint | Adhesive installed to manufacturer's specification?
| checkpoint | Record (Photo) batch number and date of manufacture of adhesive
| checkpoint | Installation of sheet membrane to floor areas (min. 50mm overlaps)?
| checkpoint | Siphonic drains detailed to manufacturers specification?
| checkpoint | Installation of Type 5 profile to junction?
| checkpoint | Installation of sheet membrane to perimeters, incl. compatible sealant as required (profiles welded)?
| checkpoint | Installation of Dilatec tape detail to existing P-1200 membrane?
| checkpoint | Area completed to manufacturer's specification? - photos attached below
| checklist | Park and Ride - Watertite Membrane Junction Installation |  | Park and Ride - Watertite Membrane Junction Installation | 1cb0a33a-55e0-4890-8686-871458d17b32
| checkpoint | Scope Description (from Bravada SOW) and item numbers
f2edc11d-034a-5740-a0f8-61ce2009ef08 | textbox | SOW description entered
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
| checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
| checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
b7aebcc3-5236-541b-a059-1c52768cb25a | note | If any of these checkpoints fail information and required action by builder provided in comments below
| checkpoint | Saw cuts (15mm deep x 5 mm wide) at Watertite membrane (Watertite side) junctions able to accept Type 5 profile?
| checkpoint | Installation of Type 5 profile to junction?
| checkpoint | Adhesive installed to manufacturer's specification?
| checkpoint | Record (Photo) batch number and date of manufacture of adhesive
| checkpoint | Installation of sheet membrane (min. 50mm overlaps) to ?
| checkpoint | Area completed to manufacturer's specification? - photos attached below
| checklist | Planter (Liquid Membrane) |  | Planter (Liquid Membrane) | 9c35b224-d34c-4656-abdf-0fb1c4aec786
| checkpoint | Scope Description (from Bravada SOW) and item numbers
55f65dfe-760b-5b73-bdb4-8997a2f087bd | textbox | Enter SOW description
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Substrate cleaned & assessed for suitability to screed to? (Attach photos below)
| checkpoint | Sufficient fall in planter base?
864ee1dd-6493-5f57-b087-011219daa789 | button | Adequate fall in substrate? | Yes,No
| checkpoint | Substrate free from pooling or ponding water?
84d00589-e713-58c8-8bd2-e8d1ce1b36d0 | note | If any of these checkpoints fail please provide information and required action by builder
c146c4e7-73dd-5f93-9540-c41f6f5bb5ab | textbox | Add Comment
| checkpoint | Liquid membrane installed to manufacturer's specification?
| checkpoint | Anti-root additive applied to manufacturer's specification?
| checkpoint | Signoff of compliant installation.
dc461f20-5f0c-559d-8d2e-4708a95a4c1f | note | Client Signature
| checklist | Planter (PVC/Butynol Membranes) |  | Planter (PVC/Butynol Membranes) | e8f23b64-39c4-472a-a757-c0ce23821604
| checkpoint | Scope Description (from Bravada SOW) and item numbers
6385cdfb-584c-5484-8cf0-89b942696a49 | textbox | Enter SOW description
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Substrate cleaned & assessed for suitability to screed to? (Attach photos below)
| checkpoint | Sufficient fall in planter base?
e58806ba-3500-59dd-bf9d-a634afd5be14 | button | Adequate fall in substrate? | Yes,No
| checkpoint | Substrate free from pooling or ponding water?
9120d6ac-b79f-5638-98bc-27ae54e817ed | note | If any of these checkpoints fail please provide information and required action by builder
a54d7a1f-e2fd-54ad-af98-15b5cd2aebfb | textbox | Add Comment
| checkpoint | Sheet membrane installed to manufacturer's specification?
| checkpoint | Termination pressure bar installed?
| checkpoint | Signoff of compliant installation.
13a895d8-1016-5913-ba46-12351a90dad5 | note | Attach Client Signature Below
4c32e160-99bc-5891-bf27-731f691ba471 | note | Client Signature
| checklist | Planter (Torch-on Membrane) |  | Planter (Torch-on Membrane) | 03188f17-04db-4616-9c98-3fe37468f3ef
| checkpoint | Scope Description (from Bravada SOW) and item numbers
d429615e-3614-51fa-9d54-eb8dffd7304f | textbox | Enter SOW description
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Substrate cleaned & assessed for suitability to screed to? (Attach photos below)
| checkpoint | Sufficient fall in planter base?
4b660411-e908-56ae-8c2e-8b590368dc37 | button | Adequate fall in substrate? | Yes,No
| checkpoint | Substrate free from pooling or ponding water?
98fbdf31-d16e-5252-b2e9-6a0dc04a7687 | note | If any of these checkpoints fail please provide information and required action by builder
1092271e-f779-5b88-8f6f-f6572056249a | textbox | Add Comment
| checkpoint | Base layer membrane installed to manufacturer's specification?
| checkpoint | Base layer membrane installed to manufacturer's specification?
| checkpoint | Anti-root layer membrane applied to manufacturer's specification?
| checkpoint | Termination pressure bar installed?
| checkpoint | Signoff of compliant installation.
8cc58af8-a282-5d42-9662-38d2a2db4483 | note | Client Signature
| checklist | PVC Installation (Sarnafil and Cosmofin) |  | PVC Installation (Sarnafil and Cosmofin) | 9350c59e-6fdc-485e-8611-85a5f46cf85b
| checkpoint | Scope Description (from Bravada SOW) and item numbers
a24842c1-6839-5ab3-bc79-de779a7aea9e | textbox | SOW description entered
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
| checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
| checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
50c2b7d1-fc5d-519d-8ad6-99e1c413f3f7 | button | Adequate fall in substrate? | Yes,No
cc4e28ab-6952-55e9-8433-8513d8a51e62 | note | If any of these checkpoints fail information and required action by builder provided in comments below
2e3e37f3-0231-5d44-a14a-567d0cd4e841 | button | Adhesive installed to manufacturer's specification? | Yes,No
| checkpoint | Record (Photo) batch number and date of manufacture of adhesive
cf871860-27b0-574e-9daf-5691153f7fd5 | note | If any of these checkpoints fail information and required action by builder provided in comments below
9e204e94-ff4b-51c7-b069-68bdfd57e394 | button | Installation of termination profiles via to perimeter upstands & wall / floor junctions as per manufacturer's specifications as required? | Yes,No,N/A
8a873277-9ffd-52c5-9636-96a3afb49e74 | button | Installation of sheet membrane (min. 50mm overlaps)? | Yes,No
1c9a2e48-224b-556b-8338-47bdfdd0c930 | button | Installation of sheet membrane to perimeters, incl. compatible sealant as required (profiles welded)? | Yes,No
| checkpoint | Area completed to manufacturer's specification? - photos attached below
| checklist | PVC Installation (Sikaplan) |  | PVC Installation (Sikaplan) | b6fe8403-1692-45db-9e64-d20ae2975b13
| checkpoint | Scope Description (from Bravada SOW) and item numbers
f4eb22f9-bcfc-5f3b-b0b9-18ecad7bbe72 | textbox | SOW description and TDS for application (Download from Simpro)
| checkpoint | Substrate Assessment
13c1fa84-a225-51ed-956d-656cac7c3da7 | textbox | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
eee51d2f-2ed0-569b-bf3e-539ecb3d72dd | textbox | Substrate temperature is not less than 10*C and no greater then 35*C
41153742-0ec7-5426-ad9d-e6c01ce4bfe7 | textbox | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
91a203aa-e157-5c64-bb7e-9b373bd34948 | textbox | Adequate fall in substrate
f7e4fbe5-2158-5198-b609-7f7995972164 | note | If any of these checkpoints fail, information and required action by builder provided in comments below
| checkpoint | Membrane Installation to Flats
684440cc-fb06-5907-a0a2-536eaeb3f056 | textbox | Record (Photo) batch number and date of manufacture of Sarnacol 2152 adhesive and SikaPlan rolls
e1c7f4c9-35d7-5f9b-a8b7-b3cef087a2e8 | textbox | Sarnacol 2152 Adhesive installed to manufacturer's specification?
f6f29d68-59ea-5e28-b647-d61de2224c8b | textbox | Install and weld Sikaplan membrane over Sarnacol 2152 adhesive (min. 50mm overlaps)
1637cd27-c0d8-51aa-b61a-8fecb7bfd1c7 | button | Sufficient lap of Sikaplan left extended beyond formwork to create upturn? | Yes,No
| checkpoint | Membrane Installation to Upturns
235410f0-442a-5600-928a-df41d41cfb7b | textbox | Record (Photo) batch number and date of manufacture of Sikadur 31 epoxy, WP Tape, Sarnacol 2152 adhesive and Sikaplan rolls
b92dd499-2b53-552a-9ae7-c3942693cd0e | textbox | Sikadur 31 epoxy installed to manufacturer's specification
ccdeb512-cbad-5705-b204-10af80392858 | textbox | WP Tape installed into Sikadur 31 epoxy installed to manufacturer's specification
35c13d7d-cff6-5a9c-877a-1eeadb187fa7 | textbox | Sarnacol 2152 Adhesive installed to manufacturer's specification
dcc2f8f0-34b1-5218-91e3-7ef3ad756b4e | textbox | Install and weld Sikaplan membrane over Sarnacol 2152 adhesive (min. 50mm overlaps)
961bd46f-455d-5297-9862-3c046f17738c | textbox | Installation of backing rod to junction
| checkpoint | Waterbar Installation to Perimeter
21f7e355-8d32-5ec7-b850-bd07bf0fbd40 | textbox | Record (Photo) batch number and date of manufacture of Sika Waterbar
15af6164-1098-5212-b529-514c25786333 | textbox | Install and weld Sika Waterbar to perimeter of Sikaplan membrane, approximately 200m from formwork.
| checkpoint | Protection Installation
03d2b305-ae2d-596d-ae77-606365457e2f | button | Protection required? | Yes,No
99f4e5f1-6a64-54fb-b854-3a3340d8244b | textbox | If "Yes" to above, install contracted protection board with non-slip rating to membrane.
| checkpoint | Area completed to manufacturer's specification - photos attached below
| checklist | PVC Installation (Wolfin) |  | PVC Installation (Wolfin) | e7863054-93cd-4fd6-b82f-35cd97b0b799
| checkpoint | Scope Description (from Bravada SOW) and item numbers
5e87aaf3-848d-54dc-aed4-fb299b5d3e1f | textbox | SOW description entered
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
| checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
| checkpoint | Substrate free from pooling or ponding water, and adequate fall in substrate (Moisture gauge photo attached below)
ab2e9244-5b07-5e30-9e9c-5a192118bbed | note | If any of these checkpoints fail information and required action by builder provided in comments below
0154b2c6-7140-5524-9aba-64f5bdb912ef | button | Bitunamel primer installed to manufacturer's specification? | Yes,No
b1a1edef-d018-52b0-b69f-5f84a94f4917 | button | Bitunamel primer given adequate time (4 hours) to cure – as per manufacturer's specification? | Yes,No
| checkpoint | Record (Photo) batch numbers and dates of manufacture of bitunamel primer
| checkpoint | Area primed and suitable for membrane application. Substrate free of contaminants - photos attached below
71ddeaa2-c7f8-5ae8-a125-df17c8d31eb0 | textbox | If inspection failed, please provide reasons and recommended course of action
43afe1ca-b3d2-5fc3-a48e-f0a2f54c5e0b | button | Installation of termination profiles via to perimeter upstands & wall / floor junctions as per manufacturer's specifications as required? | Yes,No,N/A
4b655e9d-8d96-58e7-a62c-fd139265f701 | button | Installation of sheet membrane (min. 50mm overlaps)? | Yes,No
870274a2-8afd-53fc-a7ea-931fbf24eb93 | button | Installation of sheet membrane to perimeters, incl. compatible sealant as required (profiles welded)? | Yes,No
| checkpoint | Area completed to manufacturer's specification? - photos attached below
| checkpoint | Manufacturer Inspection
0e2e8602-7fa9-5e2f-bb20-775f7eeac4a9 | note | Manufacturer's Warranty Certificate attached below
| checklist | Retaining Wall (Liquid) |  | Retaining Wall (Liquid) | f2408195-41bb-438c-8136-532454d6a443
| checkpoint-no-value | Scope
55382fce-7b7f-5401-b909-16afe9dcd713 | note | Scope Description (from Bravada SOW) and item numbers
8583a526-51ba-562e-b2bf-c9edb009eb6a | textbox | Enter SOW description
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Substrate clear of depressions or protrusions that could damage membrane? (Attach photos)
7be925a5-c873-5f84-a1b0-45dffc1a5a72 | button | Installation of liquid membrane as required? | Yes,No
| checkpoint | Area completed to manufacturer's specification? (Attach photos)
a961f6c2-4aa4-5a8c-95b4-1f44c824478a | button | Cement sheet installed? | Yes,No,N/A
f4813d74-8268-584f-881b-b135314ada18 | button | Corflute installed installed? | Yes,No,N/A
6e1b9b59-c73e-5391-94ab-937968f3479e | button | Drainage cell and geotextile fabric installed? | Yes,No,N/A
| checkpoint | Backfilled within manufacturer's specified timeframe?
1553c7ea-f385-5090-a18a-2ac00e7ff87a | note | Attach Client Signature Below
| checklist | Retaining Wall (Sheet) |  | Retaining Wall (Sheet) | d125bc12-6b81-4452-b54e-8329025e1eb3
| checkpoint | Scope Description (from Bravada SOW) and item numbers
bd2ecaf4-f6c3-5713-844a-31d581378dc8 | textbox | Enter SOW description
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Substrate clear of depressions or protrusions that could damage membrane? (Attach photos)
ae27e60e-049d-5e9e-bc00-842e9667ab99 | button | Granules installed at cold joint? | Yes,No,N/A
3fc97ba5-af3f-55b1-b989-184b5b3eeedd | button | Installation of sheet membrane as required? | Yes,No
96b13be9-072a-5ae7-bce1-a188e823f842 | button | Termination pressure bar installed as required? | Yes,No
| checkpoint | Area completed to manufacturer's specification? (Attach photos)
e887b86d-1439-5365-bb45-2c90594ad23c | textbox | If inspection failed, please provide reasons and recommended course of action.
5e3a574c-288d-537a-b40e-efded9fcf5e0 | button | Cement sheet installed? | Yes,No,N/A
bd9ae0c8-0582-5cc0-b246-cf7bef68adc2 | button | Corflute installed installed? | Yes,No,N/A
f32401ee-515d-5cf8-9444-dfdf8efc4006 | button | Drainage cell and geotextile fabric installed? | Yes,No,N/A
| checkpoint | Backfilled within manufacturer's specified timeframe?
e15e78d2-b48b-5ee2-a15e-90127b1f3c6b | note | Attach Client Signature Below
| checklist | Screed |  | Screed | c0ee6532-ea4f-434e-bc70-f1925b85ff81
| checkpoint | Scope Description (from Bravada SOW) and item numbers
3b65925b-c9f4-538a-a35e-7b32327294d1 | textbox | Enter SOW description
| checkpoint | Substrate cleaned & assessed for suitability to screed to - photos attached below
| checkpoint | Sufficient setdown depth available to create adequate fall to wastes?
| checkpoint | Substrate free from pooling or ponding water?
| checkpoint | Minimum screed thickness of 20mm at waste available to achieve 1:100 fall?
eaf08061-bc1a-5ae4-a1c3-dffd84468e82 | note | If any of these checkpoints fail please provide information and required action by builder
d89c7388-56d8-577c-a91a-472b837ee843 | textbox | Add Comment
a05daf21-0b4a-5c0b-91e6-073db66a4575 | button | Screed mixed to manufacturer's specifications? | Yes,No
6dc157d3-aa0c-5fa7-a4ba-d8cef20e914b | button | Slurry applied for bonding as per manufacturer's specification? | Yes,No
| checkpoint | Screed completed and suitable for membrane application - photos attached below
60712525-fb33-5b1c-bd95-163798d73b72 | note | Attach Client Signature Below
| checklist | Torch-On Installation |  | Torch-On Installation | 69424b12-9600-4d79-860a-e028b8243c46
| checkpoint | Scope Description (from Bravada SOW) and item numbers
d220d04b-c396-5512-a5c7-30991ea9e57d | textbox | Enter SOW description
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
| checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
| checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
121b9edb-af20-5e98-ad90-0202333ac2d6 | button | Adequate fall in substrate? | Yes,No
eee796fc-cb76-54e8-b9d0-3a7362804ccc | button | Bitumen primer installed to manufacturer's specification? | Yes,No
43e05bc0-a958-5eea-92b0-7490f58b8e23 | button | Primer given adequate time to cure – as per manufacturers specification? | Yes,No
| checkpoint | Area completed and suitable for membrane application - photos attached below
| checkpoint | Substrate clear of dust, debris and contaminants - photos attached below
| checkpoint | Substrate free from surface water? (Moisture gauge photo attached below)
468068ea-86d3-5ba6-a2f1-93241294c350 | button | Installation of base layer membrane (min. 50mm overlaps) ? | Yes,No
da69695a-e9db-5e18-9787-cc0fbd4946a7 | dropdown | Type of second layer | Normal,Mineral,Antiroot
a11ea690-2aa9-5555-bb80-81a36dc94c05 | button | Installation of second layer membrane (min. 50mm overlaps) ? | Yes,No
2f16b0d9-7fcb-5c04-bba6-4badca2e001b | button | Termination pressure bar installed to all upturns where required? | Yes,No
| checkpoint | Area completed to manufacturer's specification? - photos attached below
bf630246-37ce-58b2-904e-699c1b348510 | note | Attach Client Signature Below
| checklist | VerseSeal (Exposed) |  | VerseSeal (Exposed) | 58146530-11d5-4924-bb70-3fc94808e941
| checkpoint | Scope Description (from Bravada SOW) and item numbers
6f06d353-3dd6-5bf7-96b4-d75dbad1d3b0 | textbox | Enter SOW description
| checkpoint | Attach TDS for application (Download from Simpro)
| checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
| checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
| checkpoint | Substrate free from pooling or ponding water - Moisture gauge photo attached below
a3c34d00-a293-5232-8c95-9323634dae25 | note | If any of these checkpoints fail please provide information and required action by builder
de69f744-6ffd-50cc-9821-bd6ee42cdec1 | textbox | Add Comment
| checkpoint | Record (Photo) batch number and date of manufacture of primer
8d35f484-c9a5-5ac5-9ec0-280ec61875d8 | button | Installation of primer as required (90 minute dry time)? | Yes,No
| checkpoint | Record (Photo) batch number and date of manufacture of base coat
9c2b8149-c2f9-50fc-bdbd-d9cb088447ea | button | Installation of base coat within required maximum curing time of primer (2kg per m2 or 7.5m2 per 15kg pail)? | Yes,No
db4fdae4-d6d8-5bf9-8f01-6d801ed461bf | button | Base coat installed to minimum film thickness? | Yes,No
| checkpoint | Record (Photo) batch number and date of manufacture of top coat
8f1a8f9f-e0cc-51b5-9104-e848401bb9d7 | button | Installation of top coat (4kg per m2 or 3.75m2 per 15kg pail)? | Yes,No,N/A
ad89507b-1c01-5d23-8473-5fdce70b2618 | button | Top coat installed to minimum film thickness? | Yes,No,N/A
e9429f72-8586-5f99-bd58-a1c83787ab81 | button | Broadcast of 7mm Basalt Scoria into wet / uncured liquid rubber (trowel scoria into liquid rubber 50% depth)? | Yes,No,N/A
| checkpoint | Area completed to manufacturer's specification - photos attached below
| checkpoint | BARPA inspection & sign off (project completion)