## Project Structure (2)
Folder Structure |  |  |  | Checklists | #NAME?
Site QA
Switchboard's
|  |  | DB-MSB | Switchboards
|  |  | DB-FARMERS (Including DB-F1) | Switchboards
|  |  | DB-F2 | Switchboards
|  |  | DB-F3 | Switchboards
|  |  | DB-F4 | Switchboards
|  |  | DB-RS-101 | Switchboards
|  |  | DB-RS-102 | Switchboards
|  |  | DB-RS-103 | Switchboards
|  |  | DB-RS-201 | Switchboards
|  |  | DB-RS-202 | Switchboards
|  |  | DB-RS-203 | Switchboards
|  |  | 1600A Generator Connection Box | Switchboards
Cable Tray
|  |  | E-200-1 Area | Cable Tray
|  |  | E-200-2 Area | Cable Tray
|  |  | E-200-3 Area | Cable Tray
|  |  | E-200-4 Area | Cable Tray
|  |  | E-201-1 Area | Cable Tray
|  |  | E-201-2 Area | Cable Tray
|  |  | E-201-3 Area | Cable Tray
|  |  | E-202 Area | Cable Tray
Ducting
|  |  | Mains Incoming Ducts (6x150) | Ducting
|  |  | Under Slab ducts-South Pit (4x150) | Ducting
|  |  | Pump Duct (2x50) | Ducting
|  |  | HV Duct (1x150 HD 900mm deep) | Ducting
|  |  | MSB-Pit North (1x100) | Ducting
|  |  | North Pit-East Pit (1x100) | Ducting
|  |  | East Pit-2 x pole lights (1x50) | Ducting
|  |  | East Pit-1 x pole lights (1x50) | Ducting
|  |  | South Pit-1st Pole light (2x50) | Ducting
|  |  | South 1st Pole Light-2 x South Pole Lights (1x50) | Ducting
|  |  | South 1st Pole Light-2 x East Pole Lights (1x50) | Ducting
First Fix
Ground Level
|  |  | Exterior Pole Lighting | First Fix Electrical
|  |  | Tenancy RS-101 | First Fix Electrical
|  |  | Tenancy RS-102 | First Fix Electrical
|  |  | Tenancy RS-103 | First Fix Electrical
|  |  | MSB Room | First Fix Electrical
|  |  | Comms Cupboard | First Fix Electrical
|  |  | Farmers Store Room | First Fix Electrical
|  |  | Concourse GL (Downlights & Emergency Lighitng) | First Fix Electrical
|  |  | Stair 02 | First Fix Electrical
|  |  | Lift 02 | First Fix Electrical
|  |  | B.O.H Store Room | First Fix Electrical
|  |  | Manager Office | First Fix Electrical
|  |  | Management Office | First Fix Electrical
|  |  | Meeting Room | First Fix Electrical
|  |  | Staff Room | First Fix Electrical
|  |  | Office | First Fix Electrical
|  |  | Secure | First Fix Electrical
|  |  | Corridor - 109.8 | First Fix Electrical
|  |  | Corridor - 109.11 | First Fix Electrical
|  |  | HWC - 109.12 | First Fix Electrical
|  |  | Locker Male | First Fix Electrical
|  |  | WC Male | First Fix Electrical
|  |  | WC Female | First Fix Electrical
|  |  | Locker Female | First Fix Electrical
|  |  | Pascoes Regional Office | First Fix Electrical
|  |  | E-200-1 Power (Common DB) | First Fix Electrical
|  |  | E-200-2 Area Power (Farmers Open area) | First Fix Electrical
|  |  | Farmers Escelator x 2 Power | First Fix Electrical
|  |  | E-200-3 Area Power (Farmers Open Area) | First Fix Electrical
|  |  | E100-3 Area - Tenancy MM-109 Lighting | First Fix Electrical
|  |  | Lift 01 | First Fix Electrical
|  |  | Stair 01 | First Fix Electrical
|  |  | Farmers DB-MSB Room | First Fix Electrical
|  |  | Farmers DB-F2 Room | First Fix Electrical
|  |  | Fire Power (E200-4) | First Fix Electrical
Level 1
|  |  | Tenancy RS-201 | First Fix Electrical
|  |  | Tenancy RS-202 | First Fix Electrical
|  |  | Tenancy RS-203 | First Fix Electrical
|  |  | E-201-1 Power (Common DB Circuits) | First Fix Electrical
|  |  | Farmers DB-F3 Room | First Fix Electrical
|  |  | E-201-2 Area Power (Farmers Open area) | First Fix Electrical
|  |  | E-201-3 Area Power (Farmers Open area) | First Fix Electrical
|  |  | E101-2 & E-101-3 Area - Tenancy MM-209 Lighting | First Fix Electrical
|  |  | Farmers DB-F4 Room | First Fix Electrical
|  |  | E-201-4 & E-101-4 (Common DB WC Circuits) | First Fix Electrical
|  |  | Concourse L.01 (Downlights & Emergency Lighitng) | First Fix Electrical
Second Fix
Ground Level
|  |  | Exterior Pole Lighting | Second Fix Electrical
|  |  | Tenancy RS-101 | Second Fix Electrical
|  |  | Tenancy RS-102 | Second Fix Electrical
|  |  | Tenancy RS-103 | Second Fix Electrical
|  |  | MSB Room | Second Fix Electrical
|  |  | Comms Cupboard | Second Fix Electrical
|  |  | Farmers Store Room | Second Fix Electrical
|  |  | Concourse GL (Downlights & Emergency Lighitng) | Second Fix Electrical
|  |  | Stair 02 | Second Fix Electrical
|  |  | Lift 02 | Second Fix Electrical
|  |  | B.O.H Store Room | Second Fix Electrical
|  |  | Manager Office | Second Fix Electrical
|  |  | Management Office | Second Fix Electrical
|  |  | Meeting Room | Second Fix Electrical
|  |  | Staff Room | Second Fix Electrical
|  |  | Office | Second Fix Electrical
|  |  | Secure | Second Fix Electrical
|  |  | Corridor - 109.8 | Second Fix Electrical
|  |  | Corridor - 109.11 | Second Fix Electrical
|  |  | HWC - 109.12 | Second Fix Electrical
|  |  | Locker Male | Second Fix Electrical
|  |  | WC Male | Second Fix Electrical
|  |  | WC Female | Second Fix Electrical
|  |  | Locker Female | Second Fix Electrical
|  |  | Pascoes Regional Office | Second Fix Electrical
|  |  | E-200-1 Power (Common DB) | Second Fix Electrical
|  |  | E-200-2 Area Power (Farmers Open area) | Second Fix Electrical
|  |  | Farmers Escelator x 2 Power | Second Fix Electrical
|  |  | E-200-3 Area Power (Farmers Open Area) | Second Fix Electrical
|  |  | E100-3 Area - Tenancy MM-109 Lighting | Second Fix Electrical
|  |  | Lift 01 | Second Fix Electrical
|  |  | Stair 01 | Second Fix Electrical
|  |  | Farmers DB-MSB Room | Second Fix Electrical
|  |  | Farmers DB-F2 Room | Second Fix Electrical
|  |  | Fire Power (E200-4) | Second Fix Electrical
Level 1
|  |  | Tenancy RS-201 | Second Fix Electrical
|  |  | Tenancy RS-202 | Second Fix Electrical
|  |  | Tenancy RS-203 | Second Fix Electrical
|  |  | E-201-1 Power (Common DB Circuits) | Second Fix Electrical
|  |  | Farmers DB-F3 Room | Second Fix Electrical
|  |  | E-201-2 Area Power (Farmers Open area) | Second Fix Electrical
|  |  | E-201-3 Area Power (Farmers Open area) | Second Fix Electrical
|  |  | E101-2 & E-101-3 Area - Tenancy MM-209 Lighting | Second Fix Electrical
|  |  | Farmers DB-F4 Room | Second Fix Electrical
|  |  | E-201-4 & E-101-4 (Common DB WC Circuits) | Second Fix Electrical
|  |  | Concourse L.01 (Downlights & Emergency Lighitng) | Second Fix Electrical
FEL SM Weekly Site Checklist
| 2025-01-06 |  |  | FEL SM Weekly Site Checklist
| 2025-01-13 |  |  | FEL SM Weekly Site Checklist
| 2025-01-20 |  |  | FEL SM Weekly Site Checklist
| 2025-01-27 |  |  | FEL SM Weekly Site Checklist
| 2025-02-03 |  |  | FEL SM Weekly Site Checklist
| 2025-02-10 |  |  | FEL SM Weekly Site Checklist
| 2025-02-17 |  |  | FEL SM Weekly Site Checklist
| 2025-02-24 |  |  | FEL SM Weekly Site Checklist
| 2025-03-03 |  |  | FEL SM Weekly Site Checklist
| 2025-03-10 |  |  | FEL SM Weekly Site Checklist
| 2025-03-17 |  |  | FEL SM Weekly Site Checklist
| 2025-03-24 |  |  | FEL SM Weekly Site Checklist
| 2025-03-31 |  |  | FEL SM Weekly Site Checklist
| 2025-04-07 |  |  | FEL SM Weekly Site Checklist
| 2025-04-14 |  |  | FEL SM Weekly Site Checklist
| 2025-04-21 |  |  | FEL SM Weekly Site Checklist
| 2025-04-28 |  |  | FEL SM Weekly Site Checklist
| 2025-05-05 |  |  | FEL SM Weekly Site Checklist
| 2025-05-12 |  |  | FEL SM Weekly Site Checklist
| 2025-05-19 |  |  | FEL SM Weekly Site Checklist
| 2025-05-26 |  |  | FEL SM Weekly Site Checklist
| 2025-06-02 |  |  | FEL SM Weekly Site Checklist
| 2025-06-09 |  |  | FEL SM Weekly Site Checklist
| 2025-06-16 |  |  | FEL SM Weekly Site Checklist
| 2025-06-23 |  |  | FEL SM Weekly Site Checklist
| 2025-06-30 |  |  | FEL SM Weekly Site Checklist
| 2025-07-07 |  |  | FEL SM Weekly Site Checklist
| 2025-07-14 |  |  | FEL SM Weekly Site Checklist
| 2025-07-21 |  |  | FEL SM Weekly Site Checklist
| 2025-07-28 |  |  | FEL SM Weekly Site Checklist
| 2025-08-04 |  |  | FEL SM Weekly Site Checklist
| 2025-08-11 |  |  | FEL SM Weekly Site Checklist
| 2025-08-18 |  |  | FEL SM Weekly Site Checklist
| 2025-08-25 |  |  | FEL SM Weekly Site Checklist
| 2025-09-01 |  |  | FEL SM Weekly Site Checklist
| 2025-09-08 |  |  | FEL SM Weekly Site Checklist
| 2025-09-15 |  |  | FEL SM Weekly Site Checklist
| 2025-09-22 |  |  | FEL SM Weekly Site Checklist
| 2025-09-29 |  |  | FEL SM Weekly Site Checklist
| 2025-10-06 |  |  | FEL SM Weekly Site Checklist
| 2025-10-13 |  |  | FEL SM Weekly Site Checklist
| 2025-10-20 |  |  | FEL SM Weekly Site Checklist
| 2025-10-27 |  |  | FEL SM Weekly Site Checklist
| 2025-11-03 |  |  | FEL SM Weekly Site Checklist
| 2025-11-10 |  |  | FEL SM Weekly Site Checklist
| 2025-11-17 |  |  | FEL SM Weekly Site Checklist
| 2025-11-24 |  |  | FEL SM Weekly Site Checklist
| 2025-12-01 |  |  | FEL SM Weekly Site Checklist
| 2025-12-08 |  |  | FEL SM Weekly Site Checklist
| 2025-12-15 |  |  | FEL SM Weekly Site Checklist
| 2025-12-22 |  |  | FEL SM Weekly Site Checklist
| 2025-12-29 |  |  | FEL SM Weekly Site Checklist

## Ducting
Section | Ducting
Checkpoint | Trench marked & dug in correct location
Checkpoint | Trench correct depth
Checkpoint | Correct size & Type ducting installed
Checkpoint | Correct cable cover & danger tape installed
Checkpoint | Draw wires installed
Checkpoint | Ducting starts & stops / comes up wall in correct location
Checkpoint | Ducting in back filled & compacted correctly
Checkpoint | Pits installed in correct location & to height
Checkpoint | Ducting sealed around as they enter & exit each pit
Checkpoint | Ducting entering Light Pole cages Correctly
Checkpoint | Pole light cages & foundations installed correctly
section | Photos

## First Fix Electrical
type | name
checklist | QA - First Fix
section | Flush Boxes
checkpoint | Height as per plan
checkpoint | Location as per plan
checkpoint | Correct Flush Boxes Installed (plastic, fire including pad, acoustic)
section | Cabling
checkpoint | All Bonding cables installed (check metal benches & appliances)
checkpoint | Cat wires installed correctly (approved fixing positions)
checkpoint | Power cables installed correctly
checkpoint | Lighting cables installed correctly
checkpoint | Circuits clearly labelled on both ends of each cable
checkpoint | Separation between Data and Power at 300mm or as specified
checkpoint | All cables secured via cable ties with ends cut
section | QA - Lights
checkpoint | General Lighting Setout Correct
checkpoint | Cabling in correct location
checkpoint | Emergency/ Exit Lighting Setout Correct
checkpoint | Nogging installed for Electrical Services
checkpoint | Downlights cut into gib in correct locations
section | Photos

## Cable Tray
Section | Cable Tray
Checkpoint | Unistrutt Filed & Painted
Checkpoint | Hangers Spaced as Specified
Checkpoint | Correct Size Cable Tray Installed
Checkpoint | Tray Joined Correctly
Checkpoint | Hangers Sceismicly Restrained / Under 400mm drop
Checkpoint | Tray Fastened to Hangers
Checkpoint | Correct Anchors used fixing to Ceiling / Walls
Checkpoint | Cable Tray Bonded
section | Photos

## Switchboards
section | Switchboard
checkpoint | Spatial certificate signed if required
checkpoint | Fixings installed in wall correctly if board is wall mounted
checkpoint | All clearances sighted to ensure location is compliant
checkpoint | All cables correctly installed in protection device and earth and neutral bars and fully secured
checkpoint | Cables neatly dressed
checkpoint | Phase tabs on chassis covered
checkpoint | All earths and neutrals labelled to match phase numbers
checkpoint | Switchboard is clean on the inside and outside
checkpoint | Masking blanks installed
checkpoint | DB legend installed
checkpoint | Feisst label on the door installed
checkpoint | Switchboard has all gaps sealed to meet fire standards
section | Photos

## Second Fix Electrical
type | name | values
checklist | QA - Second fix
section | Power Outlets
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Outlet Installed level
checkpoint | Circuit Tested and results recorded
checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
section | Light Switches
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Light switch Installed level
checkpoint | Circuit Tested and results recorded
checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
section | Light Fixtures
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Tested for operation
section | Photos

## SM Weekly Checklist
type | name
checklist | FEL SM Weekly Site Checklist
section | Monday
checkpoint | Prestart Meeting with Team
checkpoint | Health Check
checkpoint | Review Tasks for the week
checkpoint | Identify Targets Including Hours
checkpoint | Approve hours by 7:30AM for previous week
checkpoint | Sign off Subcontractor Hours & Submit
checkpoint | Review SWMS
checkpoint | Site Toolbox Meeting
checkpoint | SSSP in Order
section | Tuesday
checkpoint | Follow up outstanding RFI's with PM
section | Wednesday
checkpoint | Review Roadblocks & Follow Up if still unresolved
checkpoint | QAs up to date
section | Thursday
checkpoint | Weekly planner filled out for week ahead
checkpoint | Roadblocks identified and actioned
checkpoint | Materials organized for week ahead
checkpoint | Plans printed with any relevant notes added
section | Friday
checkpoint | Submit Toolbox minutes to main contractor and FEL office
checkpoint | Job Cards up to date and submitted
checkpoint | Team tasks for week ahead filled out on whiteboard