## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Switchboards
| Scope |  |  | Site QA | Switchboards
Rows
|  | Switchboards | dynamic | Site QA | Switchboards
Columns
|  | Spatial certificate signed if required |  | Spatial certificate signed if required
|  | Fixings installed in wall correctly if board is wall mounted |  | Fixings installed in wall correctly if board is wall mounted
|  | All clearances sighted to ensure location is compliant |  | All clearances sighted to ensure location is compliant
|  | All cables correctly installed in protection device & earth & neutral bars & fully secured |  | All cables correctly installed in protection device and earth and neutral bars and fully secured
|  | Cables neatly dressed |  | Cables neatly dressed
|  | Phase tabs on chassis covered |  | Phase tabs on chassis covered
|  | All earths & neutrals labelled to match phase numbers |  | All earths and neutrals labelled to match phase numbers
|  | Switchboard is clean on the inside & outside |  | Switchboard is clean on the inside and outside
|  | Masking blanks installed |  | Masking blanks installed
|  | DB legend installed |  | DB legend installed
|  | Feisst label on the door installed |  | Feisst label on the door installed
|  | Switchboard has all gaps sealed to meet fire standards |  | Switchboard has all gaps sealed to meet fire standards
Cable Tray
| Scope |  |  | Site QA | Cable Tray
Rows
|  | Cable Tray | dynamic | Site QA | Cable Tray
Columns
|  | Unistrutt Filed & Painted |  | Unistrutt Filed & Painted
|  | Hangers Spaced as Specified |  | Hangers Spaced as Specified
|  | Correct Size Cable Tray Installed |  | Correct Size Cable Tray Installed
|  | Tray Joined Correctly |  | Tray Joined Correctly
|  | Hangers Sceismicly Restrained/Under 400mm drop |  | Hangers Sceismicly Restrained / Under 400mm drop
|  | Tray Fastened to Hangers |  | Tray Fastened to Hangers
|  | Correct Anchors used fixing to Ceiling/Walls |  | Correct Anchors used fixing to Ceiling / Walls
|  | Cable Tray Bonded |  | Cable Tray Bonded
Ducting
| Scope |  |  | Site QA | Ducting
Rows
|  | Ducting | dynamic | Site QA | Ducting
Columns
|  | Trench marked & dug in correct location |  | Trench marked & dug in correct location
|  | Trench correct depth |  | Trench correct depth
|  | Correct size & Type ducting installed |  | Correct size & Type ducting installed
|  | Correct cable cover & danger tape installed |  | Correct cable cover & danger tape installed
|  | Draw wires installed |  | Draw wires installed
|  | Ducting starts & stops/comes up wall in correct location |  | Ducting starts & stops / comes up wall in correct location
|  | Ducting in back filled & compacted correctly |  | Ducting in back filled & compacted correctly
|  | Pits installed in correct location & to height |  | Pits installed in correct location & to height
|  | Ducting sealed around as they enter & exit each pit |  | Ducting sealed around as they enter & exit each pit
|  | Ducting entering Light Pole cages Correctly |  | Ducting entering Light Pole cages Correctly
|  | Pole light cages & foundations installed correctly |  | Pole light cages & foundations installed correctly
First Fix
| Scope |  |  | Site QA | First Fix
Rows
|  | Ground Level | dynamic | Site QA | First Fix | Ground Level
|  | Level 1 |  | Site QA | First Fix | Level 1
Columns
|  | Flush Boxes - Height as per plan |  | Height as per plan | Flush Boxes
|  | Flush Boxes - Location as per plan |  | Location as per plan | Flush Boxes
|  | Flush Boxes - Correct Flush Boxes Installed (plastic, fire including pad, acoustic) |  | Correct Flush Boxes Installed (plastic, fire including pad, acoustic) | Flush Boxes
|  | Cabling - All Bonding cables installed (check metal benches & appliances) |  | All Bonding cables installed (check metal benches & appliances) | Cabling
|  | Cabling - Cat wires installed correctly (approved fixing positions) |  | Cat wires installed correctly (approved fixing positions) | Cabling
|  | Cabling - Power cables installed correctly |  | Power cables installed correctly | Cabling
|  | Cabling - Lighting cables installed correctly |  | Lighting cables installed correctly | Cabling
|  | Cabling - Circuits clearly labelled on both ends of each cable |  | Circuits clearly labelled on both ends of each cable | Cabling
|  | Cabling - Separation between Data & Power at 300mm or as specified |  | Separation between Data and Power at 300mm or as specified | Cabling
|  | Cabling - All cables secured via cable ties with ends cut |  | All cables secured via cable ties with ends cut | Cabling
|  | Lights - General Lighting Setout Correct |  | General Lighting Setout Correct | QA - Lights
|  | Lights - Cabling in correct location |  | Cabling in correct location | QA - Lights
|  | Lights - Emergency/ Exit Lighting Setout Correct |  | Emergency/ Exit Lighting Setout Correct | QA - Lights
|  | Lights - Nogging installed for Electrical Services |  | Nogging installed for Electrical Services | QA - Lights
|  | Lights - Downlights cut into gib in correct locations |  | Downlights cut into gib in correct locations | QA - Lights
Second Fix
| Scope |  |  | Site QA | Second Fix
Rows
|  | Ground Level | dynamic | Site QA | Second Fix | Ground Level
|  | Level 1 |  | Site QA | Second Fix | Level 1
Columns
|  | Power Outlets - Correct type installed |  | Correct type installed | Power Outlets
|  | Power Outlets - Correctly installed with terminations all secured properly |  | Correctly installed with terminations all secured properly | Power Outlets
|  | Power Outlets - Outlet Installed level |  | Outlet Installed level | Power Outlets
|  | Power Outlets - Circuit Tested & results recorded |  | Circuit Tested and results recorded | Power Outlets
|  | Power Outlets - Description Labelled on the outlet face with vivid & with dymo labeller on cover plate & ensure label is level |  | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level | Power Outlets
|  | Light Switches - Correct type installed |  | Correct type installed | Light Switches
|  | Light Switches - Correctly installed with terminations all secured properly |  | Correctly installed with terminations all secured properly | Light Switches
|  | Light Switches - Light switch Installed level |  | Light switch Installed level | Light Switches
|  | Light Switches - Circuit Tested & results recorded |  | Circuit Tested and results recorded | Light Switches
|  | Light Switches - Description Labelled on the outlet face with vivid & with dymo labeller on cover plate & ensure label is level |  | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level | Light Switches
|  | Light Fixtures - Correct type installed |  | Correct type installed | Light Fixtures
|  | Light Fixtures - Correctly installed with terminations all secured properly |  | Correctly installed with terminations all secured properly | Light Fixtures
|  | Light Fixtures - Tested for operation |  | Tested for operation | Light Fixtures
FEL SM Weekly Site Progress
| Scope |  |  | FEL SM Weekly Site Checklist
Rows
|  | FEL SM Weekly Site Checklist | dynamic | FEL SM Weekly Site Checklist
Columns
|  | Monday |  | Monday
|  | Prestart Meeting with Team |  | Prestart Meeting with Team
|  | Health Check |  | Health Check
|  | Review Tasks for the week |  | Review Tasks for the week
|  | Identify Targets Including Hours |  | Identify Targets Including Hours
|  | Approve hours by 9AM for previous week |  | Approve hours by 9AM for previous week
|  | Sign off Subcontractor Hours & Submit |  | Sign off Subcontractor Hours & Submit
|  | Review SWMS |  | Review SWMS
|  | Site Toolbox Meeting |  | Site Toolbox Meeting
|  | SSSP in Order |  | SSSP in Order
|  | Tuesday |  | Tuesday
|  | Follow up outstanding RFI's with PM |  | Follow up outstanding RFI's with PM
|  | Wednesday |  | Wednesday
|  | Review Roadblocks & Follow Up if still unresolved |  | Review Roadblocks & Follow Up if still unresolved
|  | QAs up to date |  | QAs up to date
|  | Thursday |  | Thursday
|  | Weekly planner filled out for week ahead |  | Weekly planner filled out for week ahead
|  | Roadblocks identified and actioned |  | Roadblocks identified and actioned
|  | Materials organized for week ahead |  | Materials organized for week ahead
|  | Plans printed with any relevant notes added |  | Plans printed with any relevant notes added
|  | Friday |  | Friday
|  | Submit Toolbox minutes to main contractor and FEL office |  | Submit Toolbox minutes to main contractor and FEL office
|  | Job Cards up to date and submitted |  | Job Cards up to date and submitted
|  | Team tasks for week ahead filled out on whiteboard |  | Team tasks for week ahead filled out on whiteboard