## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Add Documentation |  | Add Documentation | f51fa371-acaf-4bd5-af91-442d769ba09e
| section | Details
| checkpoint | Please upload all documements and press PASS.
| checklist | Carpet Installation |  | Carpet Installation | cddc37b4-dd3a-4c3f-9ef9-db69a36c3229
| section | Details
| checkpoint | Substrate clean and approved for installation?
| checkpoint | Are sills, door frames & tiles flush with carpet?
| checkpoint | Doors to be removed?
| checkpoint | Confirm plan matches site and joins ok?
| checkpoint | Confirm the underlay type from job sheet?
| checkpoint | Take photo of carpet joins?
| checkpoint | Area dust free and all rubbish removed?
| checkpoint | No damage to joinery, skirtings or walls?
| checkpoint | Has the floor been protected?
| checkpoint | Installation complete with no damage?
| signoff | Please signoff / request sign off
c755ba6d-cc14-48b7-b857-ac5c6c2947c9 | checklist | Carpet Tiles Installation |  | QA Carpet Tile Installation : | cb47124f-d3b6-4881-83e6-5c87c75b2f01
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
3e5897ea-15f3-46bf-b8f4-09ec59218523 | checkpoint | Carpet tile range and colour check and confirmed
ca7af71d-548d-4271-82d5-f91e1eb21437 | checkpoint | Area / Location to receive carpet tiles
0b919c41-9165-5e29-816f-07ff4a87f876 | textbox
3532ecac-75ae-4ea3-854d-dc05161964e5 | checkpoint | Floor prep required ?
91ba2909-8cb2-5a4b-aedb-b40d54d1bd25 | textbox
169e1a52-41ac-4c26-9a53-294cfc40585c | checkpoint | Installation direction confirmed ?
1d613fa5-4aa9-4b5d-92b7-441fd2b3f438 | checkpoint | Setting out lines square ?
02ce727b-a5dd-4c24-8eda-32c3a18156aa | checkpoint | Are all edges free from fraying ?
6192cd56-5fa2-495f-919d-a7d392832aa1 | checkpoint | Are all edges cut neat and straight?
7ae6fe07-6a0a-41ca-bec2-53b8e2010ba7 | checkpoint | Carpet tile adhesive used
7af8d0dc-ff0e-56dd-ba5a-1931b6cc8f31 | note | x1 Pictures
d2dae3fd-f1bc-4394-85d7-b6acded2717d | checkpoint | Completed Carpet Tile installation
9a74155b-f21a-5bf5-8025-8359e41031ef | note | x4 Pictures
c062a656-2501-4b33-9ade-fb586f853bfd | checkpoint | Check and clean any excess adhesive in joints, on wall, or skirting
139fcae5-bae5-43c3-bfca-24d9c03d6d2e | checkpoint | Transition between other floor covering level and flush
1606949e-9f0a-4713-83ac-d9e56454bdf1 | checkpoint | Phase completed with no damage ?
5608e008-a164-4b9c-acc1-422397f875d0 | signoff | Please signoff / request sign off
| checklist | Concrete Moisture Test - On slab method |  | Concrete Moisture Test - On slab method | 1224d924-7156-4b13-891e-ed6c12c611aa
| section | Details
| checkpoint-no-value | General Details
9a70cc11-c705-5ced-af0b-45aa134349ee | note | According to the NZS AS 1884:2013, the acceptable level of concrete moisture content is less than 4.4%
603ac0e7-5bfc-5ff1-9ae4-1cd949dc12f2 | date | Date of test
6b9d03af-3cfa-5640-ab8e-f54e0aed6f26 | textbox | Project name
| checkpoint-no-value | Hygrometer device used for test
77cf09cb-0daa-5d98-abf5-2323b4b79dd6 | tickbox | Photo of Hygrometer device uploaded?
| checkpoint-no-value | Test 1
2acde898-3ab9-50a1-89c6-1bc61119b0d4 | textbox | Area/Location of test and result
a7915bd5-68df-59ac-8fc0-26b720306594 | button | Result | PASS, FAIL
| checkpoint-no-value | Test 2
bd0b479f-82c8-5f03-a006-3c64ab14a6ac | textbox | Area/Location of test and result
b715fbdf-945a-56f1-8049-4140dc4ff7a9 | button | Result | PASS, FAIL
| checkpoint-no-value | Test 3
ac83af32-bc46-5f18-915a-59c0dd7990ec | textbox | Area/Location of test and result
75c156fa-4ce2-54d1-83e1-448419a97b81 | button | Result | PASS, FAIL
| checkpoint-no-value | Test 4
c844ac56-9769-5e79-8bba-77c09394bdb8 | textbox | Area/Location of test and result
a32adcfc-1cbf-5f42-aa2a-2761f7b1bfc0 | button | Result | PASS, FAIL
| checkpoint-no-value | Test 5
94ce18f3-9ba1-5e5e-93c5-6517440b791a | textbox | Area/Location of test and result
52b7db28-2c51-5913-b49c-4344d4bcc7e4 | button | Result | PASS, FAIL
| checkpoint-no-value | Test 6
eef7def3-e691-563e-8aed-aa649013c782 | textbox | Area/Location of test and result
78972e78-cf72-5634-810a-aeb6c8063135 | button | Result | PASS, FAIL
| checkpoint-no-value | Test 7
c46cfcf7-340c-5b68-9a4d-931b3fb58a6d | textbox | Area/Location of test and result
44f7c451-d0e3-5417-863d-a6ed5a8df6f8 | button | Result | PASS, FAIL
| checkpoint-no-value | Test 8
464c3a79-80ed-5d52-abc8-12546edf095a | textbox | Area/Location of test and result
83ae4462-5b23-50c6-8179-dc6f2044de1f | button | Result | PASS, FAIL
| checkpoint-no-value | Test 9
4e4a136d-ef85-5188-910e-ea1c3c9e68a2 | textbox | Area/Location of test and result
cc590dbf-abce-5a6e-a95f-bae67dd28acf | button | Result | PASS, FAIL
| checkpoint-no-value | Test 10
f70c5858-fb00-54ec-bd1d-490f02c51ae1 | textbox | Area/Location of test and result
a58d88e3-7a9e-5749-a4ca-5c57950b8e9e | button | Result | PASS, FAIL
| checkpoint-no-value | Remarks from examinee
bf927e70-7097-5e37-b6e8-4498437be978 | textbox | Remarks/conclusion
| signoff | Click here to signoff
| checklist | Floor Prep |  | Floor Prep | 27de56a0-1fef-4394-bc16-cf2cf710fa2a
| section | Details
| checkpoint | Survey floor for flatness?
| checkpoint | Moisture test done prior to installation?
| checkpoint | At-risk surfaces protected?
| checkpoint | Mapeproof 2x coats north to south east to west applied?
| checkpoint | All areas dammed up to prevent leaks?
| checkpoint | Floor level complete?
| checkpoint | Area clear of rubbish and debris?
| checkpoint | No damage to other surfaces?
| checkpoint | Levels checked and ready for installation?
| checkpoint | Preparation complete with no damage?
| signoff | Please signoff / request sign off
| checklist | Floor Vinyl / LVT / Marmoleum |  | Floor Vinyl / LVT / Marmoleum | 2ba9778b-3a91-4e1b-833c-4ed6b1f51d89
| checkpoint | Substrate clean and approved for installation?
| checkpoint | Moisture test done prior to installation?
| checkpoint | Specify glue to use e.g 68T, UZ2000 or Marmoleum glue.
| checkpoint | Doors to be removed?
| checkpoint | All capping installed?
| checkpoint | All butterfly corners done with templet, images required?
| checkpoint | All areas welded?
| checkpoint | No excess glue on vinyl surface?
| checkpoint | All transition trims installed?
| checkpoint | Area dust free and all rubbish removed?
| checkpoint | Has the floor been protected?
| checkpoint | Installation complete with no damage to joinery, skirtings or walls?
| signoff | Please signoff / request sign off by Site Manager
| checklist | GB Add Documentation |  | GB Add Documentation | 3be8cec6-0295-435f-9009-b744ff5e2ec5
| checkpoint | Please upload all documements and press PASS.
| checklist | GB Carpet Installation |  | GB Carpet Installation | 1a7cd0dc-632f-440e-8115-f1228f538b46
| checkpoint | Substrate clean and approved for installation?
3e32f1c4-1fcb-5059-9791-bff82f4d09ee | note | x 2 Picture
| checkpoint | Are sills, door frames & tiles flush with carpet?
bfef985e-2488-50fc-99aa-e462a77168db | note | x 2 Pictures min
| checkpoint | Doors to be removed? Take pictures before and after (proof no damage)
5722013e-711e-513d-9637-58ecceb64fb6 | note | x 2 Pictures min
| checkpoint | Confirm plan matches site and joins ok?
| checkpoint | Review job sheet confirm all detail matches e.g. colour of carpet, underlay required?
| checkpoint | Take photo of carpet joins?
0f2febc2-18e4-5780-9010-a8cf7dc4271d | note | x 2 Pictures min
| checkpoint | No damage to skirtings or walls?
165b61ab-0677-5202-8c3c-824aaa159776 | note | x 4 Pictures min
| checkpoint | Doors replaced and area left clean of offcuts and rubbish? Take pictures before and after (proof no damage)
7cefd8db-922b-5696-8c9e-4b350e41e137 | note | x 2 Pictures min
| checkpoint | Walked all areas, pins tapped down, stairs tight, no carpet lifting, all ok?
40c50288-37d9-5755-8eb0-145175110b73 | note | x 2 Pictures min
| signoff | Please signoff / request sign off
| checklist | GB Laminate |  | GB Laminate | 3d2a60dd-edc5-4811-9c37-cc3ec24c7bc2
| checkpoint | Area clear of rubbish and tradespeople?
72db1f75-fcaf-5c79-b266-c44459367260 | note | x1 Picture
| checkpoint | Survey floor, More than 3 bags and 3 hours grinding? If yes, notify the office with images & scope and wait for approval.
8a88a717-abad-524a-8193-b9ed39e95793 | note | x1 Picture
| checkpoint | Direction of planks shown on plan?
| checkpoint | Review job sheet confirm all detail matches e.g. colour of planks, underlay.
| checkpoint | At-risk surfaces protected?
d3a95cc7-a150-5eb4-9c82-e83f4424bc1d | note | x1 Picture
| checkpoint | Installation complete with no damage?
95ef133f-c26d-52e3-beef-266426fc7b0f | note | x4 Picture
| checkpoint | Walked area and checked for gapping, bouncing, expansion etc?
| checkpoint | Opened boxes left on site and unopened returned?
| checklist | GB Timber Installation |  | GB Timber Installation | 2efc0e04-0383-4884-8935-3c76665b36e1
| checkpoint | Moisture test done prior to installation?
c6bd5ecb-fb9b-5d59-9656-03acef20a023 | note | x1 Picture
| checkpoint | Floor prep assessed and deviation less than 3mm over 3m?
| checkpoint | Review job sheet confirm all detail matches e.g. colour of timber etc
| checkpoint | Timber direction confirmed on plan?
| checkpoint | Bags and hours grinding signed off by Jay before starting?
| checkpoint | Timber weighted down after installation?
e10c7478-3b56-51dd-9c62-cba5afce307e | note | x 2 Picture
| checkpoint | All transition trims installed?
86377687-e486-5e94-8cfa-78e8d100ba64 | note | x 1 Picture min
| checkpoint | Area dust free and all rubbish removed?
2c2ca45c-ce8c-5fb4-b6c8-7fb3b2cefefd | note | x 2 Picture
| checkpoint | Installation complete with no damage?
1433c2d1-7df6-5448-8d50-9939e3e0b82b | note | x 2 Pictures min
| checkpoint | Walked area, all ok no gapping or damage?
9eb2fcc0-6a17-56e0-98ff-be85eeaeaf5f | note | x 2 Pictures min
| checkpoint | Jay advised of all left over materials?
| signoff | Please signoff / request sign off
| checklist | GB Vinyl Plank |  | GB Vinyl Plank | 67ec7f46-3bb5-422f-91c4-9c8b9b314195
| checkpoint | Survey floor for flatness?
| checkpoint | Area clear of rubbish and debris?
| checkpoint | Planks have been on site and are acclimated?
| checkpoint | Direction of planks shown on plan?
| checkpoint | More than standard prep required? If yes, notify Jay with images and scope, wait for approval
| checkpoint | Moisture test done prior to installation?
f3a00935-958a-570c-9553-501ab1a7468a | note | x 2 Picture
| checkpoint | Windows with direct sunlight blocked
b0dcd706-8bbd-5060-bbd1-498e36ed532b | note | x 2 Picture
| checkpoint | 68T used 1.5m from splashzone (sink etc)
| checkpoint | At-risk surfaces protected?
33f5544b-6950-5a98-860c-218f5bfc5fd8 | note | x 2 Picture
| checkpoint | Installation complete with no damage?
1a8c9472-9154-5305-b19e-9361f9734a49 | note | x 2 Pictures min
| checkpoint | Walked all areas, checked for gapping, lifting, excess glue on boards and skirtings and all ok?
| checkpoint | Opened boxes left on site and unopened returned?
| checklist | Incident Report |  | Incident Report | 3a52769b-0f2b-4a7a-8df8-b6732a0f591b
| section | Details
| checkpoint-no-value | Project name or location
07dabc68-3100-59fc-872a-00824c27e1d1 | textbox
| checkpoint-no-value | Date & Time of Incident
071257d5-591d-579e-b924-1b3e4b4f6c8e | textbox | Date & Time
| checkpoint-no-value | Reported by
b7e746ce-2948-5be4-9bdd-38c999bd2695 | textbox | Name & Surname
| checkpoint-no-value | Reported to
eaa75a8b-8e20-5284-b098-a9a62f9762a2 | textbox | Name & Surname
| checkpoint-no-value | Incident Type
6b59a817-1236-5dc7-9597-93a2f7588e93 | textbox
2cc8aecb-707e-573d-a91c-b4997e5a9afa | note | Add Picture
| checkpoint-no-value | Details of incident (Injuries)
| checkpoint-no-value | Person involved
91ad5f8e-0ce8-5102-b815-3efabf3ad194 | textbox | Name & Surname
717a7318-b42a-5095-a580-108b8786c801 | textbox | Contact details
| checkpoint-no-value | Details of witness
1369413e-67d0-5090-82e7-87edc52b6642 | textbox | Name & Surname
262b4fb2-8be0-56ba-9b4c-4768606e1d77 | textbox | Contact details
| checkpoint-no-value | Manager Remarks - Actions and Follow up
1a822134-424d-5bbd-95aa-89eb3d31fa63 | textbox
| signoff | Review and signoff by Supervisor / Manager
| checklist | Project Stock Control |  | Project Stock Control | b741584b-5d48-415a-98cc-7f1ab18e8264
| section | Details
| checkpoint-no-value | General Details
f37f458d-36ff-5065-8318-8ef88e624600 | textbox | Project name
745fa0c2-fcd6-5954-9026-27c9ed9992ef | textbox | Job number
e82ac413-dfc5-557b-9e0e-ac9edaab17f7 | textbox | Product Manufacturer
18bec57f-a23c-592a-9061-c66f5bf36459 | textbox | Product Range
ec222718-ee16-5586-bda7-fa76a2707a90 | textbox | Product colour(s)
| checkpoint | Quantity Received from suppliers
28b6f812-0c7a-5009-b2a6-0bb58cc8741e | textbox | Boxes
1ea26e06-224f-5fee-ba7a-f67aa908cb99 | textbox | Square Metre Per/Box
e8faacd2-06b6-5c3b-93f1-3a23c8407eaf | textbox | Square Metre Per/Roll
| checkpoint-no-value | Stock issued out to installer - 1
c6c990ca-6619-54c8-8722-0d767adabc5b | textbox | Colour/Range
088eeff2-fd1d-5274-b509-0606deb44ddb | date | Date
6a3c9fe7-8064-58e7-a2da-c93877693933 | textbox | Quantity
a5bdcb57-58cd-5500-b898-50b42e4dc427 | textbox | Balance left
| signoff | SIGN HERE
| checkpoint-no-value | Stock issued out to installer - 2
1c7a5d4c-3a27-5a9b-b793-6d74fe7f224d | textbox | Colour/Range
161db394-22ab-5256-b0ef-039cab76e06a | date | Date
a61640c9-32f0-5ccb-8832-67c282b4e799 | textbox | Quantity
d2da4d12-7639-5c29-ab20-e8e936275e50 | textbox | Balance left
| signoff | SIGN HERE
| checkpoint-no-value | Stock issued out to installer - 3
0ed718b1-0f67-537a-a56e-8dd64a0b3e03 | textbox | Colour/Range
93697173-86b0-5b6f-8ee6-80947a03fdb5 | date | Date
e63751d3-3817-5a84-a7bf-3b2cd138d1e4 | textbox | Quantity
e9ad8174-d2c4-5c21-8294-437a2b26ec4e | textbox | Balance left
| signoff | SIGN HERE
| checkpoint-no-value | Stock issued out to installer - 4
6cbd3b9e-af3c-525b-85d9-8c64d13a92df | textbox | Colour/Range
a61fb706-81c8-54d3-bd06-e61aba265cfb | date | Date
2a8021f9-d138-5a7f-ab0c-cbf854ae0c0b | textbox | Quantity
2fe79ea4-1eca-5414-bce9-0be6d7d8545f | textbox | Balance left
| signoff | SIGN HERE
| checkpoint-no-value | Stock issued out to installer - 5
82f92cdd-b594-560a-8e43-e2a7ad4c60dd | textbox | Colour/Range
22c08988-eae4-5c97-983a-65187712ea7b | date | Date
8a9a5ff9-8a2d-5138-b5e0-ae3cbf3a4be4 | textbox | Quantity
1a20106c-fd8f-5876-8bf6-dcc93084ccd4 | textbox | Balance left
| signoff | SIGN HERE
| checkpoint-no-value | Julius Remarks
544adf3b-a0bc-5f32-ae24-7ff7ca02561c | textbox | Remarks
| checkpoint | Any material returned upon completion?
ed8f1f6f-e1bf-5328-beeb-9bfb8e68fe01 | textbox
| checkpoint | Signoff
| signoff | Review and signoff by Manager upon completion of project
| checklist | Timber Installation |  | Timber Installation | 5fd93f53-84a4-416e-a10e-8454c9f8bc49
| section | Details
| checkpoint | Moisture test done prior to installation?
| checkpoint | Floor prep assessed and deviation less than 3mm over 3m?
| checkpoint | Correct notch trowel used for installation of timber?
| checkpoint | Timber direction been approved?
| checkpoint | Undercut doors and joinery?
| checkpoint | Min 10mm Expansion gaps as per installation manual?
| checkpoint | Timber weighted down during installation?
| checkpoint | All transition trims installed?
| checkpoint | Area dust free and all rubbish removed?
| checkpoint | No damage to joinery, skirtings or walls?
| checkpoint | Has the floor been protected?
| checkpoint | Installation complete with no damage?
| signoff | Please signoff / request sign off
| checklist | Toolbox Talk - Site-Specific |  | Toolbox Talk - Site-Specific | 5668c933-a56a-4059-b479-8d1ad674eb49
| section | Details
| checkpoint-no-value | General Details
f0856fbd-c8c4-51c5-a725-924131fea5b5 | textbox | Project name or location
9bdcdb3e-6471-5ffc-a4ee-efd02da6867d | date | Conducted on Date
70f51bd6-7907-57e6-b1b3-c60c930370b9 | textbox | Who is running this meeting?
| checkpoint-no-value | Toolbox Topic
e7f398c7-7aa8-5231-bc79-28747a472f95 | textbox | Description
7aa62f4b-0246-588f-9930-fd1290c819ef | textbox | Actions
| checkpoint-no-value | Issues raised from site?
a2924da4-7f45-5996-b1d2-e02d290013b6 | textbox | Description
10a82592-b821-5f0f-acb6-18c37a51913c | textbox | Actions
| checkpoint-no-value | Employee raised issues?
12d21d23-54ba-5c0c-b1a8-c8e5d09561ad | textbox | Description
4cf08a58-3dfe-5c2f-9d21-20eab49d4b6c | textbox | Actions
| checkpoint-no-value | Incident or Injuries
52329ba1-8056-525f-b96a-cc9733fc02ff | button | Any Incident or Injuries to report | Yes, No
cc89d041-c9f3-5b16-91c6-923411b84cb8 | textbox | Description
df523ffe-343e-567b-850f-36aad4395ef2 | textbox | Actions
| checkpoint-no-value | Hazards
b0e46e85-8bf5-54bc-8254-02c4fcab1eb0 | button | Any Hazards to report (Dangerous activity or condition) | Yes, No
29ea1cf8-9083-5e21-a700-e9a5eec72240 | textbox | Description
6f741219-f3a0-5354-8e1d-88b25c5ee3dd | textbox | Reported to
| checkpoint-no-value | Risks
6f66b790-03e3-5958-bc4a-03dbd7d80ac7 | button | Any Risk to report (Possibility of something bad happening) | Yes, No
5268cd81-19c3-555b-a220-416eb91c7f6f | textbox | Description
6d05fd54-6ca3-54f5-8fdd-38180502a609 | textbox | Reported to
| checkpoint | PPE - Personal Protective Equipment - Correct and in good condition ?
5eac277d-d5fe-5396-9f55-49220d0cc2f4 | tickbox | Inspected
| checkpoint | Positive safe-action observations
08e01a07-5e59-501f-9f08-c6c2ca564a6f | textbox | Observations
| checkpoint | Attendance Record
| signoff | Each attendee to click here to signoff
| checkpoint | Supervisor / Manager remarks and signoff
57e8513e-a6c6-5b4e-bbe1-bf6767976203 | textbox | Manager's remarks
| signoff | Review and signoff by Supervisor / Manager