## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-003 - CTCR Pavement Construction | itp |  |  |  |  | ITP-003 - CTCR Pavement Construction
section | 1 - Preliminary Works
checkpoint | 1.1 - Delivery Vehicles
label | Frequency - Each Delivery Truck
label | Acceptance Criteria - Delivery vehicles shall have bodies ﬁtted with covers of a suitable material to prevent loss of moisture during transport. Vehicles used for delivery of material to the hoppers of pavers shall have bodies or discharge equipment which will enable the load to be discharged direct into the hopper without spillage and in such a way that segregation will be minimised.
label | Reference Documents - Vicroads std sec 306.07 (a)
label | Method - Visual Inspection
label | Record - Delivery Truck Photos (2 Per Lot)
label | WP
label | Responsibility - SWA Site Supervisor/ Engineer
checkpoint | 1.2 - Delivery Dockets
label | Frequency - Each Delivery Truck
label | Acceptance Criteria - Delivery dockets shall show:
label | (i) name of the supplier, and location of plant;
label | (ii) docket number;
label | (iii) name of user;
label | (iv) project name and location (or contract number);
label | (v) registered number or ﬂeet number of the vehicle;
label | (vi) date and time of loading;
label | (vii) nature and source of material;
label | (viii) empty and loaded masses of the vehicle (where material is scheduled for measurement by mass);
label | (ix) loose volume in delivery vehicle.
label | Reference Documents - Vicroads std sec 306.07 (b)
label | Method - Visual Inspection
label | Record - Delivery Dockets Photos (2 Per Lot)
label | WP
label | Responsibility - SWA Site Supervisor/ Engineer
section | 2 - Construction Works
checkpoint | 2.1 - Transverse Joints
label | Frequency - Check prior to placing material
label | Acceptance Criteria - Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
label | Reference Documents - Vicroads std sec 306.08 (a, b, c)
label | Method - Visual Inspection
label | Record - Signed ITP & Staging Plan
label | IP
label | Responsibility - SWA Engineer, Site Supervisor
checkpoint | 2.2 - Longitudinal Joints
label | Frequency - Check prior to placing material
label | Acceptance Criteria - Material should be spread to minimize number of joints. Longitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traﬃc lane lines or within 300 mm of the centre of a traﬃc lane.
label | Reference Documents - Vicroads std sec 304.08 (a, d, e)
label | Method - Visual Inspection
label | Record - Signed ITP & Staging Plan Photos
label | IP
label | Responsibility - SWA Engineer, Site Supervisor
checkpoint | 2.3 - Lot Size
label | Frequency - Check prior to placing material
label | Acceptance Criteria - A single lot shall be considered a single layer of 4000m2 or one day’s production in a single layer, whichever is lesser
label | Reference Documents - VcRoads Std Specs 306.09
label | Method - Daily Inspection
label | Record - Signed ITP
label | IP
label | Responsibility - SWA Engineer, Site Supervisor
checkpoint | 2.4 - Layer Thickness
label | Frequency - Each Lot
label | Acceptance Criteria - The minimum compacted thickness shall be not less than 100mm and the maximum compacted thickness shall no more than 180mm and constructed within the tolerances speciﬁed in Clause 306.03
label | Reference Documents - VcRoads Std Specs 306.03
label | Method - Visual Inspection
label | Record - Signed ITP
label | IP
label | Responsibility - SWA Engineer, Site Supervisor
checkpoint | 2.5 - Test Rolling
label | Frequency - Test roll each layer
label | Acceptance Criteria - No visible deformation or springing in presence of Superintendent's Rep. ( Cl 173) Plant to comply with requirements of Cl 173.03. Pneumatic tyred plant nominated for test rolling procedures shall have a mass of not less than 20 tonne and shall have a ground contact pressure under either the front or rear wheels of not less than 450 kPa per tyre.
label | Reference Documents - VcRoads Std Specs 173.03, 173.03 (ii) Table 306.091
label | Method - Visual Inspection
label | Record - Signed ITP
label | IHP
label | Responsibility - SWA Engineer Site Supervisor
label | AP
label | Responsibility - RRV Superintendent
checkpoint | 2.6 - Max. Working Time
label | Frequency - Test roll each layer
label | Acceptance Criteria - The cementitious treated subbase material shall be placed, trimmed to level and fully compacted within the maximum allowable working time speciﬁed in Table 306.091 depending on the binder type and the time of year the subbase is being placed.
label | Reference Documents - VcRoads Std Specs 306.09
label | Method - Visual Inspection
label | Record - Signed ITP
label | IHP
label | Responsibility - SWA Engineer, Site Supervisor
checkpoint | 2.7 - Curing and Protection of Compacted Layer
label | Frequency - Test roll each layer
label | Acceptance Criteria - The minimum compacted thickness shall be not less than 100 mm and the maximum compacted thickness shall be no more than 180 mm and constructed within the tolerances speciﬁed in Clause 306.03.
label | (a) Pavement Design Modulus of 500 MPa or where no Pavement Design Modulus is Speciﬁed
label | ○ The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane.
label | ○ Construction or other traﬃc shall not use a compacted layer within 24 hours of placement without the approval of the Superintendent.
label | ○ The subbase shall be kept in good order and condition and free from contamination.
label | Reference Documents - VcRoads Std Specs 306.11
label | Method - Visual Inspection
label | Record - Signed ITP
label | IP
label | Responsibility - SWA Engineer, Site Supervisor
section | 3 - Testing Requirements
checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
label | Frequency - Prior to testing
label | Acceptance Criteria - Table 306.031 from VicRoads Section 306 nominates the level of testing required for acceptance of Surface Level Measurement. Scale B - Initially test every lot as per Table 815.141 except where the most recent ten successive test results have met the speciﬁed requirements then the testing may be halved.
label | Reference Documents - Vicroads std sec 306.031, 815.14 & Table 815.141
label | Method - Lot Register
label | Record - Signed ITP
label | TP
label | Responsibility - SWA Engineer
checkpoint | 3.2 - Compaction Testing
label | Frequency - Each lot as required
label | Acceptance Criteria - The cementitious treated subbase material shall be placed, trimmed to level and fully compacted within the maximum allowable working time speciﬁed in Table 306.091 depending on the binder type and the time of year the subbase is being placed (May – Sep). For scale A requirements, the number of tests per lot shall be six. The lot will be accepted if the mean density ratio for the lot is not less than 96.0%.
label | Reference Documents - Vicroads std sec 306.09 & Table 306.09, 306.09 (c)
label | Method - Compaction Testing External
label | Record - Signed ITP & Test Reports
label | TP
label | Responsibility - SWA Engineer
label | AP
label | Responsibility - RRV Superintendent
checkpoint | 3.3 - UCS
label | Frequency - Each lot as required
label | Acceptance Criteria - Assessment of the UCS during production shall be on a ‘rolling average’ basis where the average of the most recent three UCS test results shall not be less than the minimum value speciﬁed in Table 821.081. (For rapid/slow setting cement the min UCS is 5 MPa for pavement >500 or <3500.)
label | Reference Documents - VcRoads Std Specs Table 821.081
label | Method - Test Results
label | Record - Signed ITP & Test Reports
label | TP
label | Responsibility - SWA Engineer
checkpoint | 3.4 - Atterberg Limits
label | Frequency - Each lot as required
label | Acceptance Criteria - The crushed concrete prior to the addition of cementitious binder shall comply with the requirements of Table 821.041
label | ○ Liquid Limit % - 35 Plasticity Index (max) – 10
label | ○ LA Value (max) - 40
label | Reference Documents - VcRoads Std Specs Table 821.041
label | Method - Test Results
label | Record - Signed ITP & Test Reports
label | TP
label | Responsibility - SWA Engineer
checkpoint | 3.5 - Moisture Content
label | Frequency - Each lot as required
label | Acceptance Criteria - The moisture content of the material at the time of spreading and compaction, expressed as a percentage by mass, shall be within plus 0.5% and minus 1.0 % from the Modiﬁed optimum moisture content.
label | Reference Documents - VcRoads Std Specs 306.05
label | Method - Test Results
label | Record - Signed ITP & Test Reports
label | TP
label | Responsibility - SWA Engineer
checkpoint | 3.6 - Cement Content
label | Frequency - Each lot as required
label | Acceptance Criteria - After mixing, the cementitious binder content of the mixture, expressed as a percentage by mass of the dry crushed rock, shall be within +/- 0.3% of the Design Cementitious Binder Content.
label | Reference Documents - VcRoads Std Specs 815.10
label | Method - Test Results
label | Record - Signed ITP & Test Reports
label | TP
label | Responsibility - SWA Engineer
checkpoint | 3.7 - Grading
label | Frequency - Each lot as required
label | Acceptance Criteria - The product shall not extend outside the speciﬁed grading limits as per table 821.071
label | Reference Documents - VcRoads Std Specs Table 821.071
label | Method - Test Results
label | Record - Signed ITP & Test Reports
label | TP
label | Responsibility - SWA Engineer
checkpoint | 3.8 - Survey Conformance
label | Frequency - Each lot as required
label | Acceptance Criteria - Layer to be ﬁnished to a smooth and uniform surface and after compaction shall conform within the following limits:
label | ○ Shape: no point deviation > 8mm from 3m straight edge in any direction
label | ○ Surface level tolerances: Range x = +6, -12mm Max S = 13 mm
label | ○ Min number of measurement levels for Scale B requirements is 40 measurements per lot
label | Reference Documents - VcRoads Std Specs 306.03 & Table 306.031, 306.032
label | Method - Survey Report
label | Record - Signed ITP & Survey Reports
label | SCP
label | Responsibility - SWA Engineer
label | AP
label | Responsibility - RRV Superintendent
checkpoint | Final Inspection
note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP