## Table 1
Structural Curtain Walls
sections | Curtain Wall External Checklist
checkpoint | Setout / grids/ datum lines (refer to Survey mark/Setting out) MUST ATTACHED SURVEY DRAWING SHOWING LEVELS AND SLAB EDGES
checkpoint | Opening acceptance as per drawings MUST ADD SURVEY DRAWING
checkpoint | Secondary Bracket Installed (refer to SD) PHOTO REQUIRED
checkpoint | Waterproofing (Check that water proofing is over area where airseal is going to be) PHOTO REQUIRED
checkpoint | Install subsill /Jamb/ Deadload blocks/ splicers / soakers
checkpoint | Splices,Top Angle fitted & soakers sealed - PHOTO REQUIRED
checkpoint | All Fixings over sealed PHOTO REQUIRED
checkpoint | Ensure no packers visable out of line where airseal is to be installed.
checkpoint | Install backer rod - PHOTO REQUIRED
checkpoint | Complete airseal within application time allowed - PHOTO REQUIRED
checkpoint | Install panels as per drawings
checkpoint | Install glazing rubber with correct orientation/ no breaks and full height between panel and frame PHOTO'S REQUIRED
checkpoint | External flashings / weather seals installed and SEALED if drawing indicates - PHOTO REQUIRED
sections | Curtain Wall Internal Checklist
checkpoint | Airseal and internal flashings
checkpoint | Ensure no packers visable out of line where airseal is to be installed.
checkpoint | Panel locked off position as per module PHOTO REQUIRED
checkpoint | Crusifix sealing done on panel to panel cross joints? PHOTO REQUIRED
sections | Internal fire seal and trunking
checkpoint | fire insulation installed - PHOTO REQUIRED
Checkpoint | Glass installed and no damaged glass
checkpoint | Trade clean / protected
Check point | All elements completed correctly as per specification, reviewed and approved
sections | Wight Aluminium Sign Off
Check point | All elements completed correctly as per specification, reviewed and approved
Hold point | Raise Remedial / Request Signoff