## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Structural Curtain Walls
section | Curtain Wall External Checklist
checkpoint | Setout/grids/datum lines (refer to Survey mark/Setting out) MUST ATTACHED SURVEY DRAWING SHOWING LEVELS AND SLAB EDGES
checkpoint | Opening acceptance as per drawings MUST ADD SURVEY DRAWING
checkpoint | Secondary Bracket Installed (refer to SD) PHOTO REQUIRED
checkpoint | Waterproofing (Check that water proofing is over area where airseal is going to be) PHOTO REQUIRED
checkpoint | Install subsill/Jamb/Deadload blocks/splicers/soakers
checkpoint | Splices, Top Angle fitted & soakers sealed - PHOTO REQUIRED
checkpoint | All Fixings over sealed PHOTO REQUIRED
checkpoint | Ensure no packers visable out of line where airseal is to be installed.
checkpoint | Install backer rod - PHOTO REQUIRED
checkpoint | Complete airseal within application time allowed - PHOTO REQUIRED
checkpoint | Install panels as per drawings
checkpoint | Install glazing rubber with correct orientation/ no breaks and full height between panel and frame PHOTO'S REQUIRED
checkpoint | External flashings / weather seals installed and SEALED if drawing indicates - PHOTO REQUIRED
section | Curtain Wall Internal Checklist
checkpoint | Airseal and internal flashings
checkpoint | Ensure no packers visable out of line where airseal is to be installed.
checkpoint | Panel locked off position as per module PHOTO REQUIRED
checkpoint | Crusifix sealing done on panel to panel cross joints? PHOTO REQUIRED
section | Internal fire seal and trunking
checkpoint | Fire insulation installed - PHOTO REQUIRED
checkpoint | Glass installed and no damaged glass
checkpoint | Trade clean / protected
checkpoint | All elements completed correctly as per specification, reviewed and approved
section | Wight Aluminium Sign Off
checkpoint | All elements completed correctly as per specification, reviewed and approved
holdpoint | Raise Remedial / Request Signoff