## Project Checklist Templates
Warnings | Id | Type | Name | Values | Prompting Name | Resource Id
|  | checklist | 40mm Metro - Thermal Heart QA |  | 40mm Metro - Thermal Heart QA | 8c91a106-ef56-4b6b-a2be-48c6a46e04ad
|  | section | 40mm Metro - Thermal Heart QA
|  | checkpoint | Opening Wraped & Prepared Correctly By Others
|  | checkpoint | Setout/Grids/Datum Lines
|  | checkpoint | External Flashings / Weather Seals As Per Shop Drawing (provide photo reference)
|  | checkpoint | Window Installed / Fixed As Per Shop Drawings
|  | checkpoint | Airseals Completed
|  | checkpoint | Site Glazing Completed - Metro Glass
|  | checkpoint | Trade Clean
|  | section | Sign Offs
|  | checkpoint | Wight Sign Off
|  | checkpoint | Naylor Love Sign Off
|  | checklist | 40mm Metro QA |  | 40mm Metro QA | c33cefea-724d-4d1c-ae5c-a8d5b90f8acc
|  | section | 40mm Metro QA:
|  | checkpoint | Opening Wraped & Prepared Correctly By Others
|  | checkpoint | Setout/Grids/Datum Lines
|  | checkpoint | External Flashings / Weather Seals As Per Shop Drawing (provide photo reference)
|  | checkpoint | Installed / Fixed As Per Shop Drawings
|  | checkpoint | Airseals Completed
|  | checkpoint | Site Glazing Completed - Metro Glass
|  | checkpoint | Trade Clean
|  | section | Sign Off
|  | checkpoint | Wight Sign Off:
|  | signoff | Wights - Sign Off
|  | checkpoint | Builder Sign Off:
|  | signoff | Builder - Sign Off
|  | checklist | 40mm Seismic Strip Windows QA Checklist |  | 40mm Seismic Strip Windows QA | 888440ae-b49c-4ede-96b4-811e9bfc6c07
|  | checkpoint | Opening Correctly Prepared By Builders
|  | checkpoint | Seismic & Window Inserts Installed As Per Shop Drawings
|  | checkpoint | Acoustic Batts & Perforated Sheet Installed As Per Shop Drawings
|  | checkpoint | MetroGlass Site Glazing - Photo Required
|  | checkpoint | Trade Clean
|  | checkpoint | Wight Sign Off
|  | checkpoint | Arrow Sign Off
|  | checklist | 100 / 125 / 135mm Flushglaze CW QA List |  | 100 / 125 / 135mm Flushglaze CW QA List | 30eb4384-0892-4ec0-b479-ec2c98f138fd
|  | section | Internal QA
|  | checkpoint | Setout/Grids/Datum Lines
|  | checkpoint | Seismic Installed As Per Shop Drawings (Photo Required)
|  | checkpoint | Secondary Steel (By Others) In Correct Place
|  | checkpoint | DL Brackets Fitted & Bolted to Correct Torque Setting
|  | checkpoint | C.W Visual Panel Insert Check
|  | checkpoint | Panel Fitted & Locked Off (Photo Required)
|  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
|  | checkpoint | Airseal and Internal Flashings
|  | checkpoint | PGI Support Clips
|  | checkpoint | PGI Fire Insulation (provide photo reference)
|  | checkpoint | Trims and Closers (smoke Seal) (provide photo reference)
|  | checkpoint | External Flashings / Weather Seals (provide photo reference)
|  | checkpoint | Site Glazing Completed - Metro Glass
|  | checkpoint | Trade Clean
|  | section | Sign Offs
|  | checkpoint | Wight Sign Off
|  | checkpoint | Naylor Love Sign Off
|  | checklist | 125mm Seismic Strip Windows QA Checklist |  | 125mm Seismic Strip Windows QA | 69981fd8-d084-449d-a77c-066a5176bc30
|  | section | Internal QA
|  | checkpoint | Opening Wraped & Prepared By Builders
|  | checkpoint | Setout/Grids/Datum Lines
|  | checkpoint | Seismic Installed As Per Shop Drawings
|  | checkpoint | Splices & Soakers Sealed (provide photo reference - required)
|  | checkpoint | Window Inserts Installed As Per Shop Drawings
|  | checkpoint | Airseals Completed - Photo Required
|  | checkpoint | Trade Clean
|  | checkpoint | Wight Signoff
|  | section | External QA
|  | checkpoint | External Flashings / Weather Seals (provide photo reference - required)
|  | checkpoint | Sun Fin Fitted & Bolted to Correct Torque Setting
|  | checkpoint | Wight Sign Off
|  | checkpoint | Arrow Sign Off
|  | checklist | 150mm Flushglaze CW QA |  | 150mm Flushglaze CW QA | 38a930ab-790e-4771-bc78-9c14e717425a
|  | checkpoint | Opening Prepared By Builders
|  | checkpoint | Setout/Grids/Datum Lines
|  | checkpoint | Seismic Installed As Per Shop Drawings (provide photo reference)
|  | checkpoint | DL Brackets Fitted & Bolted to Correct Torque Setting
|  | checkpoint | C.W Visual Panel Insert Check
|  | checkpoint | Panel Fitted & Locked Off (provide photo reference)
|  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
|  | checkpoint | Airseal and Internal Flashings (provide photo reference)
|  | checkpoint | Window Insert / Door Installed As Per Shop Drawings
|  | checkpoint | Autodoor Unit Installed - Dormakaba
|  | checkpoint | Autodoor Unit Commisioned - Dormakaba
|  | checkpoint | External Flashings / Weather Seals (provide photo reference)
|  | checkpoint | Site Glazing Completed - Metro Glass
|  | checkpoint | Trade Clean
|  | checkpoint | Wights - Sign Off
|  | checkpoint | Holmes Wellington - Sign Off
|  | checklist | 168mm SG CW QA Checklist |  | 168mm SG CW QA | a95c7c2a-8486-4f8b-87e5-fc7bf58c6a23
|  | checkpoint | Setout/Grids/Datum Lines
|  | checkpoint | Seismic Sill / Jamb Installed As Per Shop Drawings - Photo Required
|  | checkpoint | DL Brackets Fitted & Bolted to Correct Torque Setting
|  | checkpoint | C.W Visual Panel Check
|  | checkpoint | Splicers & Soakers Sealed (provide photo reference - required)
|  | checkpoint | Airseal and Internal Flashings - Photo Required
|  | checkpoint | Trims and Closers (provide photo reference - required)
|  | checkpoint | Parapet Flashing Installed As Per Shop Drawings
|  | checkpoint | External Flashings / Weather Seals Completed (provide photo reference - required)
|  | checkpoint | Trade Clean
|  | checkpoint | Wight Sign Off
|  | checkpoint | W&W Sign Off
|  | checklist | 175mm SG CW QA Checklist |  | 175mm SG CW QA List | 1b517fec-aceb-42e6-900f-5cbb6e8453c5
|  | section | Internal QA
|  | checkpoint | Seismic Head Installed As Per Shop Drawings - Photo Required
|  | checkpoint | Seismic/Stack Sill Installed As Per Shop Drawings - Photo Required
|  | checkpoint | Setout/Grids/Datum Lines
|  | checkpoint | Jordahl Cast-in Channel In Place
|  | checkpoint | DL Brackets Fitted & Bolted to Correct Torque Setting
|  | checkpoint | C.W Visual Panel Check
|  | checkpoint | Panel Locked Off - Photo Required
|  | checkpoint | Splicers & Soakers Sealed (provide photo reference - required)
|  | checkpoint | Airseal and Internal Flashings - Photo Required
|  | checkpoint | PGI Support Clips
|  | checkpoint | PGI Fire Insulation (provide photo reference - required)
|  | checkpoint | Trims and Closers (smoke seal) (provide photo reference - required)
|  | checkpoint | Trade Clean
|  | checkpoint | Wight Signoff
|  | section | External QA
|  | checkpoint | External Flashings / Weather Seals (provide photo reference - required)
|  | checkpoint | Wight Sign Off
|  | checkpoint | Arrow Sign Off
|  | checklist | Add Glazing Checklist |  | Glazing Checklist | a8b0b33c-0b79-43cb-8e8c-5781603b7b8b
|  | section | Panel
|  | checkpoint | Check Frame Square
|  | checkpoint | Check Drain Holes
|  | checkpoint | Air Blow Frame Down
|  | checkpoint | 2 Rag System Isopropyl
|  | checkpoint | Primer Wipe Only
|  | section | Glass
|  | checkpoint | Inspect / clean glass
|  | checkpoint | Glass Strength check
|  | checkpoint | Outer lite
|  | checkpoint | Inner lite
|  | checkpoint | Tape Glass
|  | checkpoint | Prep glass edge iso
|  | section | Glazing
|  | checkpoint | Install Structural Tapes
|  | checkpoint | Install Structural Bit Sealant
| 52db8474-c72c-43dc-965d-f4b8d8d35c00 | textbox | Batch number
|  | checkpoint | Install Setting blocks
|  | checkpoint | Install PEF Rod
|  | checkpoint | Install Wealther Seal
| 48344404-1f8f-4e13-9ab9-7cd75070fc51 | textbox | Batch Number
|  | checkpoint | Install ACM PEF Rod
|  | checkpoint | Install ACM Weather Seal
| 7e236acf-098e-4380-badc-c94724cca61d | textbox | Batch Number
|  | checkpoint | Clean Frame Down
|  | checklist | Add Installation of Curtain Wall - External Works |  | Installation of Curtain Wall External | 2800bf72-7cc5-4aa8-ae89-8856b6c2e5c9
|  | checkpoint | Setout / Grids / Datum Lines
|  | checkpoint | Subsill Installed (Refer Separate QA Form)
|  | checkpoint | C.W Panel Checked
|  | checkpoint | Splices & Soakers Sealed
|  | checkpoint | Brackets Welded & Painted
|  | checkpoint | Glass Fin Fixed As Specified
|  | checkpoint | Panel Locked Off
|  | checkpoint | Guardspan Joint Soakers
|  | checklist | Add Installation of Curtain Wall - Internal Works |  | Installation of Curtain Wall Internal | 10fa6d55-7821-465d-957f-fcc52583445a
|  | checkpoint | Airseal & Internal Flashings
|  | checkpoint | PGI Fire Insulation Installed
|  | checkpoint | Trade Clean / Protected
|  | checkpoint | PGI Support Clips
|  | checkpoint | Trims & Closers (Smoke Seal)
|  | checklist | Add Installation of Parapets |  | Installation of Parapets | d48af44e-9b78-48c2-9775-d187d8f303e0
|  | checkpoint | Parapet Cap Delivery
|  | checkpoint | C.W. Panel Gutter Drainage Checked / Cleaned
|  | checkpoint | Fixing Bracket Installed / Fixings Oversealed
|  | checkpoint | Install Parapet Cap Flashing
|  | checkpoint | Inspection of Membrane / Sign Off From Builder
|  | checkpoint | Parapet Under Flashing Fitted / Sealed
|  | checkpoint | Fit Parapet Joint Soakers / Seals
|  | checkpoint | Trade Clean
|  | checklist | Add Installation of Subsill |  | Installation of Subsill | 7303c120-4c44-4207-a9b7-3285e03911b5
|  | checkpoint | Setout / Grids / Datum Lines
|  | checkpoint | Markout & Drill Holes (Check Edge Distance)
|  | checkpoint | Apply Duo Kit to Hole / Around Stud
|  | checkpoint | Install Backer Rod
|  | checkpoint | Inspection of Membrane / Sign Off From Builder
|  | checkpoint | Apply Epistik Primer
|  | checkpoint | Install Subsill / Splices / Soakers
|  | checkpoint | Complete Airseal Within Application Time Allowed
|  | checklist | Add Installation of Window Units / Doors (General) |  | Installation of Window Units / Doors (General) | ccb4edda-7a45-4ed3-9e79-5a4eb9b5bb7c
|  | checkpoint | Structural Tolerances Correct
|  | checkpoint | Building Wraps / Membranes Correct
|  | checkpoint | Sill Plates Right Height / Screws Sealed
|  | checkpoint | Sill Installed / Screwed / Sealed to Frame / Structure
|  | checkpoint | Window Frame Installed Plumb / Screws Sealed
|  | checkpoint | Internal Perimeter Air Seal
|  | checkpoint | Head Flashing Fixed / Taped / End Stops
|  | checkpoint | Fixed Lite Frame Gasket Installed
|  | checkpoint | Sliders Are Adjusted / Operable
|  | checkpoint | Hardware / Door Stops Complete / Infills
|  | checkpoint | Trade Clean / Protection
|  | checklist | Add New CW Panel |  | Panel - | b0d58ccd-01fa-43a1-8208-70dee6f5c43b
|  | checklist-flat | Panel Manufacture
|  | checklist | Glazing
|  | checklist-flat | Dispatch
|  | checklist | Add New Window or Door Unit |  | Unit - | ef46890d-4ca2-4058-b965-6c17352657e6
|  | section | Window & Door Manufacture QA
|  | checkpoint | Cut & machine frame check drain holes
|  | checkpoint | Screw frame together
|  | checkpoint | Back seal frame
|  | checkpoint | Hardware fitted, strikers, door stops etc
|  | checkpoint | Support blocks fitted
|  | checkpoint | Wipe off over seal
|  | checkpoint | Fit hinges
|  | checkpoint | Read notes on manu sheet
|  | checkpoint | Final QA sign off complete
| 5dac8885-54da-4541-a965-b9cd226c0eb2 | textbox | Date completed
|  | section | Dispatch
|  | checkpoint | Panel ready for dispatch - Photo Required
|  | checklist | Add Parapet |  | Parapet Checklist | 7ceceb6d-ab5f-4bb6-973a-8f48cdd2ee8a
|  | section | Parapet
|  | checkpoint | Parapet Cap Delivery
|  | checkpoint | Inspection of Membrane / Signoff from Builders
Invalid dependant |  | signoff | Lt McGuinness Signoff
|  | checkpoint | C.W. Panel Gutter Drainage Checked / Cleaned
|  | checkpoint | Parapet Under Flashing Fitted / Sealed (provide photo reference)
|  | checkpoint | Fixing Bracket Installed / Fixings Oversealed
|  | checkpoint | Fit Parapet Jo Soaers / Seals
|  | checkpoint | Install Parapet Cap Flashing
|  | checkpoint | Trade Clean (provide photo reference)
|  | checklist | Add Windows and Doors Manufacture Checklist |  | Windows & Doors | 699102e3-d2a4-4779-a8c1-505ef8fb50e9
|  | checkpoint | Cut & machine frame check drain holes
|  | checkpoint | Screw frame together
|  | checkpoint | Back seal frame
|  | checkpoint | Hardware fitted, strikers, door stops etc
|  | checkpoint | Support blocks fitted
|  | checkpoint | Wipe off over seal
|  | checkpoint | Fit hinges
|  | checkpoint | Read notes on manu sheet
|  | checkpoint | Final QA sign off complete
| 5dac8885-54da-4541-a965-b9cd226c0eb2 | textbox | Date completed
|  | checklist | APL 100mm Shop Front |  | APL 100mm Shop Front | 6e58ae38-18ff-4d95-96a2-ec3272dbdc6f
|  | section | Internal QA
|  | checkpoint | Setout/Grids/Datum Lines
|  | checkpoint | Seismic Installed As Per Shop Drawings (Photo Required)
|  | checkpoint | Secondary Steel (By Others) In Correct Place
|  | checkpoint | DL Brackets Fitted & Bolted to Correct Torque Setting
|  | checkpoint | C.W Visual Panel Insert Check
|  | checkpoint | Panel Fitted & Locked Off (Photo Required)
|  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
|  | checkpoint | Airseal and Internal Flashings
|  | checkpoint | PGI Support Clips
|  | checkpoint | PGI Fire Insulation (provide photo reference)
|  | checkpoint | Trims and Closers (smoke Seal) (provide photo reference)
|  | checkpoint | External Flashings / Weather Seals (provide photo reference)
|  | checkpoint | Site Glazing Completed - Metro Glass
|  | section | Sign Offs
|  | checkpoint | Wight Sign Off
|  | checkpoint | Naylor Love Sign Off
|  | checklist | APL Metro - QA |  | Metro - Metro Thermal Heart Windows QA | e1a2383d-7d06-4361-8725-4bd577fc8d21
|  | checkpoint | Opening Wraped & Prepared Correctly By Others
|  | checkpoint | Setout/Grids/Datum Lines
|  | checkpoint | External Flashings / Weather Seals As Per Shop Drawing (provide photo reference)
|  | checkpoint | Window Installed / Fixed As Per Shop Drawings
|  | checkpoint | Airseals Completed (provide photo reference)
|  | checkpoint | Site Glazing Completed - Metro Glass
|  | checkpoint | Trade Clean
|  | checkpoint | Wight - Sign Off
|  | checkpoint | Holmes Wellington - Sign Off
|  | checklist | Auto Door QA Checklist |  | Auto Door QA | 08310cb3-49e0-4957-8064-61d3f24b4d90
|  | checkpoint | Opening Prepared By Builders
|  | checkpoint | Window Insert / Door Installed As Per Shop Drawings
|  | checkpoint | Autodoor Unit Installed - Dormakaba
|  | checkpoint | MetroGlass Site Glazing - Photo Required
|  | checkpoint | Trade Clean
|  | checkpoint | Autodoor Unit Commisioned - Dormakaba
|  | checkpoint | Wight Sign Off
|  | checkpoint | Arrow Sign Off
|  | checklist | Auto Doors |  | Auto Doors | 54e3b286-4e16-4c49-99b1-00156eff0631
|  | section | Auto Door QA
|  | checkpoint | Opening Prepared By Builders
|  | checkpoint | Window Insert / Door Installed As Per Shop Drawings
|  | checkpoint | Autodoor Unit Installed - Arabian
|  | checkpoint | MetroGlass Site Glazing
|  | checkpoint | Trade Clean
|  | checkpoint | Autodoor Unit Commisioned - Arabian
|  | section | Sign Offs
|  | checkpoint | Wight Sign off
|  | checkpoint | Arrow Sign off
|  | checklist | Door QA Checklist |  | Door QA | 283b1fed-9aff-436b-9ce9-f75b78b9f1ec
|  | checkpoint | Opening Prepared By Builders - Including Rebates - Photo Required
|  | checkpoint | Framless Door Installed As Per Shop Drawings - MetroGlass - Photo Required
|  | checkpoint | Trade Clean
|  | checkpoint | Wight Sign Off
|  | checkpoint | W&W Sign Off
|  | checklist | ST - S - Punch Window Frames |  | ST - S - Punch Window Frames | ca50f8ce-6f6a-4599-ad19-3e5d6bde9f67
|  | section | Glazing Install
|  | checkpoint-no-value | Glazing Install
| 9d7bf985-b665-5019-81cf-52bef8d0492b | note | Window # / Elevation / Level
|  | checkpoint | Installation (By others) completed as per detail Y/N
|  | checkpoint | Check the joinery is free from damage
|  | checkpoint | All glazing beads attached to Frame PHOTO REQUIRED
|  | checkpoint | Check Frame number PHOTO REQUIRED
|  | checkpoint | Inspection of Backing rubber - no damage and continuous around perimeter
|  | checkpoint | Glazing Blocks inserted correctly PHOTO REQUIRED
|  | checkpoint | Correct Glass units installed (Glass sticker) PHOTO REQUIRED
|  | checkpoint | Glazing Beads fitted correctly PHOTO REQUIRED
|  | checkpoint | Correct Wedge Rubber installed and rubbered off as per WGANZ guidelines
|  | checkpoint | Glass Stickers removed
|  | checkpoint | Trade Clean
|  | checkpoint | Final Inspection PHOTO REQUIRED
|  | checkpoint | Glazing complete for handover to Ryman Healthcare
|  | signoff | Raise Remedial
|  | checklist | St Pauls |  | CW | 0351bca0-9628-4867-b9a9-7e46d47e3a6a
|  | section | External Checks
|  | checkpoint | SETOUT / GRIDS / DATUM LINES
|  | checkpoint | MARKOUT AND DRILL HOLES: MIN BOLT EMBEDMENT 170mm (CHECK EDGE DISTANCE)
| a902001f-1391-4103-ab09-2eba1a5925ae | note | Photo Required
|  | checkpoint | FIT M20 GALVANSED GR.8.8 BOLTS - CLEAN OUT HOLES AND SEAL AROUND STUD - HIT-HY 200-R INJECTABLE EPOXY
|  | checkpoint | PLATE BRACKETS FITTED AND BOLTED TO CORRECT TORQUE SETTING
| b9158003-9774-40eb-9db5-e2b28e04dc50 | note | Photo Required
|  | checkpoint | BUILDING WRAPS / MEMBRANES CORRECT
|  | checkpoint | SUBSILL INSTALLED - IF REQUIRED
|  | checkpoint | SEISMIC FITTED - IF REQUIRED
|  | checkpoint | PANEL FITTED & LOCKED OFF
| 8c3bdc3a-ca93-4f67-9200-0f1f39ccb79e | note | Photo Required
|  | checkpoint | SPLICES & SOAKERS SEALED
| 3f7b543b-635c-4ff3-b9e0-1976ff8fb450 | note | Photo Required
|  | checkpoint | SPANDREL BACKPAN FITTING & AIR SEAL
|  | checkpoint | GLAZE IN INFILL PANELS (METRO)
| ddd31a21-4b98-475b-83a7-660ef3bb2e77 | note | Photo Required
|  | checkpoint | GLAZE IN GLASS PANELS (METRO)
|  | checkpoint | C.W PANEL COMPLETED
|  | checkpoint | EXTERNAL FLASHINGS / WEATHER SEALS / SOAKERED JOINTS
| ec37df9f-b71d-469d-a2ba-bc4591ca86fe | note | Photo Required
|  | checkpoint | PARAPET UNDER FLASHING FITTED / SEALED
|  | checkpoint | INSTALL PARAPET CAP FLASHING
|  | checkpoint | FIT PARAPET JOINT SOAKERS / SEALS
|  | section | Internal Checks
|  | checkpoint | PGI SUPPORT CLIPS FITTED
| e768f6e9-c62d-4c8b-968d-994304e87d09 | note | Photo Required
|  | checkpoint | PGI FIRE INSULATION INSTALLED
| 83b67728-3fba-499a-a64a-d0f2ce4224d6 | note | Photo Required
|  | checkpoint | SMOKE SEAL TRIMS AND CLOSERS INSTALLED
| 557ba676-572b-4999-8cb9-370c106e38b5 | note | Photo Required
|  | checkpoint | TRADE CLEAN
|  | checklist | Wight Area Completion |  | Wight Area Completion | 7b42e619-d031-4d82-acb8-ae1e3ae1f09f
|  | checkpoint | All elements completed correctly as per specification, reviewed and approved
|  | signoff | RAISE REMEDIAL / REQUEST SIGN OFF