## Site Management
Ryman Takapuna CONQA | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5
Site Management
Building Consents
BCO10331862 - Demolition (obsolete format)
|  |  |  | Approved Building Consent |  | prepopulate
Council Inspections
[5 empty] | IF2 - Final Commercial Inspection | ability to add
|  |  |  | Compliance Documents |  | prepopulate
BCO10331862-1 - Civil
Approved Building Consent
Minor Variations
[5 empty] | Inspection Type - Description - DD/MM/YY | ability to add
Council Inspections
[5 empty] | DD/MM/YY - Council Inspection Type | ability to add
Council Audits
[5 empty] | DD/MM/YY - Brief Description | ability to add
|  |  |  | Compliance Documentation |  | prepopulate
Compliance RFI
[5 empty] | DD/MM/YY - Brief Description | ability to add
|  |  |  | Approved CCC |  | prepopulate
Resource Consents and approved Engineering Plans
Stage 001
Stage 002
Engineering Approval

## Stage 401
Ryman Takapuna CONQA | Tier 1 | Tier 2 | Tier 3
Stage 401
Ryman Inspections
Contractors Allocated
|  |  |  | CDS Limited |  |  | ability to add | ITP - R - Contractor Allocation (Use at stage level for each subcontractor on the stage)
|  |  |  | CLL Solutions |  |  | ability to add | ITP - R - Contractor Allocation (Use at stage level for each subcontractor on the stage)
|  |  |  | Spiral Drillers |  |  | ability to add | ITP - R - Contractor Allocation (Use at stage level for each subcontractor on the stage)
|  |  |  | Vuksich & Borich |  |  | ability to add | ITP - R - Contractor Allocation (Use at stage level for each subcontractor on the stage)
|  |  |  | Shotcrete & Rock NZ Ltd |  |  | ability to add | ITP - R - Contractor Allocation (Use at stage level for each subcontractor on the stage)
Stage 401
Stormwater
Manholes
[6 empty] | SWMH 01/0 | prepopulate
[6 empty] | SWMH 01/1 | prepopulate
[6 empty] | SWMH 01/3 | prepopulate
[6 empty] | SWMH 01/4 | prepopulate
[6 empty] | SWMH 01/5 | prepopulate
[6 empty] | SWMH 01/6 | prepopulate
[6 empty] | SWMH 02/2 | prepopulate
Pipe Connections
[6 empty] | Connection from SWMH 01/0 to SWMH 01/1 | prepopulate
[6 empty] | Connection from SWMH 01/1 to SWMH 01/3 | prepopulate
[6 empty] | Connection from SWMH 01/3 to SWMH 01/4 | prepopulate
[6 empty] | Connection from SWMH 01/4 to SWMH 01/5 | prepopulate
[6 empty] | Connection from SWMH 01/5 to SWMH 01/6 | prepopulate
[6 empty] | Connection from SWMH 02/2 to SWMH 01/1 | prepopulate
[5 empty] | Connection to Public Systems |  | prepopulate
Wastewater
Manholes
[6 empty] | SSMH XX/XX | prepopulate
Pipe Connections
[6 empty] | SSMH XX/XX | prepopulate
[5 empty] | Connection to Public Systems |  | prepopulate
Water Main
Pipe Laying
Connection to Public Systems
TC1
[5 empty] | Crane Piles |  | prepopulate | Redundant Piling Checklist as works completed pre-hybrid CONQA
[5 empty] | Crane Pad - Slab Preparation |  | prepopulate | ITP - R - ON GRADE SLAB FOUNDATION CONSTRUCTION (PER AREA)
[5 empty] | Crane Pad - Concrete Planning and Pour |  | prepopulate | ITP - R - CONCRETE - PLANNING AND POUR (PER AREA)

## Stage 001
Ryman Takapuna CONQA | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
Stage 001
Ryman
Contractors Allocated
| Tier 4: Watertight |  | ability to add | ITP - R - Contractor Allocation (Use at stage level for each subcontractor on the stage)
| Tier 4: Reoco |  | ability to add | ITP - R - Contractor Allocation (Use at stage level for each subcontractor on the stage)
| Tier 4: Marin Construction |  | ability to add | ITP - R - Contractor Allocation (Use at stage level for each subcontractor on the stage)
B01 (59 ILU, 30 ALS, 4 Levels)
Foundation
| Tier 5: Lift Pit East Preparation |  | prepopulate | ITP - R - On Grade Slab Foundation Construction (per area)
| Tier 5: Lift Pit East Pour |  | prepopulate | ITP - R - Concrete - Planning and Pour (per area)
| Tier 5: Lift Pit West Preparation |  | prepopulate | ITP - R - On Grade Slab Foundation Construction (per area)
| Tier 5: Lift Pit West Pour |  | prepopulate | ITP - R - Concrete - Planning and Pour (per area)
| Tier 5: Slab Preparation - Grids A1-I15 |  | prepopulate | ITP - R - On Grade Slab Foundation Construction (per area)
| Tier 5: Pour Zone 1 (Grid A1 to C6) |  | prepopulate | ITP - R - Concrete - Planning and Pour (per area)
| Tier 5: Pour Zone 2 (Grid C1 to F6) |  | prepopulate | ITP - R - Concrete - Planning and Pour (per area)
| Tier 5: Pour Zone 3 (Grid F1 to I6) |  | prepopulate | ITP - R - Concrete - Planning and Pour (per area)
| Tier 5: Pour Zone 4 (Grid A6 to C11 |  | prepopulate | ITP - R - Concrete - Planning and Pour (per area)
| Tier 5: Pour Zone 5 (Grid C6 to F11) |  | prepopulate | ITP - R - Concrete - Planning and Pour (per area)
| Tier 5: Pour Zone 6 (Grid F6 to I11) |  | prepopulate | ITP - R - Concrete - Planning and Pour (per area)
| Tier 5: Pour Zone 7 (Grid F11 to I15) |  | prepopulate | ITP - R - Concrete - Planning and Pour (per area)
| Tier 5: Pour Zone 8 (Grid C11 to F15) |  | prepopulate | ITP - R - Concrete - Planning and Pour (per area)
| Tier 5: Pour Zone 9 (Grid A11 to C15) |  | prepopulate | ITP - R - Concrete - Planning and Pour (per area)
Slab Preparation (Grid D15 to K20)
| Tier 5: Pour Zone 10 (Grid D15 to F18) |  | prepopulate | ITP - R - Concrete - Planning and Pour (per area)
| Tier 5: Pour Zone 11 (Grid F15 to I18) |  | prepopulate | ITP - R - Concrete - Planning and Pour (per area)
| Tier 5: Pour Zone 12 (Grid F18 to K20) |  | prepopulate | ITP - R - Concrete - Planning and Pour (per area)
Structure
Basement
| Tier 6: Panel Group 1 (Grid E/I to 1/6) |  | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
| Tier 6: Panel Group 2 (Grid A/E to 1/6) |  | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
| Tier 6: Panel Group 3 (Grid I to 1/15) |  | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
| Tier 6: Panel Group 4 (Grid A/E to 6/11) |  | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
| Tier 6: Panel Group 5 (Grid A/E to 11/15) |  | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
| Tier 6: Panel Group 6 (Grid E/I to 6/11) |  | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
| Tier 6: Panel Group 7 (Grid E/I to 11/15) |  | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
| Tier 6: Panel Group 8 (Grid E/K to 15/20) |  | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
Ground Floor
Area 1 - (Grid A/E to 1/6)
[7 empty] | Pour Zone 1 | prepopulate
[7 empty] | Panel Group 1 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 2 - (Grid A/E to 10/15)
[7 empty] | Pour Zone 2 - PT slab in draft | prepopulate
[7 empty] | Panel Group 2 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 3 - (Grid A/E to 6/10)
[7 empty] | Pour Zone 3 - PT slab in draft | prepopulate
[7 empty] | Panel Group 3 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 4 - (Grid E/I to 15/20)
[7 empty] | Pour Zone 4 - PT slab in draft | prepopulate
[7 empty] | Panel Group 4 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
[7 empty] | Roof | prepopulate | ITP - R - Apartment Roofing (per area)
Area 5 - (Grid E/I to 1/6)
[7 empty] | Pour Zone 5 - PT slab in draft | prepopulate
[7 empty] | Panel Group 5 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 6 - (Grid I/K to 1/15)
[7 empty] | Pour Zone 6 - PT slab in draft | prepopulate
[7 empty] | Panel Group 6 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
[7 empty] | Roof | prepopulate | ITP - R - Apartment Roofing (per area)
Area 7 - (Grid I/L to 15/19)
[7 empty] | Pour Zone 7 - PT slab in draft | prepopulate
[7 empty] | Panel Group 7 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
[7 empty] | Roof | prepopulate | ITP - R - Apartment Roofing (per area)
Area 8 - (Grid E/I to 10/15)
[7 empty] | Pour Zone 8 - PT slab in draft | prepopulate
[7 empty] | Panel Group 8 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 9 - (Grid E/I to 6/10)
[7 empty] | Pour Zone 9 - PT slab in draft | prepopulate
[7 empty] | Panel Group 9 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Level 1
Area 1 - (Grid A/E to 1/6)
[7 empty] | Pour Zone 1 - PT slab in draft | prepopulate
[7 empty] | Panel Group 1 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 2 - (Grid E/L to 1/6)
[7 empty] | Pour Zone 2 - PT slab in draft | prepopulate
[7 empty] | Panel Group 2 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 3 - (Grid A/E to 10/15)
[7 empty] | Pour Zone 3 - PT slab in draft | prepopulate
[7 empty] | Panel Group 3 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 4 - (Grid E/L to 10/15)
[7 empty] | Pour Zone 4 - PT slab in draft | prepopulate
[7 empty] | Panel Group 4 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 5 - (Grid G/I to 15/20)
[7 empty] | Pour Zone 5 - PT slab in draft | prepopulate
[7 empty] | Panel Group 5 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Level 2
Area 1 - (Grid A/E to 1/6)
[7 empty] | Pour Zone 1 - PT slab in draft | prepopulate
[7 empty] | Panel Group 1 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 2 - (Grid E/L to 1/6)
[7 empty] | Pour Zone 2 - PT slab in draft | prepopulate
[7 empty] | Panel Group 2 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 3 - (Grid A/E to 10/15)
[7 empty] | Pour Zone 3 - PT slab in draft | prepopulate
[7 empty] | Panel Group 3 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 4 - (Grid E/L to 10/15)
[7 empty] | Pour Zone 4 - PT slab in draft | prepopulate
[7 empty] | Panel Group 4 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 5 - (Grid G/I to 15/20)
Pour Zone 5 - PT slab in draft
[7 empty] | Panel Group 5 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Level 3
Area 1 - (Grid A/E to 1/6)
[7 empty] | Pour Zone 1 - PT slab in draft | prepopulate
[7 empty] | Panel Group 1 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 2 - (Grid E/L to 1/6)
[7 empty] | Pour Zone 2 - PT slab in draft | prepopulate
[7 empty] | Panel Group 2 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 3 - (Grid A/E to 10/15)
[7 empty] | Pour Zone 3 - PT slab in draft | prepopulate
[7 empty] | Panel Group 3 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 4 - (Grid E/L to 10/15)
[7 empty] | Pour Zone 4 - PT slab in draft | prepopulate
[7 empty] | Panel Group 4 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 5 - (Grid G/I to 15/20)
[7 empty] | Pour Zone 5 - PT slab in draft | prepopulate
[7 empty] | Panel Group 5 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Level 4
Area 1 - (Grid A/E to 1/6)
[7 empty] | Pour Zone 1 - PT slab in draft | prepopulate
[7 empty] | Panel Group 1 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 2 - (Grid E/L to 1/6)
[7 empty] | Pour Zone 2 - PT slab in draft | prepopulate
[7 empty] | Panel Group 2 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 3 - (Grid A/E to 10/15)
[7 empty] | Pour Zone 3 - PT slab in draft | prepopulate
[7 empty] | Panel Group 3 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 4 - (Grid E/L to 10/15)
[7 empty] | Pour Zone 4 - PT slab in draft | prepopulate
[7 empty] | Panel Group 4 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Area 5 - (Grid G/I to 15/17)
[7 empty] | Pour Zone 5 - PT slab in draft | prepopulate
[7 empty] | Panel Group 5 | prepopulate | ITP - R - Apartment Pre Cast Element Installation (per area/level)
[7 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
| Tier 6: Roof - (Grid G/I to 17/20) |  | prepopulate | ITP - R - Apartment Roofing (per area)
Roof (Still in draft)
| Tier 6: Area 1 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Roofing (per area)
| Tier 6: Area 2 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Roofing (per area)
| Tier 6: Area 3 - Grid to be advised) |  | preopulate | ITP - R - Apartment Roofing (per area)
| Tier 6: Area 4 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Roofing (per area)
| Tier 6: Area 5 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Roofing (per area)
Pre Line, Post Line
Basement (still in draft)
| Tier 6: Area 1 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 2 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 3 - Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 4 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 5 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
Ground Floor (Still in draft)
| Tier 6: Area 1 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 2 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 3 - Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 4 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 5 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
Level 1 (Still in draft)
| Tier 6: Area 1 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 2 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 3 - Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 4 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 5 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
Level 2 (Still in draft)
| Tier 6: Area 1 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 2 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 3 - Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 4 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 5 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
Level 3 (Still in draft)
| Tier 6: Area 1 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 2 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 3 - Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 4 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 5 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
Level 4 (Still in draft)
| Tier 6: Area 1 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 2 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 3 - Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 4 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
| Tier 6: Area 5 - (Grid to be advised) |  | preopulate | ITP - R - Apartment Pre & Post Line (per area/grid)
Façade
Ground Floor (Still in draft)
| Tier 6: North Elevation (Grid A - 1/6) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: North Elevation (Grid A - 10/15) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: North Elevation (Grid E - 15/17) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: North Elevation (Grid F - 17/20) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: East Elevation (Grid 1 A/K) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: East Elevation (Grid 10 - A/I) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: East Elevation (Grid 17 - K/L) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid K - 1/20 |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid L - 17/19) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 6 - A/I) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 15 - A/E) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 17 - E/F) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 20 - F/K) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 19 - K/L) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
Level 1 (Still in draft)
| Tier 6: North Elevation (Grid A - 1/6) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: North Elevation (Grid A - 10/15) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: North Elevation (Grid G - 15/20) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: East Elevation (Grid 1 - A/L) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: East Elevation (Grid 10 - A/L |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: East Elevation (Grid 16 - K/L) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid L - 1/6) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid L - 10/15) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid K - 15/16 |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid L - 16/19) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid K - 19/20 |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 6 - A/I) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 15 - A/G) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 20 - G/K) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 19 - K/L) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 15 - K/L |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
Level 2 (Still in draft)
| Tier 6: North Elevation (Grid A - 1/6) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: North Elevation (Grid A - 10/15) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: North Elevation (Grid G - 15/20) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: East Elevation (Grid 1 - A/L) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: East Elevation (Grid 10 - A/L |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: East Elevation (Grid 16 - K/L) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid L - 1/6) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid L - 10/15) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid K - 15/16 |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid L - 16/19) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid K - 19/20 |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 6 - A/I) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 15 - A/G) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 20 - G/K) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 19 - K/L) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 15 - K/L |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
Level 3 (Still in draft)
| Tier 6: North Elevation (Grid A - 1/6) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: North Elevation (Grid A - 10/15) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: North Elevation (Grid G - 15/20) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: East Elevation (Grid 1 - A/L) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: East Elevation (Grid 10 - A/L |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: East Elevation (Grid 16 - K/L) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid L - 1/6) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid L - 10/15) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid K - 15/16 |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid L - 16/19) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid K - 19/20 |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 6 - A/I) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 15 - A/G) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 20 - G/K) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 19 - K/L) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 15 - K/L |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
Level 4 (Still in draft)
| Tier 6: North Elevation (Grid A - 1/6) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: North Elevation (Grid A - 10/15) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: North Elevation (Grid G - 15/20) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: East Elevation (Grid 1 - A/L) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: East Elevation (Grid 10 - A/L |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: East Elevation (Grid 16 - K/L) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid L - 1/6) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid L - 10/15) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid K - 15/16 |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid L - 16/19) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: South Elevation (Grid K - 19/20 |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 6 - A/I) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 15 - A/G) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 20 - G/K) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 19 - K/L) |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
| Tier 6: West Elevation (Grid 15 - K/L |  | prepopulate | ITP - R - Apartment Facade (per elevation/grid)
Fitout & Services
Basement
Resident Tool Shed
ACC W/C
Lobby 1
Lift 1
Bin Room 1
Stairwell 1
Lobby 1.1
Riser 1
HWC Back Up
DB
Maintenance
Lobby 2
Lift 2
Bin Room 2
Stairwell 2
Lobby 2.2
Riser 2
HWC
Storeroom
Main Switchboard
HWC Back Up 2
Main Comms
ACC W/C 2
Gardener Shed
Chem St
Lobby 3
Lift 3
Pool Plant Room
Bin Room 3
Car Park
Ground Floor - (8 ILU's) (Still in draft)
Level 1 - (13 ILU's, 8 ALS')
Level 2 - (13 ILU's, 8 ALS')
Level 3 - (13 ILU's, 11 ALS')
Level 4 - (14 ILU's)
Level 1 - (13 ILU's, 8 ALS') (Still in draft)

## Sheet1
Stage XX (Bxx)
Ryman
Contractors Allocated
|  |  | Rename Me | Pre-start Review |  |  | Prepopulate | ITP - R - Contractor Allocation (use at stage level for each subcontractor on the stage)
|  |  | Rename Me | Pre-start Review |  |  | Prepopulate | ITP - R - Contractor Allocation (use at stage level for each subcontractor on the stage)
BXX (XX Apartments, X Levels)
Civil
|  |  |  | Excavation |  |  | Prepopulate | ITP - R - Excavation (Bulk and Detailed)
|  |  |  | Pipe Laying |  |  | Prepopulate | ITP - R - Pipe Laying (Mains Water, Storm and Waste)
|  |  |  | Service Trenches |  |  | Prepopulate | ITP - R - Service Trenches (Common and Pulling Pits)
|  |  |  | Tanking |  |  | Prepopulate | ITP - R - Tanking/Waterproofing
Foundation
Area A or Grid XX-YY
[5 empty] | Pre-Pour |  | Prepopulate | ITP - R - On Grade Slab Pre-Pour (per area)
[7 empty] | Prepopulate | ITP - R - Concrete - Planning and Pour (per area)
[5 empty] | Piling |  | Prepopulate | ITP - R - Foundation Piling
Area B or Grid XX-YY
[5 empty] | Pre-Pour |  | Prepopulate | ITP - R - On Grade Slab Pre-Pour (per area)
[5 empty] | Pour |  | Prepopulate | ITP - R - Concrete - Planning and Pour (per area)
[5 empty] | Piling |  | Prepopulate | ITP - R - Foundation Piling
Structure
Ground Level
Walls (Grid XX-YY)
[6 empty] | Structure | prepopulate | ITP - R - Apartment Pre Cast, Timber, Insuti , Blockwork Element Installation (per area/level)
[6 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Walls (Grid XX-YY)
[6 empty] | Structure | prepopulate | ITP - R - Apartment Pre Cast, Timber, Insuti , Blockwork Element Installation (per area/level)
[6 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Walls (Grid XX-YY)
[6 empty] | Structure | prepopulate | ITP - R - Apartment Pre Cast, Timber, Insuti , Blockwork Element Installation (per area/level)
[6 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level)
Level 1
Floor (Area X or Grid XX-YY)
[7 empty] | prepopulate | ITP - R - Apartment Pre Cast Floor Structure and Concrete Pour (per level/area)
Floor (Area X or Grid XX-YY)
[7 empty] | prepopulate | ITP - R - Apartment Pre Cast Floor Structure and Concrete Pour (per level/area)
Floor (Area X or Grid XX-YY)
[7 empty] | prepopulate | ITP - R - Apartment Pre Cast Floor Structure and Concrete Pour (per level/area)
Walls (Grid XX-YY)
[6 empty] | Pre Cast Element | prepopulate | ITP - R - Apartment Pre Cast, Timber, Insuti , Blockwork Element Installation (per area/level)
[6 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level) | ITP - R - Apartment Pre Cast, Timber, Insuti , Blockwork Element Installation (per area/level)
Walls (Grid XX-YY)
[6 empty] | Pre Cast Element | prepopulate | ITP - R - Apartment Pre Cast, Timber, Insuti , Blockwork Element Installation (per area/level)
[6 empty] | Structural Steel Elements | prepopulate | ITP - R - Apartment Structural Steel (per area/level) | ITP - R - Apartment Pre Cast, Timber, Insuti , Blockwork Element Installation (per area/level)
Roof
Area A
[7 empty] | prepopulate | ITP - R - Apartment Roofing (per area)
Area B
[7 empty] | prepopulate | ITP - R - Apartment Roofing (per area)
Level Pre Line, Post Line
|  |  |  | GL Bin Room |  |  | prepopulate | ITP - R - Apartment Pre & Post Line (per area/grid/location)
|  |  |  | GL Apartment G25 |  |  | prepopulate | ITP - R - Apartment Pre & Post Line (per area/grid/location)
|  |  |  | GL Apartment G26 |  |  | prepopulate | ITP - R - Apartment Pre & Post Line (per area/grid/location)
|  |  |  | GL Entrance Area |  |  | prepopulate | ITP - R - Apartment Pre & Post Line (per area/grid/location)
|  |  |  | GL Lift Area |  |  | prepopulate | ITP - R - Apartment Pre & Post Line (per area/grid/location)
|  |  |  | Level 1 Apartment 101 |  |  | prepopulate | ITP - R - Apartment Pre & Post Line (per area/grid/location)
|  |  |  | Level 1 Apartment 102 |  |  | prepopulate | ITP - R - Apartment Pre & Post Line (per area/grid/location)
|  |  |  | Level 1 Corridor |  |  | prepopulate | ITP - R - Apartment Pre & Post Line (per area/grid/location)
Façade
|  |  |  | North Elevation - GL Grid XX-YY or something suitable |  |  | prepopulate | ITP - R - Apartment Facade (per evelation/grid)
|  |  |  | North Elevation - GL Grid XX-YY or something suitable |  |  | prepopulate | ITP - R - Apartment Facade (per evelation/grid)
|  |  |  | North Elevation - GL Grid XX-YY or something suitable |  |  | prepopulate | ITP - R - Apartment Facade (per evelation/grid)
|  |  |  | North Elevation - GL Grid XX-YY or something suitable |  |  | prepopulate | ITP - R - Apartment Facade (per evelation/grid)
|  |  |  | North Elevation - GL Grid XX-YY or something suitable |  |  | prepopulate | ITP - R - Apartment Facade (per evelation/grid)
|  |  |  | North Elevation - GL Grid XX-YY or something suitable |  |  | prepopulate | ITP - R - Apartment Facade (per evelation/grid)
|  |  |  | North Elevation - GL Grid XX-YY or something suitable |  |  | prepopulate | ITP - R - Apartment Facade (per evelation/grid)
|  |  |  | North Elevation - GL Grid XX-YY or something suitable |  |  | prepopulate | ITP - R - Apartment Facade (per evelation/grid)
Apartment Fitout & Services
Ground Level
Apartment G01
[6 empty] | Fitout | prepopulate | ITP - R - Fitout (per unit)
[6 empty] | Services | prepopulate | ITP - R - Services
Apartment G02
[6 empty] | Fitout | prepopulate | ITP - R - Fitout (per unit)
[6 empty] | Services | prepopulate | ITP - R - Services
Main Entrance Common Area
[6 empty] | Fitout | prepopulate | ITP - R - Services
|  |  |  | Level 1 |  | Services | prepopulate | ITP - R - Services
Apartment 101
[6 empty] | Fitout | prepopulate | ITP - R - Fitout (per unit)
[6 empty] | Services | prepopulate | ITP - R - Services
Apartment 102
[6 empty] | Fitout | prepopulate | ITP - R - Fitout (per unit)
[6 empty] | Services | prepopulate | ITP - R - Services
Lift Common Area
[6 empty] | Fitout | prepopulate | ITP - R - Services
[6 empty] | Services | prepopulate | ITP - R - Services
| Rename Me | Prepopulate | I - C - Site Visit Report
| Rename Me | Prepopulate | I - C - Site Visit Report
| Rename Me | Prepopulate | I - C - Site Visit Report
| Rename Me | Prepopulate | I - C - Site Visit Report