## res_1630-P200-SYM-QAC-ITP-0013.
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CC0394 - ITP-001 - Sediment Control | itp |  |  |  |  | CC0394 - ITP-001 - Sediment Control REV0
section | Lot Conformance.
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes, No
text | NCR Raised Date:
button | NCR closed? | Yes, No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP
section | 1.0 Pre-start activities
checkpoint | 1.1 - Safety
label | Ensure that the following items have been actioned:
label | – SWMS if applicable
label | – Plant Pre-start Inspection
label | – Service locations identified
label | – Traffic Management Plans (if req’d)
label | – All staff inducted
label | Ref docs - SMP
label | Acceptance criteria - SWMS submitted reviewed and accepted if required.
label | • Personnel inducted to RJE requirements.
label | • Plant inspections completed and entered.
label | • Pre-work briefings completed.
label | • Service Diagrams available and services located.
label | Freq - Once (Pre-Start)
label | Key - H
label | Resp - SS
label | RJE Key - S
checkpoint | 1.2 - Excavation Permit
label | Ref docs - SMP
label | Acceptance criteria - All identified underground services marked and potholed to confirm location and depth. No machine excavation within 1m of underground services. Permit available and signed.
label | Freq - Prior to start of works
label | Key - H
label | Resp - SS
label | RJE Key - S
checkpoint | 1.3 - Check Survey Set-out
label | Ref docs - Drawing: 5668-122-1010
label | Acceptance criteria - Survey Setout extend of works
label | Freq - Prior to start of Works
label | Key - H
label | Resp - SV, SS
label | RJE Key - S
checkpoint | 1.4 - Material Specifications Checked and Conforming
label | Ref docs - RFI Approval
label | Acceptance criteria - RJE approval of sediment fence material
label | Freq - Prior to start of Works
label | Key - H
label | Resp - SE
label | RJE Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Install works
checkpoint | 2.1 - Sediment Fence Install
label | Ref docs - Drawing: 5668-122-1010
label | Acceptance criteria - Correct fence material is onsite, Stakes installed at 2000mm spacing, silt fence buried at least 200mm into soil, Fence secured to stakes using appropriate fixtures.
label | Freq - On delivery and installation
label | Key - H
label | Resp - SS
label | RJE Key - S
checkpoint | 2.2 - Temporary swale & earth bund construction
label | Ref docs - Drawing: 5668-122-1010
label | Acceptance criteria - Construction conforms with IFC drawings unless approved otherwise.
label | Freq - On delivery and installation
label | Key - S
label | Resp - SS, SE
label | RJE Key - S
section | 3.0 Conformance check
checkpoint | 3.1 - Carry out corrections and clean-up
label | Acceptance criteria - Area clear of debris, silt fence is sturdy and intact, earth bund and swale sediment controls working as intended – efficiently carries water where required, prevents silt run-off and erosion.
label | Freq - Visual Inspection once complete
label | Key - W
label | Resp - CR
label | RJE Key - W