## res_1630-P200-SYM-QAC-ITP-0013.
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CC0394 - ITP-002 - Site Clearing | itp |  |  |  |  | CC0394 - ITP-002 - Site Clearing REV0
section | Lot Conformance.
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes, No
text | NCR Raised Date:
button | NCR closed? | Yes, No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP
section | 1.0 Pre-start activities
checkpoint | 1.1 - Determine Lot Size
label | Acceptance criteria - What is the lot size?
textbox | Acceptance |  |  | m2
label | • Maximum lot size = 4,000m2
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Work Lot Map
checkpoint | 1.2 - Safety
label | Ensure that the following items have been actioned:
label | – SWMS if applicable
label | – All staff inducted
label | – Plant Pre-start Inspection
label | – Service locations identified
label | – Traffic Management Plans (if req’d)
label | Ref docs - SMP
label | Acceptance criteria - SWMS submitted reviewed and accepted if required.
label | • Personnel inducted to RJE requirements.
label | • Plant inspections completed and entered.
label | • Pre-work briefings completed.
label | • Service diagrams available and services located.
button | Acceptance | Yes,No,N/A
label | Freq - Once (Pre-Start)
label | Key - H
label | Resp - SS
label | RJE Key - S
checkpoint | 1.3 - Excavation Permit
label | Ref docs - SMP
label | Acceptance criteria - All identified underground services marked and potholed to confirm location and depth. No machine excavation within 1m of underground services. Permit available and signed.
button | Acceptance | Yes,No,N/A
label | Freq - Prior to start of works
label | Key - H
label | Resp - SS
label | RJE Key - S
checkpoint | 1.4 - Check Survey Set-out
label | Ref docs - Construction Drawings
label | Acceptance criteria - Survey setout extend of works
button | Acceptance | Yes,No,N/A
label | Freq - Prior to start of Works
label | Key - H
label | Resp - SV, SS
label | RJE Key - S
checkpoint | 1.5 - Tree Protection
label | Ref docs - Construction Drawings
label | Acceptance criteria - Have all trees / native flora and fauna been protected including the establishment of no go zones as indicated in the construction documentation, CHMP and CAB?
button | Acceptance | Yes,No,N/A
label | Freq - Prior to start of Works
label | Key - H
label | Resp - SE
label | RJE Key - S
section | 2.0 CLEARING AND GRUBBING
checkpoint | 2.1 - Clearing and Grubbing
label | Acceptance criteria - Have the identified areas been cleared of all vegetation, refuse, unsuitable material and obstructions down to natural surface?
label | • In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed.
label | • Unsuitable material and topsoil is to be stockpiled in the designated location and is not to be used as fill material.
button | Acceptance | Yes,No,N/A
label | Freq - Visual Inspection
label | Key - H
label | Resp - SS
label | RJE Key - S
section | 3.0 Topsoil Stripping
checkpoint | 3.1 - Stripping
label | Acceptance criteria - Is the appropriate equipment being used to ensure topsoil and subsoil layers are not mixed.
button | Acceptance | Yes,No,N/A
label | Freq - Visual Inspection
checkpoint | 3.2 - Stripping
label | Acceptance criteria - Has the area been stripped and stockpiled to an appropriate depth (minimum top 50mm) removing surface topsoil and unsuitable material in a way to leave the surface evenly graded and free-draining?
button | Acceptance | Yes,No,N/A
label | Freq - Visual Inspection
label | Key - W
label | Resp - SS
label | RJE Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Top soil export / stockpiling
label | Acceptance criteria - Has the topsoil being stockpiled been approved by RJE (where applicable).
label | • Have the environmental controls as per CEMP been adhered to?
label | • Dispose material as per CEMP requirements
button | Acceptance | Yes,No,N/A
label | Freq - Visual inspection
label | Key - W
label | Resp - SS
label | RJE Key - S