## res_1630-P200-SYM-QAC-ITP-0013.
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CC0394 - ITP-003 - Bulk Earthworks | itp |  |  |  |  | CC0394 - ITP-003 - Bulk Earthworks REV0
section | Lot Conformance.
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes, No
text | NCR Raised Date:
button | NCR closed? | Yes, No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP
section | 1.0 Preliminaries
checkpoint | 1.1 - Determine lot size
label | Acceptance criteria - What is the lot size?
text | Acceptance |  |  | m2
checkpoint | 1.2 - Survey set-out
label | Ref docs - Construction drawings
label | Acceptance criteria - Has the work area been set out for line and level?
button | Acceptance | Yes,No,N/A
label | Key - W
label | RJE Key - S
checkpoint | 1.3 - Excavation material classification
label | Acceptance criteria - Has the material being excavated been inspected with category agreed upon by Superintendent?
label | • Tick category below:
bool | Topsoil
bool | Unsuitable material
bool | Fill material
button | Acceptance | Yes,No,N/A
label | Key - H
label | RJE Key - W
checkpoint | 1.4 - Fill material classification
label | Acceptance criteria - Has the material to be used been approved for use?
button | Acceptance | Yes,No,N/A
text | Material Type
label | Key - H
label | RJE Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Water management
label | Acceptance criteria - Where necessary, have batters been rounded and catch drains constructed to allow for potential surface runoff during the course of excavation?
button | Acceptance | Yes,No,N/A
label | Key - S
label | RJE Key - S
checkpoint | 1.6 - Clearing
label | Ref docs - CC0394 - ITP-002
label | Acceptance criteria - Has the area been cleared and grubbed in accordance with ITP-002?
button | Acceptance | Yes,No,N/A
label | Key - H
label | RJE Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Bulk earthworks – cut
checkpoint | 2.1 - Subgrade protection
label | Acceptance criteria - Have external factors such as weather and construction activities been considered to ensure excavations will be protected from water, erosion, deterioration and excessive drying or wetting?
button | Acceptance | Yes,No,N/A
label | Key - S
label | RJE Key - S
checkpoint | 2.2 - Subgrade preparation
label | Ref docs - Construction Drawings
label | Acceptance criteria - Has the cut surface been trimmed to an even surface free from lose material?
label | • Have surface levels been checked to avoid over excavation?
button | Acceptance | Yes,No,N/A
label | Key - S
label | RJE Key - S
checkpoint | 2.3 - Lime mix
label | Ref docs - Construction Drawings
label | Acceptance criteria - Has mix design been completed and submitted?
label | • Have Lime spreading rates been submitted to RJE?
button | Acceptance | Yes,No,N/A
label | Key - H
label | RJE Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Trial site
label | Acceptance criteria - Has trial site been established and confirmed?
button | Acceptance | Yes,No,N/A
label | Key - H
label | RJE Key - W
checkpoint | 2.5 - Lime stabilisation
label | Ref docs - Construction Drawings
label | Acceptance criteria - Has the prepared subgrade been lime stabilised as per the IFC design?
button | Acceptance | Yes,No,N/A
label | Key - S
label | RJE Key - W
checkpoint | 2.6 - Compaction
label | Acceptance criteria - Compaction Scale: 3 tests per lot. See RJE approved lots:
label | • Combi Slab: 1, 2, 3, 4, 5
label | • Temporary compound: Lot 1 & 2
label | • Has the stabilised subgrade been adequately compacted achieving 98% SMDD / 95% MMDD (in-situ materials or subgrade preparation), or 75% density index for the in-situ and fill materials. Using a nuclear density gauge.
label | • Is the subgrade material with 2% of the optimum moisture content.
label | • Is the subgrade within +/- 20mm of design surface?
button | Acceptance | Yes,No,N/A
label | Key - W
label | RJE Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 2.7 - Test Rolling
label | Acceptance criteria - Does the layer withstand test rolling without visible deformation or springing?
text | List Attendees:
button | Acceptance | Yes,No,N/A
label | • If ‘no’ please see below.
label | • If ‘yes’ please proceed
label | Key - H
label | RJE Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Identification of soft wet or unstable material
label | Acceptance criteria - What quantity of soft, wet or unstable material is present?
label | Acceptance
text |  |  |  | m2
text |  |  |  | m3
checkpoint | Treatment of unsuitable material
label | Acceptance criteria - Has rectification process been submitted to RJE for review?
label | • What was the rectification process used?
button | Acceptance | Yes,No,N/A
text | Rectification Process:
section | 3.0 Bulk earthworks - fill
checkpoint | 3.1 - Stripped surface - test rolling (If applicable)
label | Acceptance criteria - Does the stripped surface to be filled withstand test rolling without visible deformation or springing?
text | List Attendees:
button | Acceptance | Yes,No,N/A
label | • If ‘no’ please see below.
label | • If ‘yes’ please proceed to item 3.2
label | Key - H
label | RJE Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Identification of soft wet or unstable material
label | Acceptance criteria - What quantity of soft, wet or unstable material is present?
label | Acceptance
text |  |  |  | m2
text |  |  |  | m3
checkpoint | Treatment of unsuitable material
label | Acceptance criteria - What rectification process is to be undertaken?
checkpoint | 3.2 - Preparation of surface
label | Acceptance criteria - Has adequate water been added to the stripped surface to ensure adhesion to the next layer?
button | Acceptance | Yes,No,N/A
label | Key - S
label | RJE Key - S
checkpoint | 3.4 - Fill Placement
label | Acceptance criteria - Has fill been placed in maximum 300mm and minimum 100mm compacted layer thickness?
button | Acceptance | Yes,No,N/A
label | Key - S
label | RJE Key - S
checkpoint | 3.5 - Moisture
label | Acceptance criteria - Has the material maintained at optimum moisture content (within 2% of optimum moisture), with additional water being added if required during compaction?
button | Acceptance | Yes,No,N/A
label | Key - S
label | RJE Key - S
checkpoint | 3.6 - Compaction
label | Acceptance criteria - Compaction Scale: 3 tests per lot. See RJE approved lots:
label | • Combi Slab: 1, 2, 3, 4, 5
label | • Tempoary compound: Lot 1 & 2
label | • Has the subgrade been adequately compacted achieving 98% SMDD / 95% MMDD (in-situ materials or subgrade preparation), or 75% density index for the in-situ and fill materials. Using a nuclear density gauge.
label | • Is the subgrade within +/- 20mm of design surface.
button | Acceptance | Yes,No,N/A
label | Key - W
label | RJE Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 3.7 - Fill layer – test rolling
label | Acceptance criteria - Does the layer withstand test rolling without visible deformation or springing?
text | List Attendees:
button | Acceptance | Yes,No,N/A
label | • If ‘no’ please see below
label | • If ‘yes’ please proceed to fill construction
label | Key - H
label | RJE Key - W
checkpoint | Identification of soft wet or unstable material
label | Acceptance criteria - What quantity of soft, wet or unstable material is present?
label | Acceptance
text |  |  |  | m2
text |  |  |  | m3
checkpoint | Treatment of unsuitable material
label | Acceptance criteria - Has rectification process been submitted to RJE for Review?
label | • What was the rectification process used?
button | Acceptance | Yes,No,N/A
text | Rectification Process:
section | 4.0 Conformance check
checkpoint | 4.1 - Width and alignment
label | Acceptance criteria - Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings?
button | Acceptance | Yes,No,N/A
label | Key - H
label | RJE Key - S
checkpoint | 4.2 - Subgrade level and shape
label | Acceptance criteria - Has the prepared subgrade been surveyed in accordance with and verifying specified requirements?
label | • Is the subgrade within +/- 20mm of design surface.
button | Acceptance | Yes,No,N/A
label | Key - H
label | RJE Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | As built report