## res_1630-P200-SYM-QAC-ITP-0013.
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CC0394 - ITP-005 - Crushed Rock Pavement Construction | itp |  |  |  |  | CC0394 - ITP-005 - Crushed Rock Pavement Construction REV0
section | Lot Conformance.
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes, No
text | NCR Raised Date:
button | NCR closed? | Yes, No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP
section | 1.0
checkpoint | 1.1 - Determine Lot Size
label | Acceptance criteria - What is the lot size?
text | Acceptance |  |  | m2
label | • Maximum lot size = See pre-approved lot maps
label | Resp - SE
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
bool | Work Lot Map
checkpoint | 1.2 - Survey Set-out
label | Ref docs - IFC Drawings
label | Acceptance criteria - Has the work area been set out for line and level?
button | Acceptance | Yes,No,N/A
label | Key - W
label | Resp - SE
checkpoint | 1.3 - Material Classification & Source
label | Ref docs - IFC Drawings
label | Acceptance criteria - Is the correct material being used?
button | Acceptance | Yes,No,N/A
label | Please tick appropriate Box:
bool | Site Won
bool | 20mm Class 2
bool | 20mm Class 3
bool | 20mm Class 4
text | Other
label | Key - H
label | Resp - SE
section | 2.0
checkpoint | 2.1 - Conformance of Previous Layer
label | Ref docs - IFC Drawings
label | Acceptance criteria - Has the previous layer passed acceptance criteria?
button | Acceptance | Yes,No,N/A
label | Key - W
label | Resp - SE
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
bool | Refer to ITP for previous layer
section | 3.0
checkpoint | 3.1 - Placement
label | Ref docs - IFC Drawings
label | Acceptance criteria - Has the fill been placed in a maximum compacted layer as outlined below?
label | • Maximum Layer Depth: 200mm
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp - SE
checkpoint | 3.2 - Moisture
label | Ref docs - IFC Drawings
label | Acceptance criteria - Has the material maintained at optimum moisture content (>85%), with additional water being added if required during compaction?
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp - SE
checkpoint | 3.3 - Compaction
label | Ref docs - IFC Drawings Civil Specification
label | Acceptance criteria - Has the layer been adequately compacted achieving a mean value density ratio of:
label | • Lower Subbase: 98% Std
label | • Upper Subbase: 95% Mod
label | • 3 x tests to be conducted per compacted layer per approved lot map.
button | Acceptance | Yes,No,N/A
label | Key - W
label | Resp - SE
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
bool | Compaction test results
checkpoint | 3.4 - Test Rolling
label | Ref docs - IFC Drawings
label | Acceptance criteria - Does the layer withstand test rolling without visible deformation of springing?
text | List attendees:
button | Acceptance | Yes,No,N/A
label | • If ‘no’, please see sections 3.5 and 3.6.
label | • If ‘yes’, proceed to section 4.0.
label | Key - H
label | Resp - SE
label | RJE Key - W
checkpoint | 3.5 - Identification of soft, wet or unstable material
label | Acceptance criteria - What quantity of soft, wet or unstable material is present?
text | Acceptance |  |  | m
label | Resp - SE
checkpoint | 3.6 - Treatment of unsuitable material
label | Acceptance criteria - Has rectification process been submitted for review?
label | • What was the rectification process used?
button | Acceptance | Yes,No,N/A
text | Process Used:
label | Resp - SE
section | 4.0
checkpoint | 4.1 - Pavement Finish
label | Acceptance criteria - Has the pavement course been finished to a smooth and uniform surface?
button | Acceptance | Yes,No,N/A
label | Key - W
label | Resp - SE
checkpoint | 4.2 - Width & Alignment
label | Acceptance criteria - Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings?
button | Acceptance | Yes,No,N/A
label | Key - W
label | Resp - SE
checkpoint | 4.3 - Surface Level of Pavement Courses
label | Acceptance criteria - Has the prepared layer been surveyed in accordance with and verifying specified requirements?
label | All crushed rock layers:
label | • Mean Range: +10mm to -10mm
button | Acceptance | Yes,No,N/A
label | Key - H
label | Resp - SE
label | RJE Key - H
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
bool | As-Built Reports
holdpoint | AUTHORITY HOLDPOINT