## res_1630-P200-SYM-QAC-ITP-0013.
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CC0394 - ITP-011 - Kerb | itp |  |  |  |  | CC0394 - ITP-011 - Kerb REV0
section | Lot Conformance.
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes, No
text | NCR Raised Date:
button | NCR closed? | Yes, No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP
section | 1.0
checkpoint | 1.1 - Survey Set-out
label | Ref docs - IFC Drawings
label | Acceptance criteria - Prior to the commencement of works, the contractor shall engage a suitably qualified surveyor to set out the works and clearly mark its limits.
button | Acceptance | Yes,No,N/A
label | Key - W
label | Resp - SE
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
bool | Work Lot Map
checkpoint | 1.2 - Approved Material Type
label | Ref docs - IFC Drawings
label | Acceptance criteria -
label | Acceptance
text | Approved kerb mix:
label | Key - H
label | Resp - SE
checkpoint | 1.3 - Preparation of Bedding
label | Ref docs - AS2876
label | Acceptance criteria - Where kerb is constructed over pavement layers, bedding shall be provided between the pavement layer & the underside of the edging, or the edging thickened to match the pavement layer.
label | • Where edgings are not constructed over pavement layers, bedding shall be greater than 100mm compacted thickness.
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp - SE
checkpoint | 1.4 - Air Temperature
label | Ref docs - AS2876
label | Acceptance criteria - Concrete shall not be mixed when the temperature is lower than 5⁰C or greater than 35⁰C.
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp - SE
checkpoint | 1.5 - Concrete Placement
label | Ref docs - AS3610 AS2876
label | Acceptance criteria - Concrete shall be thoroughly compacted by means of continuous tamping & internal vibration shall be worked around any embedment’s & into corners of formwork to produce a dense concrete free from voids, honeycombing, segregation, or surface defects.
label | • Concrete shall be finished to ensure a smooth surface with a uniform colour & appearance, & screeded to achieve the specified level, dimensions, falls & tolerances.
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp - SE
checkpoint | 1.6 - Joints
label | Ref docs - AS3610 AS2876
label | Acceptance criteria - Transverse joints shall be constructed at regular intervals not exceeding 3m. For extruded edgings this shall be done by a method which does not damage or distort the adjacent surfaces.
label | • 6mm saw cut joints within 24-72hrs post pour
label | • Sikaflex polyurethane joint sealant or equivalent used to fill saw cuts.
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp - SE
checkpoint | 1.7 - Completion of Works
label | Ref docs - IFC Drawings
label | Acceptance criteria - Correct kerb type installed as per IFC drawings.
label | • Line & level confirmed at time of pour.
button | Acceptance | Yes,No,N/A
label | Key - H
label | Resp - SE