## ITC
type | name | values | prefix | postfix | usage count
checklist-flat | Colphene Uni NG Capping Beam (ITC)
checkpoint | Substrate - To Pile Base
button | All surfaces dry, clean, smooth and free from sharp objects, laitance, oils, grease or any foreign materials which may inhibit or reduce adhesion. | Yes,No
button | Commencement of installation shall be taken as acceptance of the substrate by the Applicator | Yes,No
checkpoint | Colphene BSW UNI NG - To Pile Base
button | Confirm rolls stored upright, with the selvedge side on top. If the product is stored outdoors confirm covered with an protective cover | Yes,No
button | Check COLPHENE BSW UNI NG thickness is 4mm | Yes,No
button | Apply COLPHENE BSW UNI NG loose laid on blinding concrete | Yes,No
button | Confirm minimum 100 mm side overlap | Yes,No
button | Confirm minimum 150 mm end lap between each strip | Yes,No
button | Confirm end laps are staggered by at least 300 mm | Yes,No
button | Confirm laps avoid excessive layering | Yes,No
button | Visual inspection of joint welds at cross laps | Yes,No
button | Confirm no laps at capping beam construction joint | Yes,No
button | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 3-8mm bleed | Yes,No
button | Confirm all angle changes (inside and outside corners) are reinforced by heat-welding on additional 300 mm piece of COLPHENE BSW UNI NG centered on the angle | Yes,No
checkpoint | Alsan EP M - To Pile Base
button | MIXING - The mix ratio is 1:1 by volume, 1 parts Part A and 1 part Part B. Care should be taken to ensure that ALSAN EP M is thoroughly mixed. | Yes,No
button | The entire contents of the hardener (Part B) tin should be poured into the base (Part A) tin and the two materials thoroughly mixed using a suitable slow-speed drill and high shear mixing paddle | Yes,No
button | Mix for 2 minutes until a fully uniform grey colour is obtained; the sides of the tins should be scraped, mixing should continue for a further 2 minutes. DO NOT OVER MIX AS THIS MAY INCORPORATE AIR BUBBLES | Yes,No
button | To facilitate mixing and application at temperatures below 10˚C, the separate components should be warmed in hot water bath or conditions to room temperature, up to a maximum temperature of 25˚C before beginning to mix. If heated to 25˚C, the subsequently mixed material will have a pot life that will be reduced to 45 minutes. | Yes,No
button | Application - brush/trowel 40mm cove, covering joint from horizontal COLPHENE BSW UNI NG to pile | Yes,No
button | Cure time @ 25˚C - 12 hours | Yes,No
button | Store Aslan EP M in chemical bunds provided by Delta | Yes,No
checkpoint | Alsan Flashing & Alsan Fleece - To Pile Base
button | Mix well the product before use | Yes,No
button | ALSAN FLASHING is applied with a with a trowel, a brush or a roller in two (2) layers. Each layer must have a minimum wet film thickness of 0.8mm | Yes,No
button | First layer must be thick enough to completely immerse the reinforcement. POLYFLEECE will be immediately covered with a second layer of ALSAN FLASHING until saturation | Yes,No
button | Ready to recoat after 2 hours Dry: 12 hours (remains tacky to touch) | Yes,No
button | Store Aslan FLASHING in chemical bunds provided by Delta | Yes,No
checkpoint | Colphene BSW UNI NG Reiforcement Strip - To Pile Base
button | Confirm rolls stored upright, with the selvedge side on top. If the product is stored outdoors confirm covered with an protective cover | Yes,No
button | Check COLPHENE BSW UNI NG thickness is 4mm | Yes,No
button | Confirm minimum 100 mm side overlap | Yes,No
button | Confirm minimum 150 mm end lap between each strip | Yes,No
button | Confirm end laps are staggered by at least 300 mm | Yes,No
button | Confirm laps avoid excessive layering | Yes,No
button | Visual inspection of joint welds at cross laps | Yes,No
button | Confirm no laps at capping beam construction joint | Yes,No
button | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 3-8mm bleed | Yes,No
button | Confirm all angle changes (inside and outside corners) are reinforced by heat-welding on additional 300 mm piece of COLPHENE BSW UNI NG centered on the angle | Yes,No
checkpoint | Colphene BSW UNI NG - To External Capping Beam Face (Post Pour)
button | ANTIROCK PRIMER can be applied with a brush or roller on clean, dry substrates free of any residue that may hinder adherence. Shake well before using. | Yes,No
button | It must be thoroughly dry before applying the waterproofing membrane. Drying time will vary depending on air and surface temperature and humidity. | Yes,No
button | Confirm rolls stored upright, with the selvedge side on top. If the product is stored outdoors confirm covered with an protective cover | Yes,No
button | Check COLPHENE BSW UNI NG thickness is 4mm | Yes,No
button | Confirm minimum 100 mm side overlap | Yes,No
button | Confirm minimum 150 mm end lap between each strip | Yes,No
button | Confirm end laps are staggered by at least 300 mm | Yes,No
button | Confirm laps avoid excessive layering | Yes,No
button | Visual inspection of joint welds at cross laps | Yes,No
button | Confirm no laps at capping beam construction joint | Yes,No
button | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 3-8mm bleed | Yes,No
button | Confirm all angle changes (inside and outside corners) are reinforced by heat-welding on additional 300 mm piece of COLPHENE BSW UNI NG centered on the angle | Yes,No
checkpoint | Sopradrain 20 - To External Capping Beam Face
button | The substrate must be firm, even, clean and free from loose materials or any construction debris on the surface. | Yes,No
button | Install SOPRADRAIN 20 with the geotextile facing the backfill. | Yes,No
button | Join by simply butting edge to edge and overlapping the geotextile overhang and securing with reinforced canvastape | Yes,No
button | Terminate SOPRADRAIN 20 by nailing pressure bar at required height | Yes,No
checkpoint | CHECKLIST COMPLETE AND SIGNED
button | ITC completed | Yes,No

## ITP
type | name | values | prefix | postfix | usage count
checklist-flat | Colphene Uni NG Capping Beam ITP
Checkpoint | CAPPING BEAM WATERPROOFING ITP | Yes,No
button | Sample Submissions Approved | Yes,No
button | Shop Drawings Approved | Yes,No
button | Substrate - To Pile Base | Yes,No
button | Colphene BSW UNI NG Installed - To Pile Base | Yes,No
button | Alsan EP M Installed - To Pile Base | Yes,No
button | Colphene BSW UNI NG Reiforcement Strip Installed - To Pile Base | Yes,No
button | Alsan Flashing & Alsan Fleece Installed - To Pile Base | Yes,No
button | Colphene BSW UNI NG - To External Capping Beam Face | Yes,No
button | Sopradrain 20 - To External Capping Beam Face | Yes,No
button | ITC Pre-Pour Complete & Signed | Yes,No
button | Client Inspections Completed & Report Closed Out | Yes,No
button | Pour Inspection & Sign Off | Yes,No
button | Colphene BSW V Installed - To External Capping Beam Face | Yes,No
button | Sopradrain 20 Installed - To External Capping Beam Face | Yes,No
button | ITC Pre-Pour Complete & Signed | Yes,No
button | Client Inspections Completed & Report Closed Out | Yes,No
button | Backfill Inspection & Sign Off | Yes,No
button | Soprema & Bravada Quality Documentation issued to Client | Yes,No