## ITP Cover Page
Landscaping Inspection and Test Plan
Project: SH1/29 Intersection Upgrade
Number and Revision: 1208 - 808 - Rev C
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | SH1/29 Intersection Upgrade |  |  |  |  | ITP Number: |  |  | 808
Project Number: |  |  | 1208 |  |  |  |  | ITP Status: |  |  | Final
ITP Description: |  |  | Landscaping Inspection and Test Plan |  |  |  |  | Revision: | 1000 |  | C
Contract Number: |  |  | 7991 |  |  |  |  | Drawing Sets:
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification:
Quality Specified: |  |  | Z8
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
A | Draft for Approval | 2023-12-18 |  | Stuart McCarron |  | Combined Remaining Items Inspection and Test Plan |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B | Draft for Approval | 2024-07-22 |  | Jayson Arroyo |  | Have made ammendments based on Stantec review |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
C | Final | 2024-09-11 |  | Hayley |  | ITP prepared by Stantec for Downers |  |  |  | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – Master ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## Landscaping
Landscaping Inspection and Test Plan
Project: SH1/29 Intersection Upgrade
Number and Revision: 1208 - 808 - Rev C
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Testing Quantity Required | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | General
| Precondition Surveys | A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site. | PS 2.13 | Precondition Survey report and plan | Prior to the Contractor taking possession of the Site. |  | H | PM
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.39 | Landscaping Material Supply
4.39.1 | Nursery Inspection | All plants inspected at nursery | P39 G-3.1 & 3.4 | Inspection Record | Invite SPEC to inspect minimum 10 days before delivery. |  | HP | SPEC
4.39.2 | Plant Substitution | Approval of Contractors proposed plant species substitution | P39 G-3.1 | Designers Approval | as need basis |  | HP | WSP
4.39.3 | Topsoil Testing | Proposed topsoil sampled and laboratory tested to F-3.1 and 3.2 | PS 25.8.1 P39 F-3.1,3.2 | Lab report | Prior to supply | 10 equal samples mixed. 1kg supplied to lab | HP | ENG
4.39.4 | Topsoil Sample Inspection | Representative sample kept on site for landscape Architects inspection, if requested | P39 F-3.2.1 | Sample | Upon request |  | I | PE
4.39.5 | Topsoil Remediation | Topsoil improvement methodology (if required by testing) and grassed area fertilisation methodology and programme | P39 B-4, P39 F-3.2 PS 25.10.2 | NTC | Prior to placement |  | R | PE
4.39.6 | Biodegradable Weedmat supply | Datasheet and sample of all types of biodegradable matting and netting supplied to Engineer. | PS 25.9.1 P39 B-4 P39 G-3.9 | NTC | Prior to procurement |  | HP | SPEC
4.39.7 | Mulch supply | Sample of bark or arb mulch provided to Engineer for approval | PS 25.9.2.1 P39 B-4 P39 G-3.9 | NTC | Prior to procurement |  | HP | SPEC
4.39.8 | Grass/Hydroseed | Provide Supplier's grass seed brand and seed mix, and application rate for Engineers approval Provide Supplier's hydroseed mix for Engineers approval | P39 H-2.1 P39 I-2.2 | NTC | Prior to procurement |  | HP | SPEC
4.39.9 | Turf / Instant turf (if required) | Provide Supplier's installation and maintenance rquirements to Engineer | PS 25.10.5 | Datasheet | Prior to installation |  | R | PE
4.39.10 | Fertilisers | provide fertiliser product details to Engineer for planting, turf, grass and hydrograss | PS 25.7.3.2 | Datasheet | Prior to procurement |  | R | SPEC
4.39.11 | Contractor to develop hard landscaping materials ITP once the design has been completed | [6 empty] | SPEC
SECTION 18 – CONSTRUCTION ACTIVITY – LANDSCAPING
18.01 | Site preperation & Topsoiling
18.01.1 | Work Plan | A detailed work plan shall be prepared for all landscape works, | P39 B-5.1 | Work Plan | Two weeks prior to landscape works |  | R | SPEC
18.01.2 | Cultivation and Inspection pre-topsoiling | Inspect cut surfaces prior to the placement of topsoil and planting. Inspect Cultivation prior to planting or topsoiling. | PS 15.10.10 Drawings PS 25.1.6(c) PS 25.8.1 P39 C-5.13 P39 B-4 P39 F-3.5.2 | Engineers Approval | 2 days prior to Topsoil Placement |  | HP | ENG
18.01.3 | Topsoil Depth check | Topsoil depth check. (Planted areas topsoil 300mm, grassed areas 100mm, pb95 tree pits 1000x1000x1000) | P39 F-3.2.1 | Survey Plan showing depth generated from before/after survey. | During Placement | Random manual dig check by Eng. | HP | ENG
18.01.4 | Pest Plant and Animal Control methodology | Submit methodology for approval | P39 D-4.2 PS 25.5.2 |  | Prior to commencing operations |  | R | PE
18.01.5 | Pest Control notification | written notification to Engineer 2 days before pest control or spraying operations. at least 24hr notice to landowners | P39 D-4.2, 4.5, 4.5.2.2 | NTE, letter | before each operation |  | R | PE
18.01.6 | Mulch Depth | 100mm depth for all planted areas once settled, not less than 75mm for trees | P39-K-6.6 | Inspection Record | Following planting | Mulch checked during planting audit | D | PE
18.03 | Planting & Grassing
18.03.01 | Plant Delivery | Inspect all plants upon delivery to site. Provide written notice to Eng min 2 days before delivery | PS 25.7.1 PS 25.1.6 P39 B-4 | Inspection Record | During/Following delivery |  | I/HP | SPEC
18.03.02 | Planting or seeding Notice | The Contractor shall provide written notice to the Engineer, at least two days prior to Planting or seeding. | PS 25.1.6 P39 B-4 | NTE | At least two days prior |  | R | PE
18.03.03 | Peg Sample Areas | The Landscape Archtect Stantec will identify sample areas to be audited to P39 B-6.1 for each planting type, and supply a sample area plan to the Contractor for pegging. | P39 B-6.1 | Planting Sample Plan | Following Planting | For planting areas < 2,000 m2, 2 No. sample areas each min. 5% of planting area. For planting areas > 2,000 m2, 2 No. sample areas each min. 2% of planting area. | O | SPEC
18.03.04 | Plant set out | Following sample area pegging, the Landscape Architect will audit sample area quantities and species composition to P39 B:6 and G:4.5 for each planting mix. Minimum of 95% plant count | P39 G-4.5, B-6 | Planting | Prior to planting until all treatments achieved. | For planting areas < 2,000 m2, 2 No. sample areas each min. 5% of planting area. For planting areas > 2,000 m2, 2 No. sample areas each min. 2% of planting area. | HP | SPEC
18.03.05 | Planting Sampling and Inspection | Condition of acceptance inspection - once areas are planted, the Landscape aarchitect will hold an inspection to sample each treatment for density, composition and quality of workmanship. 95% plant density and correct species composition | P39 B-6.1, 6.2 | P39 B-6.3 Planting sample report, B-6.2 checklist, and NTC | Following Planting | Planting areas < 500 m2, 1 per 50m2, min. 5. <2000m2, 1 per 100m2, min. 10 <5,000m2, 1 per 200m2, min. 25. <10,000, 1 per 500, min. 40 Note this is total planting m2 not sample areas Repeat sample if >2 faults in >20% of sample. If >2 faults in >20% of average of 2 sample sites, then check all plants in planting area | I | SPEC
18.03.06 | Grass and Hydro-seeding | Estbalishment 95% coverage, weeds visible not >4, bare patches <100mm diamter | SP39 B7 & B8 | P39 B-6.3 Planting 3-month maintenance inspection report, B-6.2 checklist, and NTC | Following planting and every 3 month inspection |  | V | ENG
18.03.07 | Maintenance Regime submission (if not already provided as part of work plan) | Review of regime by Landscaping Architect (Stantec). Approvals sought by local authorities for pest management and confirmed acceptance by WSP. | P39 K-2.1 | SPEC review and Designer approval | prior to installing planting works. |  | R | SPEC/WSP
18.03.08 | Site visit maintenance period Notice | Written notice to the Engineer, at least 5 days prior to Site visits during maintenance period. Contractor to submit report | PS 25.1.6 P39 B-4 & K-2.1 | Notice | At least five days prior |  | R | PE
18.03.09 | Defects Liability Reporting | Plants inspected and measured for growth, checked for health - quartely inspectons until achieved targets. Observe grass coverage 80% canopy coverage, 100% survival of trees and grass areas 95% - <100mm dia gap acceptable defects liability period and maintenance period for 5years | P39 Section K 6.3 & 6.4 & section B 6,7,8 | P39 B-3 & B-6.3 Planting 3-month maintenance inspection report, B-6.2 checklist, and NTC | Every 3 months during defects liability and maintenance period (5years) | Planting areas < 500 m2, 1 per 50m2, min. 5. <2000m2, 1 per 100m2, min. 10 <5,000m2, 1 per 200m2, min. 25. <10,000, 1 per 500, min. 40 Note this is total planting m2 not sample areas | I | SPEC
18.03.10 | Final End of maintenance Inspection | 100% Large plants >PB27 healthy, maximum 10% small plant loss, 80% plant canopy, planted area weeds limited to 4 visible at any point 95% grass cover, weeds <4 visible, no kikuyu | P39 A-2 P39 G-1 P39 H-4.7 P39 K-1.1 | End of Planting Defects Liability | 1 inspection upon completion of defects and maintenance period |  | I/V | SPEC
18.04 | Fencing
18.04.01 | Temporary Stockproof boundary Fence | Record of Landowner liaison confirming temporary fence | PS 25.12.1 | Comms | Prior to Installation |  | S | PE
18.04.02 | Permanent Stockproof boundary Fence | Fenceline ground contour finalised prior to discussing fence with landowner | PS 25.12.2 | Comms | Prior to Installation |  | I | PE
18.04.03 | Permanent Stockproof boundary Fence | Record of Landowner liaison confirming permanent 7-wire P&W fence and gate provision in accordfance with landowner agreement | PS 25.12.2 | Comms | Prior to Installation |  | R | PE
18.04.04 | Permanent Stockproof boundary Fence | Fence postion tolerance survey | PS 25.12.2 | Asbuilt dwg | Within 10 days of installation |  | S | SV
18.05 | Hard Landscaping
18.05.1 | Contractor to develop hard landscaping ITP once the design has been completed