## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Landscaping - 808 - Rev C | itp |  |  |  |  | ITP - Landscaping - 808 - Rev C
section | 3.01 General
checkpoint | Precondition Surveys
label | Acceptance / Conformance Criteria - A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site.
label | Standard / Specification - PS 2.13
label | Verifying Document - Precondition Survey report and plan
label | Frequency - Prior to the Contractor taking possession of the Site.
label | Verification Activity: Activity - H
label | Verification Activity: By - PM
section | 4.39 Landscaping Material Supply
checkpoint | 4.39.1 - Nursery Inspection
label | Acceptance / Conformance Criteria - All plants inspected at nursery
label | Standard / Specification - P39 G-3.1 & 3.4
label | Verifying Document - Inspection Record
label | Frequency - Invite SPEC to inspect minimum 10 days before delivery.
label | Verification Activity: Activity - HP
label | Verification Activity: By - SPEC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.39.2 - Plant Substitution
label | Acceptance / Conformance Criteria - Approval of Contractors proposed plant species substitution
label | Standard / Specification - P39 G-3.1
label | Verifying Document - Designers Approval
label | Frequency - as need basis
label | Verification Activity: Activity - HP
label | Verification Activity: By - WSP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.39.3 - Topsoil Testing
label | Acceptance / Conformance Criteria - Proposed topsoil sampled and laboratory tested to F-3.1 and 3.2
label | Standard / Specification - PS 25.8.1, P39 F-3.1,3.2
label | Verifying Document - Lab report
label | Frequency - Prior to supply
label | Testing Quantity Required - 10 equal samples mixed. 1kg supplied to lab
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.39.4 - Topsoil Sample Inspection
label | Acceptance / Conformance Criteria - Representative sample kept on site for landscape Architects inspection, if requested
label | Standard / Specification - P39 F-3.2.1
label | Verifying Document - Sample
label | Frequency - Upon request
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 4.39.5 - Topsoil Remediation
label | Acceptance / Conformance Criteria - Topsoil improvement methodology (if required by testing) and grassed area fertilisation methodology and programme
label | Standard / Specification - P39 B-4, P39 F-3.2, PS 25.10.2
label | Verifying Document - NTC
label | Frequency - Prior to placement
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 4.39.6 - Biodegradable Weedmat supply
label | Acceptance / Conformance Criteria - Datasheet and sample of all types of biodegradable matting and netting supplied to Engineer.
label | Standard / Specification - PS 25.9.1, P39 B-4, P39 G-3.9
label | Verifying Document - NTC
label | Frequency - Prior to procurement
label | Verification Activity: Activity - HP
label | Verification Activity: By - SPEC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.39.7 - Mulch supply
label | Acceptance / Conformance Criteria - Sample of bark or arb mulch provided to Engineer for approval
label | Standard / Specification - PS 25.9.2.1, P39 B-4, P39 G-3.9
label | Verifying Document - NTC
label | Frequency - Prior to procurement
label | Verification Activity: Activity - HP
label | Verification Activity: By - SPEC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.39.8 - Grass/Hydroseed
label | Acceptance / Conformance Criteria - Provide Supplier's grass seed brand and seed mix, and application rate for Engineers approval
label | ○ Provide Supplier's hydroseed mix for Engineers approval
label | Standard / Specification - P39 H-2.1, P39 I-2.2
label | Verifying Document - NTC
label | Frequency - Prior to procurement
label | Verification Activity: Activity - HP
label | Verification Activity: By - SPEC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.39.9 - Turf / Instant turf (if required)
label | Acceptance / Conformance Criteria - Provide Supplier's installation and maintenance rquirements to Engineer
label | Standard / Specification - PS 25.10.5
label | Verifying Document - Datasheet
label | Frequency - Prior to installation
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 4.39.10 - Fertilisers
label | Acceptance / Conformance Criteria - provide fertiliser product details to Engineer for planting, turf, grass and hydrograss
label | Standard / Specification - PS 25.7.3.2
label | Verifying Document - Datasheet
label | Frequency - Prior to procurement
label | Verification Activity: Activity - R
label | Verification Activity: By - SPEC
checkpoint | 4.39.11 - Contractor to develop hard landscaping materials ITP once the design has been completed
label | Verification Activity: By - SPEC
section | 18.01 Site preperation & Topsoiling
checkpoint | 18.01.1 - Work Plan
label | Acceptance / Conformance Criteria - A detailed work plan shall be prepared for all landscape works,
label | Standard / Specification - P39 B-5.1
label | Verifying Document - Work Plan
label | Frequency - Two weeks prior to landscape works
label | Verification Activity: Activity - R
label | Verification Activity: By - SPEC
checkpoint | 18.01.2 - Cultivation and Inspection pre-topsoiling
label | Acceptance / Conformance Criteria - Inspect cut surfaces prior to the placement of topsoil and planting. Inspect Cultivation prior to planting or topsoiling.
label | Standard / Specification - PS 15.10.10 Drawings, PS 25.1.6(c), PS 25.8.1, P39 C-5.13, P39 B-4, P39 F-3.5.2
label | Verifying Document - Engineers Approval
label | Frequency - 2 days prior to Topsoil Placement
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 18.01.3 - Topsoil Depth check
label | Acceptance / Conformance Criteria - Topsoil depth check. (Planted areas topsoil 300mm, grassed areas 100mm, pb95 tree pits 1000x1000x1000)
label | Standard / Specification - P39 F-3.2.1
label | Verifying Document - Survey Plan showing depth generated from before/after survey.
label | Frequency - During Placement
label | Testing Quantity Required - Random manual dig check by Eng.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 18.01.4 - Pest Plant and Animal Control methodology
label | Acceptance / Conformance Criteria - Submit methodology for approval
label | Standard / Specification - P39 D-4.2, PS 25.5.2
label | Frequency - Prior to commencing operations
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 18.01.5 - Pest Control notification
label | Acceptance / Conformance Criteria - written notification to Engineer 2 days before pest control or spraying operations. at least 24hr notice to landowners
label | Standard / Specification - P39 D-4.2, 4.5, 4.5.2.2
label | Verifying Document - NTE, letter
label | Frequency - before each operation
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 18.01.6 - Mulch Depth
label | Acceptance / Conformance Criteria - 100mm depth for all planted areas once settled, not less than 75mm for trees
label | Standard / Specification - P39-K-6.6
label | Verifying Document - Inspection Record
label | Frequency - Following planting
label | Testing Quantity Required - Mulch checked during planting audit
label | Verification Activity: Activity - D
label | Verification Activity: By - PE
section | 18.03 Planting & Grassing
checkpoint | 18.03.01 - Plant Delivery
label | Acceptance / Conformance Criteria - Inspect all plants upon delivery to site.
label | ○ Provide written notice to Eng min 2 days before delivery
label | Standard / Specification - PS 25.7.1, PS 25.1.6, P39 B-4
label | Verifying Document - Inspection Record
label | Frequency - During/Following delivery
label | Verification Activity: Activity - I/HP
label | Verification Activity: By - SPEC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 18.03.02 - Planting or seeding Notice
label | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Planting or seeding.
label | Standard / Specification - PS 25.1.6, P39 B-4
label | Verifying Document - NTE
label | Frequency - At least two days prior
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 18.03.03 - Peg Sample Areas
label | Acceptance / Conformance Criteria - The Landscape Archtect Stantec will identify sample areas to be audited to P39 B-6.1 for each planting type, and supply a sample area plan to the Contractor for pegging.
label | Standard / Specification - P39 B-6.1
label | Verifying Document - Planting Sample Plan
label | Frequency - Following Planting
label | Testing Quantity Required - For planting areas < 2,000 m2, 2 No. sample areas each min. 5% of planting area.
label | ○ For planting areas > 2,000 m2, 2 No. sample areas each min. 2% of planting area.
label | Verification Activity: Activity - O
label | Verification Activity: By - SPEC
checkpoint | 18.03.04 - Plant set out
label | Acceptance / Conformance Criteria - Following sample area pegging, the Landscape Architect will audit sample area quantities and species composition to P39 B:6 and G:4.5 for each planting mix. Minimum of 95% plant count
label | Standard / Specification - P39 G-4.5, B-6
label | Verifying Document - Planting
label | Frequency - Prior to planting until all treatments achieved.
label | Testing Quantity Required - For planting areas < 2,000 m2, 2 No. sample areas each min. 5% of planting area.
label | ○ For planting areas > 2,000 m2, 2 No. sample areas each min. 2% of planting area.
label | Verification Activity: Activity - HP
label | Verification Activity: By - SPEC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 18.03.05 - Planting Sampling and Inspection
label | Acceptance / Conformance Criteria - Condition of acceptance inspection - once areas are planted, the Landscape aarchitect will hold an inspection to sample each treatment for density, composition and quality of workmanship.
label | ○ 95% plant density and correct species composition
label | Standard / Specification - P39 B-6.1, 6.2
label | Verifying Document - P39 B-6.3, Planting sample report, B-6.2 checklist, and NTC
label | Frequency - Following Planting
label | Testing Quantity Required - Planting areas < 500 m2, 1 per 50m2, min. 5.
label | ○ <2000m2, 1 per 100m2, min. 10
label | ○ <5,000m2, 1 per 200m2, min. 25.
label | ○ <10,000, 1 per 500, min. 40
label | – Note this is total planting m2 not sample areas
label | – Repeat sample if >2 faults in >20% of sample. If >2 faults in >20% of average of 2 sample sites, then check all plants in planting area
label | Verification Activity: Activity - I
label | Verification Activity: By - SPEC
checkpoint | 18.03.06 - Grass and Hydro-seeding
label | Acceptance / Conformance Criteria - Estbalishment 95% coverage, weeds visible not >4, bare patches <100mm diamter
label | Standard / Specification - SP39 B7 & B8
label | Verifying Document - P39 B-6.3, Planting 3-month maintenance inspection report, B-6.2 checklist, and NTC
label | Frequency - Following planting and every 3 month inspection
label | Verification Activity: Activity - V
label | Verification Activity: By - ENG
checkpoint | 18.03.07 - Maintenance Regime submission (if not already provided as part of work plan)
label | Acceptance / Conformance Criteria - Review of regime by Landscaping Architect (Stantec). Approvals sought by local authorities for pest management and confirmed acceptance by WSP.
label | Standard / Specification - P39 K-2.1
label | Verifying Document - SPEC review and Designer approval
label | Frequency - prior to installing planting works.
label | Verification Activity: Activity - R
label | Verification Activity: By - SPEC/WSP
checkpoint | 18.03.08 - Site visit maintenance period Notice
label | Acceptance / Conformance Criteria - Written notice to the Engineer, at least 5 days prior to Site visits during maintenance period. Contractor to submit report
label | Standard / Specification - PS 25.1.6, P39 B-4 & K-2.1
label | Verifying Document - Notice
label | Frequency - At least five days prior
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 18.03.09 - Defects Liability Reporting
label | Acceptance / Conformance Criteria - Plants inspected and measured for growth, checked for health - quartely inspectons until achieved targets. Observe grass coverage 80% canopy coverage, 100% survival of trees and grass areas 95% - <100mm dia gap acceptable defects liability period and maintenance period for 5years
label | Standard / Specification - P39 Section K 6.3 & 6.4 & section B 6,7,8
label | Verifying Document - P39 B-3 & B-6.3, Planting 3-month maintenance inspection report, B-6.2 checklist, and NTC
label | Frequency - Every 3 months during defects liability and maintenance period (5years)
label | Testing Quantity Required - Planting areas < 500 m2, 1 per 50m2, min. 5.
label | ○ <2000m2, 1 per 100m2, min. 10
label | ○ <5,000m2, 1 per 200m2, min. 25.
label | ○ <10,000, 1 per 500, min. 40
label | – Note this is total planting m2 not sample areas
label | Verification Activity: Activity - I
label | Verification Activity: By - SPEC
checkpoint | 18.03.10 - Final End of maintenance Inspection
label | Acceptance / Conformance Criteria - 100% Large plants >PB27 healthy, maximum 10% small plant loss, 80% plant canopy, planted area weeds limited to 4 visible at any point
label | ○ 95% grass cover, weeds <4 visible, no kikuyu
label | Standard / Specification - P39 A-2, P39 G-1, P39 H-4.7, P39 K-1.1
label | Verifying Document - End of Planting Defects Liability
label | Frequency - 1 inspection upon completion of defects and maintenance period
label | Verification Activity: Activity - I/V
label | Verification Activity: By - SPEC
section | 18.04 Fencing
checkpoint | 18.04.01 - Temporary Stockproof boundary Fence
label | Acceptance / Conformance Criteria - Record of Landowner liaison confirming temporary fence
label | Standard / Specification - PS 25.12.1
label | Verifying Document - Comms
label | Frequency - Prior to Installation
label | Verification Activity: Activity - S
label | Verification Activity: By - PE
checkpoint | 18.04.02 - Permanent Stockproof boundary Fence
label | Acceptance / Conformance Criteria - Fenceline ground contour finalised prior to discussing fence with landowner
label | Standard / Specification - PS 25.12.2
label | Verifying Document - Comms
label | Frequency - Prior to Installation
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 18.04.03 - Permanent Stockproof boundary Fence
label | Acceptance / Conformance Criteria - Record of Landowner liaison confirming permanent 7-wire P&W fence and gate provision in accordfance with landowner agreement
label | Standard / Specification - PS 25.12.2
label | Verifying Document - Comms
label | Frequency - Prior to Installation
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 18.04.04 - Permanent Stockproof boundary Fence
label | Acceptance / Conformance Criteria - Fence postion tolerance survey
label | Standard / Specification - PS 25.12.2
label | Verifying Document - Asbuilt dwg
label | Frequency - Within 10 days of installation
label | Verification Activity: Activity - S
label | Verification Activity: By - SV
section | 18.05 Hard Landscaping
checkpoint | 18.05.1 - Contractor to develop hard landscaping ITP once the design has been completed