## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
b26f3c91-5f3d-4ee3-8534-642684b09b45 | checklist | Preliminary Activities and Materials Approval Checklist |  | Preliminary Activities and Materials Approval Checklist
778067be-6c51-4a6a-9e4c-b1cce1e81fa1 | section | Preliminary Activities (Approved by Client)
709b7048-8688-4c33-b2a3-6fe19e38ba53 | checkpoint | Compliance to AS/NZ ISO 9001:2015
25c2f1d7-6914-456f-8eb1-c099593c6390 | checkpoint | Permacast Project Quality Management Plan
fc5cd8a3-e849-4388-881f-5d44f86b6318 | checkpoint | Inspection & Test Plan
0a0c01f4-c084-424e-88ac-75d1ce8973c7 | checkpoint | MDR Index
cc7cfe30-da6d-49c5-b2af-b6e97621d731 | checkpoint | Work Method Statement (WMS) - Prestress
62a8c879-8096-4105-82ee-acb585fcd0d4 | checkpoint | Concrete Repair Methodology
892abc4f-27f7-418c-a791-3916553a5679 | checkpoint | Shop Drawings
b2f04bc2-acbd-4c81-b6a2-02a1546e13eb | checkpoint | Test Panel Prepared and Inspected by Client
8f25f040-ce63-471c-86ae-8102e3b3adc2 | checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
4751a869-d76e-40c9-91e8-bc358e5970e4 | section | Concrete
d853db68-22d2-4ddf-9b76-45f46753a08d | checkpoint | S50 Concrete Mix Design Approved by Client
0fa5d9d2-a07f-420e-880e-679459ddd2cc | section | Steel Reinforcement
50cdbfd5-be7d-457c-80c2-bcfbf1bc68e7 | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
d67ecc5f-4975-435c-98ea-bd34573d9fdf | checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
0ddc4e10-5f43-4711-9f33-4be24db1f851 | section | Prestressing Tendons
d545bc63-4c2a-4721-b4b7-ed07bdcf165f | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
a97db483-6ba2-4aac-831f-f796828147d5 | checkpoint | Ensure that all Coil Numbers are recorded
866e816c-2439-400e-8f02-ad1dd8b76381 | checkpoint | Stressing Calculations Submitted and Approved by Client for Works
62bf8fe4-5df5-42f2-a878-955db097f3ba | checkpoint | Stressing Jack Calibration Certificates
c2f81996-511e-427c-ab08-b535e1f3b234 | section | Lifting Anchors
6dff2e65-4b1e-4218-8d84-ed5f17fabf95 | checkpoint | Lifting Design Approved by Client
8f190fd1-5c73-4cfd-8373-a0461337650b | checkpoint | Lifting Devices Approved by Client
cff9975c-8e08-41fc-b2bd-03419f884af3 | checkpoint | Inspection of Delivery for Completeness and Quality
a48d819a-3617-44f3-a9ae-7af206d9caf2 | section | Cast-in Items and Ferrules
7461ad6d-75a2-4c2c-b88d-2e9eb34063c6 | checkpoint | All Cast in Materials Approved
508b670e-a4a2-4906-ba4a-326a99e9e405 | checkpoint | Inspection of Delivery for Completeness and Quality
6dd399c3-a1f6-4069-8ff9-9b692b1718c4 | checklist | S2M Prestressed Planks |  | S2M Prestressed Planks
50bad73e-b6a2-4b8e-9f3e-33c547b16016 | section | Pre-Pour Checklist
82a31d9b-86b1-448d-8239-2412e7abad77 | checkpoint | Pre-Pour Checklist completed
61fbf2f9-3d67-5852-bb81-e6bfc2d6406d | textbox | Cast Number
d08d40d6-c4ac-4ea6-bb72-18298fc4e65f | checkpoint | Shop Drawings approved for Works
0da3f127-da01-4655-8147-9b0048ee351a | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
f3642b11-aa98-592b-a3c1-18f1772e3502 | note | Length
f621a882-e6fc-57d7-8278-c9d0a46751e3 | note | Width
0b89426d-cd6a-5a62-982e-af373dfe9f5b | note | Height
8a5404ad-b90b-5df4-80c0-775dbf2b2acf | note | Straightness
8022fc65-55c1-5a60-b7fe-474e8ee44b9f | note | Cross-section
d9fff931-af9c-4f3b-8e65-4dd90155ba35 | checkpoint | Mould Surface Checked
2a948276-5d18-5ea2-a769-c478611c92d6 | note | Cleaned
95b98e56-544d-5e15-b67e-a04da3e9fc28 | note | Sealed
30886d74-39fc-561a-862c-35c7d9e12125 | note | Rubbers in Place
809eae25-5044-5c19-aa12-ae04e3338ce7 | note | Oiled
76464994-542d-5520-8cdc-ba559bd895d7 | note | Chamfers in Place
76a45560-3cc7-4f6b-ad44-c0ab6ccb6dc8 | checkpoint | Reinforcement in Accordance with Drawings
d3ad35d9-9832-53e4-83b5-7ae4c4012417 | note | Reinforcement size
be8c233a-56b9-596a-8d9e-1146c3221745 | note | Lap Length
45aae23c-5f06-5b12-900f-9b7f11d861d0 | note | Bar Chairs
d9b11598-4cdb-47ac-a89f-434addd594df | checkpoint | Detailed inspection of Mould and cage
7aa8e061-4060-4673-8f73-a7077be57c38 | checkpoint | Cover maintained and within tolerance
8e63c601-6e91-48bc-a33a-aa5bb367dc87 | checkpoint | All Lifting Inserts are installed in accordance with Drawings
f216f8b2-77e6-54d6-bc22-f52272fd7759 | textbox | Lifters
2a0dd871-a2d9-4e7a-950e-94c349190059 | checkpoint | All Dowels are installed as per drawings
9a43e092-64d9-57f3-959e-340e5432e65a | textbox | Specify Dowel size
4e3f0bdd-b7ca-5248-8e55-9530c66587ed | note | Dowel in correct position
9ba43bad-ae44-4458-80b9-49b2dec20ceb | checkpoint | Prestressing Strands
bdae9bdd-08b6-58c2-9a96-8a3d1543df4b | textbox | Coil Number Used for this Cast
5ddedfe9-40eb-5ba9-8b29-a7e36fbaa3b0 | textbox | Dia and No. of strands
44e5ca5d-7db6-5a4a-98fc-7cf88b8945ad | textbox | Strands arrangement verified
26596a1f-f1a3-5ebb-8d54-2537738f9929 | note | Sag Load all Strands
a562ecfb-0499-50a8-a6c8-ac0a0aeb67ad | note | Mutli-Stress as per Pre-stressing Procedures
ee48ef65-ad54-5219-8ab0-e09012781369 | note | Verify debonding strands
7525de49-e767-4bac-9ecd-e8ddadb3f606 | checkpoint | Pre-lifting cage inspection (Client present)
68cfcab7-ee63-4901-9711-cfb4bf79cdc3 | checkpoint | Stressing Records subject to Client Review
62bc8d31-4a38-469b-b9b0-f79546600652 | signoff | (HOLD POINT FOR CLIENT TO SIGN OFF)
81e2b2ca-ef1f-496e-aae8-62aae1c543ee | checkpoint | QA Engineer Check Completed by
2f8dbe89-306d-49ad-9853-ce13291da753 | checkpoint | Pre-pour cage/mould inspection (Client Present)
c9589065-ae91-4bec-b760-65521f8f5141 | signoff | (HOLD POINT FOR CLIENT TO SIGN OFF)
dc4eb385-2202-46dc-9c44-2daf50178f67 | section | Supervisor Release
daecd3cb-9623-4db4-9976-4ea5c5a4b390 | checkpoint | Supervisor Release to Engineering Team
79165fc1-5eff-4344-a78c-438440d63c8f | section | Casting Checklist
177c160c-1a41-462d-8c42-1531adc82da7 | checkpoint | Casting Information
e88a546c-746a-52b9-94f2-08de03c0ba94 | textbox | Cast Date
4f6c61e7-91b2-4693-9193-262e995a071c | checkpoint | Concrete Delivery Dockets
38a3d2e4-1892-5b4c-8693-3f7deaf8593e | textbox | Concrete Delivery Dockets (list all)
7872aa61-5b77-44a4-92ae-694ffbc804ec | checkpoint | Total Concrete Volume
21c2f50b-aa6a-56e8-8c3c-771943f01f94 | textbox | Volume (m3)
43776149-6467-450e-9da3-6fc38e076da9 | checkpoint | Mix Design Verified
7a73fd4e-b88c-55d2-af66-7b89eaad7b45 | textbox | Specify mix used
3427477d-ec2c-4b9a-8bab-0735a8a883e8 | checkpoint | Ambient Temperature within Limits
ab178484-1210-5dc8-a412-d8cd91170224 | note | max 38°C
e0bea595-a17d-45de-9723-551588de51ea | checkpoint | Concrete Temperature
d64bd531-88fd-5411-89f9-4ae8adf3f94c | note | max 32°C
9ebcc717-708b-41e8-a7b3-711e4bbe7f51 | checkpoint | Slump within Allowable Tolerance (200+/-40) (Tested 1st truck and subsequently for every 20m3)
7c727a8f-d575-5f5b-8e78-f438dfe678ba | textbox | Slump (list all)
fa72055f-a96a-43ee-8be1-3c427dc6dd32 | checkpoint | Trucks Tested for strength
d47ae758-3216-5d98-b4ad-caadefffe917 | textbox | Test Report Reference Number (list all)
45d72a48-fbdd-45a9-a812-5b19f02066c2 | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
5025c071-94b2-48eb-b45e-20f756c25f1b | checkpoint | Concrete Placed within allowable time from Batching Plant, not exceeding 90 minutes
6f7b324d-75ff-4568-a5d0-846e23b21f67 | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
bf470e74-473e-4059-ba71-9cc22b5bfb55 | checkpoint | Required Finish Applied as per Drawings
ca8f7291-fd59-49cc-88f4-f81082381e4d | checkpoint | Retarders applied on Green Cut areas as shown in drawings
d775b691-5bea-441d-ae3e-0be99843ea86 | checkpoint | Concrete Covered Overnight
a960b80b-c7e9-4ddc-9d58-e6a30a9f6cd4 | checkpoint | Cylinders Stored next to Bed
74f8a2a5-ea21-4a5e-be5d-d02acdf6e0f5 | section | Stripping Checklist
1ad422b9-308a-408f-b7c5-6ea2170b5e59 | checkpoint | Date Stripped
6a77559e-c2b8-5149-b1b8-60314ae7d037 | textbox | Enter Date
886d703a-f13e-40e2-b79d-3cb30e146f09 | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
f2ac1691-25d2-57ac-b442-c06652b3817f | note | Conversion KN to MPa = Reading / 7.851
17d95f1b-c6d7-5cf7-9282-44e70cad68cc | note | Stripping strength 37MPa
5eddbe78-78f3-51f0-ba82-e86c6d308b32 | textbox | Stripping Strength
75b8bf2d-fa8d-4d6c-b9e3-f22ce751f371 | signoff | (HOLD POINT FOR CLIENT TO SIGN OFF)
dd003744-eb03-4611-b1a1-e88df47241d5 | checkpoint | Lifting Strength Achieved
2a324ebf-178b-58c7-80bc-942bc63ea370 | note | Lifting strength required - 37MPa
42964788-318b-5d95-9891-f6bcea79c058 | textbox | Specify strength at time of lifting
170da0f8-e800-40db-a610-3f80d2bf4db1 | checkpoint | Lifted and Handled as per Drawings
5c2925b7-7634-4194-8021-01c0d85c4c27 | checkpoint | Product Clearly Labelled
d8ddba11-9266-461e-a88a-71af077de570 | checkpoint | Additional Curing
e2069d1f-8099-5b6a-b9d4-bca93e09392a | note | Plank covered for 7 days
520ec8f3-21e8-4add-b4d3-5e3a445d7df9 | checkpoint | Storage as per Approved Temporary Works Drawings
a1457a7a-f730-4613-99f7-f0bbf2b82f59 | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
04cd2f07-8ed9-5dda-b453-48b68b7bfc8f | note | Length
34b21058-129d-59e3-b05e-04fca07e4ec8 | note | Width
7751b84a-895d-5629-a1eb-6870e5da8d19 | note | Height
136fb3cb-dc3a-5418-9b46-9586158cc410 | note | Straightness
eb0dce24-ddc7-5ae0-b570-277e7b8a6c0b | note | Cross-section
4ba58109-b474-45cd-9082-0faba8ebb7f7 | checkpoint | Specified Finish Achieved
3a148111-6d89-4d5f-b95b-51111840dd73 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
2ba4d0d0-e2ce-5522-a414-1ac20b39141d | textbox | Lifters
5431c9a0-de84-569e-acb9-dfd2f2439c66 | textbox | Dowels
b729ab4c-bd86-4fc8-a9ca-1ae404841109 | checkpoint | Post-Pour Works Completed (As Required)
c31284cb-6843-56c6-91a0-4ae2c73807b1 | textbox | Strands are Cut Flush and Epoxied
e1f31270-4107-5d7c-8e17-a66c81c2dfa2 | textbox | Lifters are cleaned
c8d2c7fe-3a69-5b6f-a7a1-b6cdc86d0098 | textbox | Roughened Surfaces are Greencut
e9624f5b-5879-5da3-bdc8-6bfa066d0810 | textbox | All Miscellaneous Items are Completed
9970c18c-d56c-50f9-b0b0-dbdf7e875e4c | textbox | Bottom surface clear from tie wire (Attach Pictures)
8ea82719-cdb1-4a7f-b3da-c5fe52fb4e79 | checkpoint | Survey Hog of Beams
797145d3-56c4-591e-bf2f-958e3facf6b9 | textbox | First Reading (Within 2 days of Stripping)
3ff5b67b-7db1-56e6-9bcb-9f9c28629b4c | textbox | Final Reading (7 days prior to scheduled delivery)
eacfab56-5f81-4a61-8b83-baee4ac80e50 | section | Any Defect Identified
fd4581e2-946e-4d7a-8860-d3b2752ce3ed | checkpoint | Punchlist Completed
6da2cb28-e2e6-4dd5-88d5-340291e2813a | checkpoint | Repairs Required (if applicable)
96966513-4ed2-49e3-9a7a-857961a81a64 | checkpoint | Repairs Completed as per approved WMS (if applicable)
76269332-a989-42a4-b495-40566dd02132 | checkpoint | Crack Map Completed (if applicable)
34ff3e31-1b4f-4439-91d9-7a6580e710e9 | checkpoint | Any NCR Required (if applicable)
3dd2ad46-cb07-47bb-abd0-c89817844a72 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
b1612369-fff1-4d3e-98f6-2d1b52f96125 | section | As-Built Drawings
8b7be622-6ba8-43e3-b7cb-aa4e9e4f4931 | checkpoint | As-Built Drawings Completed, Stamped and Attached
cdfde02c-1aa7-4690-a939-9e7c27984dfb | section | Concrete Strength Test Report
0b14128c-3964-4ce0-8072-3b2a00841af6 | checkpoint | Concrete Strength Test Report Received
44574a61-60de-5e54-8193-780252b1fcab | textbox | Concrete Test Report
12aff73d-f347-5379-beff-4738dedb947c | textbox | 7 Day Strength (List all)
7067ef96-9f2f-564f-9030-18e86f86f00c | textbox | 28 Day Strength (List all)
49459885-d78f-4281-bddd-e8e54c6c9bb3 | section | Transportation Requirements
6654e28c-2768-4908-ae3a-d825af386161 | checkpoint | Certificate of Conformance
c286ad13-860c-4eb9-b3ff-4f1ccba72dcf | checkpoint | Inspection Release Certificate
db21264f-a943-4637-bc1b-886baab426bb | checkpoint | Punchlist signed copy
43d4d451-26d2-4392-b809-5deece893a4c | checkpoint | Delivery Notes
b67899a3-4414-4bdc-b84a-d168ca703daf | checkpoint | Delivery Docket
9903f0d6-7975-4666-9436-988f221e00c6 | section | Final Acceptance
6660fee2-695f-49b5-b3fc-6ec75abc94a3 | checkpoint | Completed by
4c251765-0385-4abf-af93-dbf498b09e84 | checkpoint | Reviewed by
c9ee8f18-c66d-47ff-88f6-718c41b7be71 | checkpoint | Client Representative (if applicable)