## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Overall Progress
| Scope |  |  | Site QA
Rows
|  | Byford Type D&E Beams | dynamic | Byford Type D&E Beams | Site QA
Columns
|  | Cast Number | Cast Number | Pre-Pour Checklist completed
|  | Cast Date | Cast Date | Casting Information
|  | Plank number | Plank number | Pre-Pour Checklist completed
|  | Plank type | Plank type | Pre-Pour Checklist completed
|  | Concrete Delivery Dockets | Concrete Delivery Dockets (list all) | Concrete Delivery Dockets
|  | Slump | Slump (list all) | Slump within Allowable Tolerance (200+/-40) (Tested 1st truck and subsequently for every 20m3)
|  | Concrete Test Report | Concrete Test Report | Concrete Strength Test Report Received
|  | Stripping Strength | Stripping Strength | Concrete Cylinders Crushed and Checked for stripping strength
|  | 7 Day Strength | 7 Day Strength (List all) | Concrete Strength Test Report Received
|  | 28 Day Strength | 28 Day Strength (List all) | Concrete Strength Test Report Received