## Master List Templates
Id | Type | Name | Values | Prompting Name
b8b7ffb6-7e20-443d-adb4-789b31da8e2f | checklist | 3PM QA Form |  | 3PM QA Form
f8eec44c-0346-44db-8b63-c1f542f84f1f | section | Nuraply 3PM Check Sheets and Maintenance Programme
1627eb42-1e50-407c-804a-4bcb55a65464 | checkpoint | Substrate readiness form completed
522acdce-f7ec-4fa0-b2ab-cb1a23c1833d | checkpoint | Under flashings installed to all corners and upstands (pay attention to parapets, gutters, junctions)
03227616-4584-4d91-9602-78515d2d8a8e | checkpoint | Gutters correctly and neatly installed, particularly the internal corners
18e5b44e-56d0-4dd3-a42c-322ab38f5d8a | checkpoint | Roof drains & overflows installed to specification and watertight
8d52a530-6758-440b-9568-867bf141f1da | checkpoint | Membrane adequately adhered to substrate with no evidence of bubbles or lifting. Correct quantities of primer or adhesive used as per specification.
cb9d0040-5deb-467d-a8d7-894f1fa2f5ca | checkpoint | Cap sheet and basesheet fully bonded together, no areas of delamination.
c7a935f1-787b-4af0-836f-a411f9aa39b5 | checkpoint | Cap sheet side laps 80mm and end laps 100mm fully welded and tidily seamed off.
6d3157c9-0328-4fdf-93c3-bcf2c746ddb0 | checkpoint | No sign of overheating/excessive bitumen bleed from laps (over 2-3mm).
89829ed3-e95c-414e-bff1-64e1014700d9 | checkpoint | Cap sheet and base sheet laps offset satisfactorily. No three layer lap build-ups
f0e74b63-20c4-4819-8bd3-7f572e0dc6cb | checkpoint | Overall installation free of wrinkles, creases and splits
8b63dda2-e79f-4813-8bf7-2c3eb8893b69 | checkpoint | All penetration details completed to specification including under/over flashing
2e4715cd-8ae9-423b-ac72-a2504ed629c7 | checkpoint | Standard details used throughout including at upstands, parapets, construction joints
a38e7ff6-856d-41b5-9c75-3811b716838e | checkpoint | All non-standard details installed as per pre-approved specifications (attach approved drawing)
6e503555-039b-4453-9f54-c76020cce158 | checkpoint | Gutters and outlets have been flood tested
a48e7dd5-715f-42fd-a306-50be1f175745 | checkpoint | Any damage to cap sheet repaired to specification.
9c5efdb9-d021-451a-829c-6772c37cd2c5 | checkpoint-no-value | Note:
28893435-64e6-54e6-a9ea-a184692c63f4 | note | Where an element identified in the above checklist is not applicable, please record N/A.
1316f126-9749-4cbe-85e6-e0d51a5b2693 | checklist | Allsheet 500 |  | Allsheet 500
d7654004-c2d7-4a1a-9cd8-d8be515d1e68 | checkpoint | Substrate is exectable
7182083d-f00f-4604-bb7e-08082d3733b1 | checkpoint | All laps and joins are taped and have a 150mm lap as per specifaction
9b650e3a-10a8-42b9-9784-a21ac53cffd0 | checkpoint | Photos
b8426e55-f96e-4f3b-b7d8-5d12a8dfbdf3 | checklist | ARDEX Butynol |  | ARDEX Butynol
d90924af-9f78-4926-872d-fa076ce81885 | section | Details
a08e2981-0588-461d-9513-d17c1bbeec0d | checkpoint | Q1 - Work areas are clean and tidy and conforms with the relevant ARDEX Substrate Specification documents, completed seperately
c24647c7-85a9-4f45-85dc-9a0c405fd37b | checkpoint | Q2 - Substrate moisture content acceptable?
259a9ce3-8a59-4c3d-bf59-4b631e40ae52 | checkpoint | Q3 - Install underflashing tape in correct locations
386120a4-f547-4edf-8c4b-8aa067209046 | checkpoint | Q4 - Membrane laid over clean substrate using correct adhesive
8f7a0b5d-23b8-4c6d-9ac6-b8a1d03f745b | checkpoint | Q5 - sheets well set out, parallel lines, laps running correct direction and to correct fall
e5fc2d79-e2b3-46b2-a2cc-34fc4ac5456a | checkpoint | Q6 - Membrane lying flat on substrate with no bubbling
c65da23f-5032-470f-9dc8-c4d238e98913 | checkpoint | Q7 - Laps primed and taped, with clean edges, no excess seam tape, glue overspray
8e9e9751-1281-40d9-81eb-36781bea1778 | checkpoint | Q8 - Outlets detailed to correct ARDEX specification
92020475-d2bc-4072-9b22-e79ccd617327 | checkpoint | Q9 - Membrane termination completed to ARDEX details
b899f4f6-a9ab-4dbc-9afe-e728be2da610 | checkpoint | Q10 - Post-installation rubbish removed from work area
75c3df86-c26c-42fd-8ea9-c11df6db22b5 | checkpoint | Q11 - Conforms with ARDEX specifications
0f285263-6c21-4bda-9471-32fbef71347e | checkpoint | Q12 - ARDEX membrane installation completed to specification
8a3fe1c5-9f14-4272-ae18-355e35521f44 | checklist | ARDEX Quality Assurance checklist |  | ARDEX Quality Assurance checklist
834278a1-b742-43f3-bf23-b88333d22d26 | section | Details
0951c7e8-9983-404f-ad96-9532c516b73b | checkpoint | Sheets well set out, parallel lines, laps running correct direction and to correct fall
c6ccceec-eefb-4c86-920d-2e1f2a61f7a1 | checkpoint | Substrate are clean and tidy (Photos)
315cb3ac-b43f-44b0-86c8-b2b2c2432712 | checkpoint | Membrane lying flat on substrate with no bubbling
826cb621-bcee-44d2-934b-6590884af45f | checkpoint | Post installation rubbish removal from work area
54240147-fcad-4a71-80bb-ea0bfedf8431 | checkpoint | Membrane laid over clean substrate
f1023a28-db7b-4763-9cf8-e7429fe2a474 | checkpoint | Correct ARDEX material, colour and thickness
85c88144-067a-4389-bf42-e05c26002679 | checkpoint | Membrane termination completed to ARDEX details
7ff90a46-8c2c-49b5-bb96-dd976e564256 | checkpoint | Outlets detailed to correct ARDEX specification
ba653771-6548-4321-949f-dd656bcc13b8 | checkpoint | Laps welded, with clean edges, no excess seam tape, glue overspray or excessive bleed
e6512ca8-c743-4764-9c57-e087c333391e | checkpoint | Substrate conforms with ARDEX specification documents
3fc0d360-9854-4b17-9b39-f8d3011f6c0f | checkpoint | Any nonstandard details installed as per pre-approved specifications (to be noted within comments sections)
2aefc1a0-094b-4904-bfef-03fdc687a779 | checkpoint | Issues to note or raised during installation:
6b4400ab-0583-42d6-b125-f25d50b00cc1 | checklist | Coloursteel Roofing |  | Coloursteel Roofing
a3b0a2e3-2918-4ff8-a1c0-257bf3dee0cc | section | Prestart
305f7e79-84fb-4d83-887b-428c61a710d4 | checkpoint | Edge protection/scaffold in place
ec02f9d7-60ce-46ba-9dcd-2f4ccdb102ff | signoff | Raise remedial / request review
dd1b3012-efb2-4e6e-901b-65123af0bc70 | checkpoint | Safety nets installed
7837907a-1236-423e-9161-23bf9e2d9c17 | signoff | Raise remedial / request review
7d34d829-b9b1-499c-85c6-989178d2a912 | checkpoint | Purlins/battens & all necessary timberwork complete
ddfcffe9-bb3f-48d5-827c-3f39126d77cc | signoff | Raise remedial / request review
15e35633-d3dd-4679-b2fa-fcc3c59532f9 | section | Substrate Checklist : Enviroclad Plywood
e32d13eb-eeb8-405d-bee7-f2be37504e86 | checkpoint | Framing supports at 400mm centres (in one direction). All plywood edges must also be supported.
f0db1618-2c16-50aa-9238-e0b7dd3358a9 | note | Do not use tongue and groove plywood. Viking Roofspec can accept the maximum support spacings provided in Table 15C of CHH Ecoply Specification Guide.
a8bf9405-4d83-4687-96b1-7db854aa13d5 | checkpoint | Minimum thickness 17mm, F8, CCA H3.2 treated, structural plywood (not LOSP treated).
9ceedeab-b902-46bd-b1e5-c81103c1df20 | checkpoint | Minimum CD grade with the sanded C face upwards.
f361cc0c-a4af-4315-b76d-b0a1ee347393 | checkpoint | Plywood laid with face grain at right angles to supports.
68e0488f-32f7-44bb-a94a-d3a693ae57e7 | checkpoint | Plywood is to be laid with staggered joints in a brick bond pattern with a 3mm expansion gap between plywood sheet edges.
5b8fc8bd-9ff9-4a24-95d0-ac07398ab199 | checkpoint | Plywood is screw-fixed with 10g x 50mm SS counter-sunk screws at 150mm centres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm.
fe3bbb51-94f0-4817-9a29-ec468951a80d | checkpoint | Chamfer all external edges with a minimum radius of 5mm.
cb7d24cd-b85c-5cd7-81d5-ee00761799af | note | *Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood and framing supports to be at no more than 18%moisture content.
45687ced-a80a-46d9-8c8b-f7ca2189b514 | checkpoint | For Roofs and Roof Decks over living spaces, all cavities must be ventilated and insulated in compliance with clause H1 NZBC. Cavity ventilation is not required for a Warm Roof system which meets or exceeds the minimum R value requirements.
e5bc4a53-5321-4ebc-984d-2ef258e7cfef | checkpoint | All drains and outlets are membrane compatible.
0afca60d-3dc5-58d0-8cef-7a34ca9bb598 | note | Note that TPO membranes cannot be welded to Stainless Steel scuppers or sumps. Accessories must have Clamped Grates or be TPO weldable.
cc472b27-f57a-4346-9c75-5fca3c3bfde5 | checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
08159c01-f64d-48ff-9172-6143ba16ee5f | section | Roof QA
b4f148c3-1410-4dd8-811a-ee957965ecde | checkpoint | Fascia straight, cut in correctly
92292faf-d73e-4c15-827d-ab6f6c0720c5 | checkpoint | Spouting installed with correct falls & outlets as per plans
2b41dd4b-d39c-4b25-b00d-2718863d6aa5 | checkpoint | Underlay over fascia & trimmed neatly
1680745d-8d51-4125-a77b-02de12439de9 | checkpoint | Valleys straight
25fed7f2-afce-483a-9885-0ae84b2eec12 | checkpoint | Screws installed correctly & washers intact
9d960cfb-21c2-4c8d-a643-454546105b4e | checkpoint | Roof clean from debris & swarf
84b2f37d-6513-4984-a983-a6aaaa9158d8 | checkpoint | Flashing junctions tidy & sealed correctly
7108bcdc-1dcd-4b56-bb34-b882312b11fe | checkpoint | Roof laid correctly & damage free
6db0cd7d-87d2-4fa8-bfad-274f46475489 | checkpoint | Site clean, rubbish in bin or removed
0b8273e8-36fc-49ef-b49e-cd69436a35c4 | checklist | COLPHENE 3000 |  | COLPHENE 3000
a8e8f649-4351-4492-8b74-88208e174d09 | section | Details
c9cf18e2-3959-4526-9727-2493f227fb60 | checkpoint | Concrete and other surfaces satisfactory for installation of COLPHENE 3000 by Equus Certified Applicator.
e4c33682-545d-4fec-9f61-d8b0ba1de591 | checkpoint | All vertical areas such as foundation walls shall be primed with Equus Peel and Stick Primer at a rate of 6 to 8 m2/L and allowed to dry for minimum 1 hour.
22f7367e-38e1-4399-83e3-100f6110ca8a | checkpoint | Apply COLPHENE 3000 reinforcement strip to in all internal and external corners and connections between floor and wall areas.
07a8b07f-462f-4643-8efe-a51cb2286fc0 | checkpoint | Apply COLPHENE 3000 self-adhesive membrane to walls by removing the siliconized film and pressing against the primed surface.
6b368d83-aa16-4e4b-8f33-6aeed6008480 | checkpoint | Heat weld all sheet joints by hot air welder if required and ensure all are well sealed. Including end joints. Ensure a minimum of 75mm overlap at all connections.
d0cdf870-db64-43c7-8a83-f7482b05c790 | checkpoint | Install vertical Equus Thermal Insulation against COLPHENE 3000 membrane, held in place by dots of DOUBLESTICK
d8ce19d4-65a3-43db-815f-f710672a3f05 | checkpoint | Inspection of all areas before Equus drainage layer installation.
68a9d654-8f00-4f5b-b1b1-e64d8331fefa | checkpoint | Areas that have been perforated or damaged to be repaired by self-adhering a piece of COLPHENE 3000 including a minimum 150mm overlap.
9425169a-0546-42ab-9459-db909cc0fcf8 | checkpoint | Waterstops placed where required. Cold joins and stitch joins.
fde077e7-bc2c-4903-b764-f31019fbf976 | checkpoint | Install Equus drainage layer against COLPHENE 3000, and secure with Equus Termination Bar and SOPRASEAL sealant.
cfd34fc6-fc4b-4097-aed7-6185d33c2b46 | checkpoint | Final Inspection required prior to back filling.
421dbd69-680a-4ee2-bba4-f031e4ff3d5b | checklist | COLPHENE BSW |  | COLPHENE BSW
4454c7d4-f778-486b-b80e-d71eae81342a | section | Details
e6133e74-1372-4d81-bbc8-24c16a94baf6 | checkpoint | Concrete and other surfaces satisfactory for installation of COLPHENE BSW by Equus Certified Applicator.
00c1cdfe-fca0-4722-9560-c72001675831 | checkpoint | Loose-lay COLPHENE BSW H to lift pits Ensure sheet joints are closed using DUO SELVEDGE lap technology (over thermal insulation where required).
8db141b0-ced3-4fea-a7c1-ef89e18d1bfd | checkpoint | Ensure all pile caps, beams, piles, and pillar caps are reinforced with a strip of COLPHENE BSW H over SOPRADERE QUICK Primer.
f0aaed82-5fda-4361-b203-1e5f80bfad08 | checkpoint | Install thermal insulation where required in a brick bond pattern.
09bc8c3b-f16a-4215-b2ab-ce7079f54b45 | checkpoint | HORIZONTAL: Loose lay COLPHENE BSW H to fit inside the formwork, compacted hardfill covered with sand or site concrete with sanded surface facing upwards.
a64bc91b-af32-4bd2-9986-16e1cc9594eb | checkpoint | HORIZONTAL: Sheet joints are closed using DUO SELVEDGE lap with a minimum 100mm ensure all are well sealed. Minimum end laps shall be 150mm
4c2ef354-f747-4821-8908-7fd01693bf6c | checkpoint | Any details shall be carried out using ALSAN FLASHING, ALSAN FLASHING QUADRO or Matacryl Thix.
9f09d7f8-1a2f-46cb-a443-f452d0ea9a78 | checkpoint | VERTICAL PRE-APPLIED against lost formwork: Install drainage layer within mechanical fixings and apply COLPHENE BSW V to the drainage layer. (Where thermal-insulation is required, install against lost formwork before drainage layer. Held in place with DOUBLESTICK tape or EQUUS SOPREMA Fixings.)
7e204c17-93f7-4db4-b155-3ea4744ffb99 | checkpoint | VERTICAL PRE-APPLIED against lost formwork: Sheet joints are closed using DUO SELVEDGE lap with a minimum 100mm ensure all are well sealed by torch or hot air.
976dc6ee-9eaf-41f2-b47d-e76a071f69c5 | checkpoint | VERTICAL POST-APPLIED: Install COLPHENE BSW H (for torched on applications) or COLPHENE BSW V (for self-adhered applications) reinforcement strip in all internal and external corners, connections between the floor and wall and all cold joints.
4443ac26-413e-49c0-a332-d692000bd8e2 | checkpoint | VERTICAL POST-APPLIED: Install the COLPHENE BSW H (for torched on applications) or COLPHENE BSW V (for self-adhered applications) membrane against the wall.
5ecce690-e87e-490a-aa54-002c68fb5d29 | checkpoint | VERTICAL POST-APPLIED: Sheet joints are closed using DUO SELVEDGE lap with a minimum 100mm ensure all are well sealed with torch or (BSW V only) hot air.
0f15fd31-2ea3-412e-bb28-67457760f8d5 | checkpoint | Any details shall be carried out using ALSAN FLASHING, ALSAN FLASHING QUADRO or Matacryl Thix.
3d6ef2a2-7965-4c6c-83bb-2e108153eae6 | checkpoint | Install vertical Equus Thermal Insulation against COLPHENE membrane, held in place by dots of DOUBLESTICK tape.
420433dc-bfe7-4159-9f6d-7898c7606a75 | checkpoint | Install Equus drainage layer against vertical COLPHENE membrane, and secure with Equus Termination Bar and sealant.
c22cfeb2-93b7-4952-bf66-b0f5bd5be3f8 | checkpoint | VERTICAL POST APPLIED (Alternative options for areas with low risk of hydrostatic water pressure up to 3m deep): Install a COLPHENE 3000 self-adhesive reinforcement
fe2e1ecc-a638-433b-8c56-4fef7db57c5b | checkpoint | strip in all internal and external corners and connections between the floor and wall. Followed by application of COLPHENE 3000 selfadhered to the wall. Hot air is used to ensure laps are well sealed.
495e7513-ebcf-4969-9d6e-3e28c07126da | checkpoint | Installation of Steel work by others.
95d859f9-c350-4e3d-b86b-e509ebf61eef | checkpoint | Areas that have been perforated or damaged to be repaired by heat welding a piece of COLPHENE BSW H including a minimum 150mm overlap.
1248e4ad-f664-4c9e-9850-c7aff0b59908 | checkpoint | Concrete pour by others.
1c790f13-bd0f-4ad8-90a8-3b9de8ed2fbc | checkpoint | Precast panels or blockwork stood by others.
cd263ab3-d19e-4e70-a6fa-3ca73d9fa79a | checkpoint | Waterstops placed where required. Cold joins and stitch joins.
6d5ab773-68da-4c7b-a372-26b49239994f | checkpoint | Any loose areas on the upper edge of the membrane can be torched into place or sealed with the Equus Termination Bar and bead of ALSAN MASTIC 2200 sealant.
a89ea8ab-d63c-4227-b0c8-fb0ce5e545f8 | checklist | Drawings attached |  | Document:
700d5cd3-d75b-4707-b6f5-7eb22e64b1b2 | checkpoint | Document Attached
5ad4a00a-309d-44f0-a062-9f65e650139b | checklist | Equus Soprema DuOtherm Warm Roof (Concrete) |  | Equus Soprema DuOtherm Warm Roof (Concrete)
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
a7792a31-9451-4706-834f-5b86523ceb24 | checkpoint | Substrate ready and acceptable
ea3b52ab-cac4-5818-b6d8-de972fff6289 | note | Surface satisfactory for installation of DuoTherm Warm Roof System by Equus Applicator.
91ea34a3-b1ad-4f0f-aacd-f63588ca1fed | checkpoint | Apply one full coat of Soprema DuO Primer by brush/roller at spreading rate 5sqm/litre.
0af56729-5e3e-5acf-adb7-9e3a6e0ecc61 | note | Allow to dry 4 - 24 hours, depending on prevailing conditions.
62fc7951-d88b-4d21-bb82-6cdd4f0db716 | checkpoint | Vapour barrier installed and carried up parapets a minimum 50mm past Equus PIR Insulation board.
8ecb1f1e-3e5b-5eea-af99-1e544f201f95 | note | Install tapered PIR Insulation system as per project specific tapered scheme with one mechanical fixing through the centre of each sheet or spot stick with Easyfoam
001b68f7-3730-5811-aa61-5b60dded8f32 | note | Install Permabase Dek roof cover board. Follow job specific Equus Soprema fixing pattern.
5ca2c2a4-7c6e-4d91-9308-34c51f7643c2 | checkpoint | Apply one full coat of Soprema Sopradere Quick Primer by brush/roller at spreading rate 5 sqm/litre.
6512f1fb-be4d-5ad9-abaa-47ff44f01b56 | note | Allow to dry 4 - 24 hours, depending on prevailing conditions.
3f71aff8-d23a-5fc9-b9ed-afaf2be381a5 | note | Prime upstands and details only where membrane shall be fully bonded.
7dabfc96-d2bc-42a8-99fa-e8fa0b348ec7 | checkpoint | Unroll DuO basesheet, align and cut to length. Allow to relax and re-roll to the centre.
f821ef1c-29a9-559f-ac0b-7afc7a8ab4e5 | note | Unroll the roll and torch evenly as per manufacturer recommendations.
7957ff28-be49-553f-a7f0-68b447e6e383 | note | All laps torched closed
682fbae0-341e-574a-abd1-8e0ad6e63667 | note | Maintain side laps of 80mm and 100mm for head laps
16b4f1e1-4909-4820-9015-7b425fd91de8 | checkpoint | Unroll DuO cap sheet, align and cut to length. Re-roll each end back to centre after relaxing.
2ab86c20-0af7-5769-9215-6ff443a0a912 | note | Unroll, torch evenly across the roll and off-set laps to not coincide with basesheet.
be8138ad-5590-522f-9f38-310d6e9002db | note | All joints may be back sealed separately to ensure they are correctly closed.
01c7b5f1-538b-544f-b8b2-c643ebf39166 | note | Maintain side laps of 80mm and 100mm for head laps
aeaa374f-33f8-476a-9268-0f3c32268b8e | checkpoint | Detailing shall occur using DuO cap sheet and/or Matacryl Thix/Dexx Topcoat on all outlets, pipe penetrations, gutter stops ends and anything above or below roof surface.
abd84148-576b-47e3-8861-6a6236fa4f09 | checkpoint | System to be inspected on completion.
d5fa6da5-ba8b-46b1-a51a-6c79c832b2b2 | checklist | Equus Soprema DuOtherm Warm Roof (Metal Deck) |  | Equus Soprema DuOtherm Warm Roof (Metal Deck)
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c6f58d35-9150-4db9-bfcc-a7d9a9782ea7 | checkpoint | Substrate ready and acceptable
d3024e4e-1ef7-55b6-bea8-e8f214a06b6f | note | Metal deck installed in accordance with Manufacturer’s recommendation
2a49ff95-8b53-516c-8563-60cc93e61eb4 | note | Metal roof edges overhanging into gutters are cut back and timber upstand installed.
bacd5832-5326-4c6d-bf66-850449f30a58 | checkpoint | Vapour barrier installed and carried up parapets a minimum 50mm past Equus Insulation board.
56be2616-ce5a-5db7-b84c-a67c7640301e | note | Install 2x 60mm Soprarock HD60 insulation system in a brick pattern and tight butt jointed with one mechanical fixing through the centre of each sheet.
10b73f4a-5f34-53ed-80a2-9ab36354398f | note | Spot stick with Easyfoam.
abe260cb-215e-538d-aeb2-17183e5f810e | note | Install Permabase Dek roof cover board. Follow job specific Equus Soprema fixing pattern.
fd78ebc0-bba7-4162-b431-eedb23d93d61 | checkpoint | Apply one full coat of Soprema Sopradere Quick Primer by brush/roller at spreading rate 5 sqm/litre.
d4c09201-2cbb-52c8-a6d7-7ea95b5b8734 | note | Allow to dry 4 - 24 hours, depending on prevailing conditions.
ff903a44-703e-527f-a1b2-b8f64ba62158 | note | Prime upstands and details only where membrane shall be fully bonded.
d6badb0c-480b-4145-a6cc-1c9175297c4b | checkpoint | Unroll DuO basesheet, align and cut to length. Allow to relax and re-roll to the centre.
ffcef71e-ad2d-5541-b0ad-d8301c03baac | note | Unroll the roll and torch evenly as per manufacturer recommendations.
be34f420-3524-5ab1-a229-d1bb6180bf5f | note | All laps torched closed
6a1d398a-a9a1-54bf-a091-8140a2d4ea8a | note | Maintain side laps of 80mm and 100mm for head laps
c0fd51c3-7591-4a21-85a7-b78d49821988 | checkpoint | Unroll DuO cap sheet, align and cut to length. Re-roll each end back to centre after relaxing.
e4079b30-8031-5693-b48e-78f2338d3c7b | note | Unroll, torch evenly across the roll and off-set laps to not coincide with basesheet.
e41daaa7-e247-5c99-b9e0-fe2092ccdbff | note | All joints may be back sealed separately to ensure they are correctly closed.
dbd5cb56-a6d9-569e-a01a-72e5e9b12c2a | note | Maintain side laps of 80mm and 100mm for head laps
24c8dd23-2d28-4ed3-8662-5fff1f1d68e9 | checkpoint | Detailing shall occur using DuO cap sheet and/or Matacryl Thix/Dexx Topcoat on all outlets, pipe penetrations, gutter stops ends and anything above or below roof surface.
87a15814-d21b-47f3-b401-a53837343d84 | checkpoint | System to be inspected on completion.
107df86a-f3a0-4aa7-b65a-efd1ddfa6c4f | checklist | Equus Soprema DuOtherm Warm Roof (Plywood) |  | Equus Soprema DuOtherm Warm Roof (Plywood)
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
6ac315bc-8048-4d6e-8578-2b3045085b9e | checkpoint | Substrate ready and acceptable
e331268c-5f1f-49ad-8420-549627b48a35 | checkpoint | Apply one full coat of Soprema DuO Primer by brush/roller at spreading rate 5sqm/litre.
8918e0e1-7c38-5012-a317-fa5066a496f8 | note | Allow to dry 4 - 24 hours, depending on prevailing conditions.
cb5d3ea1-83e7-49cd-a860-62fac44495ab | checkpoint | Vapour barrier installed and carried up parapets a minimum 50mm past Equus Insulation board.
6dbe9871-f731-5554-a660-9228655f74eb | note | Install 2x 60mm Soprarock HD60 insulation system in a brick pattern and tight butt jointed with one mechanical fixing through the centre of each sheet.
6ed3f86c-074e-5ef9-afc5-4f3e3cf5667e | note | Spot stick with Easyfoam.
eb1cf32c-50da-5de0-9f03-280293f511c5 | note | Install Permabase Dek roof cover board. Follow job specific Equus Soprema fixing pattern.
6258200f-14fd-4d2c-b1d2-e53c056dc2a8 | checkpoint | Apply one full coat of Soprema Sopradere Quick Primer by brush/roller at spreading rate 5 sqm/litre.
3b7a339e-2454-5227-8fb0-2ea74a563c75 | note | Allow to dry 4 - 24 hours, depending on prevailing conditions.
bd4e9973-d055-5114-8624-55f3266e8f03 | note | Prime upstands and details only where membrane shall be fully bonded.
f5d26cf0-0641-43d5-8111-9c9a32bbd793 | checkpoint | Unroll DuO basesheet, align and cut to length. Allow to relax and re-roll to the centre.
0d7eff4a-9407-5de2-b960-8692e8dc57af | note | Unroll the roll and torch evenly as per manufacturer recommendations.
f545e884-dd6c-5e43-99e5-09b63f17dcbe | note | All laps torched closed
43759abb-0eba-5425-ae76-37e1d15bc974 | note | Maintain side laps of 80mm and 100mm for head laps
306a6bf7-4046-42ed-9596-e66320c93d36 | checkpoint | Unroll DuO cap sheet, align and cut to length. Re-roll each end back to centre after relaxing.
46bef6e2-ce1d-5c92-ab3d-cc885c75b0ed | note | Unroll, torch evenly across the roll and off-set laps to not coincide with basesheet.
2e379eeb-4d4f-5e1f-8e6b-d9b6e226d601 | note | All joints may be back sealed separately to ensure they are correctly closed.
7b6c17b8-ac8a-5e02-8490-2e57f9cff374 | note | Maintain side laps of 80mm and 100mm for head laps
f9853e41-eecb-4515-963d-b11cecfa52e2 | checkpoint | Detailing shall occur using DuO cap sheet and/or Matacryl Thix/Dexx Topcoat on all outlets, pipe penetrations, gutter stops ends and anything above or below roof surface.
ee6325f6-44f6-4859-a0ed-20abb13a1489 | checkpoint | System to be inspected on completion.
f71c7c7f-1f96-4564-800d-1501555aa312 | checklist | Markup Drawings |  | Markup Drawings
cfb32156-837d-4489-b870-ac011b7dd7fd | checkpoint-no-value | Upload drawings
d0dfa8f4-cd85-4f22-aeeb-b7397e8c09c8 | checklist | Preprufe 300R Plus & Bituthene 3000 |  | Preprufe 300R Plus & Bituthene 3000
f57fb196-16c8-4b55-83ed-e64454783235 | checkpoint | Substrate clean, dry and free from foreign matter.
d38d1f8b-29d4-4453-8ad9-f59dd9d285ed | checkpoint | Water stops installed to construction joints as per specification and located 50mm from rebar.
d41e4de3-d53e-428d-b14e-94a590832df6 | checkpoint | Underflashings installed to all corners and upstands.
74640352-7695-493b-b1c1-28009a2ef817 | checkpoint | Side laps 100mm and end laps 150mm, fully bonded and over-rolled to give a good seal.
7366ac81-d2e7-427e-92c9-d5d1082041e2 | checkpoint | All penetration details completed to specification including under/overflashing.
48093045-8a93-4dff-8fca-916101092d4d | checkpoint | Floor-to-wall junctions detailed to specification with good seal, and watertight.
608bdeb7-44e2-4aae-adf3-82cf3ce2e89e | checkpoint | Termination detail completed to specification.
75f541c1-82d6-4284-9d23-a4b02880b4a8 | checkpoint | Any mechanical damage to membrane repaired to specification.
61cfb5a8-1a90-40fb-809f-f4eb39114b14 | checkpoint | Suitable drainage system installed below footing, placed 150mm from membrane.
6383c246-4cca-4a8e-b0e6-b393587e4fe1 | checkpoint | Protection boards installed correctly.
cdafea3f-7469-4856-b19d-514961bcd09b | checkpoint | All non-standard details installed as per pre-approved specification with approved drawings attached.
4a06e245-f975-44e1-8a63-9c12b2bde328 | checkpoint | Overall installation free of wrinkles, creases and splits. Any defects repaired prior to covering.
d49a8cbe-53f2-4996-aacf-1481f01214d3 | checklist | QA - Aquafin |  | QA - Aquafin
be65f18a-697a-40b2-91b8-d6e4ff595075 | section | Details
2d596054-6437-4307-94fb-fe45cdbd20ce | checkpoint | Ensure all concrete surfaces are cleaned sufficiently for application of Equus Chevacryl Admix primer.
268a8ebb-3e4f-49eb-9432-722b3a8f195a | signoff | Signed off by Building Contractor
5b04b9ca-741e-45b6-a484-d4763eb4ee47 | checkpoint | Apply Equus Chevacryl Admix 50/50 primer to concrete substrate.
9cc2cbaa-607c-4676-a6ce-931af22f25ab | checkpoint | Apply Equus Epistixx AC primer to all ferrous substrate. Allow to cure.
88847a4c-8e69-4697-a4c1-c6ee99b52a38 | checkpoint | Apply first coat of Aquafin 2-K/M Plus by brush or trowel at approx. 2kgs per m2
8be9ecc1-a653-470f-bc48-d643731c0941 | checkpoint | Apply an Equus Schomburg Aquafin 2-K/M Plus reinforcement bandage to nominated areas-penetrations, concrete to termination bar
bca2849c-f49d-4152-bf91-2f83d04afd4c | checkpoint | Apply second coat of Aquafin 2-K/M Plus by brush at approx. 2kgs per m2.
48ec03a5-d7c7-4706-acef-83cfee4d2833 | checkpoint | Check for pinholes and touch up as necessary by means of brush.
7d12c50a-73b2-4a2a-82b9-8f9e6e7cb856 | checkpoint | System to be inspected on completion.
79cc2044-484a-4fde-852b-f8cff6d9824f | checklist | QA - Colphene BSW |  | QA - Colphene BSW
d87d800e-3f79-4597-844a-c0634e34d9f8 | section | Details
1e2c5ec5-7bc2-49b5-b767-8d5a07537e1b | checkpoint | Concrete and other site surfaces satisfactory for installation of COLPHENE BSW by Equus Certified Applicator.
e54e1f59-6da9-4b60-9350-8aceab340f4c | checkpoint | Loose-lay COLPHENE BSW H to lift pits. Ensure sheet joints are closed using DUO SELVEDGE lap technology
d47db35d-0f36-423b-975a-2af3af9df851 | checkpoint | Ensure all pile caps, beams, piles, and pillar caps are reinforced with a strip of COLPHENE BSW H over SOPRADERE QUICK Primer.
8d3aa927-82d8-45ed-a747-c34e3bd410f4 | checkpoint | Any details shall be carried out using ALSAN FLASHING with reinforcement fleece a minimum 150mm all direction
e9315e08-0667-4962-8605-c740ce0f7583 | checkpoint | HORIZONTAL: Loose lay COLPHENE BSW H
ee5d9903-e731-4697-80aa-9b31cc9e52c4 | checkpoint | To fit inside the formwork, compacted hardfill covered with sand or site concrete with sanded surface facing upwards.
15192a46-430c-4cce-9f68-1ae86aa251be | checkpoint | HORIZONTAL: Sheet joints are closed using DUO SELVEDGE lap with a minimum 100mm ensure all are well sealed. Minimum end laps shall be 150mm
9c34f8f7-3374-43e2-a5e6-651366617433 | checkpoint | Any details shall be carried out using ALSAN FLASHING with reinforcement fleece a minimum 150mm all direction
019e4d83-e0b2-4355-b558-0a8384cc7b80 | checkpoint | VERTICAL PRE-APPLIED against lost formwork: Install drainage layer within mechanical fixings and apply COLPHENE BSW V to the drainage layer. (Where thermal insulation is required, install against lost formwork before drainage layer. Held in place with DOUBLE-STICK tape or EQUUS SOPREMA Fixings.)
efa76902-1cf3-415e-b5ec-5b98142c0412 | checkpoint | VERTICAL PRE-APPLIED against lost formwork: Sheet joints are closed using DUO SEL- VEDGE lap with a minimum 100mm ensure all are well sealed by torch or hot air.
5e0387d8-b058-4270-88b5-eefa79040117 | checkpoint | Any details shall be carried out using ALSAN FLASHING with reinforcement fleece a minimum 150mm all direction
7c720175-f57f-45cd-98cd-cf790e8426e8 | checkpoint | Install vertical Equus Thermal Insulation against COLPHENE membrane, held in place by dots of DOUBLESTICK tape.
d2dd4c52-e8af-4b63-a51f-cdefcf86080f | checkpoint | Install Equus drainage layer against vertical COLPHENE membrane, and secure with Equus Termination Bar and sealant.
805dc0c2-befd-452a-8abc-1572fbf70d2d | checkpoint | VERTICAL POST-APPLIED REFER TO "4131EB 4.4 COLPHENE 3000 METHOD AND STATEMENT"
96cc527c-a83b-4847-8577-2d22f1e182dd | checkpoint | Installation of Steel work by others.
faf987f6-0b16-4489-a975-b8a3a7d4192a | checkpoint | Areas that have been perforated or damaged to be repaired by heat welding a piece of COLPHENE BSW H including a minimum 150mm overlap.
1061c11b-18a2-4272-8af5-6f025fb2fbd3 | checkpoint | Concrete pour by others.
f785de35-c9b6-4302-91d1-f5e66efc5ccc | checkpoint | Precast panels or blockwork stood by others.
93cdd1e9-8add-496d-a2ce-09ae7fc0adbf | checkpoint | Waterstops placed where required. Cold joins and stitch joins.
f5f40116-4cfa-4f36-b4a7-e3b7d7b5436f | checkpoint | Any loose areas on the upper edge of the membrane can be torched into place or sealed with the Equus Termination Bar and bead of ALSAN MASTIC 2200 sealant.
6ca87ded-321a-4133-aeee-c80e6c185c78 | checkpoint | System to be inspected on completion.
7f24cf36-eb4d-457b-a3f4-c9434e5f23f1 | signoff | Signed off by Building Contractor
3730dcb0-cb43-4493-b72f-afcb84f557f7 | checklist | QA - Cophene 3000 |  | QA - Cophene 3000
f4fd486d-11c9-4175-a17c-010957e0299d | section | Details
b8e10dbf-4d30-498e-910f-a71c68d6d240 | checkpoint | Concrete and other surfaces satisfactory for installation of COLPHENE 3000 by Equus Certified Applicator.(Note:Any sharpe corner please shamper edge).
7927ca53-bed6-4e24-83e1-99fa72f06a16 | checkpoint | All vertical areas such as foundation walls shall be primed with Equus Peel and Stick Primer at a rate of 6 to 8 m2/L and allowed to dry for minimum 1 hour.
8b0dc617-4294-4568-aaed-78c03fa869ea | checkpoint | Apply COLPHENE 3000 reinforcement strip to in all internal and external corners and connections between floor and wall areas.
314348ab-8e46-497b-86b3-777da8722304 | checkpoint | Apply COLPHENE 3000 self-adhesive membrane to walls by removing the siliconized film and pressing against the primed surface.
df16030a-2db4-438e-9d63-c074f46b5863 | checkpoint | Heat weld all sheet joints by hot air welder if required and ensure all are well sealed.
f37d2dad-52c1-4ca7-88f8-049a4fbc47ad | checkpoint | Including end joints. Ensure a minimum of 75mm overlap at all connections.
d221e961-9721-4727-b100-1575fdd108c9 | checkpoint | (where required) Install vertical Equus Thermal Insulation against COLPHENE 3000 membrane, held in place by dots of DOUBLE-STICK tape.
ca88fec7-7bca-49ee-925e-5a916865bd99 | checkpoint | (where requierd) Asian Flashing with reinforcement fleece a minimum 150mm all direction
1860e8b2-50a4-480f-abb1-0834b1814799 | checkpoint | Inspection of all areas before Equus drainage layer installation.
bc676a51-083c-401e-b893-eab8fd88942d | checkpoint | Areas that have been perforated or damaged to be repaired by self-adhering a piece of COLPHENE 3000 including a minimum 150mm overlap.
8e5e746b-1cc4-4895-aa27-14526b5791b2 | checkpoint | Waterstops placed where required. Cold joins and stitch joins.
c196d1fb-7aed-47da-82a8-d906225c1c65 | checkpoint | Install Equus drainage layer against COLPHENE 3000, and secure with Equus Termination Bar and nominated sealant or Aquafin 2KM. (For Aquafin application refer to "Aquafin 2-K/M Checklist and Method Statement ")
219d7e23-420a-4f8c-9625-94e0c6410f8f | checkpoint | Final Inspection required prior to back filling.
63d48266-8047-4718-b53e-74904fdcd91c | signoff | Signed off by Building Contractor
12c653a0-db07-40fb-b81d-42401ab2fc45 | checklist | QA - Mohan TPO |  | QA - Mohan TPO
537cbd6c-359b-4475-a194-fb0a9238bf21 | checkpoint-no-value | Details
8fe9586b-7ceb-5d99-ba57-0d1d60424327 | textbox | Work Area Covered by QC Sheet:
54dd5f0f-0218-4d53-8c6e-324643421322 | checkpoint | Substrate clean, dry and free from foreign matter and sharp edges. If in doubt, check substrate moisture.
eed0f64a-6a82-4cc9-ab8c-d9824392fde8 | checkpoint | Movement joints identified and installed to approved specification/detail.
52fe517d-40e7-49db-858f-706df2862163 | checkpoint | Underflashings installed to all corners and upstands.
99ce7da8-f49b-4103-b4d0-c9a648b0f825 | checkpoint | All TPO seam-welded with complete lap integrity.
f8bf26dc-8142-4a36-81f6-ce099f508061 | checkpoint | Gutters correctly and neatly installed, particularly the internal corners - laps above roof line.
e23a81fa-e4af-4296-a8cd-67091fb41ed2 | checkpoint | Roof drains installed to specification and watertight.
df0bfa13-0910-4b1f-b853-2449fc1973e8 | checkpoint | Overflows installed to specification and local body requirements and watertight.
29eceb1b-52cf-4b7d-b040-df216eae23a9 | checkpoint | Membrane termination completed to approved detail.
138ef2a7-a806-4102-8973-393ca1629c6c | checkpoint | All penetration details completed to specification including under/overflashing.
91338e8e-ffb1-4472-a980-139da42c1c80 | checkpoint | Overall installation free of wrinkles, creases and splits.
de99f566-b11b-494d-915d-e633b3daeb55 | checkpoint | Where practical flood test horizontal applications with a minimum 50mm depth of water for 24 hours. Make good any lack of water tightness when the surface is completely dry.
a0cddf3b-c2a1-4714-9f0c-e44b22ebac64 | checkpoint-no-value | Additional Notes
c01126b7-9f03-5bc7-9c4a-a36cb6a4338c | textbox | Issues to note or raised during installation:
fa49e097-154e-529d-9f36-a2982bf1c454 | textbox | Remedial action required:
84a4009f-7030-5006-9ee5-65b8d3bfdcac | textbox | Note of damaged areas repaired:
d26dca60-145a-5c76-9583-70181b3e964c | button | Photographs taken | YES,NO
aea5d178-0eeb-5264-a9e2-4b101225ad3a | date | Date of completion
f8a187be-d725-4b73-8d55-ea955eeebb27 | signoff | Work Area Sign Off
60f0fc44-2a87-4a26-a56e-3ed27cd34fc8 | checklist | Roofing QA - Torch-On Concrete Checklist |  | Torch-On Concrete Checklist
a0a7d0ea-78b0-428b-a8cb-aa63ebfbabd5 | section | Substrate Check
c0b4a20d-39e3-47ed-930e-cc813464f5d3 | checkpoint | Concrete substrate has been allowed to fully cure - at least 28 days from pour
b38d2d6f-7d08-5827-890d-e0e4a8dd4b6a | textbox | Concrete Pour date:
67131977-9b5e-43e0-b684-0d6a505c64b9 | checkpoint | Fill hallows or holes with a cement plaster, or FLC
904eb277-bbe0-4141-b8fe-e3b1e70b072d | checkpoint | Surface smooth, clean, dry and free of debris or release agents
f320e300-ba2d-4d83-a8cf-ac39508dd31b | checkpoint | Substrate venting installed as required
374a47be-0d52-4393-ac37-ef0b53989821 | checkpoint | Minimum 20mm triangular fillets at the base of upstands
ff8cd3ad-d340-4d5a-a237-795312c51ad2 | checkpoint | All drains and outlets are membrane compatible. Refer to your Allco Representative prior to installation if unsure.
58d1c91a-5236-42c5-bf10-3ee5d562912e | checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
66230e6c-0aa1-4489-892b-251b16fe4703 | section | Torch-On Horizontal & Vertical Application
4592d02b-5872-431e-a72e-8ec83fa292a1 | checkpoint | Check sheets are correctly aligned, unrolled completely and positioning them
1c3cf6f1-4e26-4b69-a05c-9920dae5baea | checkpoint | Ensure side laps are at least 100mm and at head laps should be 150mm
93997d1c-9d30-41b5-8552-bd28ba39aded | checkpoint | Ensure dermaprimer is used appropriately on the substrate
8f7663d6-503e-426f-b4cd-ccf2527fe230 | checkpoint | The second layer fully bonded on to the first layer, staggering the side overlaps by 500mm and the head overlaps by half a roll
5d56d67c-8b03-40bc-8702-ef85057ac204 | checkpoint | Ensure 150mm upstand height of membrane
68643d72-fe63-43a1-883d-f28b6fbf0de7 | checkpoint | Attach application photos (1 photo per 20m2)
c7f9690e-99b7-40ac-8c03-321d9a822148 | section | Torch-On Detailing (Drains, Gutters, Joints, Overflows, Penetrations)
58f3f19f-43aa-4e21-9b2d-dd4f4c7edd21 | checkpoint | Roof Drains & Outlets - appropriate detailing techniques used
ba888980-1c57-5f63-bb96-6a49662810b4 | tickbox | Attach Photos (1 photo per drain/outlet )
064587d9-aaf3-4288-8d1d-13ea6afa9920 | checkpoint | Penetrations - appropriate detailing techniques used
f31a1b29-7078-5cb4-802f-414cb26d94de | button | Ensure 100mm extension from edge of penetration in all sides | Yes, No, N/A
09992164-ec39-55a3-9a66-517abeed5338 | button | Ensure 100mm upstand extension over pipe | Yes, No, N/A
aefd8f5d-72ec-5fdb-98d3-c05353a6be32 | tickbox | Attach Photo (1 photo per penetration)
d45853cb-0434-4945-ad25-00f520b6c225 | checkpoint | Transitions - appropriate detailing techniques used
fd60130f-83c5-515d-93b2-9af3d5a1b265 | button | All transitions sharply formed and having no irregular surfaces or edges | Yes, No, N/A
802cbdb8-f708-5c6a-ae6b-13f57415558d | tickbox | Application photos of transitions
eecdf4e0-06fe-4ae0-a16d-58025b70a1e1 | checkpoint | Joints - appropriate detailing techniques used
44af4e31-9771-563e-960d-0b2e9177136f | button | For expansion joints, ensure there is 150mm extension cover over the joint | Yes, No, N/A
cbcae9f4-ce8a-5819-a33c-83d0c10f49fe | tickbox | Application photos (1 photo per joint)
013cdd1f-8b90-4024-a62c-3ba5a0492382 | section | Torch-On Terminations
b89c13c5-1d27-4cdc-b59e-c7e2a373215b | checkpoint | Ensure appropriate 100mm laps at transitions
368a2b90-d3e6-4d2c-8e56-9dcb3ec3757f | checkpoint | Ensure appropriate detailing is used on terminations
994e0e8f-180b-40dd-8b67-765d6f4ebfb1 | checkpoint | Application photos (1 photo per termination)
e301fef6-5031-475d-9f74-30dc5305d121 | checklist | Roofing QA - Torch-On Plywood Checklist |  | Torch-On Plywood Checklist
8d1e98d6-43b0-4194-8fd1-c6053271d91b | section | Substrate Check
91e50886-febd-4b9c-8147-80a00011bbea | checkpoint | Framing supports at 400mm centres for 17.5m ply (in one direction). All plywood edges must also be supported.
9822e387-181f-444a-9db9-1d6686266d9f | checkpoint | Framing supports at 600mm centres for 19.5m ply (in one direction). All edges must also be supported.
a3c7caba-c699-43ab-8fe5-02b9e1d38c7b | checkpoint | Minimum 17mm, F8, CCA H3.2 treated, structural plywood (not LOSP treated).
a9f25e63-c316-4a0f-b03d-dd9fc3a3c5f0 | checkpoint | Plywood screw-fixed with 10g x 50mm SS counter sunk screws at 150mm centres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm.
32d6e7e6-99f9-4c8b-92c5-524be6e4b43f | checkpoint | Plywood laid with face grain at right angles to supports.
e89384f0-0918-4241-8f10-737bbbc64afa | checkpoint | Plywood is to be laid with staggered joints in a brick-bond pattern with a continuous bead of suitable construction adhesive on top of timber supports. Sheet edges to be carefully glued with a continuous bead of suitable construction adhesive (no spot gluing) and tight butt-jointed. Once sheets have been placed together remove any excess adhesive by scraping the joint with a chisel. Ensure joints and sheets are not walked on within 2 hours of application. When fully cured remove excess and sand off joints.
bfecf290-3f01-4038-b299-7f75f3e476bd | checkpoint | Provide min. 20mm timber fillets at the base of all upstands.
5d8b7e6a-0d24-47e2-8c92-48ebad7c233a | checkpoint | Chamfer all external edges with a minimum radius of 5mm.
dd0ceb95-a30f-4208-9be9-e368d4865d7e | checkpoint | Plywood is to be laid with staggered joints in a brick-bond pattern with a continuous bead of suitable construction adhesive on top of timber supports. Sheet edges to be carefully glued with a continuous bead of suitable construction adhesive (no spot gluing) and tight butt-jointed. Once sheets have been placed together remove any excess adhesive by scraping the joint with a chisel.
987da9ca-b404-45ca-80c5-9ed5e11b57a1 | checkpoint | Ensure joints and sheets are not walked on within 2 hours of application. When fully cured remove excess and sand off joints
e225d91c-9c1f-4269-b024-07dbaa6a826b | checkpoint | Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood and framing supports to be at no more than 18% moisture content.
e486ab2e-8e0f-46e6-8143-a1d560c028ba | checkpoint | Leave a 5mm minimum expansion gap around the perimeter of the plane. The fixing specification allows for a maximum 50m2 without expansion joints (dependant on design). 5mm expansion joints should be used on areas over 50m2 . For further information regarding placement of expansion joints for your design, please contact your Allco Representative .
63f7aaca-dbd9-469a-a6e5-0d4e390df6a5 | checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
2dbd927f-d007-46b5-88a8-576f2c62f167 | checkpoint | All drains and outlets are membrane compatible. Refer to your Allco Representative prior to installation if unsure.
fdcd5235-2805-43cb-8fde-813c38f7a7c0 | section | Torch-On Horizontal & Vertical Application
bac72a24-7916-49f7-af68-1346db9b9c9a | checkpoint | Check sheets are correctly aligned, unrolled completely and positioning them
7a8a52a4-5afc-4296-8305-8160bd547b13 | checkpoint | Ensure side laps are at least 100mm and at head laps should be 150mm
1f5d29a9-635a-4f93-82c3-1a8e2ea710d6 | checkpoint | Ensure dermaprimer is used appropriately on the substrate
0c374dc0-b0ea-4fb0-b589-890c234ff6a7 | checkpoint | The second layer fully bonded on to the first layer, staggering the side overlaps by 500mm and the head overlaps by half a roll
937f42c4-689d-472d-8677-75ec00e8ab50 | checkpoint | Ensure 150mm upstand height of membrane
4173f0e1-c10e-4e4f-9af8-a81f79f27cad | checkpoint | Attach application photos (1 photo per 20m2)
68d545ee-1d61-4a72-abb6-b50bc73a8bc7 | section | Torch-On Detailing (Drains, Gutters, Joints, Overflows, Penetrations)
b3023129-d61c-4b2f-af55-a3331efa1bc4 | checkpoint | Roof Drains & Outlets - appropriate detailing techniques used
51b40b76-fa95-5722-a335-3774f53270e0 | tickbox | Attach Photos (1 photo per drain/outlet )
20b1c39e-fa95-42af-8c24-d923177a57dd | checkpoint | Penetrations - appropriate detailing techniques used
4627ef16-5959-5a0c-b96d-bc21a873a689 | button | Ensure 100mm extension from edge of penetration in all sides | Yes, No, N/A
ad1bf6be-1edf-510a-bc7f-03e5a26bc52d | button | Ensure 100mm upstand extension over pipe | Yes, No, N/A
fd5606fb-1140-5b4e-8ffe-460d48e94a41 | tickbox | Attach Photo (1 photo per penetration)
ce1d0f38-3989-4591-8e61-b74c63f681e5 | checkpoint | Transitions - appropriate detailing techniques used
38843f71-4737-51b7-8200-1c122fb5e4d7 | button | All transitions sharply formed and having no irregular surfaces or edges | Yes, No, N/A
8be7613c-5353-54bb-85a0-83cd00e30cc7 | tickbox | Application photos of transitions
b66a53b2-45f4-4cbb-bd1c-96a3046e2dda | checkpoint | Joints - appropriate detailing techniques used
5ae4b605-ef23-585a-b46b-662a84b1913e | button | For expansion joints, ensure there is 150mm extension cover over the joint | Yes, No, N/A
e96c7424-4e02-5129-9539-94704d93f080 | tickbox | Application photos (1 photo per joint)
cdde9b48-f3c7-48d2-a98c-8384a6edbf72 | section | Torch-On Terminations
e1ee3865-867e-4755-8dff-b51348378b5c | checkpoint | Areas of installation input
1a4141dc-ddf0-552b-924b-dcca1c0c56bf | textbox | Description, grid sections, etc
24c9d016-fa9c-40fe-be01-1477e1e906d2 | checkpoint | Ensure appropriate 100mm laps at transitions
ce273bbd-6546-471b-95de-7f5d1a1cd70b | checkpoint | Ensure appropriate detailing is used on terminations
c294866b-13bf-4134-ace4-7d248eeeb6dd | checkpoint | Application photos (1 photo per termination)
0ab8d4f7-050e-44a9-8f75-f90336aa9ec0 | checklist | Roofing QA - TPO Concrete Checklist |  | TPO Concrete Checklist
0a5276d2-9e6d-4420-a745-d0e864d272d0 | section | Substrate Check
17c46294-b9b4-49f4-8acc-cb726ef2f18b | checkpoint | Concrete substrate has been allowed to fully cure - at least 28 days from pour
83d107d2-1cb1-5f5d-b5c7-c0a523d0e573 | textbox | Concrete Pour date:
cb565a15-0c8a-4192-9fcf-771b7cea9275 | checkpoint | Fill hallows or holes with a cement plaster, or FLC
b3f7c929-f74c-45ca-92bf-acc36c3a2b5a | checkpoint | Surface smooth, clean, dry and free of debris or release agents
31a5b93e-95ce-4f1f-961f-091379f6e0cf | checkpoint | Substrate venting installed as required
1fe814da-64c9-4203-bc45-7eb6b13acb8f | checkpoint | All drains and outlets are membrane compatible. Refer to your Allco Representative prior to installation if unsure.
cb5009d0-2109-41dd-b4c5-8039b4e83e55 | checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
71bf0533-b51d-4631-bcc6-4899eb1769fd | section | TPO Horizontal & Vertical Application
5c66c30d-1321-4b41-9acf-3175b4f01b19 | checkpoint | Conducted test weld on an off cut of membrane prior to installation?
304dc290-75ce-45bf-98d1-d465f880dd39 | checkpoint | Ensure even coating of approved adhesive used on JM sheet as well as substrate
d236eebd-40f2-4163-a536-ff34d2d2093e | checkpoint | Ensure 40mm minimum sheet laps
90ccf5d5-95ca-414a-8ab1-69e81f1e011f | checkpoint | Ensure all weld areas thoroughly cleaned with JMCLEAN membrane cleaner
6a732944-e91e-4399-89ec-054e9d836b87 | checkpoint | Test all welds with a seam probe
fce8a021-1e20-467e-91ef-7306b77c8875 | checkpoint | Attach application photos (1 photo per 20m2)
65544047-2ee5-4f0e-81fc-60c056ecfb30 | section | TPO Detailing (Gutters, Corners, Overflows)
0d90d3f2-392f-4124-801a-5f8a24cb590d | checkpoint | Roof Drains & Outlets - appropriate detailing techniques used
f97f614b-44a8-5297-b7d6-9f491aa0a3d6 | button | Ensure the correct JM accessories are used? | Yes, No, N/A
7e96e8a2-4cf5-5fc9-9816-a3d0c120861d | tickbox | Attach Photos (1 photo per drain/outlet )
76d3517e-d1b3-4c0d-977d-b715ea5cb516 | checkpoint | Penetrations - appropriate detailing techniques used
dd9fa737-a8fb-5718-bb87-9b42290057eb | button | Ensure JM Single ply caulking is applied on appropriate areas? | Yes, No, N/A
b02779db-06d2-5e40-ad85-dd8d4da76204 | button | Ensure 200mm upstand extension over pipe penetrations, and 150 mm for vent and square post (deck) penetrations | Yes, No, N/A
4d886059-3b59-5f6e-ad6e-c5f4653922a3 | tickbox | Attach Photo (1 photo per penetration)
f1b4dcc5-9ec0-4d5d-8973-afd30349459e | checkpoint | Transitions - appropriate detailing techniques used
5108f476-ecaa-5def-a4f4-63b2835fd5f4 | button | All transitions sharply formed and having no irregular surfaces or edges | Yes, No, N/A
fe20bbda-6024-5112-bbaa-e3fbac784a5d | tickbox | Application photos of transitions
fae1a3f3-7133-445c-888c-598eb4dfeaf9 | checkpoint | External & Internal Corners - appropriate detailing techniques used
70315edb-9ac6-5816-8a19-055436d8b0a7 | button | Ensure appropriate JM corners accessories are used? | Yes, No, N/A
f7b60770-2c04-50e7-ac00-9ee34f62d8c6 | button | Ensure appropriate detailing techniques used? | Yes, No, N/A
aa7b6fc3-7518-5934-8e8b-aff06be50c1e | button | Ensure 40mm wield length on all sides and corner fully welded | Yes, No, N/A
6b685fbd-f3f0-5b82-93ce-20f6b952f2ae | tickbox | Application photos of corners ( 1 per corner)
faf9a86d-9d37-442b-b83e-110ad76faa5f | section | TPO Concrete Termination
85a2aea6-0010-45c4-a2cd-619fc662bcee | checkpoint | Ensure appropriate detailing used for termination?
f00f23db-4fde-414d-aa5d-751215c8ab4c | checkpoint | Ensure 40mm hot weld between TPO and steel folded flashing (if appropriate)
692ba202-d8bf-44eb-bfd3-7b2f7007c726 | checkpoint | Application photos of terminations (1 photo per termination)
4ee753fa-b026-46df-becf-857659828a07 | checklist | Roofing QA - TPO Plywood Checklist |  | TPO Plywood Checklist
7b101946-7c62-49a5-beb5-b9de69a13bf7 | section | Substrate Check
e838d4d4-1fec-4a51-a22d-9cff6497fd4f | checkpoint | Framing supports at 400mm centres for 17.5m ply (in one direction). All plywood edges must also be supported.
85bb9fc1-1a39-4e4a-8ab2-2c877862617e | checkpoint | Tongue and groove plywood NOT used
fa853cc8-8008-4157-96f6-39efbd6a99f9 | checkpoint | Framing supports at 600mm centres for 19.5m ply (in one direction). All plywood edges must also be supported.
64cf4cee-93ad-4264-b090-df85052b7d65 | checkpoint | Minimum thickness 17mm, F8, CCA H3.2 treated, structural plywood (not LOSP treated).
caa73ff7-7d02-4a69-a14b-237575e4f217 | checkpoint | Minimum CD grade with the sanded C face upwards
8bc1b614-fe39-43e8-8e8a-158107eda411 | checkpoint | Plywood to be laid at right angles (90 degrees) to supporting timber.
8b46def0-373c-4c8b-b2be-904bd9908145 | checkpoint | Plywood is to be laid with staggered joints in a brick bond pattern with a 3mm expansion gap between plywood sheet edges.
c11bda70-df09-4eb7-9b84-3e6982d77f0d | checkpoint | Plywood is screw-fixed with 10g x 50mm SS counter-sunk screws at 150mm centres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm.
3b9cd57c-f4ec-4a87-bbf9-f8c828d9634c | checkpoint | Chamfer all external edges with a minimum radius of 5mm.
b9d04148-d231-434e-842c-d69a8ea8b656 | checkpoint | Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood to be at no more than 18%moisture content.
1c5be848-0dd5-4358-a93c-9a32d672e322 | checkpoint | For Roofs and Roof Decks over living spaces, all cavities must be ventilated and insulated in compliance with clause H1 NZBC. - 1 vent for the first 40m2 and one for every 50m2 thereafter. Cavity ventilation is not required for a Warm Roof system which meets or exceeds the minimum R value requirements.
9f65ac5b-0cb2-4c7c-959c-d424be4167bc | checkpoint | All drains and outlets are membrane compatible. Note that TPO membranes cannot be welded to Stainless Steel scuppers or sumps. Accessories must have Clamped Grates or be TPO weldable.
d570db2e-3cee-4b0b-a93c-e83373399c0e | checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
804d8eef-aab2-43d5-9ca7-0e9ba306d28d | section | TPO Horizontal & Vertical Application
6d7ad279-79d2-4640-91f8-3e544265b583 | checkpoint | Conducted test weld on an off cut of membrane prior to installation?
69e0f0d4-aa95-4e72-be56-f925e3546f62 | checkpoint | Ensure even coating of approved adhesive used on JM sheet as well as substrate
397f7f2d-84ea-4ff8-9a81-96cd38442d51 | checkpoint | Ensure 40mm minimum sheet laps
e73cf3d8-acd0-4929-b1fa-a09cb4cff688 | checkpoint | Ensure all weld areas thoroughly cleaned with JMCLEAN membrane cleaner
d12ed89a-9e70-4f28-a808-c2533edca866 | checkpoint | Test all welds with a seam probe
933fc5a0-d147-43eb-a2cd-e9fbf0186bd0 | checkpoint | Attach application photos (1 photo per 20m2)
296cbed0-b5ef-4d16-9cdf-0ab7f1fd506e | section | TPO Detailing (Gutters, Corners, Overflows)
0f9f48af-a974-4347-8ed2-8623cd719290 | checkpoint | Roof Drains & Outlets - appropriate detailing techniques used
55051658-0e82-50d7-957b-75c58c2ec217 | button | Ensure the correct JM accessories are used? | Yes, No, N/A
76be6cf6-36b2-5ef7-be2e-2dc120961807 | tickbox | Attach Photos (1 photo per drain/outlet )
fa8e31fc-4002-4948-a353-566b303ebf1e | checkpoint | Penetrations - appropriate detailing techniques used
5b081a9e-9f2b-5b34-99d9-33b80e5693a3 | button | Ensure JM Single ply caulking is applied on appropriate areas? | Yes, No, N/A
8c2d69b7-4643-5eef-aa03-96593a9ea88f | button | Ensure 200mm upstand extension over pipe penetrations, and 150 mm for vent and square post (deck) penetrations | Yes, No, N/A
5555c8d0-f50a-53b7-a241-1de820754033 | tickbox | Attach Photo (1 photo per penetration)
e9806f13-2522-4739-830b-c6dd2407ad6d | checkpoint | Transitions - appropriate detailing techniques used
92349111-625a-5974-bcf0-9475f26cdc4b | button | All transitions sharply formed and having no irregular surfaces or edges | Yes, No, N/A
de39d17b-09e9-5095-87ae-fde5e9e9929b | tickbox | Application photos of transitions
6d8fb997-af06-409e-8e3d-b470312c4097 | checkpoint | External & Internal Corners - appropriate detailing techniques used
99fb4c58-e97f-5425-8f41-43ea1400ced8 | button | Ensure appropriate JM corners accessories are used? | Yes, No, N/A
ed84b504-f598-5dba-b53c-977fc4c3842c | button | Ensure appropriate detailing techniques used? | Yes, No, N/A
b572370c-b744-5568-9747-7833ba749d60 | button | Ensure 40mm wield length on all sides and corner fully welded | Yes, No, N/A
4d40a78e-f510-526f-ba42-814a44e94757 | tickbox | Application photos of corners ( 1 per corner)
370559d2-9999-4bd5-b3f3-51bba851417d | section | TPO Plywood Termination
8fa92dcd-139c-42f9-957b-3f4dd2372165 | checkpoint | Ensure appropriate detailing used for termination?
06c5db5d-b9a1-4798-aba8-dd6341702177 | checkpoint | Ensure 40mm hot weld between TPO and steel folded flashing (if appropriate)
c687c58f-ab82-4df9-a548-0977847d161d | checkpoint | Application photos of terminations (1 photo per termination)
dade64e4-5c54-4ed9-b8df-a3a93f0ac2b8 | checklist | Sikalastic 152 perimeter |  | Sikalastic 152 perimeter
574ca633-e84f-49a2-ac2f-ee99f12b702f | section | Details
445994d3-dbc1-497b-b1d4-6ff17d792bc8 | checkpoint | Area clean and accessible (attach photo)
c3e12499-43bd-4902-a4c2-7929aea93891 | checkpoint | Concrete in acceptable condition, dry and free from dust and other contaminants
8d47d5c1-3073-4fad-b549-7932e5714311 | checkpoint | Sika Products used last 6 digits of batch number (attach photo)
d54ec0f1-4233-5339-b217-db1e614065a6 | textbox | 152 required
4b73d86a-6850-4b71-8a30-b66f553168f2 | checkpoint | Attach general site comments and photos
a162b43c-35ad-4da5-8103-650e3e7ff4b3 | checkpoint | Work completed as per spec and area left neat and tidy
b2e5029c-856c-41d7-afa8-72430c1d5aa4 | checklist | Sikaroof I-Cure |  | Sikaroof I-Cure
e81e389f-37f0-4372-9711-d6914428d813 | checkpoint | Substrate inspected and is clean and ready
bf63020c-d6eb-455c-b9cf-3412eac44435 | checkpoint | Sika Concrete Primer
b8923d5a-2dca-4bb7-9ffb-d3558a52df3a | checkpoint | Body Coat Sikaroof I-CURE 631
8dc31cad-ec7c-4905-9922-4fae2489f746 | checkpoint | Sika Reemat Reinforcing mat
e8915e77-73d2-4a96-a77c-3ab43687f35f | checkpoint | Top coat Sikaroof I-CURE 641
80fdf22e-378f-429d-9b19-a51aa4996c7e | checkpoint | Detail any penotrations
78c46d96-9126-4603-84ab-e19bf7852f5a | checkpoint | Measured wet film thickness
62fd0175-9266-4170-8094-63bbea0acf67 | checkpoint | Ambient Temperature
101d6d51-f6a0-48bb-830b-d41b5ffcff80 | checklist | TA - Site Visit |  | Site Visit date:
3b44dfed-46ef-4f40-9c66-1e24d6db2236 | checkpoint | Site Details
08b397d9-cae9-5704-baf4-41956f084809 | textbox | Project Name/Address:
3dc2bb04-4a86-5107-a7ab-1967e5428834 | textbox | Contractor Name:
4ed3981e-fbc0-5c33-a805-12a04216e7ff | textbox | Applicator Name:
d48eb27a-5dd5-54a6-8cdc-82ea9c48799f | button | System Warranty | Yes, No
e710f19d-57e3-4854-a72d-894def8af076 | checkpoint | Product(s) Used
17b749b4-143a-5147-a691-99cb085b90cb | tickbox | Voltex
7dd0d95c-ce61-5251-9892-9850820ec2a3 | tickbox | Voltex DS
4e902ab6-63dd-5e80-9d82-ea34410c2c49 | tickbox | Voltex SWR
e48961ef-61a1-51bf-8ad8-c50a2c683ead | tickbox | Sweltite
1caf4385-df75-55dd-94f0-c983b1d34624 | tickbox | Rx Waterstop 101
0f3afd36-d654-539d-89e5-7d634e2a8bbd | tickbox | Rx Waterstop 102
e19ad193-1ed8-5f21-843a-a3096eb00916 | tickbox | Aquadrain
f127add9-4eba-527c-9a13-e9e5b5580602 | tickbox | Corflute
1d234e03-3347-5411-8bca-892b98a53b9c | tickbox | Accessories
4c251d93-ddfc-5023-9a8b-bafb1a65b446 | textbox | Other
f81ab4ae-aee2-495f-861e-0f9754b9e981 | checkpoint | Site Visit complete and NO REPAIRS REQUESTED
2232c4fe-3e77-5264-aedb-de724743ce29 | button | Substrate acceptable | Yes, No
d6bcd1cf-db8c-5fcd-96b7-091868328b98 | textbox | Location or Grid Lines:
5aa387f2-766e-54ee-80a1-5db918854e3c | textbox | Inspection Notes
466025f6-5406-4f2e-a064-5b9a3f3a6199 | checklist | Torch-on Membrane |  | Torch-on Membrane
955b634e-3de0-4bd8-9411-e1a5c72302b2 | checkpoint | Substrate checklist completed and attached
9a5d1530-e8a2-4c3b-88d0-c819afd211e6 | checkpoint | Substrate clean, dry and free from foreign matter and sharp edges. If in doubt, check substrate moisture.
373517f8-52e8-4496-a920-8f5822da9b89 | checkpoint | Substrate primed - good even coverage/penetration.
59c08ed6-a31d-40cd-b5a3-7c3ef641bfa0 | checkpoint | The First layer is fully bonded to the substrate all laps tested and welded.
453a9210-2220-4f2e-aa8a-729de4fbe039 | checkpoint | The Second layer is fully bonded onto the first layer all laps checked and test to ensure membrane integrity.
7706ed32-45b1-41f0-a777-17b27dadcf69 | checkpoint | The Second layer is offset 500mm from the lap edge where practical.
8b01a5aa-8077-4004-bbde-5e673138e0a7 | checkpoint | The Second Layer is offset and stagger at the end laps
0d370b5c-933f-453f-8bdf-1e5cd07effbb | checkpoint | Movement joints identified and installed to approved specification/detail.
4586a5ac-9f71-4164-98b8-5f0202171a25 | checkpoint | Under flashings installed to all corners and upstands.
e310cf3f-5eee-4fcf-9c7e-1b2de92b6aeb | checkpoint | Membrane torched to substrate allowing for 100mm side laps and 150mm end laps.
c8defe0f-627d-4d43-9712-d71e3cf3d8a8 | checkpoint | Gutters correctly and neatly installed, particularly the internal corners - laps above roof line.
3fc3e6b0-92a5-4eb5-b6b1-d4d4844603d9 | checkpoint | Roof drains installed to specification and watertight.
9b6578c2-0932-46b1-8810-2ab60652502d | checkpoint | Overflows installed to specification and local body requirements and watertight.
fc60c05e-0087-4fba-b685-729448ab6597 | checkpoint | Membrane termination completed to approved detail.
f1433a77-5b2a-4e91-a97c-803509b55907 | checkpoint | All penetration details completed to specification including under/overflashing.
0e49e44f-efcd-41fa-b95d-79412e9c0a9a | checkpoint | No sign of overheating/excessive bitumen bleed from laps (2-3mm).
8758fe22-2273-45b2-91ed-404becf0d72d | checkpoint | Overall installation free of wrinkles, creases, and splits.
0cb6caa8-54d0-4c10-9a19-e76869f77f24 | checkpoint | Ensure membrane is clean, dust free for cure coating system.
b0523d8b-cb1b-4691-9787-de3df5331796 | checkpoint | ILD Tested
e4c4eb16-8054-4947-8c46-dcb7ec85d291 | checkpoint-no-value | Work area signed off
12d21c59-6c02-4f53-888c-d6550795fb1c | signoff
e10ad774-73f1-4c74-bf7d-7eb8476bfecb | checklist | Viking Warmspan Checklist |  | Viking Warmspan Checklist
6ee57445-7670-4e50-8603-9d7a16ad980b | section | Prestart
a6136a16-a96f-4b32-85bd-81a3614c2886 | checkpoint | All workers inducted to site
e37cbeb1-1cc6-4c66-b648-436fe6b5d0d0 | checkpoint | Prestart safety meeting held
02988180-5740-4da2-958f-38c0db44ef4a | checkpoint | Area Accessible
fb59594b-93d2-44c4-bc08-521bff08377b | checkpoint | Edge protection and safety installed
1464d37f-5d36-4df1-a416-696eb6ed2e45 | checkpoint | Purlins in place
a60f06ae-ddae-4912-83b3-23d2bcdfdc8d | section | Warm Roof Metal deck substrate install
8ace69aa-71fe-4084-a02f-c401e898888d | checkpoint | Pre-start o discuss details and execution of system
fce56655-d846-40d9-b2fc-1af5afcc2fd6 | checkpoint | Metal deck installed in accordance with Manufacturer’s recommendation.
a8debcec-a450-44fd-924b-b9a2e5b1c588 | checkpoint | Outlets are sufficiently sized for anticipated run-off.
64a9e7d4-f648-4264-9874-af8be91dada4 | checkpoint | Metal roof edges overhanging into gutters are cut back and timber upstand installed at the height of PIR board.
56f67eb8-4a7d-4d4e-aad6-3d0d2a6c2fbd | checkpoint | Metal surface satisfactory for installation of Duo membrane by Equus Applicator.
f0df4e49-a8fe-4abb-94a3-9ca4f0d1c8d8 | checkpoint | Sufficient and correct fixings installed
e9b66af2-2244-41c1-90d6-83e7dc0128ae | checkpoint | No metal edges protruding up high
db72d341-9dc6-442b-b674-f98ab2099906 | checkpoint | Flashings installed over hips/ridges and valleys
dcc2d79b-2899-40aa-87a0-a66ed498df1b | checkpoint | all swarf swept from roof
28cd12b7-7888-49a0-b194-2aeb350aad13 | section | Vapour Barrier installation
022b5958-ac3d-425c-83a8-3a89b2ec52d9 | checkpoint | Primer applied evenly and consistent to all surfaces and penetrations to the required height up upstands and parapets etc
eced6bd1-1800-4cc2-9c86-010da012a3d1 | checkpoint | Vapour barrier installed and carried up parapets a minimum 50mm past PIR Insulation board.
7bb8fd18-5e05-47e9-8177-bf82c7833cbb | checkpoint | Correct side laps and end laps
067cd70b-fa37-4e09-8136-1783a637f186 | checkpoint | Vapour barrier terminated correctly to ensure vapour layer continuity at roof openings, transitions and horizontal to vertical roof openings
18f59676-5910-486d-8ba7-ae23f8246703 | checkpoint | Any damage to vapour layer to be repaired to 100 % continuous
0d4f352f-8bed-4348-8c89-9e1421eeeeac | section | Insulation
0580110c-ec19-4300-bb0b-e57386bf45b7 | checkpoint | Correct insulation delivered as per plans and specs
2a6e77cc-523c-4ca6-987f-a574a37d8d65 | checkpoint | Insulation damage free no crushed edges etc
a3b66c3a-986f-46a0-b2ae-f1bec2cdf540 | checkpoint | Insulation has been kept dry out of weather at all times
c9c61d9b-b9f3-4afc-b629-d824e6e0c610 | checkpoint | Ends of insulation to be protected by a hard edge with timber or flashing
2537bfbc-f30b-4f51-a3f5-7cbc27a60a7c | checkpoint | Insulation to be installed in a brick bond pattern
c77bfd76-8a9c-415c-8263-5e4ffb333308 | checkpoint | Correct fixing being used including the correct insulation plate or thermal plug or adhesive
3d8c1830-0653-491c-ab47-8df135a3f13a | checkpoint | Correct fixing pattern used as per manufacturers specs or site specific wind uplift calculation
0f40b6df-b6fb-4e7f-b8fc-1f617da09f24 | checkpoint | Evenly distributed weight if FAST adhesive used
cf50e869-d6df-4f6a-9acb-6fe97906911a | checkpoint | No edges protruding high
7d46097d-cefa-46de-ab16-a371979a3702 | section | Coverboard
3e7e0adc-dedf-4492-a658-23a58bfbb58c | checkpoint | Correct coverboard delivered as per plans and specs
27bde908-b5f1-44b1-8236-b7e71f2bc98f | checkpoint | Any damaged insulation board to be cut out and replaced with new or not used (minimum repair 300 x 300mm)
e09094f5-deba-4a38-b552-c520e4f86bc2 | checkpoint | Correct fastening method ie glue or fixings
e44af369-0c9c-4075-bb39-53ee5ca92ad5 | checkpoint | Correct fixing pattern used as per manufacturers specs or site specific wind uplift calculation
99c2db2f-b3aa-41f8-98ef-ae824dc99e35 | section | Viking Enviroclad installation
02a7f631-eb27-422a-bbc5-76ff329e50db | checkpoint | Ensure substrate is completely free from debris, dust etc
ee5b5fe8-e445-4a24-a357-5fa98d0b667d | checkpoint | Taken into account ambient tempratures prior to installation beginning
eda8b55b-4e7c-4f52-88c5-52e8ed868a76 | checkpoint | Taken into account incoming weather prior to installation beginning
d25d1d91-1525-495c-9f75-fea62b350b2d | checkpoint | Adhesive applied as per specification (refer to relevant section in specification)
b59d0de3-7edb-4c39-a25d-fd9b31192225 | checkpoint | Membrane layout to the roof has been considered carefully
90b9c46c-0cb5-412d-a699-5e4c8d24a50e | checkpoint | Membrane has been installed in the correct sequence, starting from the outlets up-to the highest point of the roof/deck or gutter
f1d3dc39-fe15-4b22-86d1-093aea19f4ff | checkpoint | Correct laps in Enviroclad overlapping edges a minimum of 50mm to provide for a minimum 40mm hot air weld.
16526f3b-7cea-447d-84e2-5fd377f0d28f | checkpoint | Laps are cleaned prior to welding
771c1700-cd6b-4ac8-9536-df1763e01cad | checkpoint | Membrane has been fully rolled to ensure a consistent bond
56ec9d3d-aad6-486f-b55d-2af2611a303a | checkpoint | Terminations up walls, parapets etc to be completed as detailed or to minimum code requirements
c1108992-01c9-4a3c-a0c8-c536076ad151 | checkpoint | Terminations up walls, parapets etc to be mechanically fastened by flashing, fastening bar, TPO coated steel
fa17d114-519d-48a6-8fbc-96b6d6adb238 | checkpoint | Proprietary accessories have been used for all corners and terminations
b0f06770-4a45-466b-9f88-31aa24020676 | checkpoint | Proprietary accessories have been used for all penetrations ie Pourable pocket etc
96b2adb9-931e-421e-827c-3a3978681367 | checkpoint | All welds seam probed and any inconsistencies in weld rectified
be2fa05a-ed12-4df7-bb9f-794b7b6f39e1 | checkpoint | Cut edges of membrane to be penny welded or lap seam primer installed
ad45bb02-ec3e-4394-a9fd-b074735434d8 | section | Flashings
43cde2ec-7c2e-4190-9a62-46c6578531e1 | checkpoint | Flashings made in specified material/colour
f7ad195a-c4d2-4e6f-970f-7ffa13c877ec | checkpoint | Flashings installed neatly and fixed sufficiently
e8a6f7b7-ed78-4d8c-ba93-238baba5e50d | checkpoint | Flashings sealed with correct sealant
1c42420d-659c-4ea2-b014-48392deb944b | section | Clean up
74db9d20-7892-4e2e-b48e-2c97cb1e6b5e | checkpoint | All rubbish from all stages removed from site
66b40714-28af-46a7-815d-9489d768cc7e | checkpoint | Roofs cleaned down
c5c3b4b9-b6f5-446a-b8c5-dc9bcf4a6ba3 | checkpoint | Scaffold checked on every level for rubbish
73d2b0e9-37f5-4295-b1ad-2dc0eb969041 | checkpoint | Grounds checked for rubbish (under scaffold etc)
680b9eb4-abf4-4fcd-ad0d-064aba993af8 | checkpoint | Site forman agrees site is clean
3c12ece9-b3ee-42af-9e93-3e9c16938d04 | checklist | Water Testing Checklist |  | Water Testing Checklist
8c4736f6-4466-475d-aff4-1eee276d39b7 | section | Details
b81cb220-596e-4d05-81f9-081d3f22558a | checkpoint | Check all laps, internal, external corners outlets and overflows for damage and breeches
8b7b267a-882a-46c3-9de4-29b75da06da2 | checkpoint | Correctly block outlets and overflows
b463d2b0-47a2-422c-a8a4-87fb6f0a34bf | checkpoint | Fill with water to correct height and leave for agreed timing
3abeddc4-d0ef-4b5c-8cec-cbd72a7262f0 | checkpoint | Repair any leaks or breeches
b6920b2c-7f1b-4331-8dea-03bdc6b3a6b5 | checkpoint | Retest area
6d46c200-9913-4f17-a03b-60f6aca10d36 | checkpoint | Remove and release all water and bungs
53863a47-650a-4894-9566-ce000c964f51 | checklist | Waterproofing - Sika Blackseal Elastic |  | Waterproofing - Sika Blackseal Elastic
9ab086fd-81b8-4ce8-bb6b-c6979d016d28 | checkpoint | Area clean and accessible (attach photo)
df846fa7-0dde-4ca1-9ba1-a7281bf92227 | checkpoint | Control joints installed, backing rod with Blackseal-1
404c9985-1e7a-401a-8a4e-2128fde85976 | checkpoint | Footing / wall junction fillet applied
9e806528-3a76-4337-b033-c3554e7d9286 | checkpoint | Sharp external corners rounded off
9be0b028-4be3-4062-89d3-072caedac6ef | checkpoint | Sika MonoTop Fairing coat applied, if necessary
c0187a64-92bc-4b29-8f81-b762b69dfd3e | checkpoint | Penetrations through wall sealed with Blackseal-1
9dff4a61-0c46-4f0b-a586-8fda66c6d88f | checkpoint | Walls & footings primed with 50/50 mix of Blackseal & water
5a73316d-a85b-47e3-aa6c-8c947ca33906 | checkpoint | Apply minimum 2 coats per manufacturers instructions
dc8e2188-cdbc-4f64-808a-e51ced85f15a | checkpoint | Penetrations - Apply membrane per manufacturers instuctions
9ade1340-ebed-4ac6-aca6-7709b81891c4 | checkpoint | Floor/wall Junction - Apply membrane per manufacturers instuctions
26fcdf08-f649-4c62-9ae8-f940997317c3 | checkpoint | Allowed to cure 48 hours before fixing protection sheet
1df609ec-aac1-493a-bfd1-ee37e0ff980e | checkpoint | Ensure protection sheets fixed with dimpled side to waterproofing membrane
901a99b7-bc4e-46ad-af2c-f39c16af286a | checklist | Waterproofing QA - Hydrotech Checklist |  | Hydrotech for Area:
8adcb96b-baed-4145-bf89-9264f0ffd4c3 | section | Hydrotech Area of Installation
9ac65781-fab5-445d-a2b7-bf8c13812549 | checkpoint | Checklist named with location or text box below or marked up drawing attached
2d3d4c20-fb70-5d83-96fd-207f0dd3a956 | textbox | Description, grid sections, etc:
7cc8a01b-0988-42df-8f11-36e7682866cf | section | Hydrotech Site & Substrate Prep
cc28b9ae-176c-40eb-8901-cc95bce1ab08 | checkpoint | Wind uplift has been considered prior to installation
7c058cb1-5fef-42e3-85a7-220393d2c906 | checkpoint | Ensure all drains and outlets are membrane compatible. Confirm with Allco rep if required
2975547b-fad7-465e-9a20-b776f97641d4 | checkpoint | Concrete substrate has been allowed to fully cure with a minimum wood float finish
8de8e338-34c9-4c27-aca2-82c9b160e43a | checkpoint | Substrate clean, dry and free of debris or release agents
c2a3c2a8-38fa-46a1-8f7d-cca61ac4ce13 | checkpoint | Substrate photos taken
1caa264a-b3ae-4a18-9ef2-539115790946 | section | Hydrotech Horizontal & Vertical Application
d5b1ff75-1880-4b75-9caf-7b0f999cbdb3 | checkpoint | Test conducted to ensure membrane creates a mechanical bond to the substrate
40874f5c-c1ce-5481-adc2-2f53299527a8 | note | Attach application photo (1 photo per 20m2 or separate area)
1e99df68-a7ed-4a08-a1f7-664e18cf7df8 | checkpoint | First membrane layer applied at 3mm thickness
b04ecb4d-0965-5d27-b902-50ddb82afc51 | note | Attach application photos (1 photo per 20m2)
8d4952e1-35a5-493b-9bef-155b5d4012b6 | checkpoint | Top coat of Hydrotech applied at 3mm thickness
9546d650-1820-523e-be13-805dfef4cfcf | note | Attach application photos (1 photo per 20m2)
6c4d4502-75f4-47bb-b6d5-3f72940bc834 | checkpoint | Photo proving total thickness of membrane system is 9mm (including protection layer)
1c53b810-360b-449c-af5d-1e7eb1fffd73 | checkpoint | Photo of complete installation
aca8684d-842e-4d8f-8d1d-61c9453661d0 | section | Hydrotech Detailing
c4901fb1-3b61-4cbc-bad3-6cc549f75dac | checkpoint | All penetrations have detailed as per Allco specifications
f8f7671f-c3e1-4552-bdf4-530899b33d0d | section | Hydrotech Terminations
ae6308c2-7bbf-4783-a160-ad79c94c225d | checkpoint | Ensure the approved sealant or tape is used for termination
58d57f41-97b1-4d48-a8e2-71c3abde86be | checklist | Waterproofing QA - Protection & Backfill Checklist |  | Protection & Backfill for Area:
50739d80-0144-4562-b22e-1f8d896422b4 | checkpoint | Checklist named with location or text box below or marked up drawing attached
59231477-162a-5580-aea2-dccab183f5b4 | textbox | Description, grid sections, etc:
d21e51dc-9387-40d2-bd43-7ee4c1d393a6 | checkpoint | Allguard has been installed as per Allco specifications?
cf9a872a-aa12-4f89-b1e1-50ca0014d9f6 | checkpoint | Hydrostatic Conditions - Backfill compacted every 400mm?
bba2a201-8152-58ce-8d6c-9ab9490030cb | textbox | Backfill date
9db91ca0-99c1-4522-9435-93216f1527bb | checklist | Waterproofing QA - Sweltite Checklist |  | Sweltite for Area:
01f2112b-3174-490a-b14c-994bad1ef2e0 | section | Sweltite Area of Installation
277604ae-9fe5-4ce3-9adf-028115d9c3ec | checkpoint | Checklist named with location or text box below or marked up drawing attached
1e8ed08f-80a0-5b0d-a678-e215d747965b | textbox | Description, grid sections, etc:
04e4d099-be5b-4fff-af45-5b022cb83b37 | section | Sweltite Site & Substrate Prep
8293854d-d51e-46b3-b2dc-eb22793ae7ed | checkpoint | Appropriate site conditions for installation
e4b9588d-2fc2-4fd1-bee9-b3d230cdecd3 | checkpoint | Appropriate water control in place
27d3c552-6673-4a99-885a-1a6d78b2528f | checkpoint | Substrate photos taken
e3e1774e-92e3-4a3c-b49c-097299f0d871 | section | Sweltite - Foundation walls
f10d1a30-5622-449a-a20d-951f4daf6328 | checkpoint | Appropriate detailing done as per Allco specifications
b077bc2f-7be5-4d90-97da-8cc7715a97e5 | checkpoint | Ensure 100mm laps between membrane
f197622e-d5e1-4bd1-8917-c6e7267ada6c | checkpoint | All laps seam taped horizontally & vertically using Allco seam tape
52aa348b-d37a-4ac6-b948-69367bf0c0af | checkpoint | Sweltite exceeds 150mm past F.F.L
8302047e-86fd-409c-b425-7345ff6897b2 | checkpoint | Drainage coil has been placed 100mm from the floor/wall joint
c45272df-270a-4bae-937a-876272e9f985 | section | Sweltite Penetrations
2536ead9-0d43-4ba7-af69-798c129bb267 | checkpoint | Penetrations detailed appropriately using appropriate accessory Volclay products
53c52454-4c30-41b3-93a6-457daaa4dcd2 | section | Sweltite Termination
8f0b8ab6-63e6-4530-9bf6-bfaf47b6d092 | checkpoint | Termination bar used on vertical & horizonal edges
8253bee4-e8f3-43b4-9c28-9d4ef5a1d760 | checkpoint | Cetcoat applied at appropriate areas
365ff4ff-9ecd-4b37-854e-b116ee5a8c19 | checkpoint | Termination sealed off correctly (i.e. M2000, Cetseal)
5d0f334c-420e-4e7a-9480-05ed147ca8af | section | Sweltite Backfill & Protection
10558d80-0c10-4f3f-8588-34c47747fe83 | checkpoint | Allguard has been installed as per Allco specifications
2c34474a-d894-4d9e-89c2-2176feda778b | checkpoint | Hydrostatic Conditions - Backfill compacted every 400mm
12ea88f5-0476-56b6-96bd-fd5150dcce4d | textbox | Backfill date
a3825b2c-df0c-4253-ab36-8d3983216e2a | checklist | Waterproofing QA - Voltex Checklist |  | Voltex for Area:
20edd108-c87b-4115-b605-1b0ad912ec5e | section | Voltex Area of Installation
8c5f7c7f-ec48-47b5-8830-bc80e2e16c56 | checkpoint | Checklist named with location or text box below or marked up drawing attached
345fe001-05ba-5e52-bc8e-d281f8fd964c | textbox | Description, grid sections, etc:
ec2928c3-46ab-417c-8b81-2a3625a9d1ee | section | Voltex Site & Substrate Prep
859d9da9-03cc-4ff4-b2ea-980eef615e92 | checkpoint | Appropriate site conditions for installation
fab6781b-f22f-4962-aba5-95ae04feaa9b | checkpoint | Appropriate water control in place
5af86c0a-73e9-59b9-b097-42759eeb694f | textbox | Concrete pour date
d9753dbe-84b1-40e4-a241-9c1b5a9ffc0d | checkpoint | Substrate photos taken
cbe0849a-6ac4-4db1-aff3-5d672f20adfe | section | Voltex Walls, Underslab and Footings
28ff86f6-9c2f-4c12-a931-8bcbb2b0f82d | checkpoint | Membrane appropriately laid on substrate with dark grey (woven) side up
47ea485b-7bdc-4b5d-a481-46d025a4940e | checkpoint | 100 mm overlap between each sheet, and stagger sheets end at a minimum of 300mm
6751a0c0-0044-4582-852d-ad70713cfeec | checkpoint | Appropriate detailing done to external/internal corners
fdcd2b28-6101-4642-a8c6-b632a55eee75 | section | Voltex Penetrations
7f5d8170-f436-4d22-a83e-4bec410431b7 | checkpoint | Penetrations detailed as per Allcos recommendations
d16e5558-1ff0-43d0-98bf-7fa98ca4d99c | section | Voltex Backfill & Protection
eef358bd-8a4b-4622-9dde-7630fa4196f4 | checkpoint | Allguard has been installed as per Allco specifications
9c3e8769-9e67-4937-9632-f4bd2f7f75fa | checkpoint | Hydrostatic Conditions - Backfill compacted every 400mm
d0e82439-9d99-5db4-821d-a9d69c6c4400 | textbox | Backfill date
b9db1e20-cd5f-477f-9465-6b75da1ac94d | checklist | Waterproofing QA - Waterstop-RX Checklist |  | Waterstop-RX for Area:
2b8bf332-68d0-4a6c-b20a-b05d576a52d9 | section | Waterstop-RX Area of Installation
8690111c-79f6-4d8f-85c6-cd91b84cc375 | checkpoint | Checklist named with location or text box below or marked up drawing attached
75d6dba4-47e4-50ec-bee6-387daf2d6af3 | textbox | Description, grid sections, etc:
16830878-e2c7-4ca1-9a7e-00a8c862d69e | section | Waterstop-RX Site & Substrate Prep
5bd055ab-d5b1-4f88-96cf-699a6c5c254a | checkpoint | Substrate is acceptable
5f8c1e92-7115-4192-b1cf-fd520f5e1185 | checkpoint | Confirm appropriate Waterstop-RX is going to be used in relation to concrete thickness
bdde70d4-e30b-5c50-ac40-bf1df3880cae | textbox | Concrete pour date
60209e19-d2be-478e-81e7-b85452ed019c | checkpoint | Substrate photos taken
83086c8d-b95a-4953-8476-fe9884ae30c8 | section | Waterstop-RX Installation
ca3a7ab2-f2b1-44c1-aa5e-79f7da01b1bb | checkpoint | Waterstop-RX has been installed as per Allco specifications
6a060df3-9bc0-44c4-84e6-d3e14c7de853 | checkpoint | All parties aware of Waterstop-RX requirements with exposure to climatic conditions