## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Alliance EPDM | [5 empty] | Alliance EPDM
section | Details
checkpoint | Q1 - Work areas are clean and tidy and conforms with the relevant Substrate Specification documents, completed seperately
checkpoint | Q2 - Substrate moisture content acceptable?
checkpoint | Q3 - Install underflashing tape in correct locations
checkpoint | Q4 - Membrane laid over clean substrate using correct adhesive
checkpoint | Q5 - sheets well set out, parallel lines, laps running correct direction and to correct fall
checkpoint | Q6 - Membrane lying flat on substrate with no bubbling
checkpoint | Q7 - Laps primed and taped, with clean edges, no excess seam tape, glue overspray
checkpoint | Q8 - Outlets detailed to correct specification
checkpoint | Q9 - Membrane termination completed to details
checkpoint | Q10 - Membrane installation completed to specification
checkpoint | Q11 - Surface Sealer applied