## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
7639e772-e021-4c52-b9dd-0f30241d221d | checklist | Tahunanui Back Beach Remediation ITP | itp | Tahunanui Back Beach Remediation ITP
04b3eb31-5c30-4d06-967e-529c0c27a897 | section | 1.1 - Pre Construction
3c08e01a-91cb-4884-bccd-edb54e571e90 | checkpoint | 1.2 - Vegetation Clearance
67432d55-0541-571d-a6e7-2cf3f80cdccb | note | Inspection Point: Quality Control Activity - Removal of trees, and other plants within the area of works
885362d9-95f5-502e-8261-002fcb0cec76 | note | Acceptance Criteria - Trees and plants removed in the area of works
0d25e83f-d1df-5fe2-aa56-6e568bfe54b9 | note | Verifying Document - Visual
e3d81e06-dee2-5a42-b084-cf3f88ced4f4 | note | Frequency - Pre Construction
9283566e-41d5-5ea0-9b42-75c9afeda89e | note | Inspection Type (Visual, other) - Operation, Hold point
b0f14966-0113-584e-8745-c88b1c9858ea | note | Inspection: Key - SUB
42aa6c37-e081-59e4-b215-c7ece7731348 | note | Inspection: By (Role Key) - Nelmac
b211afe1-79bb-48b1-a2d2-f2ad471cccbc | signoff | AUTHORITY HOLDPOINT
f277cf6d-13f0-40c2-bfe8-b6921703d896 | checkpoint | 1.3 - Ecological Clearance
b75ac592-412e-52eb-9dbf-ba7519e18370 | note | Inspection Point: Quality Control Activity - Pre-clearance surveys for nesting birds, implimentation of Lizard Management Plan and accidental discovery protocals for lizards and birds.
117478d1-6867-5b8f-858a-940b063666ac | note | Acceptance Criteria -
73c6f7d0-5f6d-5889-9b43-f5d096f46892 | note | Verifying Document - Visual
285a3779-43ea-5d68-bdea-8f7500190b5c | note | Frequency - Pre Construction
ffeb1d88-da73-516c-9543-f4a6ea2e2912 | note | Inspection Type (Visual, other) -
f3d5787c-886f-5696-a359-a56084448bc4 | note | Inspection: Key - SV, ECO
4cf43d81-8676-59aa-96f9-d3ded268352e | note | Inspection: By (Role Key) - Downer, T+T
df9c82cc-67a5-4ce5-a844-100fb055dc50 | checkpoint | 1.4 - Traffic Management
93784497-3032-5bd8-ab73-42ab66bbec3d | note | Inspection Point: Quality Control Activity - Implementation of Traffic Management
606a2dfb-cd98-5402-9bb7-85398787d464 | note | Acceptance Criteria - Traffic Management set up in accordance with approved TMP
6da57df9-1435-56e3-af9d-329e199afc51 | note | Verifying Document - Visual
d84e594c-154e-55ec-b733-47bec9098025 | note | Frequency - Constant monitoring
aeab2b36-f312-53eb-8fef-ab3b1ffd4aa7 | note | Inspection Type (Visual, other) - Visual verification, Hold point
952e9b6d-9814-5caf-b12c-554505c9d965 | note | Inspection: Key - STMS
6cebdb6b-06f3-5428-84d0-bc7dda497782 | note | Inspection: By (Role Key) - Downer
8aaaad4d-58d1-4934-9482-9bc3c0d42a7a | signoff | AUTHORITY HOLDPOINT
533d81b1-c9f7-443b-8222-f66aed32f950 | checkpoint | 1.5 - Service Location and Clearance
cd517c50-6b22-527c-a71b-0421c7c373ff | note | Inspection Point: Quality Control Activity - Service locations complete
04cf5933-dab4-59bc-863a-729d1867c7db | note | Acceptance Criteria -
dc666cae-a4d7-5308-aaeb-ffda7045e125 | note | Verifying Document - Locator record of confirmation
3167cf20-ac2b-54ce-874b-22f94d183a6e | note | Frequency - Pre Construction
ea9c5510-5903-57e1-9e81-f393f8c235c4 | note | Inspection Type (Visual, other) - Inspection, Hold point
9d9b4153-175f-5286-9194-360e681d3bf9 | note | Inspection: Key - PM, ENG
952a4226-86ef-5252-98a3-16fe69f84d6e | note | Inspection: By (Role Key) - Downer
791aba10-d72f-4c8e-b03f-f0094338a185 | signoff | AUTHORITY HOLDPOINT
2b74fc7b-fca0-435f-b0b5-c933a3b8dd52 | checkpoint | 1.6 - Survey and Set out
6afe6540-7a1c-54a3-9cfd-a1d7e5cdbaa8 | note | Inspection Point: Quality Control Activity - Pre construction survey and site set out
1637406d-ab43-5490-bfc8-5cc22aac7308 | note | Acceptance Criteria - Set out follows provided coordinates
596dac80-a6cf-5c85-968d-db266956b807 | note | Verifying Document - Visual
dfac3be1-e1c7-5467-a334-fe4ada697ba9 | note | Frequency - Pre Construction
d13a2dcf-dab1-57fd-898e-18c32cd268bb | note | Inspection Type (Visual, other) - Inspection, Hold point
890307d9-f51a-5d6e-a1f2-d67c8acc47b2 | note | Inspection: Key - SV, ENG
09afca7d-ea19-5edb-9c25-a239a58fa7a3 | note | Inspection: By (Role Key) - Downer, T+T
a52be2df-4a8a-4fa0-b650-58fc6bed09c1 | signoff | AUTHORITY HOLDPOINT
e941409b-b480-4b05-9876-3a8f20aba838 | checkpoint | 1.7 - Equipment Free of Contamination
07eadaea-3fe3-5ac9-bb56-9e57cec788d6 | note | Inspection Point: Quality Control Activity - Any equipment coming onto the site shall be washed and cleaned of visible dirt prior to entering the site to manage potential biosecurity risks. Washdown area has been established on site.
c0e72485-cf69-588a-a647-fc4888b1f4c8 | note | Acceptance Criteria -
805a19fc-3595-5cea-be12-5c4ba14843b1 | note | Verifying Document -
5a7be9d3-af09-5a4e-9d88-837bb10b6af7 | note | Frequency -
d550958c-6e40-5616-be70-5a6edd364cea | note | Inspection Type (Visual, other) -
144cb1ba-683d-5a48-962f-f2a1bc314818 | note | Inspection: Key -
de1ac1d3-2c7b-5bc9-821b-6714baf99cbd | note | Inspection: By (Role Key) -
b803644c-dac6-4191-b56f-383696e2fa4f | section | 2 - Stage 1
39cfe3c9-f1c5-4f08-8cd8-756930767cc9 | checkpoint | 2.1 - Removal of carpark gravel and placement of new benched haul road area and capping layer to protect exposed contaminated material.
c1e2c868-cc3b-5fff-ae63-0ae8ba91c219 | note | Inspection Point: Quality Control Activity - Confirm protecting capping layer placed.
d3a5884c-e21f-5317-b622-00081cdce90c | note | Acceptance Criteria -
b01fb92a-3570-57c5-9d82-add1eeb458dc | note | Verifying Document -
4c57b375-77ef-502e-9ae5-1262c9401e8f | note | Frequency -
2aff1abd-f3d7-5ed3-a0d9-ae98011d9721 | note | Inspection Type (Visual, other) -
e361b30e-605b-5905-a14e-4ca6aec91ee6 | note | Inspection: Key -
83b23112-a931-5cc0-928b-aade415065b1 | note | Inspection: By (Role Key) -
00bc7422-dfc1-4213-b146-780bd9720297 | checkpoint | 2.2 - Excavation has reached the proposed first cut level.
eb3293c0-b4ba-5dc6-9b97-03aec22162be | note | Inspection Point: Quality Control Activity - Confirm extents of excavation
3aaedd1f-41dd-5102-9b65-c9d89601662a | note | Acceptance Criteria -
8a9a1e6b-352b-5b0e-ae90-9c80b2e8c95a | note | Verifying Document -
7c107a84-212f-50b9-b14d-0419d2e2b723 | note | Frequency -
102f5d60-b362-5cc8-ba79-03f360c5696b | note | Inspection Type (Visual, other) -
7a5af3c7-6ccf-5a24-ac5c-dbe0443b4966 | note | Inspection: Key -
81a14d87-11d7-5850-8903-c85132cb4aeb | note | Inspection: By (Role Key) -
6b5226d6-0361-46d2-984e-13a9b1bac5cc | section | 3 - Zone A Excavation - Stage 2A
a22696cf-ad15-4895-bbea-69241b4e30b0 | checkpoint | 3.1 - Confirmation of survey limits of excavation
f7d96e41-91ad-522d-84d7-ae745b8e6771 | note | Inspection Point: Quality Control Activity -
0e566156-ba2d-5e0c-820c-4ee0883a2ab0 | note | Acceptance Criteria -
d3879a5c-3805-5933-b634-49e3c3049ce4 | note | Verifying Document -
e611e570-c9d4-5ed2-89f9-b72bc4465bef | note | Frequency -
1f01e6de-7962-5826-8307-e2d32fe26d8f | note | Inspection Type (Visual, other) -
0da560d4-c9a9-5f35-a935-737eb13d6d7e | note | Inspection: Key -
0d753762-36cc-57eb-be84-768a7cb88a47 | note | Inspection: By (Role Key) -
6b67e428-7004-40e1-9652-7d5cb6ed78d1 | checkpoint | 3.2 - Final Excavation Level
8931c5d1-ae9b-586f-8505-9c153a65869a | note | Inspection Point: Quality Control Activity - Visual confirmation that visible sawdust is removed.
91974232-dec7-5355-86d2-ea6ffae17107 | note | Acceptance Criteria - No sawdust remaining in section of approval
640bc4a6-fc30-5442-b731-a142f7b63459 | note | Verifying Document - Visual
e33d1f45-4d6b-51e8-be1b-8d15cfbe3994 | note | Frequency - Every 25m of the completed excavation on a 5m grid.
96fb3ce6-0037-5567-aaff-3cdb0cf2a1a3 | note | Inspection Type (Visual, other) - Inspection, Hold point
77c408c9-f566-5b15-99ae-8fb4efbc2dc3 | note | Inspection: Key - CONTAM
90ec9274-d276-5672-8e49-b3e65de37970 | note | Inspection: By (Role Key) - T+T
8d3aadfe-265b-4839-97dc-7148bd82591f | signoff | AUTHORITY HOLDPOINT
9db0218b-f126-469f-8c69-a8db36a2c653 | checkpoint | 3.3 - Final Excavation Level
831d4f09-9c71-5d85-94dd-2037c9b9e059 | note | Inspection Point: Quality Control Activity - XRF Contamination Testing
57a7fef5-0ab2-5eb7-a13e-6a9675344cc8 | note | Acceptance Criteria - Excavation free of contaminants
5feefdd0-a181-5c9a-a188-7991619163dc | note | Verifying Document - Engineer approval
0a1d8364-c741-5760-a9e6-08d9c2b219dd | note | Frequency - Every 25m of the completed excavation on a 5m grid.
e3c51a6b-871e-58f6-aebf-52d37c8f103e | note | Inspection Type (Visual, other) - Inspection, Hold point
983fb406-b479-50b9-854c-59557187cc50 | note | Inspection: Key - ENG
00714346-2e51-5fad-ba0e-3888b64f9ea1 | note | Inspection: By (Role Key) - T+T
b2c718b1-6fc0-412a-ab12-34d9a897d1bb | signoff | AUTHORITY HOLDPOINT
81323f8c-4994-4de1-b802-22a1ad16a873 | section | 4 - Sand Mining
31ec2cc2-3f72-4b04-8500-e69472d1eeff | checkpoint | 4.1 - Ecological Clearance
ab409f7a-43a1-55f5-9fc2-04bcab82772d | note | Inspection Point: Quality Control Activity - Ecologist to assess for any active nests above MHWS during peak bird breeding season.
a316c4f9-5fce-5f50-8315-222ce73c1ce4 | note | Acceptance Criteria -
8a35eef9-13b3-55d1-94b3-d3e4e022ead9 | note | Verifying Document -
4091695d-20a7-5358-934b-4187669f302e | note | Frequency -
2fbf77d8-dfef-53fd-a41d-79f9fcacd3e1 | note | Inspection Type (Visual, other) -
ff725033-ab07-5639-9786-cc01888a0c51 | note | Inspection: Key - PM, ECO
b66588ba-fcc1-5f80-a319-235392b9e567 | note | Inspection: By (Role Key) - T+T
0a514b37-af96-4f34-87cb-af349b7169fc | checkpoint | 4.2 - Limits of excavation established
efca525b-bc17-54a1-988e-5210b72223a3 | note | Inspection Point: Quality Control Activity - Area marked out
f934b521-d9ce-5d97-88ec-d609f6d3bf00 | note | Acceptance Criteria -
4539d340-2203-5933-8d0a-44a76f897740 | note | Verifying Document -
19524cc0-b37f-566a-9d50-1b5175815eda | note | Frequency -
0182f130-12bb-5631-8698-fff612e88aa7 | note | Inspection Type (Visual, other) -
6e67f99d-83c2-5dbb-b7e7-f26b57d27d9b | note | Inspection: Key - PM
07ae8ea7-800a-5e4d-8a81-099c8c1bd2b5 | note | Inspection: By (Role Key) - Downer
a2d9b633-d847-45bc-bc48-e8819a56cf7b | checkpoint | 4.3 - Washdown of equipment between used beach and site
a4644980-1ad7-5dce-86d7-128e2c193316 | note | Inspection Point: Quality Control Activity - Equipment repurposed for sandmining to be cleaned on contaminants
6cc6ad43-9e33-5827-b66b-1a964f4903c6 | note | Acceptance Criteria -
df2be8b8-b5b1-51a5-a639-7b3df859d0c8 | note | Verifying Document -
b1cd3678-7156-569d-8e9f-9a2f91b10920 | note | Frequency -
9e9c9756-7c33-5d73-a66b-97d2fb622dd3 | note | Inspection Type (Visual, other) -
f1211b8a-82e8-5fca-babd-030188a67be1 | note | Inspection: Key - PM
659c4605-6e1b-5a79-a89a-1ad2d53413d0 | note | Inspection: By (Role Key) - Downer
b5524ad7-d4de-4ae6-aa3e-024426f88c36 | checkpoint | 4.4 - Minimum 10 buffer established between MHWS and sand extraction area
1f5f5025-5277-58b2-8d6f-e167b5e62eca | note | Inspection Point: Quality Control Activity - Buffer confirmed
e1c768fd-1c3f-5695-bb1d-a219b6d8b2c4 | note | Acceptance Criteria -
4b36e10d-e2f1-5d67-878e-b63a783698b6 | note | Verifying Document -
3c9ca8fc-19a9-5688-998f-3c89a173bc08 | note | Frequency -
db173706-5e23-50c3-9dc4-3b24b8ec37c3 | note | Inspection Type (Visual, other) -
d5a7a0c0-3afd-5b38-878d-d604d0ed5b8c | note | Inspection: Key - PM
e3d115ae-c733-5899-a736-2988290909b4 | note | Inspection: By (Role Key) - Downer
441455b7-3aa4-4483-83df-d7093358ef29 | checkpoint | 4.5 - Haul Route demarcated and established in allignment with high tide mark.
8332b1c1-fd03-5e7d-a3dd-eb34ea4f194b | note | Inspection Point: Quality Control Activity - Haul route clearly delineated and confirmed to be in proper position
a550ea32-b41a-556b-8cf5-d0d96a920707 | note | Acceptance Criteria -
8b72c691-260e-55ee-bbd6-7a0fdf79a46c | note | Verifying Document -
d3d08016-c760-5e03-9824-42f700f02214 | note | Frequency -
9deb8960-84ae-570f-bb3b-7fec247ada76 | note | Inspection Type (Visual, other) -
f2138f58-251f-5403-9572-9b819e5c0956 | note | Inspection: Key - PM
e4bcb15a-c318-58e8-9743-de05bc43a1a6 | note | Inspection: By (Role Key) - Downer
1f47fe07-7414-42a3-90d0-dc1903382e38 | checkpoint | 4.6 - Sand deposited to create temporary bund adjacent to Stage 2B works.
422a6b67-cf25-57bd-969b-65bf621710b4 | note | Inspection Point: Quality Control Activity - Stockpiling target confirmed
00c07c5d-e641-5543-9c53-391aedddbca7 | note | Acceptance Criteria -
c9c375c1-5c5a-55f3-8749-cfc44cb64bab | note | Verifying Document -
5e8b021f-ade4-59ad-9b53-0046dbe936c1 | note | Frequency -
c0b0e779-eddb-543e-ba09-4360ce2098b4 | note | Inspection Type (Visual, other) -
8c46ad76-035c-50bf-bb71-c4b92d60aef2 | note | Inspection: Key - PM
1f5133d4-fce6-5013-907e-003b2e18b0c7 | note | Inspection: By (Role Key) - Downer
7a10b53f-bafd-4835-912f-c3b21066b09e | checkpoint | 4.7 - Site maintained in good order
6b84571b-66d0-5d6d-911b-699c4ff8fb6b | note | Inspection Point: Quality Control Activity - No construction materials shall be left in a position where they could be carried away by storms, floods, waves or other natural events; and All machinery, equipment, loose construction materials and surplus spoil shall be removed from the Coastal Marine Area at the completion of each day’s work and/or when the incoming tides dictates that work must be ceased.
8bd772df-78ae-5a1a-9e2b-a21ac192e8d1 | note | Acceptance Criteria -
2716bcc3-7bcd-571f-b5fe-e963ce98fa86 | note | Verifying Document -
2eb2687e-7ebd-5cd9-883a-3a504321f071 | note | Frequency -
cd89b640-80cc-50a2-aa41-ad06f1e2c2b1 | note | Inspection Type (Visual, other) -
74c34da6-d63e-58ef-9193-e7929d1592ce | note | Inspection: Key - PM
dc9e8868-677e-5ecb-9508-0c6fbba6ff32 | note | Inspection: By (Role Key) - Downer
4b631845-f327-4643-ac03-d3a17b8af4d6 | section | 5 - Zone B Excavation - Stage 2B
f7c778a7-4322-4bef-9b50-b6502a4be9d9 | checkpoint | 5.1 - Sufficient sand stockpiles for Stage 2B excavation to commence.
ccc16721-3591-5a32-8711-dedf56813a2f | note | Inspection Point: Quality Control Activity - Prior to works ensure sufficient sand is stockpiled.
d8d314f7-4b66-5a4d-a3e3-140d529bce52 | note | Acceptance Criteria -
195ce0d5-b0c7-50d8-97ee-b00c1c261ef7 | note | Verifying Document -
13cdd418-a532-5d40-af40-482f6ff7766e | note | Frequency -
d76d36cb-1409-5628-9cb9-4e6a5a71a662 | note | Inspection Type (Visual, other) -
fc3225de-31ca-5359-873a-3bb6fd2ad0a1 | note | Inspection: Key -
9853b3e6-afcd-5dc5-8849-e697669b852a | note | Inspection: By (Role Key) -
47961162-503b-498a-9902-d432753f8f24 | checkpoint | 5.2 - Confirmation of survey limits of excavation
d9b4cfc7-dcd6-5580-88c9-8845fac4e126 | note | Inspection Point: Quality Control Activity - Verify limits.
57b5d720-1735-5ba8-a6cf-9890c22326db | note | Acceptance Criteria -
8ac9e4d9-5a75-5d4f-84db-6da09b225095 | note | Verifying Document -
35d83468-37bb-5e58-83ce-3eb79d0581e2 | note | Frequency -
513017f1-67be-5645-8d19-974a931df61c | note | Inspection Type (Visual, other) -
20e548b1-2519-5eac-b67b-0da8dba6e90e | note | Inspection: Key -
2f3ab645-4c9c-5729-bff4-e9752f081605 | note | Inspection: By (Role Key) -
9b950358-3d58-485d-8a13-cc281e3b3c56 | checkpoint | 5.3 - Excavation confirmed not to be performed under Highest Astronomical Tide.
2c554eb2-c748-5513-b8d9-3dcf38e153b6 | note | Inspection Point: Quality Control Activity - Confirm excavation duration does not fall under HAT.
34142905-3716-596a-8c47-7dc06dd2e7c3 | note | Acceptance Criteria -
018658fc-81ad-5433-8c4b-535527e2438a | note | Verifying Document -
56797d3b-da6e-5467-b554-718dea7aedac | note | Frequency -
cc6dc736-963b-502a-a422-e4f00dd66454 | note | Inspection Type (Visual, other) -
cd6d6748-42b5-50dc-b0e6-2e4b87beeb7c | note | Inspection: Key -
1601db2d-9307-532d-84f5-a5b9e015f73e | note | Inspection: By (Role Key) -
f0f678d1-624c-4441-a6b1-9c64301a2342 | checkpoint | 5.4 - Final Excavation Level
74fc82b2-9f0d-58db-8a46-4d3ebd76d4f4 | note | Inspection Point: Quality Control Activity - Visual confirmation that visible sawdust is removed.
8493e780-439a-537e-a8ac-5dca801299a8 | note | Acceptance Criteria - No sawdust remaining in section of approval
d571dfc0-ff37-5199-952e-865c0235e22a | note | Verifying Document - Visual
dd1652e3-7d27-50fc-a08d-7abcb29105c5 | note | Frequency - Every 25m of the completed excavation on a 5m grid.
971946c6-536a-576d-b03e-718e7b174cfc | note | Inspection Type (Visual, other) - Inspection, Hold point
26d53151-6f2d-57ee-80be-db0fec65fb4d | note | Inspection: Key - CONTAM
85a2fe56-9771-5f00-8ed3-7b5187e5ef87 | note | Inspection: By (Role Key) - T+T
b7d8a0b5-e2d0-463c-b938-4f4a63c0598e | signoff | AUTHORITY HOLDPOINT
1113e14a-2739-4d2f-9ef3-23c3e3be257b | checkpoint | 5.5 - Final Excavation Level
13030127-76c2-581c-95ed-a2131cf43e48 | note | Inspection Point: Quality Control Activity - XRF Contamination Testing
6d5dc3a0-0ec4-58ca-9792-a512571c4060 | note | Acceptance Criteria - Excavation free of contaminants
6b456d77-d425-5801-a7e3-8848c04c12df | note | Verifying Document - Engineer approval
c99a8fdf-7be8-51e9-b30f-0a5187cb444d | note | Frequency - Every 25m of the completed excavation on a 5m grid.
392b3486-c51e-5548-a4f7-01a63af8e952 | note | Inspection Type (Visual, other) - Inspection, Hold point
c695f166-dadf-54b9-865c-b7e364e8ceb1 | note | Inspection: Key - ENG
492cd0eb-8867-58e2-8893-f95d50146b65 | note | Inspection: By (Role Key) - T+T
09c451db-fbae-4b3e-be1e-3aadc9d695d5 | signoff | AUTHORITY HOLDPOINT
bb2b6f35-7de1-47bc-9674-f5c41b056665 | section | 6 - Stage 2C
c6c27458-b6a5-4d7c-8db6-54183814faf2 | checkpoint | 6.1 - Stage 2B excavation and fill complete
bae04892-c12c-57cb-bc6a-eba84062c3e1 | note | Inspection Point: Quality Control Activity -
db3aebe7-33ab-5309-a72e-ec875671a3a6 | note | Acceptance Criteria -
44b454c3-19d6-5193-9d75-5e1af3523ab7 | note | Verifying Document -
bc267000-5f7a-514b-9e9d-c33995d328e4 | note | Frequency -
c39e9cfe-da39-565c-a57b-dedcd3cd0ef3 | note | Inspection Type (Visual, other) -
7614ae7a-4779-5cf1-8764-e9f80f93eeeb | note | Inspection: Key -
ded77dbb-3d2c-5e23-bba2-c34a8711f5f5 | note | Inspection: By (Role Key) -
a42e0f49-033a-4265-b987-42b534cf6807 | checkpoint | 6.2 - Exacavation to final level for all areas of Stage 2A and 2C.
35477040-b841-5782-b13a-242c9a0ccad8 | note | Inspection Point: Quality Control Activity - Survey confirmation.
036fb3d2-60fb-5e4f-a846-190b1305469e | note | Acceptance Criteria -
b014ddde-7654-5fa9-a36c-95d060ba7784 | note | Verifying Document -
4e69ce6e-42da-5e17-b2c3-a2cdd2ccbc13 | note | Frequency -
f631a7f7-5b37-5855-80ef-29716a6fc2a3 | note | Inspection Type (Visual, other) -
528cf809-b0b5-56b6-97d1-b3a5c7bc2dd0 | note | Inspection: Key -
60db15f1-bcc4-58bf-9089-a9fa0a61090b | note | Inspection: By (Role Key) -
7e072bc9-b4ac-4e61-9642-86ca08183904 | checkpoint | 6.3 - Final Excavation Level
78829f9b-c1f6-559a-81b6-c8aaf2d7fa65 | note | Inspection Point: Quality Control Activity - XRF Contamination Testing
c91d10d2-8c31-54c8-b103-55c5aa2b9efd | note | Acceptance Criteria - Excavation free of contaminants
f7a672f4-aa28-5296-bf4e-c91d627c3e3b | note | Verifying Document - Engineer approval
849c29ac-bd22-5592-9132-575ecb6154cd | note | Frequency - Every 25m of the completed excavation on a 5m grid.
47ca1b10-d4c4-5d67-917e-7443816094f7 | note | Inspection Type (Visual, other) - Inspection, Hold point
c7902f26-246b-5fb5-b405-c9c405f1744c | note | Inspection: Key - ENG
d1421cad-17ad-5d42-a55f-bfc8913ea559 | note | Inspection: By (Role Key) - T+T
58b34b3d-067b-4ea8-b946-06dd7285a952 | signoff | AUTHORITY HOLDPOINT
a86eb41a-3774-40a3-8081-942885d2d1c9 | checkpoint | 6.4 - Grading of site for subsequent reinstatment complete
0e0c0498-f83b-573f-90a6-c78d1f9fb3a0 | note | Inspection Point: Quality Control Activity - Grade prepared for enstatement of dune profile
f01df92c-9237-5caf-a83e-19118e51310f | note | Acceptance Criteria -
3a310d26-2e06-5ff9-9407-8efe5dae1b69 | note | Verifying Document -
5bf2d2d2-5037-5482-ac2b-b838aefdc72d | note | Frequency -
0f036262-21f4-55c5-83b2-4d3c6f9f0c00 | note | Inspection Type (Visual, other) -
89575b80-02c7-551d-a90a-a193cf121816 | note | Inspection: Key -
15c11db6-418c-5775-9f37-894da2e86ea8 | note | Inspection: By (Role Key) -
802e50cf-73eb-444b-b4f0-fbaf64e6171b | checkpoint | 6.5 - New fill/ Dune profile enstated.
9edb0bed-6425-5111-92f5-8498e6f70c4c | note | Inspection Point: Quality Control Activity - Dune system has been reinstated using sand excavated from sand mining site.
a34e9e46-fd92-56aa-b801-9ccbc16b835f | note | Acceptance Criteria - Dune system established per Contract drawings
4f2b2921-a8c9-5068-88b0-1d7f3ed8f23a | note | Verifying Document -
cc82d3c0-81a2-554c-ae3c-9dcc3e600950 | note | Frequency -
7bed936a-24ee-5b6f-bd8f-e4bdb8213004 | note | Inspection Type (Visual, other) -
e2f0f05b-bd6b-5232-9c69-fcd73e7986d1 | note | Inspection: Key -
4dbd9fac-e730-5ce4-9b04-b4429e150280 | note | Inspection: By (Role Key) -
a5a7d686-43cd-497f-8886-aa98c79c3996 | section | 7 - Carpark Construction
6399ab42-56b5-4f51-9fc9-10c36bd537ff | checkpoint | 7.1 - AP40 Compaction
38738b5a-fa03-5786-bb3b-bb8027c61ef8 | note | Inspection Point: Quality Control Activity - NDM Testing
6c52b5e1-d73f-54fc-824b-ea31d40430f6 | note | Acceptance Criteria - Mean Value ≥98%, Min Value ≥95%
a6f5ae24-3008-5720-bd50-cf81f4906339 | note | Verifying Document - Lab Report
a681fc5c-4367-537f-b562-eb7ca1f61134 | note | Frequency - 1 lot ( 5 tests)
ce0333fc-01b7-5242-a023-f9d2b541b994 | note | Inspection Type (Visual, other) - Testing
ef6cafc8-dd79-5b20-a709-b637d6b716ef | note | Inspection: Key - SUB
76e87561-2759-5a28-9736-056c518e7c13 | note | Inspection: By (Role Key) - Civil Engineering Labs
e7273d9a-0953-4af7-a1a6-aa8f1432d046 | checkpoint | 7.2 - AP40 Compaction
fcffc84f-5b15-573c-941d-8d03820249ee | note | Inspection Point: Quality Control Activity - Beam Testing
f1a4bc04-0ad1-5f11-8d52-01adfb5eccbd | note | Acceptance Criteria - Maximum Deflection 2.0mm
94a47d24-4862-5892-a47a-ffaab6056b4a | note | Verifying Document - Lab Report
863f7e73-9de3-5fc7-963a-56802c1d50a6 | note | Frequency - Every wheel track at 20m intervals
26081b15-b781-5d20-a2ce-bdf12bb18023 | note | Inspection Type (Visual, other) - Testing
ae04c002-7363-5b01-b728-43a978d2e67d | note | Inspection: Key - SUB
f64e75df-1c50-579d-b2a2-20b9d340999e | note | Inspection: By (Role Key) - Civil Engineering Labs
be609d67-9fde-4022-9ee4-d7a93616c123 | checkpoint | 7.3 - Survey and Set out of carkpark timber fence, concrete pad, and gravel extents.
53a65bd6-4349-5cdd-8eed-a37f7bd0f6f8 | note | Inspection Point: Quality Control Activity - Construction survey and site set out
672478e6-2057-536e-a0a8-4ad47cfb3cc7 | note | Acceptance Criteria - Set out follows provided coordinates
b3782b9f-bef1-5b84-b9c0-f17b9263050c | note | Verifying Document - Visual
d43251ce-1371-5186-9d6f-d311b7ef7862 | note | Frequency - During Construction
e5092f58-917d-5ce1-8373-1836ae2075eb | note | Inspection Type (Visual, other) - Inspection, Hold point
53f47e4f-e64a-5edf-88e9-6764a4517a9a | note | Inspection: Key - SV, ENG
5082e33b-e56c-51cc-b1cc-8fc4e2a94e78 | note | Inspection: By (Role Key) - Downer, T+T
ff639c13-9559-4859-93d1-fe9376da2118 | signoff | AUTHORITY HOLDPOINT
029f9240-edfa-4174-930b-664d8cbe61f7 | checkpoint | 7.4 - Waterworks
f6c2829f-78b7-50a1-bde8-cc6378702370 | note | Inspection Point: Quality Control Activity - Verify existing watermain is blanked off and installation of new tap for beach users on a 1.5m x 1.5m pad.
25492c0b-c5ca-5ab9-a3cb-96c9b9996a16 | note | Acceptance Criteria -
adcbec52-7892-560d-9ff3-85891e554906 | note | Verifying Document -
16d5c5c7-2bf0-524b-a489-166d41df78aa | note | Frequency - During Construction
75b6c43a-f105-5726-b841-361f3a256476 | note | Inspection Type (Visual, other) -
914b6791-915e-5e59-a870-c387a07004d7 | note | Inspection: Key - PM, ENG
d4d7b81d-3f78-51c2-ad02-df40dba7a23f | note | Inspection: By (Role Key) - Downer, T+T
9e44f8e9-ccdb-4eb1-a742-632ae2ce8710 | checkpoint | 7.5 - Reinstatement of existing post and rope fence around new gravel car park`
3618985c-17f4-5666-8a83-4f03de962e1c | note | Inspection Point: Quality Control Activity - Verify per Contract Drawings
9ef430ec-1675-5c6c-85af-00a48a381f2f | note | Acceptance Criteria - Per Contract Drawings
09d86f71-a163-593d-b3fc-fbdd191e8bd2 | note | Verifying Document -
60478638-7f8f-5bde-815b-125f94b04af5 | note | Frequency -
8e5dd083-0d1e-5960-97f9-91e815b1924f | note | Inspection Type (Visual, other) -
6db75ca8-1476-57a4-bbe9-4992b91dcb91 | note | Inspection: Key - PM, ENG
f7884318-050b-5f62-b543-be662d341b91 | note | Inspection: By (Role Key) - Downer, T+T
97d2f8a8-9a7c-49c2-9099-615fa13a159b | section | 8 - Miscellaneous and Finishing
bfe18144-fe78-4a08-9e97-48f8e8ca0922 | checkpoint | 8.1 - As-built Survey
577ac48a-0924-5953-930f-eff1fe8c5ce1 | note | Inspection Point: Quality Control Activity -
f2a298f7-78ca-5f8d-9528-f2db42206ef9 | note | Acceptance Criteria -
c10dd868-36da-5c58-8979-2958c18763a3 | note | Verifying Document -
a0f5964c-340d-560f-955e-9fd993aeef9d | note | Frequency - Upon Completion of Works
5886b25d-7210-5106-87eb-a2b6c0749014 | note | Inspection Type (Visual, other) -
c6717454-442e-5d51-ba1f-7f1b03bb6519 | note | Inspection: Key -
5a7f2674-86cf-53f8-bb8c-f53886e25a9a | note | Inspection: By (Role Key) - Downer
f112c228-5f7a-49c3-ac76-98a36027cb5b | checkpoint | 8.2 - Post Condition Assessment of existing infrastructure.
b8c794fe-a69d-5162-bcbb-690fceb7408d | note | Inspection Point: Quality Control Activity -
73eac9f2-f425-503b-a0c4-5b30f04fd8a4 | note | Acceptance Criteria -
a4fce978-4148-5690-8e35-bcf7c1eafb07 | note | Verifying Document -
6746c680-9765-51de-910d-3de125373510 | note | Frequency - Upon Completion of Works
096c13d3-d7b1-54a4-8d20-627f23dbb78d | note | Inspection Type (Visual, other) -
963ae0e3-0bd4-5bf7-9fb3-48f4d110bc8c | note | Inspection: Key -
266db0aa-dcf2-5a4d-b392-bc190fafbbbf | note | Inspection: By (Role Key) - Downer
d2596499-7416-4006-9d43-55cd16f5c16d | checkpoint | 8.3 - PC Walkover
2a2a4044-949d-590e-8b00-33bec6c48ebc | note | Inspection Point: Quality Control Activity -
32d196b8-075e-557f-a504-590b80592222 | note | Acceptance Criteria -
ea0003e0-a8c0-58d6-83ee-03482a3a2b51 | note | Verifying Document -
92b9b0fd-d13c-5229-b224-9adbb5775197 | note | Frequency - Upon Completion of Works
69a94996-e9e5-59e7-b094-6aeadbdea84c | note | Inspection Type (Visual, other) -
a71f040e-9803-53cb-bca8-de2de3c2ad4d | note | Inspection: Key - PM,ENG, Client Rep.
d701a13a-5b5e-54b7-95b6-cb412185987b | note | Inspection: By (Role Key) - Downer, T+T, NCC
3263d353-6fc9-4cc7-a941-39c49507479a | checkpoint | 8.4 - Ecological Clearance
ecd9408e-0f11-5940-9edc-dbb3264afe9c | note | Inspection Point: Quality Control Activity - Checks for lizards and penguins, Accidental discovery protocal
f291d511-9143-5d34-88b2-602ed2fae152 | note | Acceptance Criteria -
56a4bd6a-122a-532e-a7f4-a604267dd5e9 | note | Verifying Document -
0cf92185-806f-5784-9bc5-ebf6cb6e15b8 | note | Frequency - Daily,during construction
c640b45f-129b-5048-8af0-8c03735af6a4 | note | Inspection Type (Visual, other) -
b0d153cb-cdfc-51c5-af5c-b67aa3fc94c6 | note | Inspection: Key - PM,ECO
7754692d-0449-59ea-8e5b-8b94d34f9d6e | note | Inspection: By (Role Key) - Downer, T+T
f01049da-e5d9-493d-91ab-6ed46842a5c4 | checkpoint | 8.5 - Boundary Fencing
cea5a69a-8821-5b30-a402-15d3b2fd4c68 | note | Inspection Point: Quality Control Activity - Check temporary fences
041a69f6-edd3-5390-87cb-333f48bad7e4 | note | Acceptance Criteria -
18437178-4c7c-590a-8535-1a147742322a | note | Verifying Document -
7ce0a017-5f34-5bc8-b2f3-4ca446fa5f76 | note | Frequency - Daily,during construction
2725b334-81ac-5429-981e-610b913eac5e | note | Inspection Type (Visual, other) -
18aa176a-751a-5c6f-8c72-6ffeb21596d3 | note | Inspection: Key -
476c305c-1650-5d5b-abfb-5835059ed44a | note | Inspection: By (Role Key) -
3ec5bcc9-6eb5-40cd-a424-59dae4f726d6 | checkpoint | 8.6 - Topsoil and grass sowing
ea20551c-66ce-57e8-adb3-92f5fa8feb6c | note | Inspection Point: Quality Control Activity - Verify topsoil placement and grass sowing
6db577b7-954d-510d-93b0-e54731d1fea9 | note | Acceptance Criteria - Topsoil measured to a consolidated layer of 100mm. Designated areas have been grass seeded and fertilised.
f7175c6c-d41b-5fce-a782-023f0fffb835 | note | Verifying Document -
c2c78b48-06dd-5deb-b710-75eba245e7c8 | note | Frequency - During Construction
f7e8a96e-e27c-5547-8e5a-1b355827974f | note | Inspection Type (Visual, other) -
e548ebe7-dd2c-57c4-b742-ede3334efd72 | note | Inspection: Key -
40a28dae-9467-5711-9688-97e477573bb7 | note | Inspection: By (Role Key) -
8da5274c-bd8f-42e5-9d99-cc882825d414 | checkpoint | 8.7 - Grass strike
fb5bc878-aec0-540c-971f-b2758ab204cf | note | Inspection Point: Quality Control Activity - Verify grass seed has struck
4f381f31-e00c-5e68-bbc0-f69aa3df8429 | note | Acceptance Criteria - Presence of grass.
df57c41d-2b83-57ba-910f-4ccc1fc65859 | note | Verifying Document -
55e48bd2-839f-563c-8f4f-a085505ce2af | note | Frequency - Post Construction
80d7fa62-91c4-5910-b980-5d46c19fd76a | note | Inspection Type (Visual, other) -
aaa9ccb9-5d1d-5b59-a22f-230b4586a578 | note | Inspection: Key -
ce5e1eb4-4910-554f-af3a-f3a338b86937 | note | Inspection: By (Role Key) -
dc9f706b-9c0a-49d0-a0fc-d7e03e693ee0 | checkpoint | 8.8 - Geofabric installation
a92b4cb1-e017-56e3-b669-ab20ad1590a8 | note | Inspection Point: Quality Control Activity - Verify placement of BIDIM A12, Terram 2000, or similar to bottom of subbase layer.
a0108147-4cd9-5ee6-8bfb-7cfc54aaa2f3 | note | Acceptance Criteria -
d250d213-e83e-56ea-b9d3-e3244a1eab5e | note | Verifying Document -
51c7b322-6e4e-51eb-a0bd-93fe9567a8f4 | note | Frequency - During Construction
65502e73-4f0b-5284-810d-9963fb217502 | note | Inspection Type (Visual, other) -
ed3d38a9-0a7e-59d9-8fd5-00df57f045ed | note | Inspection: Key -
46d14628-0fc6-59f6-ae3f-49e80867b4e1 | note | Inspection: By (Role Key) -
e50a4e9c-7690-4228-a247-218cc413ba24 | checkpoint | 8.9 - Sand bund protection during construction
076d9ef9-0440-57e3-a332-78457c0cedc1 | note | Inspection Point: Quality Control Activity - Confirm existing sand bund protection on each frontage for duration of works
2962412d-b42b-5454-86fe-207204c89938 | note | Acceptance Criteria -
b039bc62-302d-59f9-892e-635c194af85b | note | Verifying Document -
64498029-c33c-556c-8910-bb79cd6c4c6a | note | Frequency - Daily,during construction
8d7541ea-c246-5d4b-8b68-2afb3df3f967 | note | Inspection Type (Visual, other) -
613864fa-4b1b-5198-8fe2-ff7e026470ff | note | Inspection: Key -
0ad0ba10-e34a-5965-8f67-fae21d69abab | note | Inspection: By (Role Key) -
c3e6cf5a-6a33-47c2-8ac7-6cba55c45951 | checkpoint | 8.10. - Dust control
f4f5dd23-e79c-51f0-a9c1-a14aad91313c | note | Inspection Point: Quality Control Activity - Dust control measures in place and assessments performed to prevent airborne dispersion
b5aeb227-23fe-5e0e-a83b-e266f6b790eb | note | Acceptance Criteria -
21657435-688e-51ed-8672-32b336689454 | note | Verifying Document -
6ed943ce-209d-5b04-8cbf-6b3698981edc | note | Frequency - Daily,during construction
68af5f3a-2cd4-514a-a0e8-0a8f1368b64d | note | Inspection Type (Visual, other) -
e0d4a1e4-1981-5508-983a-e60445668733 | note | Inspection: Key -
dbe35a1f-3fe7-5bf1-bac4-a4fe35b43040 | note | Inspection: By (Role Key) -
67a24def-04c5-4ad6-861d-b43d194ce699 | checkpoint | 8.11 - Dust control
0a3ccde6-2878-5f5d-8f88-fc07609bec18 | note | Inspection Point: Quality Control Activity - Exposed areas covered with appropriate geotextile or polythene, secured adequately against the weather if they are unattended for extended periods
f355683b-8874-53e5-a9c7-7ea379cfcd7c | note | Acceptance Criteria -
8e026f4a-c233-57d8-ac8f-fcc729ca4004 | note | Verifying Document -
1c850b80-191b-5e96-874d-1bc141d735ff | note | Frequency - Daily,during construction
5af34b9a-328e-54bc-8652-d091990adc48 | note | Inspection Type (Visual, other) -
b2998780-4bf0-5ec1-a706-502d142418ed | note | Inspection: Key -
2a6caac4-1c08-5331-9afc-fda7115e9a3b | note | Inspection: By (Role Key) -
1710a645-1e8f-4fb6-bc46-b9b821b7f19d | checkpoint | 8.12 - Stockpiling
b0bdccfb-28ac-50a8-b253-e3d6e3e5ff0a | note | Inspection Point: Quality Control Activity - Waste material shall be excavated directly to truck or from excavator to loader to truck. Where temporary stockpiling is required, stockpiles shall be formed on impermeable sheeting. Ideally stockpiles shall not be left overnight, but where this is not possible, stockpiles shall be covered with impermeable sheeting that is secured against wind.
5768f60f-ffe4-522f-a210-27a246df7332 | note | Acceptance Criteria -
81996037-c70d-55cd-b0a6-484f058bf75a | note | Verifying Document -
092a2848-b017-5ced-afcb-1bdab13354a5 | note | Frequency - Daily,during construction
1df4ae86-6d64-5757-a336-a792753461fb | note | Inspection Type (Visual, other) -
df020048-73c8-5593-b1b0-0ed5d9bce008 | note | Inspection: Key -
860672cd-b33e-582a-9428-b7c79d59aa87 | note | Inspection: By (Role Key) -
a4f6b69a-44f6-4a3e-989d-be4b36d1a8a8 | checkpoint | 8.13 - Equipment Decontamination
b7e9221f-3045-5984-9ed1-b9d946870613 | note | Inspection Point: Quality Control Activity - Any equipment coming into contact with contaminated sawdust/sand within the remediation area shall be decontaminated in a designated wash area prior to leaving the site.
acdc1fd1-63b2-5820-b163-5f330d91fc69 | note | Acceptance Criteria -
33b7354c-2713-55e4-a767-ab2b9d8eb7da | note | Verifying Document -
60f85bb6-10b6-5d76-8d24-f0e5b3997812 | note | Frequency - Upon Completion of Works/ between transferring equipment form site to adjacent work areas.
bf74fd2d-c232-52e5-b18d-dca9aa381efa | note | Inspection Type (Visual, other) -
8d43067c-00c1-5097-a489-70ca77989f57 | note | Inspection: Key -
ae4dfec5-1435-5e12-8e3c-d4b24a1d0163 | note | Inspection: By (Role Key) -
ab38337e-ba7a-4305-ada8-bb8322e7ba73 | checkpoint | 8.14 - Offsite transport
64df89b7-befa-55a8-8ce6-673b6c3b7681 | note | Inspection Point: Quality Control Activity - Trucks transporting sawdust or sand offsite shall be decontaminated prior to leaving site (refer Section 5.4.7), shall be free of debris prior to leaving site, and there shall be no tracking of material onto roads or footpaths.
98a75bd6-da46-55f3-8a87-b8984ae21796 | note | Acceptance Criteria -
4f1674b9-fdfc-580c-8366-d6ba885734e4 | note | Verifying Document -
97d09fcb-1f8e-5fe2-8196-38485cb533f6 | note | Frequency - Daily,during construction
8d9caec8-145b-58eb-85b8-43a5894701c6 | note | Inspection Type (Visual, other) -
77d639fa-577a-509b-b144-6ae298118b6a | note | Inspection: Key -
3ead7e5d-33c2-5913-87cf-2e6de1f5d782 | note | Inspection: By (Role Key) -
a963d59b-8128-4d61-b4a0-aed65606d391 | checkpoint | 8.15 - Offsite transport
d298e77e-21d6-59da-89b4-b5950bbea50e | note | Inspection Point: Quality Control Activity - Loads are covered prior to leaving site.
f0f3196b-3d61-5c83-92b7-e4cb280c205a | note | Acceptance Criteria -
b78faad6-5276-5a3f-964b-5ec71c0041a0 | note | Verifying Document -
3b85bd4a-f697-5368-a14c-558e3cae2d6f | note | Frequency - Daily,during construction
f7679387-090b-5f7f-bd36-706259a7d194 | note | Inspection Type (Visual, other) -
4ac44cb2-bc78-5787-9a6f-6f24de26b3e2 | note | Inspection: Key -
73f88943-5507-52f6-8525-b9a6aae24fd6 | note | Inspection: By (Role Key) -
fe1f305b-7199-4615-a867-275ff0ffb410 | checkpoint | 8.16 - Offsite transport Load Tracking
573a48f1-ac99-5175-907c-e254addd4b66 | note | Inspection Point: Quality Control Activity - Details of each load removed from site are recorded onsite to enable reconciliation against the disposal site weighbridge documentation.
32bebbb0-2dba-54ee-9670-ed40757d3488 | note | Acceptance Criteria -
49c5ffe9-ebe3-5910-80c0-8803c3aa16c3 | note | Verifying Document -
5be4f3a0-e450-5512-b926-b1329ad37d4d | note | Frequency - Daily,during construction
b2dad37b-241e-5303-a88e-960a78788266 | note | Inspection Type (Visual, other) -
771efabc-9add-5888-956c-9e7253589b22 | note | Inspection: Key -
4a5ea194-696d-598f-8f20-8b2d9f187db7 | note | Inspection: By (Role Key) -
e16741c8-2f2a-45c8-9559-89ca0fe5daf5 | checkpoint | 8.17 - Unexpected Contamination
6170cec6-f416-5f9b-823c-df92102a4ce6 | note | Inspection Point: Quality Control Activity - Advise NCC and SQEP immedialty should evidence of unexpected contaminated be encountered during the works on site.
3bc96eba-c1c7-508d-9f51-d4732c6b0824 | note | Acceptance Criteria -
22a65ca1-ec99-5a8e-ac5e-04376d9c7dfe | note | Verifying Document -
dcff8f04-6081-5bac-9743-3ebb60fafec4 | note | Frequency - Daily,during construction
cef4f33e-8e41-5a55-8f83-a3a950a881c5 | note | Inspection Type (Visual, other) -
f6abb39b-0dcc-5543-8449-706b05e59381 | note | Inspection: Key -
02641b6c-2dea-511d-ac49-444148361a85 | note | Inspection: By (Role Key) -