## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL DETAILS
Project Name: | Tahunanui Back Beach Remediation |  |  |  |  | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | To be confirmed |  |  |  |  | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Nelson City Council |  |  |  |  | B | Report by Breach | CM | Construction Manager | Wayne Oldfield | WO
Contract Number: | 151991 |  |  |  |  | C | Check | NCC | Nelson City Council | Ajith Rajmohan | AR
Area/ Sub-System: |  |  | Lot ID Number: |  |  | D | Dimension Inspection | SUB | Subcontractor | Nelmac | NM
[6 empty] | E | Examine |  | Subcontractor | Civil Engineering Labs | CELS
ITP Number: | 1 |  | Version: | 1 |  | H | Hold Point | CE | Civil Engineering Cadet | Tyler Peppin | TP
ITP Description: | Inspection and Test Plan for the Tahunanui Back Beach Remediation. |  |  |  |  | I | Inspection | PM | Project Manager | Jaco van Noordwyk | JVN
Discipline: | Civil Construction, Earthworks. |  |  |  |  | M | Monitor on Random Basis | PS | Project Supervisor | Lawrence McCarthy | LM
Specification: | [5 empty] | O | Operation | SV | Surveyor | Mark Frost | MF
[6 empty] | R | Review | ENG | Engineer | Tonkin + Taylor | T+T
Drawings: | 1006675.5130-00 - 10 |  |  |  |  | S | Subcontractor | STMS | STMS | Downer | /
[6 empty] | V | Visual Verification
Prepared By: (Name) | Tyler Peppin |  | Date: | 2024-09-09 |  | W | Witness Point
Quality Specified:
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
1.1 | Pre Construction
1.2 | Vegetation Clearance | Removal of trees, and other plants within the area of works | Trees and plants removed in the area of works | Visual | Pre Construction | Operation, Hold point | SUB | Nelmac
1.3 | Ecological Clearance | Pre-clearance surveys for nesting birds, implimentation of Lizard Management Plan and accidental discovery protocals for lizards and birds. |  | Visual | Pre Construction |  | SV, ECO | Downer, T+T
1.4 | Traffic Management | Implementation of Traffic Management | Traffic Management set up in accordance with approved TMP | Visual | Constant monitoring | Visual verification, Hold point | STMS | Downer
1.5 | Service Location and Clearance | Service locations complete |  | Locator record of confirmation | Pre Construction | Inspection, Hold point | PM, ENG | Downer
1.6 | Survey and Set out | Pre construction survey and site set out | Set out follows provided coordinates | Visual | Pre Construction | Inspection, Hold point | SV, ENG | Downer, T+T
1.7 | Equipment Free of Contamination | Any equipment coming onto the site shall be washed and cleaned of visible dirt prior to entering the site to manage potential biosecurity risks. Washdown area has been established on site.
2 | Stage 1
2.1 | Removal of carpark gravel and placement of new benched haul road area and capping layer to protect exposed contaminated material. | Confirm protecting capping layer placed.
2.2 | Excavation has reached the proposed first cut level. | Confirm extents of excavation
3 | Zone A Excavation - Stage 2A
3.1 | Confirmation of survey limits of excavation
3.2 | Final Excavation Level | Visual confirmation that visible sawdust is removed. | No sawdust remaining in section of approval | Visual | Every 25m of the completed excavation on a 5m grid. | Inspection, Hold point | CONTAM | T+T
3.3 | Final Excavation Level | XRF Contamination Testing | Excavation free of contaminants | Engineer approval | Every 25m of the completed excavation on a 5m grid. | Inspection, Hold point | ENG | T+T
4 | Sand Mining
4.1 | Ecological Clearance | Ecologist to assess for any active nests above MHWS during peak bird breeding season. |  |  |  |  | PM, ECO | T+T
4.2 | Limits of excavation established | Area marked out |  |  |  |  | PM | Downer
4.3 | Washdown of equipment between used beach and site | Equipment repurposed for sandmining to be cleaned on contaminants |  |  |  |  | PM | Downer
4.4 | Minimum 10 buffer established between MHWS and sand extraction area | Buffer confirmed |  |  |  |  | PM | Downer
4.5 | Haul Route demarcated and established in allignment with high tide mark. | Haul route clearly delineated and confirmed to be in proper position |  |  |  |  | PM | Downer
4.6 | Sand deposited to create temporary bund adjacent to Stage 2B works. | Stockpiling target confirmed |  |  |  |  | PM | Downer
4.7 | Site maintained in good order | No construction materials shall be left in a position where they could be carried away by storms, floods, waves or other natural events; and All machinery, equipment, loose construction materials and surplus spoil shall be removed from the Coastal Marine Area at the completion of each day’s work and/or when the incoming tides dictates that work must be ceased. |  |  |  |  | PM | Downer
5 | Zone B Excavation - Stage 2B
5.1 | Sufficient sand stockpiles for Stage 2B excavation to commence. | Prior to works ensure sufficient sand is stockpiled.
5.2 | Confirmation of survey limits of excavation | Verify limits.
5.3 | Excavation confirmed not to be performed under Highest Astronomical Tide. | Confirm excavation duration does not fall under HAT.
5.4 | Final Excavation Level | Visual confirmation that visible sawdust is removed. | No sawdust remaining in section of approval | Visual | Every 25m of the completed excavation on a 5m grid. | Inspection, Hold point | CONTAM | T+T
5.5 | Final Excavation Level | XRF Contamination Testing | Excavation free of contaminants | Engineer approval | Every 25m of the completed excavation on a 5m grid. | Inspection, Hold point | ENG | T+T
6 | Stage 2C
6.1 | Stage 2B excavation and fill complete
6.2 | Exacavation to final level for all areas of Stage 2A and 2C. | Survey confirmation.
6.3 | Final Excavation Level | XRF Contamination Testing | Excavation free of contaminants | Engineer approval | Every 25m of the completed excavation on a 5m grid. | Inspection, Hold point | ENG | T+T
6.4 | Grading of site for subsequent reinstatment complete | Grade prepared for enstatement of dune profile
6.5 | New fill/ Dune profile enstated. | Dune system has been reinstated using sand excavated from sand mining site. | Dune system established per Contract drawings
7 | Carpark Construction
7.1 | AP40 Compaction | NDM Testing | Mean Value ≥98%, Min Value ≥95% | Lab Report | 1 lot ( 5 tests) | Testing | SUB | Civil Engineering Labs
7.2 | AP40 Compaction | Beam Testing | Maximum Deflection 2.0mm | Lab Report | Every wheel track at 20m intervals | Testing | SUB | Civil Engineering Labs
7.3 | Survey and Set out of carkpark timber fence, concrete pad, and gravel extents. | Construction survey and site set out | Set out follows provided coordinates | Visual | During Construction | Inspection, Hold point | SV, ENG | Downer, T+T
7.4 | Waterworks | Verify existing watermain is blanked off and installation of new tap for beach users on a 1.5m x 1.5m pad. |  |  | During Construction |  | PM, ENG | Downer, T+T
7.5 | Reinstatement of existing post and rope fence around new gravel car park` | Verify per Contract Drawings | Per Contract Drawings |  |  |  | PM, ENG | Downer, T+T
8 | Miscellaneous and Finishing
8.1 | As-built Survey |  |  |  | Upon Completion of Works |  |  | Downer
8.2 | Post Condition Assessment of existing infrastructure. |  |  |  | Upon Completion of Works |  |  | Downer
8.3 | PC Walkover |  |  |  | Upon Completion of Works |  | PM,ENG, Client Rep. | Downer, T+T, NCC
8.4 | Ecological Clearance | Checks for lizards and penguins, Accidental discovery protocal |  |  | Daily,during construction |  | PM,ECO | Downer, T+T
8.5 | Boundary Fencing | Check temporary fences |  |  | Daily,during construction
8.6 | Topsoil and grass sowing | Verify topsoil placement and grass sowing | Topsoil measured to a consolidated layer of 100mm. Designated areas have been grass seeded and fertilised. |  | During Construction
8.7 | Grass strike | Verify grass seed has struck | Presence of grass. |  | Post Construction
8.8 | Geofabric installation | Verify placement of BIDIM A12, Terram 2000, or similar to bottom of subbase layer. |  |  | During Construction
8.9 | Sand bund protection during construction | Confirm existing sand bund protection on each frontage for duration of works |  |  | Daily,during construction
8.10. | Dust control | Dust control measures in place and assessments performed to prevent airborne dispersion |  |  | Daily,during construction
8.11 | Dust control | Exposed areas covered with appropriate geotextile or polythene, secured adequately against the weather if they are unattended for extended periods |  |  | Daily,during construction
8.12 | Stockpiling | Waste material shall be excavated directly to truck or from excavator to loader to truck. Where temporary stockpiling is required, stockpiles shall be formed on impermeable sheeting. Ideally stockpiles shall not be left overnight, but where this is not possible, stockpiles shall be covered with impermeable sheeting that is secured against wind. |  |  | Daily,during construction
8.13 | Equipment Decontamination | Any equipment coming into contact with contaminated sawdust/sand within the remediation area shall be decontaminated in a designated wash area prior to leaving the site. |  |  | Upon Completion of Works/ between transferring equipment form site to adjacent work areas.
8.14 | Offsite transport | Trucks transporting sawdust or sand offsite shall be decontaminated prior to leaving site (refer Section 5.4.7), shall be free of debris prior to leaving site, and there shall be no tracking of material onto roads or footpaths. |  |  | Daily,during construction
8.15 | Offsite transport | Loads are covered prior to leaving site. |  |  | Daily,during construction
8.16 | Offsite transport Load Tracking | Details of each load removed from site are recorded onsite to enable reconciliation against the disposal site weighbridge documentation. |  |  | Daily,during construction
8.17 | Unexpected Contamination | Advise NCC and SQEP immedialty should evidence of unexpected contaminated be encountered during the works on site. |  |  | Daily,during construction
Note on A8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add item for service clearance.
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Make consistent with revised methodology. Is this Stage 2a?
Note on B14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Make consistent with revised methodology. Is this Stage 2a?
Note on B18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Make consistent with revised methodology. Is this Stage 2b?
Note on B26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Make consistent with revised methodology. Is this Stage 2b?
Note on B32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Make consistent with revised methodology. Is this Stage 2b?

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
4.1
4.2
4.3
4.4
4.5
4.6
4.7
4.8
4.9
4.10

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
5.1
5.2
5.3
5.4
5.5
5.6
5.7
5.8
5.9
5.10
SECTION 6 – COMMENTS
|  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: