## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL DETAILS
Project Name: | Tahunanui Back Beach Remediation |  |  |  |  | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | To be confirmed |  |  |  |  | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Nelson City Council |  |  |  |  | B | Report by Breach | CM | Construction Manager | Wayne Oldfield | WO
Contract Number: | 151991 |  |  |  |  | C | Check | NCC | Nelson City Council | Ajith Rajmohan | AR
Area/ Sub-System: |  |  | Lot ID Number: |  |  | D | Dimension Inspection | SUB | Subcontractor | Nelmac | NM
[6 empty] | E | Examine |  | Subcontractor | Civil Engineering Labs | CELS
ITP Number: | 1 |  | Version: | 1 |  | H | Hold Point | CE | Civil Engineering Cadet | Tyler Peppin | TP
ITP Description: | Inspection and Test Plan for the Tahunanui Back Beach Remediation. |  |  |  |  | I | Inspection | PM | Project Manager | Jaco van Noordwyk | JVN
Discipline: | Civil Construction, Earthworks. |  |  |  |  | M | Monitor on Random Basis | PS | Project Supervisor | Lawrence McCarthy | LM
Specification: | [5 empty] | O | Operation | SV | Surveyor | Mark Frost | MF
[6 empty] | R | Review | ENG | Engineer | Tonkin + Taylor | T+T
Drawings: | 1006675.5130-00 - 10 |  |  |  |  | S | Subcontractor | STMS | STMS | Downer | /
[6 empty] | V | Visual Verification | FORE | Foreman | Downer
Prepared By: (Name) | Tyler Peppin |  | Date: | 2024-09-09 |  | W | Witness Point
Quality Specified:
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
1.1 | Pre Construction
1.2 | Vegetation Clearance | Removal of trees, and other plants within the area of works | Trees and plants removed in the area of works | Ecologist approval | Pre Construction | Visual, Hold point | SUB | Nelmac
1.3 | Ecological Clearance | Pre-clearance surveys for nesting birds, implimentation of Lizard Management Plan and accidental discovery protocals for lizards and birds. | Area has been demmed cleared of nesting birds and lizards | Ecologist approval | Pre Construction | Visual, Hold point | ECO | T+T
1.4 | Traffic Management | Implementation of Traffic Management | Traffic Management set up in accordance with approved TMP | Written confirmation from Eng Rep | Constant monitoring | Visual verification, Hold point | STMS, ENG | Downer, T+T
1.5 | Service Location and Clearance | Service locations complete | Services have been identified, approved controls are in place | Locator record of confirmation | Pre Construction | Inspection, Hold point | CE, ENG | Downer
1.6 | Survey and Set out | Pre construction survey and site set out | Set out follows provided coordinates | Written Confirmation | Pre Construction | Inspection, Hold point | CE, SV, ENG | Downer, T+T
1.7 | Equipment Free of Contamination | Any equipment coming onto the site shall be washed and cleaned of visible dirt prior to entering the site to manage potential biosecurity risks. Washdown area has been established on site. | No visible dirt, leaks, contamination | None | Before Works | Visual | PS | Downer
2 | Stage 1
2.1 | Ecological Clearance | Ecologist to assess for any active nests above MHWS during peak bird breeding season. | Area is clear of any active nests | Ecologist approval | Before Works | Confirmation | ECO | T+T
2.2 | Removal of carpark gravel and placement of new benched haul road area and capping layer to protect exposed contaminated material. | Confirm protecting capping layer placed. | Contaminated materials covered by capping layer | None | During Construction | Visual, Action | FORE | Downer
2.3 | Excavation has reached the proposed first cut level. | Confirm extents of excavation | Survey check with excavator | None | During Construction | Visual, Check with GPS | FORE | Downer
3 | Zone A Excavation - Stage 2A
3.1 | Confirmation of survey limits of excavation | Confirm extents of excavation | Survey check | Survey asbuilts | During Construction | Hold points | CE, SV | Downer
3.2 | Final Excavation Level | Visual confirmation that visible sawdust is removed. | No sawdust remaining in section of approval | SQEP approval | Every 25m of the completed excavation on a 5m grid. | Inspection, Hold point | SQEP | T+T
3.3 | Final Excavation Level | XRF Contamination Testing | Excavation free of contaminants | SQEP approval | Every 25m of the completed excavation on a 5m grid. | Inspection, Hold point | SQEP | T+T
4 | Sand Mining
4.1 | Ecological Clearance | Ecologist to assess for any active nests above MHWS during peak bird breeding season. | Area is clear of any active nests | Ecologist approval | Before Sand Mining | Confirmation | ECO | T+T
4.2 | Limits of excavation established | Limits of excavations marked out for sand mining | Survey check | None | During Construction | Visual, Check with GPS | CE, SV | Downer
4.3 | Washdown of equipment between used beach and site | Equipment repurposed for sandmining to be cleaned on contaminants | Equipment used for sand mining cleaned prior to works | None | Every Disestablishment | Action | PS | Downer
4.4 | Minimum 10 buffer established between MHWS and sand extraction area | Buffer confirmed | Survey check | None | During Construction | Action | FORE | Downer
4.5 | Haul Route demarcated and established in allignment with high tide mark. | Haul route clearly delineated and confirmed to be in proper position | Markers placed a long the haul route | None | Before Sand Mining | Confirmation | FORE | Downer
4.6 | Sand deposited to create temporary bund adjacent to Stage 2B works. | Stockpiling target confirmed | Survey check w/ volume | None | During Construction | Confirmation | FORE, CE, SV | Downer
4.7 | Site maintained in good order | No construction materials shall be left in a position where they could be carried away by storms, floods, waves or other natural events; and All machinery, equipment, loose construction materials and surplus spoil shall be removed from the Coastal Marine Area at the completion of each day’s work and/or when the incoming tides dictates that work must be ceased. | No loose construction debris present | None | Each Day | Confirmation | FORE | Downer
5 | Zone B Excavation - Stage 2B
5.1 | Sufficient sand stockpiles for Stage 2B excavation to commence. | Prior to works ensure sufficient sand is stockpiled. | Survey check for volume | None | Before Works | Confirmation | FORE, CE, SV | Downer
5.2 | Confirmation of survey limits of excavation | Confirm extents of excavation | Survey check | Survey asbuilts | During Construction | Hold point | FORE, ENG, CE, SV | Downer, T+T
5.3 | Excavation confirmed not to be performed under Highest Astronomical Tide. | Confirm excavation duration does not fall under HAT. | Site Eng to provide confirmation that works do not fall under HAT | Written | During Construction | Confirmation | CE | Downer
5.4 | Final Excavation Level | Visual confirmation that visible sawdust is removed. | No sawdust remaining in section of approval | SQEP approval | Every 25m of the completed excavation on a 5m grid. | Inspection, Hold point | SQEP | T+T
5.5 | Final Excavation Level | XRF Contamination Testing | Excavation free of contaminants | SQEP approval | Every 25m of the completed excavation on a 5m grid. | Inspection, Hold point | SQEP | T+T
6 | Stage 2C
6.1 | Stage 2B excavation and fill complete | Completion of activity / stage | Survey check with excavator | None | Before Works | Confirmation | FORE | Downer
6.2 | Excavation to final level for all areas of Stage 2A and 2C. | Survey confirmation. | Survey check with excavator | None | During Construction | Visual, Check with GPS | FORE, ENG | Downer, T+T
6.3 | Final Excavation Level | XRF Contamination Testing | Excavation free of contaminants | SQEP approval | Every 25m of the completed excavation on a 5m grid. | Inspection, Hold point | SQEP | T+T
6.4 | Grading of site for subsequent reinstatment complete | Grade prepared for enstatement of dune profile | Survey check | None | During Construction | Action | FORE | Downer
6.5 | New fill/ Dune profile enstated. | Dune system has been reinstated using sand excavated from sand mining site. | Meets IFC Design | As-builts | During Construction | Hold point | FORE, CE, SV | Downer
7 | Carpark Construction
7.1 | AP40 Compaction | NDM Testing | Mean Value ≥98%, Min Value ≥95% | Lab Report | 1 lot ( 5 tests) | Testing | SUB | Civil Engineering Labs
7.2 | AP40 Compaction | Beam Testing | Maximum Deflection 2.0mm | Lab Report | Every wheel track at 20m intervals | Testing | SUB | Civil Engineering Labs
7.3 | Survey and Set out of carkpark timber fence, concrete pad, and gravel extents. | Construction survey and site set out | Set out follows provided coordinates, meets IFC design | Survey asbuilts | During Construction | Inspection, Hold point | SV, ENG, CE | Downer, T+T
7.4 | Waterworks | Verify existing watermain is blanked off and installation of new tap for beach users on a 1.5m x 1.5m pad. | meets IFC design | As-builts | During Construction | Hold point | PM, ENG, CE | Downer, T+T
7.5 | Reinstatement of existing post and rope fence around new gravel car park` | Verify per Contract Drawings | Per IFC Design | As-builts | During Construction | Action | PM, ENG, CE | Downer, T+T
8 | Miscellaneous and Finishing
8.1 | As-built Survey | Summary asbuilts of contractor works | conforms to IFC design and engineer approvals | Surmmary as-built report and redline drawings | Upon Completion of Works | Action | SV, CE | Downer
8.2 | Post Condition Assessment of existing infrastructure. | Summary provided to client for consideration of acceptance | Client acceptance | Video log / report | Upon Completion of Works | Inspection | CE | Downer
8.3 | Practical Completion Walkover | Walkover with Eng, Client and Contractor | Contract works agreed to be practically complete with construction defects noted. | Construction defects list, PC Cert | Upon Completion of Works | Inspection | PM,ENG, Client Rep. | Downer, T+T, NCC
8.5 | All Site Fencing | Check temporary fences | Daily confirmation safety fences are continuous and per the approrved TMP. Ecological fences are continous and free of damages and gaps | Photos, written record of completion | Twice daily during construction | Inspection | STMS | Downer
8.6 | Topsoil and grass sowing | Verify topsoil placement and grass sowing | Topsoil measured to a consolidated layer of 100mm. Designated areas have been grass seeded and fertilised. | None | During Construction | Inspection | FORE | Downer
8.7 | Grass strike | Verify grass seed has struck | Presence of grass. | None | Post Construction | Inspection | PS | Downer
8.8 | Geofabric installation | Verify placement of BIDIM A12, Terram 2000, or similar to bottom of subbase layer. | Per IFC Design | None | During Construction | Inspection | FORE | Downer
8.9 | Sand bund protection during construction | Confirm existing sand bund protection on each frontage for duration of works | Per methodology | None | Daily,during construction | Inspection | FORE | Downer
8.10. | Dust control | Dust control measures in place and assessments performed to prevent airborne dispersion | Per RAP | None | Daily,during construction | Hold point | FORE, ENG | Downer, T+T
8.11 | Dust control | Exposed areas covered with appropriate geotextile or polythene, secured adequately against the weather if they are unattended for extended periods | Per Rap | None | Daily,during construction | Inspection | FORE | Downer
8.12 | Stockpiling | Waste material shall be excavated directly to truck or from excavator to loader to truck. Where temporary stockpiling is required, stockpiles shall be formed on impermeable sheeting. Ideally stockpiles shall not be left overnight, but where this is not possible, stockpiles shall be covered with impermeable sheeting that is secured against wind. | Per RAP | None | Daily,during construction | Inspection | FORE | Downer
8.13 | Equipment Decontamination | Any equipment coming into contact with contaminated sawdust/sand within the remediation area shall be decontaminated in a designated wash area prior to leaving the site. | Per RAP | None | Upon Completion of Works/ between transferring equipment form site to adjacent work areas. | Inspection | FORE, PS | Downer
8.14 | Offsite transport | Trucks transporting sawdust or sand offsite shall be decontaminated prior to leaving site (refer Section 5.4.7), shall be free of debris prior to leaving site, and there shall be no tracking of material onto roads or footpaths. | Per RAP | None | Daily,during construction | Inspection | FORE, PS, SUB | Downer, Sub Transport
8.15 | Offsite transport | Loads are covered prior to leaving site. | Per RAP | None | Daily,during construction | Inspection | FORE, SUB | Downer, Sub Transport
8.16 | Offsite transport Load Tracking | Details of each load removed from site are recorded onsite to enable reconciliation against the disposal site weighbridge documentation. | Per RAP | None | Daily,during construction | Inspection | FORE, SUB | Downer, Sub Transport
8.17 | Unexpected Contamination | Advise NCC and SQEP immedialty should evidence of unexpected contaminated be encountered during the works on site. | Per RAP | None | Daily,during construction | Inspection | FORE, PS | Downer
Note on A8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add item for service clearance.
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Make consistent with revised methodology. Is this Stage 2a?
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Make consistent with revised methodology. Is this Stage 2a?
Note on B19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Make consistent with revised methodology. Is this Stage 2b?
Note on B27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Make consistent with revised methodology. Is this Stage 2b?
Note on B33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Make consistent with revised methodology. Is this Stage 2b?

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
4.1
4.2
4.3
4.4
4.5
4.6
4.7
4.8
4.9
4.10

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
5.1
5.2
5.3
5.4
5.5
5.6
5.7
5.8
5.9
5.10
SECTION 6 – COMMENTS
|  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: