## Sheet1
Type | Name | Values | Prefix | Postfix | Usage Count | User Addable | Template Name
checklist | BP QAC - Aluminium Cable Installation
checkpoint | 1 - Construction Checks
button | 1.1 - Inspection to confirm installed equipment is in accordance with the approved design | PASS,FAIL
button | 1.2 - Should avoid cable joints. If necessary, they must be agreed on the type and location with bp prior to installation | PASS,FAIL
button | 1.3 - AS/NZS approved cable manufacturer cable, lugs and technical datasheet compliance. Ensure bi-metal lugs are suitable for the installation. Flexible cable only. | PASS,FAIL
button | 1.4 - The cabling shall be an end-to-end propriety system including cables, crimp lugs, crimp dies, and heat shrink seals if applicable. Apply antioxidant treatment as per OEM requirements. | PASS,FAIL
button | 1.5 - Aluminium cable routes must be clearly labelled as per AS/NZS3000 using durable material such as traffolyte. | PASS,FAIL
button | HOLD POINT – Before energisation of electrical systems occurs, contractor to notify BP who will arrange an electrical engineering inspection & report. This will then be used to assist in completion of the Pre-Start Safety Review (PSSR) by BP (refer BP template TEMPLT-ALL-050-001 for guidance on checks to be conducted by BP). Electrical systems shall not be energised until PSSR is completed and BP has provided approval to proceed. | PASS,FAIL
textbox | 1.6 - BP have completed PSSR and approval to energise the system was given on (date) | Yes,N/A
signoff | ENTEC - I have completed the required activities and provided the specified evidence to BP.
signoff | BP - I have received the required evidence from the contractor and confirm it is acceptable.
`
0
2