## Table 1
|  |  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-003 Revision : 1
Client: Project: |  |  | SGSC Sanders Road , Raceby |  | Construction Process: Earthworks Foundation |  | Prepared by: Name: Signed : 15/08/24 | Ruby Lewis | Reviewed by : Name: Cameron Beattie |  |  | Approved by : Name: | Cameron Beattie
Contract No: |  |  |  |  | Specifications: VicRoads Specifications Section 204, 205 and 173
[5 empty] | Structure / Component: Earthworks/Civil |  |  |  | Signed : |  |  | Signed :
[5 empty] | Location:Sanders Road , Raceby |  |  |  | Date : 15/08/24 |  |  | Date : | 2024-08-15
Lot No: Lot Details: Lot Size/ Quantity:
Item No. |  | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility Project Engineer Site Engineer Superintendent Surveyor Foreman | Checked by:
|  |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  |  | Client | Fulton Hogan | FH's Sub- contractor | Date
1 |  | Preliminary Works
1.1 |  | Induction |  | Prior to Commencing Work | All personnel on site have completed site specific induction | Induction Register | Document Review | This ITP signed | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.2 |  | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS | PSP, CEMP, TMP, JSEA, SWMS, | Document Review | This ITP signed | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.3 |  | Excavation Permit issued |  | Prior to commencing | Current Excavation Permit signed and specific for the area where works will be executed. | Excavation Permit | Document Review | Excavation Permit No. | IP | Site Engineer & Superintendent | N/A |  | N/A
1.4 |  | Check that current revision drawings are being used |  | Prior to Commencing Work | Issued For Construction (IFC) and latest available revision used | IFC Drawings | Document Review | This ITP Signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
1.5 |  | Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place |  | Prior to Commencing Work | All environmental measures and site controls to be implemented as per current CEMP and CHMP. Sediment control measures to be installed and protected vegetation to be clearly identified | IFC Drawings CEMP CHMP | Document Review | This ITP Signed off | IP | Site Engineer / Site Foreman | N/A
Item No. | Task/Activity Description |  |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility Project Engineer Site Engineer Superintendent Surveyor Foreman | Checked by:
|  |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  |  | Client | Fulton Hogan | FH's Sub- contractor | Date
1.6 | Verification of Site Clearing |  |  | Prior to Commencing | In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment. | VicRoads Spec. Cl.201.05 ITP-001 | Visual Inspection | This ITP Signed off | IP | Project Engineer | N/A |  | N/A
1.7 | Placing Fill |  |  | Prior to Commencing Fill | Placing fill shall not commence on the prepared areas until the area has been reviewed by the Superintendent | VicRoads Spec. Cl. 204.10(b) | Visual Inspection | This ITP Signed off | IP | Project Engineer |  |  | N/A
1.8 | Rock Subgrade |  |  | During Excavation | Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance. Details of any necessary amendments to the sub surface drainage design including trasverse subsurface drainage at the interfaces shall be submitted to the Superintendent for review. | VicRoads Spec. Cl. 204.06(f) | Visual Inspection | This ITP Signed off | IP | Project Engineer |  |  | N/A
1.9 | Ground Water |  |  | During Excavation | The Superintendent shall be notified where groundwater or seepage is encountered and the proposed action to be taken, shall be submitted for review. Any necessary approvals from relevant authorities for treatment and disposal of this groundwater shall also be submitted . | VicRoads Spec. Cl. 204.06(h) | Visual Inspection | This ITP Signed off | IP | Project Engineer |  |  | N/A
1.1 | Unsuitable Material |  |  | During Excavation | Where unsuitable material is encountered, actions shall be: a) excavate the unsuitable material and backfill with 20mm Class 3 Crushed rock and compacted to min 98% Standard MDD to the approval of Superintendent | IFC Drawings | Visual Inspection | This ITP Signed off | IP | Project Engineer |  |  | N/A
2 | Construction Works
2.1 | Survey set-out |  |  | Prior to Commencing | The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. Survey activities undertaken to ensure and validate that all Works meet level and location requirements. Verification of conformity with latest IFC drawings. | IFC Drawings | Site Inspection | Survey records & pegs on the ground | SCP | Project Engineer/ Superintendent | N/A |  | N/A
2.2 | Placement of Geotextiles |  |  | On cut surfaces | Geotextiles / fabrics placed as per manufacturers specification | Drawings, Manufactuer specification | Verify | This ITP Signed off | IP | This ITP Signed off | N/A |  | N/A
| The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: | [9 empty] | Date: | / /
Legend
HP | Hold Point |  | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point |  | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
Item No. | Task/Activity Description |  |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility Project Engineer Site Engineer Superintendent Surveyor Foreman | Checked by:
|  |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  |  | Client | Fulton Hogan | FH's Sub- contractor | Date
WP | Witness Point |  | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point |  | Written or verbal approval given by the Superintendent