## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Plastering & Internal Hebel
| Scope |  |  | Site QA | Plastering & Internal Hebel
Rows
|  | Building C - Level 01 | dynamic | Level 01 | Building C | Site QA
|  | Building C - Level 02 | dynamic | Level 02 | Building C | Site QA
|  | Building C - Level 03 | dynamic | Level 03 | Building C | Site QA
|  | Building C - Level 04 | dynamic | Level 04 | Building C | Site QA
|  | Building C - Level 05 | dynamic | Level 05 | Building C | Site QA
|  | Building C - Level 06 | dynamic | Level 06 | Building C | Site QA
|  | Building C - Level 07 | dynamic | Level 07 | Building C | Site QA
|  | Building C - Level 08 | dynamic | Level 08 | Building C | Site QA
|  | Building C - Level 09 | dynamic | Level 09 | Building C | Site QA
|  | Building C - Level 10 | dynamic | Level 10 | Building C | Site QA
|  | Building C - Level 11 | dynamic | Level 11 | Building C | Site QA
|  | Building C - Level 12 | dynamic | Level 12 | Building C | Site QA
|  | Building C - Level 13 | dynamic | Level 13 | Building C | Site QA
|  | Building C - Level 14 | dynamic | Level 14 | Building C | Site QA
|  | Building C - Level 15 | dynamic | Level 15 | Building C | Site QA
|  | Building F - Level 01 | dynamic | Level 01 | Building F | Site QA
|  | Building F - Level 02 | dynamic | Level 02 | Building F | Site QA
|  | Building F - Level 03 | dynamic | Level 03 | Building F | Site QA
|  | Building F - Level 04 | dynamic | Level 04 | Building F | Site QA
|  | Building F - Level 05 | dynamic | Level 05 | Building F | Site QA
|  | Building F - Level 06 | dynamic | Level 06 | Building F | Site QA
|  | Building F - Level 07 | dynamic | Level 07 | Building F | Site QA
|  | Building F - Level 08 | dynamic | Level 08 | Building F | Site QA
|  | Building F - Level 09 | dynamic | Level 09 | Building F | Site QA
|  | Building F - Level 10 | dynamic | Level 10 | Building F | Site QA
|  | Building F - Level 11 | dynamic | Level 11 | Building F | Site QA
|  | Building F - Level 12 | dynamic | Level 12 | Building F | Site QA
|  | Building F - Level 13 | dynamic | Level 13 | Building F | Site QA
|  | Building F - Level 14 | dynamic | Level 14 | Building F | Site QA
|  | Building F - Level 15 | dynamic | Level 15 | Building F | Site QA
Columns
|  | External & internal Framing - All frames/studs set out correctly |  | All frames/studs set out correctly | External and internal Framing
|  | External & internal Framing - All frames plumb & square |  | All frames plumb and square | External and internal Framing
|  | External & internal Framing - Fix to structural members |  | Fix to structural members | External and internal Framing
|  | External & internal Framing - All window & sliding door openings are as per plan & line up with above elements |  | All window and sliding door openings are as per plan and line up with above elements | External and internal Framing
|  | External & internal Framing - Nogging all installed correctly |  | Nogging all installed correctly | External and internal Framing
|  | External & internal Framing - Door frames fixing |  | Door frames fixing | External and internal Framing
|  | External & internal Framing - Studco Supplier inspection (Provide report to builder) |  | Studco Supplier inspection (Provide report to builder) | External and internal Framing
|  | Internal Hebel wall - Angle/sarking/top hats in place |  | Angle/sarking/top hats in place | Internal Hebel wall
|  | Internal Hebel wall - Hebel panels Alignment |  | Hebel panels Alignment | Internal Hebel wall
|  | Internal Hebel wall - Ensure Hebel installed plumb & level with adjoining surfaces |  | Ensure Hebel installed plumb and level with adjoining surfaces | Internal Hebel wall
|  | Internal Hebel wall - Ensure Hebel panels are in full & not cracked |  | Ensure Hebel panels are in full and not cracked | Internal Hebel wall
|  | Internal Hebel wall - Ensure control joints have been installed in accordance with manufacturers specifications & installation guide |  | Ensure control joints have been installed in accordance with manufacturers specifications and installation guide | Internal Hebel wall
|  | Internal Hebel wall - Panels finish(patches done) |  | Panels finish(patches done) | Internal Hebel wall
|  | Internal Hebel wall - Fire-rated caulking & sealing |  | Fire-rated caulking and sealing | Internal Hebel wall
|  | Internal Hebel wall - Satisfaction & sign off from CSR inspection (Provide report to builder) |  | Satisfaction and sign off from CSR inspection (Provide report to builder) | Internal Hebel wall
|  | Plasterboard for Walls - Ply nogging |  | Ply nogging | Plasterboard for Walls
|  | Plasterboard for Walls - Rough-in sign off |  | Rough-in sign off | Plasterboard for Walls
|  | Plasterboard for Walls - Insulation installed as per AS/BCA |  | Insulation installed as per AS/BCA | Plasterboard for Walls
|  | Plasterboard for Walls - Correct type of plasterboards & thickness installed as per wall details, project drawings & BCA requirements |  | Correct type of plasterboards and thickness installed as per wall details, project drawings and BCA requirements | Plasterboard for Walls
|  | Plasterboard for Walls - WR/ Villaboard to wet areas ONLY |  | WR/ Villaboard to wet areas ONLY | Plasterboard for Walls
|  | Plasterboard for Walls - Plasterboard Lining to be installed as wall set out plan |  | Plasterboard Lining to be installed as wall set out plan | Plasterboard for Walls
|  | Plasterboard for Ceiling - Confirm Ceiling height |  | Confirm Ceiling height | Plasterboard for Ceiling
|  | Plasterboard for Ceiling - Confirm Access panel location |  | Confirm Access panel location | Plasterboard for Ceiling
|  | Plasterboard for Ceiling - Ceiling frame work |  | Ceiling frame work | Plasterboard for Ceiling
|  | Plasterboard for Ceiling - Ceiling bulkheads where required |  | Ceiling bulkheads where required | Plasterboard for Ceiling
|  | Plasterboard for Ceiling - Pelmets |  | Pelmets | Plasterboard for Ceiling
|  | Plasterboard for Ceiling - Ceiling insulation where required as per AS/BCA |  | Ceiling insulation where required as per AS/BCA | Plasterboard for Ceiling
|  | Plasterboard for Ceiling - Correct type of plasterboards & thickness installed as per wall details, project drawings & BCA requirements |  | Correct type of plasterboards and thickness installed as per wall details, project drawings and BCA requirements | Plasterboard for Ceiling
|  | Plasterboard for Ceiling - Ceiling plasterboard Lining |  | Ceiling plasterboard Lining | Plasterboard for Ceiling
|  | Setting & Sanding - Angle/LB/P50 install |  | Angle/LB/P50 install | Setting & Sanding
|  | Setting & Sanding - First coat setting |  | First coat setting | Setting & Sanding
|  | Setting & Sanding - Second coat setting |  | Second coat setting | Setting & Sanding
|  | Setting & Sanding - Final coat setting |  | Final coat setting | Setting & Sanding
|  | Setting & Sanding - Sanding |  | Sanding | Setting & Sanding
|  | Setting & Sanding - Patching |  | Patching | Setting & Sanding
|  | Setting & Sanding - Defects |  | Defects | Setting & Sanding
|  | Setting & Sanding - Final Inspection |  | Final Inspection | Setting & Sanding
External Hebel Wall
| Scope |  |  | Site QA | External Hebel Wall
Rows
|  | Building C - Level 01 | dynamic | Level 01 | Building C | Site QA
|  | Building C - Level 02 | dynamic | Level 02 | Building C | Site QA
|  | Building C - Level 03 | dynamic | Level 03 | Building C | Site QA
|  | Building C - Level 04 | dynamic | Level 04 | Building C | Site QA
|  | Building C - Level 05 | dynamic | Level 05 | Building C | Site QA
|  | Building C - Level 06 | dynamic | Level 06 | Building C | Site QA
|  | Building C - Level 07 | dynamic | Level 07 | Building C | Site QA
|  | Building C - Level 08 | dynamic | Level 08 | Building C | Site QA
|  | Building C - Level 09 | dynamic | Level 09 | Building C | Site QA
|  | Building C - Level 10 | dynamic | Level 10 | Building C | Site QA
|  | Building C - Level 11 | dynamic | Level 11 | Building C | Site QA
|  | Building C - Level 12 | dynamic | Level 12 | Building C | Site QA
|  | Building C - Level 13 | dynamic | Level 13 | Building C | Site QA
|  | Building C - Level 14 | dynamic | Level 14 | Building C | Site QA
|  | Building C - Level 15 | dynamic | Level 15 | Building C | Site QA
|  | Building F - Level 01 | dynamic | Level 01 | Building F | Site QA
|  | Building F - Level 02 | dynamic | Level 02 | Building F | Site QA
|  | Building F - Level 03 | dynamic | Level 03 | Building F | Site QA
|  | Building F - Level 04 | dynamic | Level 04 | Building F | Site QA
|  | Building F - Level 05 | dynamic | Level 05 | Building F | Site QA
|  | Building F - Level 06 | dynamic | Level 06 | Building F | Site QA
|  | Building F - Level 07 | dynamic | Level 07 | Building F | Site QA
|  | Building F - Level 08 | dynamic | Level 08 | Building F | Site QA
|  | Building F - Level 09 | dynamic | Level 09 | Building F | Site QA
|  | Building F - Level 10 | dynamic | Level 10 | Building F | Site QA
|  | Building F - Level 11 | dynamic | Level 11 | Building F | Site QA
|  | Building F - Level 12 | dynamic | Level 12 | Building F | Site QA
|  | Building F - Level 13 | dynamic | Level 13 | Building F | Site QA
|  | Building F - Level 14 | dynamic | Level 14 | Building F | Site QA
|  | Building F - Level 15 | dynamic | Level 15 | Building F | Site QA
Columns
|  | Angle/Sarking or RAB Board/Top Hats in place |  | Angle/Sarking or RAB Board/Top Hats in place
|  | Hebel Planels Alignment |  | Hebel Planels Alignment
|  | Ensure Hebel PowerPanel finish are as per the finishes shown on project drawings & elevations |  | Ensure Hebel PowerPanel finish are as per the finishes shown on project drawings and elevations
|  | All Sarking/RAB Board has been installed as per manufacturer's recommendations |  | All Sarking/RAB Board has been installed as per manufacturer's recommendations
|  | Sarking overlap flashing by min. 150mm |  | Sarking overlap flashing by min. 150mm
|  | Flashing are installed correctly, are continuous & free of any imperfections |  | Flashing are installed correctly, are continuous and free of any imperfections
|  | Ensure Hebel installed plumb & level with adjoining surfaces |  | Ensure Hebel installed plumb and level with adjoining surfaces
|  | Window seal cuts to be neat & consistent |  | Window seal cuts to be neat and consistent
|  | Hebel panel cut treatment reinforcement |  | Hebel panel cut treatment reinforcement
|  | Ensure Hebel panels are in full & not cracked |  | Ensure Hebel panels are in full and not cracked
|  | Ensure on site routing of panels to be perfectly straight & level |  | Ensure on site routing of panels to be perfectly straight and level
|  | Ensure control joints have been installed in accordance with manufacturer's specifications & installation guides |  | Ensure control joints have been installed in accordance with manufacturer's specifications and installation guides
|  | Hebel expansion joins have been installed & are consistent, including slab junctions |  | Hebel expansion joins have been installed and are consistent, including slab junctions
|  | Weep holes have been installed correctly & at correct heights & spacing |  | Weep holes have been installed correctly and at correct heights and spacing
|  | All Hebel walls to line up with elements above |  | All Hebel walls to line up with elements above
|  | Panels finish (patches done) |  | Panels finish (patches done)
|  | Fire-rated caulking & sealing (junctions should be treated with sealant & backing rod - for both top & bottom junctions) |  | Fire-rated caulking and sealing (junctions should be treated with sealant and backing rod - for both top and bottom junctions)
|  | Satisfaction & sign off from CSR inspection (Provide report to builder) |  | Satisfaction and sign off from CSR inspection (Provide report to builder)
External CSR Cemintel CFC
| Scope |  |  | Site QA | External CSR Cemintel CFC
Rows
|  | Building C - Level 01 | dynamic | Level 01 | Building C | Site QA
|  | Building C - Level 02 | dynamic | Level 02 | Building C | Site QA
|  | Building C - Level 03 | dynamic | Level 03 | Building C | Site QA
|  | Building C - Level 04 | dynamic | Level 04 | Building C | Site QA
|  | Building C - Level 05 | dynamic | Level 05 | Building C | Site QA
|  | Building C - Level 06 | dynamic | Level 06 | Building C | Site QA
|  | Building C - Level 07 | dynamic | Level 07 | Building C | Site QA
|  | Building C - Level 08 | dynamic | Level 08 | Building C | Site QA
|  | Building C - Level 09 | dynamic | Level 09 | Building C | Site QA
|  | Building C - Level 10 | dynamic | Level 10 | Building C | Site QA
|  | Building C - Level 11 | dynamic | Level 11 | Building C | Site QA
|  | Building C - Level 12 | dynamic | Level 12 | Building C | Site QA
|  | Building C - Level 13 | dynamic | Level 13 | Building C | Site QA
|  | Building C - Level 14 | dynamic | Level 14 | Building C | Site QA
|  | Building C - Level 15 | dynamic | Level 15 | Building C | Site QA
|  | Building F - Level 01 | dynamic | Level 01 | Building F | Site QA
|  | Building F - Level 02 | dynamic | Level 02 | Building F | Site QA
|  | Building F - Level 03 | dynamic | Level 03 | Building F | Site QA
|  | Building F - Level 04 | dynamic | Level 04 | Building F | Site QA
|  | Building F - Level 05 | dynamic | Level 05 | Building F | Site QA
|  | Building F - Level 06 | dynamic | Level 06 | Building F | Site QA
|  | Building F - Level 07 | dynamic | Level 07 | Building F | Site QA
|  | Building F - Level 08 | dynamic | Level 08 | Building F | Site QA
|  | Building F - Level 09 | dynamic | Level 09 | Building F | Site QA
|  | Building F - Level 10 | dynamic | Level 10 | Building F | Site QA
|  | Building F - Level 11 | dynamic | Level 11 | Building F | Site QA
|  | Building F - Level 12 | dynamic | Level 12 | Building F | Site QA
|  | Building F - Level 13 | dynamic | Level 13 | Building F | Site QA
|  | Building F - Level 14 | dynamic | Level 14 | Building F | Site QA
|  | Building F - Level 15 | dynamic | Level 15 | Building F | Site QA
Columns
|  | Check external wall frames alignment |  | Check external wall frames alignment
|  | Install all flashing as per wall detail & project drawings |  | Install all flashing as per wall detail and project drawings
|  | Install sarking & tophats |  | Install sarking and tophats
|  | Horizontal & Vertical Alignment |  | Horizontal & Vertical Alignment
|  | Install CFC |  | Install CFC
|  | Joints caulking & Sealing |  | Joints caulking & Sealing
|  | Defects |  | Defects
|  | Final Inspection (water test by builder) |  | Final Inspection (water test by builder)