## Concrete
CIVIL INSPECTION & TEST PLAN
Concrete - ITP |  |  |  |  | Rev: | Originator | Date | Approved | Date
[5 empty] | 0 | Cameron Hinge | 2024-06-14
| H - HOLD |  |  |  | 1
P - PERFORM
W - WITNESS
R - REVIEW
ITEM | TASK | SPECIFICATION REFERENCE | ACCEPTANCE CRITERIA | DATE/SIGN |  |  | COMMENTS
1 | Issued For Construction Drawings | IFC Drawings Issued by Client/Engineer | Issued For Construction Drawings Available | Contractor Rep - H
2 | Excavate to depth to ensure adequate cover over the batten to gain minimum cover as per drawing detail | Drawing detail Permit to Work | Permit to Work issued Excavation enough to ensure formwork can be constructed to give minimum cover to concrete over batten | Contractor Rep - P
3 | Formwork & Steel | IFC Drawing | Remove topsoil back to subgrade material and place in suitable storage location with silt controls | Contractor Rep - P
4 | Pour Concrete | Prepour Inspection | Prepour Inspection completed and signed off prior to pouring concrete | Civil Inspector - H
5 | Apply Sealant | IFC Drawing | Sika Flex Fire400 applied as per manufacturers instructions and IFC Drawing | Contractor Rep - P Civil Inspector - W
6 | As Built & Final Design Documentation |  | Final ASBUILT data picked up of what foundations have had concrete beams added to them | Contractor Rep - H