## res_ITP_1_Inspection_and_Test_P
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Concrete Beams over Battens | itp |  |  |  |  | ITP - Concrete Beams over Battens
section | Details
checkpoint | 1 - Issued For Construction Drawings
label | SPECIFICATION REFERENCE - IFC Drawings Issued by Client/Engineer
label | ACCEPTANCE CRITERIA - Issued For Construction Drawings Available
label | DATE/SIGN - Contractor Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Excavate to depth to ensure adequate cover over the batten to gain minimum cover as per drawing detail
label | SPECIFICATION REFERENCE - Drawing detail, Permit to Work
label | ACCEPTANCE CRITERIA - Permit to Work issued
label | ○ Excavation enough to ensure formwork can be constructed to give minimum cover to concrete over batten
label | DATE/SIGN - Contractor Rep - P
checkpoint | 3 - Formwork & Steel
label | SPECIFICATION REFERENCE - IFC Drawing
label | ACCEPTANCE CRITERIA - Remove topsoil back to subgrade material and place in suitable storage location with silt controls
label | DATE/SIGN - Contractor Rep - P
checkpoint | 4 - Pour Concrete
label | SPECIFICATION REFERENCE - Prepour Inspection
label | ACCEPTANCE CRITERIA - Prepour Inspection completed and signed off prior to pouring concrete
label | DATE/SIGN - Civil Inspector - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Apply Sealant
label | SPECIFICATION REFERENCE - IFC Drawing
label | ACCEPTANCE CRITERIA - Sika Flex Fire400 applied as per manufacturers instructions and IFC Drawing
label | DATE/SIGN - Contractor Rep - P, Civil Inspector - W
checkpoint | 6 - As Built & Final Design Documentation
label | ACCEPTANCE CRITERIA - Final ASBUILT data picked up of what foundations have had concrete beams added to them
label | DATE/SIGN - Contractor Rep - H
holdpoint | AUTHORITY HOLDPOINT