## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
4cbe5940-170d-4935-b20f-cae955dc5fe3 | checklist | Ceiling Framing ITP |  | Ceiling Framing ITP
c7493462-d6bd-4a4c-8dd7-ef81351db250 | section | Prior to Commencement – The following documentation completed and approved
8c697c39-27f7-48c9-a079-1d6ddbda46ec | checkpoint | Area accessible & ready
4386d80e-6869-4d5f-a99f-6c6614dd2594 | checkpoint | Structural design, documentation and certification for framed ceiling and bulkheads
e3a35b1c-729c-4e7b-8917-01c9af6d9e24 | checkpoint | Shop drawings submitted and approved
eddb8fef-8380-4e45-bdfb-987872517f9d | checkpoint | Samples and prototypes submitted and approved (Fire sealants approved)
6c1554e2-0468-4789-b5bb-68fa2c90b5f0 | checkpoint | Test results of prototypes submitted (section 1.19)
ef2fede1-a1e2-4d5e-943f-d68312f07a48 | section | Set out
bf7a46e3-e2fa-4d75-888b-8a4b257ea977 | checkpoint | Reflected ceiling plans current revisions checked and ceiling set out completed as per the current plans
4d6fc46a-f352-484b-9f39-3f5bd4732e68 | section | Construction Generally
6aea7b41-9208-471d-9d4f-497871ba3ad9 | checkpoint | Install & fix to prevent looseness or rattling of ceiling components
3bd306c7-b734-4282-a7ec-1987ecc09a19 | checkpoint | Ceiling systems do not amplify structural-borne sounds.
b8f74a2c-b814-417c-a70c-d365ff81bafc | checkpoint | Install the ceiling to allow for differential movement at abutting surfaces
3fa8dfa6-275f-43b8-9c7b-05b4d3e4ded3 | checkpoint | Post tensioned concrete: Minimum embedment for fixing: 45mm and minimum clearance of fixing from any tendon: 25mm
e2b0cb28-c7a0-4453-8371-cb9f579aa532 | section | Construction – Suspension system
f81b8515-4ec2-4bd3-bfc5-3fc15611bb2a | checkpoint | Provide suspension system and workmanship as per supplier installation guides.
06daa44f-f0d0-41a7-9af5-46302f799aab | checkpoint | Services: Do not fix to the installed services
cb813e2e-8166-5271-813c-4968f9d6f030 | note | Where services obstruct the ceiling supports, provide bridging and suspension on each side of the services
2c3e1ae9-ce65-5167-9dce-1b7516bfcf18 | note | Provide additional back support or suspension members to prevent distortion, overloading or excessive vertical deflection.
861b6fb9-f8b8-4823-83d6-87c613af75cf | checkpoint | Ensure that the failure of any one suspension point does not cause a progressive failure of the ceiling.
7d9daee3-452d-552f-a501-b0225afae07b | note | Provide height adjustment with a length adjustment device at each suspension point, permitting length variation of at least 50mm
9f8bcb87-e275-5ea4-9662-a9b1e35096d1 | note | Seismic resistant: Provide bracing and clips to framing members to prevent lateral movement and to resist seismic action.
1e0e35f7-cdd7-57d8-9637-6b1b954167b1 | note | Do not provide visible fixings (screws or rivets) where they will be exposed to view.
e4ed57fe-870d-49a4-a434-7042a4dedc94 | checkpoint | Uplift: Suspension system and framing to resist uplift.
19d0c07d-90d3-5d69-a0fc-a7d23d379ad2 | note | Tolerances: Flatness, twist, winding and bow: 1.5mm deviation from a 1.5m straightedge places in any position
e5bf3530-b06a-4de3-8818-7901f984687e | section | Hold Point
fcb62ad7-ddd8-4cb9-baae-7056d501c216 | checkpoint | Suspension system completed – Ready for installation of ceiling tiles, lining and panels.
6bc976ef-a184-4b62-8544-315f9e599708 | checkpoint | Confirm all service trades are complete & ready for closing in of ceilings.
3d891320-9560-4a06-87f5-9f2141354047 | section | Bulkheads
951303dc-25c9-4972-a396-1c534b22c4b6 | checkpoint | Integrate bulkheads with the ceiling structure and brace to prevent lateral movement. Where ceiling is terminated at the bulkhead, provide for seismic requirements
9c152176-7ca5-423d-b157-74e73eaa1ce2 | section | Smoke baffles and acoustic baffles
438a287f-2029-4e51-9951-b3556ae87f0d | checkpoint | Provide approved smoke and acoustic baffles secured fixed to metal angles and smoke sealed at board joints and to adjoining building elements
ec31beb7-3750-4c2a-aef5-b12c40a74dfd | section | BVT Engineering Inspection
de20b477-dd04-45cb-9e49-9e77566a49db | checkpoint | BVT to complete construction monitoring on ceilings, in line with Rondo PS1 and provide report.
393fb255-4e25-48ce-ad8c-394734b76eb9 | checkpoint | BVT to complete in depth sign-off sheet for all ceilings once engineering & construction is confirmed.
cae2f248-79fa-45be-a944-117bfdf4d27d | checkpoint | Include sign off sheet & register with ITP
c50bdc52-0248-4016-9ceb-c0e464260262 | section | Acoustic installation
ef196022-4e08-40f6-bdf5-710564efdf45 | checkpoint | Place mineral fibre batts on top of ceilings system and butt to each other and to partitions.
8bd3df4b-e043-458f-a7ea-e56ff21c5733 | checkpoint | Tightly butt and trim neatly around services items and other items
5869fab8-071e-4074-a626-54aca6d1cc8b | checkpoint | CPB final sign off - add signature
faafc124-00b2-41fa-9b03-71dd4cc90ff3 | checklist | Ceiling Lining ITP |  | Ceiling Lining ITP
d9afdedb-2927-4211-87db-6d4c8cc394e9 | section | Construction – Tile ceiling, Grid ceiling, Lining
7bc7c55e-bfa9-4338-93ac-5ab6a0fedf6d | checkpoint | Area accessible & ready
7d1653b8-1299-4c83-bf87-f56ecec8523f | checkpoint | Provide board lining to a finish and workmanship as per supplier installation guides.
25b575fa-6356-41eb-adf2-7d6cf6605538 | checkpoint | Fit accurately and neatly, without distortion and free from air leakage and staining.
c7dda36f-0739-5f6f-a5d8-0c7a829720c1 | note | Clip locks: Where ceiling units are exposed to loads from wind actions or as required, insert lock clips at the junction of carrier rails and units.
3f7ac865-dea8-4cb4-8fba-f32dc4651ad8 | checkpoint | Set out patterned or heavily textured materials with a consistent direction of pattern or texture.
9ff35720-de9a-4a4e-a95d-e054bbad2d4b | checkpoint | Cut ceiling unit edges: conceal, or finish to match prefinished edges.
7244d0b8-0555-4a50-b9e8-df39a1609ef0 | checkpoint | Multiple sheet layers to fire rated and acoustic rated elements
9340e218-7703-5d4f-ad5d-79d8fa69bb05 | note | Fill & flush up all joints and fixings in each layer and caulk up perimeters and penetrations before commencing succeeding layers. Stagger all sheet joints by minimum 200mm.
ca7edf95-b9e9-4438-bac0-3bdab440b89e | checkpoint | Board joints support: Provide framing parallel to the joint on each side. Do not fix the lining to abutting building surfaces
3756876b-5a5e-4488-94f7-b84603fa9670 | checkpoint | Flush joints: Provide recessed edge sheets and finish flush using perforated paper reinforcing tape. Locate & position joints to intersect light fixtures, vents or air diffusers.
2d583d71-b687-5faf-87e0-4b3b2a52aaeb | note | Tolerances: Suspension system bearing surface for flush lined ceiling to AS/NZS 2589 table 4.2.2
44d28b4b-0279-44c1-be06-7c2822c532a6 | checkpoint | Levelness: Max tolerance of ±5mm relative to the documented height datum for the particular ceiling in each room or space.
9a6e5496-26a9-4ac8-9711-9a28f52bd916 | checkpoint | Trims & accessories: Provide trims at junctions with other building elements and surfaces, including walls, beams and penetrations.
e12958dc-6422-4209-9d60-20b64c0afc97 | section | Control joints
9e81255e-650b-4b85-8824-9d248393e824 | checkpoint | Align ceiling control joints with the structural control joints. Do not bridge structural control joints.
5ed5e4f4-68e1-496e-ad21-95425ee6c16c | checkpoint | Provide purpose made metallic coated control joint beads where documented.
cc9af38c-a393-48a8-8500-64da89f06496 | checkpoint | Provide framing parallel to the joint on each side.
c45e3c9c-5d92-5f0e-a754-8abc6cfafd30 | note | Plasterboard lining: 12m centres
7b5afa3d-6f8b-5995-a2a5-f8a813c5141d | note | Fibre cement lining: 7.2m centres
fd8d7ed7-6f90-4586-a8f0-4e513aaa485e | checkpoint | Infection control: Provide full depth paintable sealant, finished flush with the face of the lining, to locate where documented.
da78ad7d-e460-4698-bd10-40398bd73521 | section | Bulkheads
29339282-92b4-4546-8694-2b8a7aac7218 | checkpoint | Integrate bulkheads with the ceiling structure and brace to prevent lateral movement. Where ceiling is terminated at the bulkhead, provide for seismic requirements
e32505f4-b75f-41d4-ad73-bce39ccaba9f | section | Access panels
033e8d99-06b9-43fc-8818-b7178d7c2ccc | checkpoint | Match the access panels to the ceiling in appearance and performance
cda4aa89-d084-430f-b6b8-01fd52e0b876 | checkpoint | Provide each access panel with an ID - Record ID in comments
70cb5b7b-c47f-52ed-9b8b-f4517d61bc5c | note | Provide access panels supported and anchored to permit ready removal and refixing
d1ae9687-fa85-4c66-887e-12c703ea69f7 | checkpoint | Reinforce the back of the access panel to prevent warping and facilitate handling
8b71dade-5b7a-50ad-8f76-6e1ba1367f74 | note | Provide fire rated and acoustic rated panels where documented or where required to maintain the designated rating of the ceiling element
23539a4c-2038-422e-9f4c-cceab0d8ac29 | section | Additional checks for fire-protective board lining
6dcea947-2ccb-47a7-9b18-928618d351e5 | checkpoint | Check the fire resistance levels: Drawings and Spec Sec 4.6 Misc. Items Schedule
45b04367-3d84-4694-9ea5-acab8c39d33f | checkpoint | Fixings: Direct to concrete elements and to purpose made steel framing
3ab8d168-e1f0-4ac0-8c45-b94bb744dbfb | checkpoint | Penetrations: Seal penetrations in the board lining to maintain the integrity of the required fire resistance level including suspended ceiling hangers and suspension systems for services.
192ad387-b9a6-450f-a972-6d5e87e8c8eb | checkpoint | Board perimeter: Provide fire sealant and trims at junctions with other building elements and surfaces, including walls, beams and penetrations to maintain the required fire resistance levels.
dd1900ab-95f6-5c89-8ad5-fec1fd63123b | note | Label each fire stopping to AS/NZS 2589.1
8fd6e4fe-0c8d-40df-9533-7b474feb96f4 | checkpoint | CPB final sign off - add signature
a4139b95-6069-4b9d-aa56-6087a76918d8 | checklist | Door Installation |  | Door Installation
a6151564-819a-43f8-97f8-41e5505215d8 | section | Prior to Commencement – The following documentation are completed and approved:
6bbf6002-1614-4a79-8471-488a028e0d9f | checkpoint | Shop drawings submitted and approved (BY PDS)
1dff025d-ec8d-4d18-b955-68eed411ace2 | signoff | Shop Drawing Holdpoint
cde1fd8d-cc72-4b60-a440-2399c100bb59 | section | Take Delivery of Door Units:
eb3099c3-d5ad-4ec1-9b97-08b3594c2f8d | checkpoint | The door has been identified and is the correct size to the shop drawings
4b4d27f7-7df9-4c7b-a9a3-dd84f9c65a82 | checkpoint | The door is sound & undamaged. No rusting to frame, or door leaf.
6eb5f3f6-1e29-48c5-bf99-311b263b2834 | section | Preinstall Door Checks / Openings Prepared to Receive Doors:
67f2ac55-c67b-4e86-b9a4-493391889e34 | checkpoint | Opening has been allocated by CPB
90be55b7-d770-41eb-b061-1eb81e003640 | checkpoint | The door type is known and has been identified for fire rating, acoustic and containment
fccfdc0f-1ccb-41ff-9ab4-61124f597dfc | section | Door Installation (Part 1):
17c3144d-8d00-48ce-bab6-d1d3bbfa3d7a | checkpoint | Shop Drawings and typical details for appropriate door install have been sighted & understood.
f51a2411-0711-418c-b47b-f11156c986a2 | checkpoint | Check frame to ensure any penetrations or possible grout leak points not accessible after install are sealed (if applicable).
692d0085-09c6-437b-ad2d-da7f2ee01bd7 | checkpoint | Door frame is packed with Ceramic Wool / Acoustic Wool (if applicable).
a325482b-8a25-42db-afbf-05b44a4df775 | checkpoint | The correct fixings have been used, are fully driven home, and tensioned. The head of fixings is not covered and has not been sealed.
66361ec1-f653-4fb2-9c8c-1d24345a2c0c | checkpoint | Correct & adequate packers have been used. Packing is trimmed back so as not to impede correct sealant depth or wall lining install.
48a156d9-192e-4f7b-ad7e-8659ad5bec53 | checkpoint | The door is installed plumb, square, and at the correct wall lining schedule.
04461d76-7133-40d0-bceb-a8f13689db8c | section | Door Installation (Part 2):
a4a79d5a-7106-4590-bc23-342afb28eab8 | checkpoint | Wiring for the security has been chased & not damaged (By Honeywell).
6f26c84d-a959-4904-a20b-43774a2dc1f1 | checkpoint | Security Contractor advised conduits & prewire can be complete (if applicable)
cce31cff-eea9-4e16-9e76-6bbd47f290c4 | section | Honeywell Sign Off:
ea6043c5-bb24-43aa-af96-852e9827093c | checkpoint | Confirmation from the security contractor that all their works are complete & installation can progress to final stage
e1ec5ae9-e355-43c4-b33f-84749cf91655 | signoff | Honeywell HOLDPOINT
37810b88-198e-4a68-bee7-dfbc8df9562e | section | CPB Sign Off (Part 1):
cbec37cf-be68-4aa4-b2b4-ad784cdb8482 | checkpoint | CPB to complete their QA checks on installed units, including completing witness point of our install to this point.
c5a90d21-e4d7-42d3-ac94-98b7f1bb00ce | signoff | CPB HOLDPOINT
c01b2e21-bc98-4b76-b023-2121ad22d99d | section | Door Installation (Part 3):
aa7c76a0-3ae2-478c-a0b4-84dc87d91519 | checkpoint | Sealant is applied to correct depth on backing rod as required.
a4c059ba-957f-45ce-950a-045e923f24c4 | checkpoint | Sealant is set back far enough to receive Non pick sealant by subsequent trade in prisoner accessible areas (if applicable).
f89fd0bb-a899-42c6-9c2d-ab44a418855a | checkpoint | The head of the fixing bolts is packed & sealed using correct sealant filler.
3e9d90cb-fd1f-4a49-9106-2aa2fce7d957 | checkpoint | Before grouting can commence, the sealant must have been allowed to fully cure
633ceea7-f274-4162-a389-ce58fda6133d | checkpoint | Check for any potential leak points for grouting.
9562eda5-afe3-45d2-b4c1-176ddf390132 | checkpoint | Leaf to frame clearances checked prior to grouting
63660be8-981a-4a40-a128-77a6222a3215 | checkpoint | Frame is braced (if applicable)
e9888504-3100-4249-9cfa-79b7a9c4f12c | section | Final Checks
d6e57feb-fe03-46c7-b0d7-203d2f3f321b | checkpoint | Door has been sealed
c50ac79a-8c0c-4b8b-9fc1-c2428b7ae24e | checkpoint | Door has been grouted (if applicable)
e6ea1ac0-9b29-40fc-b323-fe3992f74f1f | checkpoint | Door has no damage or rust visible
79b581ee-5ee3-406b-bf61-175e456b73e3 | checkpoint | Door has been cleaned and is in a satisfactory standard to hand over to the subsequent trade (Hardware install by PDS)
74f5456d-2726-4721-8130-90ab99dc2134 | section | CPB Sign Off (Part 2):
d33407d4-75f8-4a06-94f3-4e7fc759d68d | checkpoint | CPB to complete final checks & sign-off unit
0091e685-2704-423a-919f-6ca7c803864f | signoff | CPB HOLDPOINT
15e88069-d943-48f0-9817-fd574fcea8b0 | section | Final Sealant
382109d8-28ff-4493-a811-2d443a6c67df | checkpoint | Final sealant installed at junction of window frame & cladding (where applicable)
26b540e5-6f86-4455-9818-d5203fe8a9ec | section | Site Hose Testing for External Doors (Post hardware install):
5057cb19-7a24-4492-9c8f-d522ed102585 | checkpoint | Each door is to be site hose tested by approved & certified water testing specialists.
99a954d6-e3e1-4a04-9651-d21652d70c98 | checkpoint | Test Results to be included with this ITP
502ebda1-b5d0-4d1d-a2a9-3ae9a1d83659 | checklist | Louvre Installation |  | Louvre Installation
9cb0f9b8-0f64-4d87-adfb-f8d372a8713b | section | Prior to Commencement – The following documentation are completed and approved
1a2e0b03-172f-4300-b2b0-45c8603995f5 | checkpoint | Shop drawings submitted and approved (BY PDS)
2bcf5fee-cee7-40d7-85f9-bd123bab4274 | signoff | Shop Drawing Holdpoint
b3bf13be-15e6-4c5a-bc36-b1d09e296424 | section | Take Delivery of Louvre Units
c697b5f4-3d19-4283-a63d-38da0c6886ac | checkpoint | The louvre has been identified and is the correct size to the shop drawings
a15be8c8-f125-4c49-a9e8-1e0a92f3b1e8 | checkpoint | The louvre is sound & undamaged. No rusting to frame, or door leaf.
a6efa0a2-756b-4a62-a3db-4fb3c1d07108 | section | Preinstall Door Checks / Openings Prepared to Receive Louvres:
ae04cf4a-ef52-4894-b46b-50027a6dcfe9 | checkpoint | Opening has been allocated by CPB
3e4b6033-fa45-4a22-9395-160caf2e65a7 | checkpoint | The louvre type is known and has been identified for fire rating, acoustic and containment
adda802a-36c5-4da5-9de0-d79e9fcfad99 | section | Louvre Installation (Part 1):
6eb7958d-90a1-42cb-93df-6d14c86630e8 | checkpoint | Shop Drawings and typical details for appropriate louvre install have been sighted & understood.
da684752-7f40-43d0-bfa4-03ddf547eff3 | checkpoint | Check frame to ensure any penetrations or possible grout leak points not accessible after install are sealed (if applicable).
7278f256-3f7d-4e82-810b-45e7790729d8 | checkpoint | The correct fixings have been used, are fully driven home, and tensioned. The head of fixings is not covered and has not been sealed.
84e953e9-916b-4b2f-a425-4eee96b25e82 | checkpoint | Correct & adequate packers have been used. Packing is trimmed back so as not to impede correct sealant depth or wall lining install.
9d51b874-08e8-424e-a634-b1f39abfd6cc | checkpoint | The louvre is installed plumb, square, and at the correct wall lining schedule.
b0488c04-8db9-4c84-8e8f-dd7cab218eec | section | CPB Sign Off (Part 1):
b7512924-ef0e-469e-98d5-5bada1907476 | checkpoint | CPB to complete their QA checks on installed units, including completing witness point of our install to this point.
7c0b32e8-2051-45b3-b601-653799fe2e4a | signoff | CPB HOLDPOINT
8d446dce-38a5-46b0-8a2e-c78a5113e7cc | section | Louvre Installation (Part 2):
8a06b544-c42f-4306-bc4d-4a6c421c969f | checkpoint | Sealant is applied to correct depth on back rod as required.
d782f4a8-95cf-44d6-ac0f-8ad7e6f51ce2 | checkpoint | Sealant is set back far enough to receive Non pick sealant by subsequent trade in prisoner accessible areas (if applicable).
36c16fc7-f1e5-4354-8411-64ec515f9fb5 | checkpoint | The head of the fixing bolts is packed & sealed using correct sealant filler.
78da56fb-6b9f-4698-bec9-532de4e9455d | checkpoint | Before grouting can commence, the sealant must have been allowed to fully cure
0e29e241-82cb-4538-86bc-393011363c17 | checkpoint | Check for any potential leak points for grouting.
d741c4cc-c429-43cd-b188-ca43b6434806 | checkpoint | Leaf to frame clearances checked prior to grouting
b21b1aec-532a-46de-a4f5-1984aa625bf9 | section | Final Checks
50aab367-2150-4cb1-ad2c-5a459bab3234 | checkpoint | Louvre has been sealed
9d2c2b9a-777e-450e-a3e0-de96cae855ee | checkpoint | Louvre has been grouted (if applicable)
b0af9f13-102c-46d9-bf25-2149af28a060 | checkpoint | Louvre has no damage or rustvisible
9aabb693-496f-4ab0-bfc6-73af3c48e968 | checkpoint | Sealant continuous, clean & no air pockets
be3d78e9-bfc5-44f7-815f-b79de3c1c10c | checkpoint | All fixings installed & tightened with good hold & no signs of stripping
76515eb7-ae3b-4590-8ca3-e1edab0cf240 | checkpoint | Louvre has been cleaned and is in a satisfactory standard to hand over to the subsequent trade (Hardware install by PDS)
0b4c7f67-00e3-44ce-bdb9-13d14ad4c81a | section | CPB Sign Off (Part 2):
9dfda7eb-855a-4de0-ba10-dbc7c5a3fcbb | checkpoint | CPB to complete final checks & sign-off unit
feca88ca-9162-474d-9f82-fd5112980ea9 | signoff | CPB HOLDPOINT
8a9de0c8-d048-4def-9e65-cc5e6d4e9a59 | section | Final Sealant
0571de78-0de3-4440-9fa3-291533da98cf | checkpoint | Final sealant installed at junction of window frame & cladding (where applicable)
0b7666c0-7d1c-4688-a56e-bcde74de85b4 | checklist | Partition Framing ITP |  | Partition Framing ITP
15a071ad-bd3e-49dc-9b1b-f3631d759621 | section | Prior to Commencement – The following documentation are completed & approved
ef15469a-6e36-4488-862a-ae0749656d27 | checkpoint | Area ready & accessible
eb8367cd-aa8c-5ff5-a754-f9be90ec90f4 | note | 1400 Series & Rondo PS1
04168265-8ca3-5d4c-a2a7-9376eb773da9 | note | Structural design, documentation & certification for secondary structural steel elements providing support for partitions & fixtures
720506cc-4533-5da3-a893-e061fbadcb74 | note | Shop drawings submitted & approved
3fcb8e0f-ff60-5403-9482-46c7289723e0 | note | Samples & prototypes submitted & approved (Fire sealants approved)
e0981874-c802-5d10-9907-18899b582c6f | note | Test results of prototypes submitted (section 1.19)
3a8ebcfb-c336-4750-8628-a35e63a1eff5 | section | Set out
046c9ee6-e5b7-44ae-b786-a4b5e0849768 | checkpoint | Partitions set out plans current revisions checked & wall set out competed as per the current plans
5edffdcd-f802-5fac-94f9-e4995c3a8405 | textbox | Revision no.
ab58594c-2fd1-45f0-aee9-da8c41126b19 | section | Stud Framing / Wall Strapping
28d4324a-b5de-4e6c-9456-3a4f6394a23d | checkpoint | Inspect the framing of walls as per Rondo PS1
08a8528b-8fa8-456d-8099-d8241888a4b2 | checkpoint | Check sizes & spaces as per the partition types
70e29842-0541-4396-9d25-86e9a2237378 | checkpoint | Fix tracks 600mm centres & 100mm from ends
f250f93f-bbdf-4be9-aa5b-a6bb8f81431a | checkpoint | Fixing to post tensioned concrete: Maximum embedment for fixings = 45mm
526302c1-9ad0-4b57-839e-8c52a9134c74 | checkpoint | Install boxed double studs at jambs to all openings
86def223-ea82-4bb2-a1ac-fab3037987d0 | checkpoint | Part height partitions: Brace as per Rondo PS1
51c67c5d-d71f-4464-baf3-0f3ecc4ea0a9 | checkpoint | Full height partitions: Fix deflection head tracks to the floor slab soffit to allow a minimum deflection capacity of 20mm
7252b957-a09c-4224-a8a9-b30a62dc4bec | checkpoint | Achieve overlap of at least 30mm of the deflection head channel’s section vertical leg with the top plate of the wall framing
42fa99ed-6818-44ca-9fa8-c413437afc47 | checkpoint | Rotate intermediate studs into tracks for friction fixing
538a1b7c-6dcc-469b-88b9-726a4bff4abd | checkpoint | Staggered stud framing walls: Studs staggered at 300mm centres set in oversized top & bottom plates to allow each face to have stud fixing at 600mm centres
b7181791-13cc-4907-9713-266dabbcb220 | checkpoint | Structural floor control joints: Disconnect partitions over joints with detached double studs & ensure bottom tracks, bracing & top tracks are not fastened across joints
cf29bb2e-0bf2-4688-9989-e733358674fb | checkpoint | Stud service holes: Splice additional stiffening to studs if site cut service holes exceed 1/3 the width of the member
15bc5eb8-1aaf-42a4-8350-0020365bd0f8 | checkpoint | Metal separation: Provide isolation layers & lagging to isolate incompatible metals
6bf52cd4-7d42-4db9-9407-7753a2bc1585 | checkpoint | Provide fire, smoke & acoustic sealing where indicated on the drawings/details
1d2974ea-46e4-488c-9bce-82b9ee0b375c | checkpoint | Provide vermin barriers (where indicated on drawings / required)
df093996-771a-41b8-89d0-119ab83a168c | section | BVT Engineering Inspection
bb3edf92-f095-442e-b40c-1919db15c0c2 | checkpoint | BVT Sign Off - please attach any relevant documentation & photos
0f2a2dab-fe27-4f34-a4f0-44be9646f32b | checkpoint | BVT to complete construction monitoring on walls, in line with Rondo PS1 & provide report.
e678cb1e-2035-4abc-8213-714330e26a0c | checkpoint | BVT to complete in depth sign-off sheet for all walls once engineering & construction is confirmed.B
3c295086-50d9-492d-9011-0189b1d9f4ac | section | In-Wall Noggins / Fixtures
9dba37bc-2f0f-419d-88ad-0f2528154786 | checkpoint | Fix noggins as required for the framing system, skirting, door stops & to accommodate in-wall & in-ceiling services
0551c039-a852-49e5-88bd-d86d19e85150 | section | Insulation
f71aa428-15e9-461a-ba68-d03763e65b2b | checkpoint | Install acoustic. Refer to Component & Finishes Schedule, drawings & details.
28c6fce0-7561-4568-8ce5-b3abace672fe | checkpoint | Thermal insulation Refer to Component & Finishes Schedule, drawings & details (Works Completion Test – IR to inspect – WCT-08)
3faa033e-be76-4b48-a255-9bf3f33e3365 | section | In Wall Services
ee4c652e-ba3a-4326-b7d2-7e46311a759d | checkpoint | All service trades to complete sign-off on walls as per room sign of sheet prior to sheeting commencement.
0600ebd2-c602-44be-9c35-07ea70f9fe46 | section | Sign Offs
f9df4baf-a32c-456c-a0ce-6a3b1a057267 | checkpoint | Wadsworth final sign off - add signature
6ff507da-221c-4508-9757-73625e9cdddc | checkpoint | CPB final sign off - add signature
a709390b-4ed6-47df-9e56-ce5b205d9e01 | checklist | Partition Lining ITP V2 |  | Partition Lining ITP
dc459b33-d22a-4643-8207-2fc618299e21 | section | Board Lining
4a95412f-9c46-4983-87e0-a5c07b2a3c65 | checkpoint | Area ready & accessible
1d7fe3f8-0a75-5f5e-85c1-893f8a653b6e | note | 1400 Series & USG BORAL Specifications
e985c137-1cac-4db3-9ac0-7c214809a279 | checkpoint | Inspect the sheeting of walls as per BORAL specification & checklist below
440a1416-544f-4812-b778-e3eba520b19d | checkpoint | Run sheets across the framing members (refer BORAL standard details)
4452f96d-1353-44b8-be73-e9935a9f8183 | checkpoint | Stagger end joints in a brick pattern & locate them on framing members away from the corners of large opening
0d4c8d25-a3c3-4e1f-b551-4849d4518899 | checkpoint | Achieve level of finish as specified in the material, component & finishes schedule (Sec 4.2)
6855c3cb-589d-43e1-9072-5e742884907a | checkpoint | Multiple sheet layers: Fill & flush up all joints & fixings in each layer & caulk up perimeters & penetrations before commencing succeeding layers
28d67939-0c70-4af6-8e6b-545395fe3d64 | checkpoint | Stagger all sheet joints by minimum 200mm
1ff67000-b4c3-460c-affe-bf28bf0d0905 | section | Doors & Internal Windows
6690d30d-bb71-4e78-8802-f4aaaed12e83 | checkpoint | Doors & internal window opening: check door schedule, window schedule & kit of parts
e48487bd-8f08-4c93-8d63-c8bb0f1055fe | checkpoint | Board joints: Do not fix the lining to abutting building surfaces
b1577c20-986a-4e4d-9d89-41b6531ab863 | checkpoint | Butt joints: Provide perforated paper reinforcing tape
780c4a39-690f-4b5d-b0e8-ef2b709a55db | checkpoint | External corners: Provide matching purpose made beads
a792f733-21f2-4bf9-b183-87712282334b | checkpoint | Internal corners: Provide paper tape & bedding compound
930dda9f-a7ba-4ab8-9cdb-016ca596eb66 | checkpoint | Provide sealants at junctions between partition systems & with other building elements
cf0b2d6e-d070-425c-85a0-0995cf620c31 | checkpoint | Provide trim such as beads, moulding & stops to make neat junctions between lining components, finishes & adjacent surfaces
48f3ca6b-b2e0-4458-81b0-c4db3d415dec | section | Fire Walls
28e5c44a-2140-4a85-a40b-e6f466b083cf | checkpoint | 1st Fix - Installed as per BORAL design & install specification
f7fca3e1-7a8b-4676-b675-f9f6bb7540d8 | checkpoint | Council/Holmes Inspection of first fix (if required)
35d58bf1-315e-4754-956f-3da89ceda357 | checkpoint | 2nd Fix - Installed as per BORAL design & install specification
54fa40df-4ac2-4221-9581-83a4389fc52a | checkpoint | Council/Holmes Inspection of second fix (if required)
a51dde57-0c7b-44a9-9ec3-f1dffef122be | checkpoint | Correct FRL achieved
551d294f-ba01-43d2-8e8b-a453ccec9259 | checkpoint | Deflection heads & all joints sealed, taped & set (fire sealant is approved prior)
19366fe9-1a64-473d-8f17-377c70d4e18e | checkpoint | All penetrations through fire walls below & above ceiling protected/sealed
5bbe2842-9a69-4f51-9751-68933ff4f7ac | section | Smoke Walls
cff7a502-c04a-46ff-9637-9920e8c3d2d3 | checkpoint | 1st Fix - Installed as per BORAL design & install specification
c80550b5-d6ef-42d4-a038-83fcb01e365e | checkpoint | Council/Holmes Inspection of first fix (if required)
3dd4b1f3-d5e3-4534-bd37-b194c4735af6 | checkpoint | 2nd Fix - Installed as per BORAL design & install specification
aacb6793-0da4-4155-86c2-ec26bebc6917 | checkpoint | Council/Holmes Inspection of second fix (if required)
1e2fd878-8fd8-49bb-8ded-6ba8f832872b | checkpoint | Deflection heads & all joints sealed, taped & set (sealant is approved prior)
c9556ddd-1ed3-4e09-91d8-0f0e3a916671 | checkpoint | All penetrations through smoke walls below & above ceiling protected/sealed
29362e10-a840-4171-bed2-e4d459e53602 | section | Acoustic Walls
6e560a94-7a85-4f29-8af3-13f4dcffc7e8 | checkpoint | Installed as per BORAL design & install specification.
0d5ba871-1363-4446-b54d-0570ab6d72d7 | checkpoint | Deflection heads & all joints sealed, taped & set (sealant is approved prior)
e017d0cd-d537-42c8-b12d-88fca0d30f86 | checkpoint | All penetrations through acoustic walls below & above ceiling protected/sealed
938e29e1-f39d-421d-9643-8c72c232398d | section | Sign Offs
90a0f360-4d43-4135-b1f1-c8a5a24a4b8b | checkpoint | Wadsworth final sign off - add signature
15e91fa1-36dc-40dd-b9b1-2ced8a8d5519 | checkpoint | CPB final sign off - add signature
a9ee0463-b1b4-4130-ab14-d7e8cc263eca | checklist | Retrofit Bar Installation |  | Retrofit Bar Installation
e56ee382-58af-48d2-ba40-7dfd9642dd0a | section | Prior to Commencement – The following documentation are completed and approved:
fe8d409d-6133-4d3b-9c92-5db498258f65 | checkpoint | Shop drawings submitted and approved by CPB.
c8dea5ad-63d7-48b9-a36e-d6f3975aea7e | signoff | Shop Drawing Holdpoint.
88b8deb5-b753-4a21-b3c9-c845d94680ed | section | Take Delivery of Retrofit Bar:
7233de39-aed0-4e5c-80d9-15c2154d45ea | checkpoint | The Retrofit Bar has been identified and is the correct size to the shop drawings.
3121c6fc-0706-4567-915d-4f177db9eee4 | checkpoint | The Retrofit Bar is sound & undamaged. No rusting to Retrofit Bar.
192e0efe-c72d-4fd9-a77b-82efef7cbc60 | section | Preinstall Window Checks Prepared to Receive Retrofit Bar:
8aeb5b0a-4e93-4c66-9e74-bd971957e131 | checkpoint | Preinstalled window has been QA approved and allocated by CPB.
17575763-f4f0-48e3-aad0-917f7b504af2 | checkpoint | Drill fixing holes to preinstalled window to receive Retrofit Bar.
e1344ce9-83da-4f31-b43a-be4330ea5028 | section | Retrofit Bar Installation:
b1999d78-d5fa-441a-a091-c0b3162a793f | checkpoint | Shop Drawings and typical details for appropriate Retrofit Bar install have been sighted & understood.
98ede4f5-5935-41a5-aa87-e5d63e3af4af | checkpoint | Glazing tape inserted between bar and glazing.
46853325-78a9-4881-a68a-b66694e0799d | checkpoint | The correct fixings have been used or reused, are fully driven home, and tensioned. The head of fixings is not covered or sealed.
53dbf102-67cd-4e62-a1a6-880e203d7b6e | checkpoint | All fixings installed & tightened with good hold & no signs of stripping.
d945121b-e7cb-45ad-ade7-6d69b86e40a8 | checkpoint | The Retrofit Bar is installed plumb, square, and at the correct preinstalled window.
96d47ad4-9de6-49aa-822f-45d8444dd97f | section | CPB Sign Off:
dabbc9d3-a2ec-4a31-9e28-84dbcc98bf8b | checkpoint | CPB to complete their QA checks, final checks & sign-off unit
a7bb3842-110e-4226-b3ac-5edcd46a517d | signoff | CPB HOLDPOINT
57545d33-ff22-47c2-be2f-269041c4ab77 | checklist | SYS - Partition Lining ITP V1 |  | Partition Lining
c088ed6e-e8f7-4c70-b9a1-9f95d8d534d7 | section | Board Lining
53ce2f58-4153-4303-96e7-da8dfac548bd | checkpoint | Area ready & accessible
c08e9936-a498-5be5-8ef5-690ba532e933 | note | 1400 Series & USG BORAL Specifications
4f7588da-b0a3-4b7d-a145-00b7c66b3f85 | checkpoint | Inspect the sheeting of walls as per BORAL specification & checklist below
4365b0d1-5aad-4174-b54a-e97c485ad13c | checkpoint | Run sheets across the framing members (refer BORAL standard details)
f56cb52c-ac83-4ec4-9be7-b527dafda7de | checkpoint | Stagger end joints in a brick pattern & locate them on framing members away from the corners of large opening
d57cfc77-f362-4b27-b400-021b5785d253 | checkpoint | Achieve level of finish as specified in the material, component & finishes schedule (Sec 4.2)
16462055-ab04-48db-97b5-26a96e056b02 | checkpoint | Multiple sheet layers: Fill & flush up all joints & fixings in each layer & caulk up perimeters & penetrations before commencing succeeding layers
938a1f17-def2-41c5-8360-abb5c63108a7 | checkpoint | Stagger all sheet joints by minimum 200mm
f2fdb579-ff64-48b0-b646-2ab6e489f5cb | section | Doors & Internal Windows
ede97bc9-9f28-4cbf-9a9d-f5fb7ae2f3c5 | checkpoint | Doors & internal window opening: check door schedule, window schedule & kit of parts
59254f12-1dd7-48b1-b4de-68383b852c8f | checkpoint | Board joints: Do not fix the lining to abutting building surfaces
337ac63c-7025-4035-b6af-ecf1c8d8c2f9 | checkpoint | Butt joints: Provide perforated paper reinforcing tape
9d503423-8216-4620-aaa5-730edbe7f116 | checkpoint | External corners: Provide matching purpose made beads
7684dfb1-9cf7-4aea-9bb3-73baf464c38a | checkpoint | Internal corners: Provide paper tape & bedding compound
5b362c5d-3f74-477e-8243-69713150a3b1 | checkpoint | Provide sealants at junctions between partition systems & with other building elements
772c5a01-8e08-4917-95f6-4820dae6d8e5 | checkpoint | Provide trim such as beads, moulding & stops to make neat junctions between lining components, finishes & adjacent surfaces
eea424ef-e095-43df-bb2a-c359cd02b388 | section | Fire Walls
0ee8af08-7931-4064-a3f7-6fb58ff0964f | checkpoint | Installed as per BORAL design & install specification
ea38d2a8-c2fa-48c6-988d-921d55b2c2e6 | checkpoint | Correct FRL achieved
47484404-a6dd-4802-a2bc-23c159892fa2 | checkpoint | Deflection heads & all joints sealed, taped & set (fire sealant is approved prior)
3d17cafd-1ccd-47a3-9157-3cf0b16af1e7 | checkpoint | All penetrations through fire walls below & above ceiling protected/sealed
6577ad1d-01d0-4f94-801d-99697a53b2f7 | section | Smoke Walls
320ba0b0-7f53-4314-bc1e-efc30f5eab9b | checkpoint | Installed as per BORAL design & install specification
4285b8b7-f007-496e-8989-744cf9925370 | checkpoint | Deflection heads & all joints sealed, taped & set (sealant is approved prior)
2b57a1d6-ed3c-409e-8d0c-0d1f69ed416e | checkpoint | All penetrations through smoke walls below & above ceiling protected/sealed
6f4ac8dc-8b8b-454e-87e8-3be727e41000 | section | Acoustic Walls
4a513b34-6118-4bb8-963b-16e295fb1613 | checkpoint | Installed as per BORAL design & install specification.
b7c2a1e2-9a99-42c6-a213-c222c32e8ba0 | checkpoint | Deflection heads & all joints sealed, taped & set (sealant is approved prior)
e299805b-5c82-4d4e-b1c6-296370fefd50 | checkpoint | All penetrations through acoustic walls below & above ceiling protected/sealed
36abb64c-fa1a-46b2-9eca-3f76e78b00e0 | section | Sign Offs
0454ba57-b719-464e-9d19-dfb2a0bdbff4 | checkpoint | Wadsworth final sign off - add signature
7d11346b-fd2f-465d-877a-2a2274ae3f55 | checkpoint | CPB final sign off - add signature
70e83bae-4df8-46f9-a487-d41cf1ebd83e | checklist | Threshold Installation |  | Threshold Installation
241ec1a9-7150-4041-bb36-0df341e6bb93 | section | Prior to Commencement – The following documentation are completed and approved:
4887e019-9ba2-46ce-ba97-6bbe941c8167 | checkpoint | Shop drawings submitted and approved by CPB.
5b8d82d8-2796-42ba-941e-69632cce77a0 | signoff | Shop Drawing Holdpoint.
c3e2a0dc-caf1-4150-a45e-4488ab957b53 | section | Take Delivery of Threshold:
79334f30-2af6-49f9-976e-a266da9efb2e | checkpoint | The Threshold has been identified and is the correct size to the shop drawings.
6abdb930-64fe-4500-a7f9-b77e131877ff | checkpoint | The Threshold is sound & undamaged. No rusting to Threshold.
aea5dba2-2ad8-49b1-ae8a-6730aebe3a60 | section | Preinstall Door Checks / Openings Prepared to Receive Threshold:
cac70f18-c97b-4267-87f0-b9d72e54353a | checkpoint | Preinstalled door has been QA approved and allocated by CPB.
99a73ff3-bc3e-48f3-bab7-b62bf5f68013 | checkpoint | Drill fixing holes to flooring to receive Threshold.
7b276e0a-2b2a-4f04-8bb0-caf99b16b47b | section | Threshold Installation:
95b79f42-c577-454c-af10-1c7037477ca1 | checkpoint | Shop Drawings and typical details for appropriate Threshold install have been sighted & understood.
c94332b2-6856-466e-800a-40e8af53c455 | checkpoint | The correct adhesive and fixings have been used, are fully driven home, and tensioned. The head of the fixings will finish flush with the threshold so no non pick is necessary.
ba6c1013-90a7-4457-b3c2-f88cf67a5cdd | checkpoint | The Threshold is installed at minimum allowed distance from the correct preintalled door leaf.
74ce7303-5afc-47d5-b625-93d894d0c830 | section | CPB Sign Off:
d0f5d88e-64c6-461b-bb49-d0f8b95dd732 | checkpoint | CPB to complete their QA checks, final checks & sign-off unit
3dff7bd8-bc28-4536-87ee-16754208b784 | signoff | CPB HOLDPOINT
dcccd0c9-ed49-46ba-9ad9-64794afb61d9 | checklist | Window Installation |  | Window Installation
e04a9e6f-bb45-4360-8e9d-e7ce02634704 | section | Prior to Commencement – The following documentation are completed and approved:
19f37b62-b5f5-4156-bc2a-3c9a2bdb960a | checkpoint | Shop drawings submitted and approved (BY PDS)
b8630895-a06e-4a04-af24-58a2862ef1e2 | signoff | Shop Drawing Holdpoint
066c6302-e3d4-4210-a238-cf61532a14fc | section | Take Delivery of Window Units:
ef2523be-ca92-4fe3-ac74-a09667629677 | checkpoint | The window has been identified and is the correct size to the shop drawings
27ad2aa1-c0c8-44f2-98f4-6b4ea6030d94 | checkpoint | The window is sound & undamaged. No rusting to frame, or door leaf.
33ce3192-5a04-4963-b0c0-137bdf81f14c | section | Preinstall Door Checks / Openings Prepared to Receive Windows:
12194e46-2312-47c9-948c-eec1abdaff58 | checkpoint | Opening has been allocated by CPB
54ae06e5-9fed-4565-a320-55de5d3ea8c6 | checkpoint | The window type is known and has been identified for fire rating, acoustic and containment
6c56730e-5993-490f-8b93-6f32063462de | section | Window Installation (Part 1):
d2d2718b-5807-49f9-a25c-0b497a8f29d4 | checkpoint | Shop Drawings and typical details for appropriate window install have been sighted & understood.
d28b89ee-60e1-479f-aed6-cc7013822443 | checkpoint | Check frame to ensure any penetrations or possible grout leak points not accessible after install are sealed (if applicable).
e4c2361c-6c90-4a6e-a98e-814a8bdc18fb | checkpoint | The correct fixings have been used, are fully driven home, and tensioned. The head of fixings is not covered and has not been sealed.
a40e04c2-a0d6-4147-a483-85e3e2370aa8 | checkpoint | Correct & adequate packers have been used. Packing is trimmed back so as not to impede correct sealant depth or wall lining install.
1aac14a9-08ff-4b50-bb6d-4f01e5b00711 | checkpoint | The window is installed plumb, square, and at the correct wall lining schedule.
346b91f2-eb4b-4963-8e44-bf0da2507664 | section | CPB Sign Off (Part 1):
ec2c9644-650b-42e4-93ae-01de9232eca2 | checkpoint | CPB to complete their QA checks on installed units, including completing witness point of our install to this point.
e95f3989-7cb7-49e9-8fc2-bafba1f10ca5 | signoff | CPB HOLDPOINT
bb019b20-572e-4d9e-bfa7-57291dc99a44 | section | Window Installation (Part 2):
8e33312c-4aae-478b-8c63-6a4490a55fa0 | checkpoint | Sealant is applied to correct depth on back rod as required.
9b15a886-00ce-470f-8764-7d8150a7e8d5 | checkpoint | Sealant is set back far enough to receive Non pick sealant by subsequent trade in prisoner accessible areas (if applicable).
8ce2fc57-866b-45f1-bedd-254a1fa55cdb | checkpoint | The head of the fixing bolts is packed & sealed using correct sealant filler.
8864d850-43db-4bd5-8812-3455386a3bd7 | checkpoint | Before grouting can commence, the sealant must have been allowed to fully cure
fff8de81-21ba-4842-961b-e5d125bf8897 | checkpoint | Check for any potential leak points for grouting.
da7c7806-04c2-4abc-b062-a2f8ae474198 | checkpoint | Leaf to frame clearances checked prior to grouting
974b1d6b-1016-46ae-b72d-3770f9d1ac1b | checkpoint | Open Glass Pallet & check glass is undamaged, correct sizes including type & thickness
5bc80bfa-76c0-436d-9a27-646469b6435f | checkpoint | Protective Film to glass is peeled back enough to allow sealant to bond fully to glass
803ad4b5-c265-441a-8c5f-fea8c6899151 | checkpoint | Glazing tape set to 6mm from edge of glass to achieve correct sealant depth
af187e5b-377a-4bb6-99f9-cdca174aaa2e | checkpoint | DOWSIL 791 silicone weatherproofing sealant applied to exterior glazing in accordance with installation instructions
a2702646-b144-4eed-8c66-d2bcbc130152 | section | Final Checks
0389fe1d-eeba-460a-8ca0-43bdc3d56135 | checkpoint | Window has been sealed
eb9c8091-1b01-4e50-ac45-32742208ba94 | checkpoint | Window has been grouted (if applicable)
800d27de-e462-4c0c-ac89-55301a0d179f | checkpoint | Window has no damage or rustvisible
2321904f-2b50-4319-b437-5fc178100621 | checkpoint | Glass checked for damage, scratches & ensure protective film is still in place
1b99bb99-d05a-4e7c-8fb6-8bc9ff13385e | checkpoint | Sealant continuous, clean & no air pockets
057f5d70-d4e6-4e4a-a8bb-b0b934931ea3 | checkpoint | All fixings installed & tightened with good hold & no signs of stripping
1d65a5a1-52fe-4d1c-a706-ef631b1bd028 | checkpoint | Window has been cleaned and is in a satisfactory standard to hand over to the subsequent trade (Hardware install by PDS)
4423e0b9-2c74-45e1-b6db-98c65ed85155 | section | CPB Sign Off (Part 2):
c277e4c5-3e2a-4ea5-b816-5916f496f162 | checkpoint | CPB to complete final checks & sign-off unit
511819ac-4a96-45de-aaf7-24e8da760924 | signoff | CPB HOLDPOINT
e1bf6f79-852e-408e-9d97-fef27d99ad52 | section | Final Sealant
1a494057-00e5-4f87-bfe1-fc1e5496abb4 | checkpoint | Final sealant installed at junction of window frame & cladding (where applicable)
8bed517c-2460-4caf-bbe9-4e9ef2050cfe | section | Site Hose Testing for External Windows:
ade53f84-b684-4636-abf2-3d5667971487 | checkpoint | Each window is to be site hose tested by approved & certified water testing specialists.
d1256493-2e6c-4b32-aa19-7383021c7c46 | checkpoint | Test Results to be included with this ITP