## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | AXXX - West Dapto - ITC 001 (ITP001) - Subsoil and Formation Drains | [5 empty] | AXXX - West Dapto - ITC 001 (ITP001) - Subsoil and Formation Drains
checkpoint | 1 - Preparation Works
label | REQUIREMENTS / REFERENCE: Project Safety Plan, Project Environment Plan
label | ACCEPTANCE CRITERIA:
label | • All site personnel inducted, required SWMS completed and signed, Safety Plan approved
label | • ERSED controls installed on site, air quality visually monitored for dust etc due to construction activities, Environment Plan approved
label | • Contact DBYD and complete excavation permit, extent of works set out with survey pegs
text | INSPECTION:
checkpoint | 2 - Materials
label | REQUIREMENTS / REFERENCE:
label | • 1172 Cl 2
label | • 1172 Cl 6
label | • WCC 7000 C07
label | ACCEPTANCE CRITERIA:
label | • Subsoil agg line: 100mm sleeved subsoil drainage pipe, slotted uPVC or perforated, ribbed HDPE to AS2439.1. Minimum class for uPVC pipe and fittings shall be Class 12.
label | • Fabric: Non-woven geotextile, Strength Class A.
label | • Drainage aggregate: 10 or 20mm stone size drainage aggregate.
label | • No Fines concrete: 20mm no fines concrete (without liner), 8:1 aggregate to cement ratio, f’c = 10 MPa, water / cement ratio = 0.41
text | INSPECTION:
checkpoint | 3 - Excavation – Inspection of trench and bedding
label | REQUIREMENTS / REFERENCE:
label | • 1172 Cl 3.2
label | • 1172 Cl 3.3
label | • 1172 Cl 3.4
label | • 1172 Cl 3.7
label | ACCEPTANCE CRITERIA:
label | • Excavate trench as per drawings, backfill any over-excavation to the required level and compact to at least 95% relative compaction.
label | • Place 50mm thick compacted filter material or no fines concrete as per the drawings to create a bedding layer
label | • HOLD POINT: Client will inspect trench alignment and compaction of bedding prior to pipe placement
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 4 - Installation – Survey of laid pipe
label | REQUIREMENTS / REFERENCE:
label | • 1172 Cl 3.2
label | • 1172 Cl 3.3
label | • 1172 Cl 3.4
label | • 1172 Cl 3.7
label | ACCEPTANCE CRITERIA:
label | • Place sock-wrapped subsoils centrally within the trench on top of the filter material bedding at the correct dept, line and grades
label | • HOLD POINT: Complete survey of laid pipe levels and location of centre of pipe, survey the top of the subsoil pipe every 10 metres. Provide this survey to the Client
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Backfill
label | REQUIREMENTS / REFERENCE: 1172 Cl 3.5
label | ACCEPTANCE CRITERIA:
label | • Backfill with no fines concrete or filter material as per drawings.
label | • For no fines concrete, minimise any segregation of the concrete mix
label | • For filter material, compact in maximum 300mm layers, taking care not to damage the subsoil lines
text | INSPECTION:
label | COMMENTS / ATTACHMENTS: Concrete Pour Docket (if pouring no fines)
checkpoint | 6 - Testing
label | REQUIREMENTS / REFERENCE: 1172 Cl 3.9
label | ACCEPTANCE CRITERIA:
label | • If over-excavation has occurred (refer Activity #3), provide test result(s) showing 95% relative compaction was achieved here
label | • Completion tests: Pump clean water into the flush point at the start of each subsoil run until only clean water discharges at the outlet (Min. rate of water flow = 100 L / min at the flush point inlet)
text | INSPECTION:
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature