## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | AXXX - West Dapto - ITC 002 (ITP002) - Stormwater & Trench Drains Installation | [5 empty] | AXXX - West Dapto - ITC 002 (ITP002) - Stormwater & Trench Drains Installation
checkpoint | 1 - Preparation Works
label | REQUIREMENTS / REFERENCE: Project Safety Plan, Project Environment Plan
label | ACCEPTANCE CRITERIA:
label | • All site personnel inducted, required SWMS completed and signed, Safety Plan approved
label | • ERSED controls installed on site, air quality visually monitored for dust etc due to construction activities, Environment Plan approved
label | • Contact DBYD and complete excavation permit, extent of works set out with survey pegs
text | INSPECTION:
checkpoint | 2 - Materials – Flexible Plastic Pipes (1)
label | REQUIREMENTS / REFERENCE:
label | • AS/NZS 5065
label | • WCC 1352 Cl 2.3
label | • WCC 1352 Cl 1.4
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit certificate of conformance for all pipes and fittings used (if required)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 3 - Materials – Flexible Plastic Pipes (2)
label | REQUIREMENTS / REFERENCE: WCC 1352 Cl 1.4
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit sample of pipes and fittings to principal (if required)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 4 - Materials – Precast Concrete Drainage Structures
label | REQUIREMENTS / REFERENCE: WCC 1354 Cl 1.5
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submission of all quality documents specified in clause 1.5 at least 5 days prior to date of delivery (if required)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Setting Out (1)
label | REQUIREMENTS / REFERENCE: WCC 1351 Annex 4.1
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Details of any proposed changes to designed system 5 days before commencement (if required)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 6 - Setting Out (2)
label | REQUIREMENTS / REFERENCE:
label | • WCC 1351 Cl 3.1
label | • WCC 1351 Annex 4.1
label | • WCC 1121 Cl 3.1
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Notify principal that set-out of location design levels and design cover will be completed 3 days prior to set-out
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 7 - Soil Conditions (1)
label | REQUIREMENTS / REFERENCE: WCC 1351 Annex 4.1
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: 5 days prior to commencement of site activities, submit soil durability test results to the principal
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 8 - Soil Conditions (2)
label | REQUIREMENTS / REFERENCE: WCC 1351 Annex 4.1
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit a notification confirming soil type conforms to soil type used for stormwater system design
text | INSPECTION:
checkpoint | 9 - ERSED Controls, Temporary Drainage
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit to the Principal details of procedures / devices for temporary bypass drainage during construction
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 10 - Excavation (1)
label | REQUIREMENTS / REFERENCE: WCC 1351 Cl 3.3
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Provide notification 3 days prior to excavation of drainage structures (other than pipes) for an inspection of the drainage pit such that clear width of excavation is either:
label | • One third of excavation face height or a minimum of 300mm
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 11 - Excavation (2)
label | REQUIREMENTS / REFERENCE: WCC 1351 Cl 3.3
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Provide notice of completed excavation and compaction of foundation 1 day prior to commencement of drainage structure and foundation construction
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 12 - Inadequate Foundation Material
label | REQUIREMENTS / REFERENCE:
label | • WCC 1351 Cl 3.3
label | • WCC 1351 Annex 4.1
label | • WCC 1112 Cl 4.3
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Provide notification to the Principal of the area containing unsuitable material to support the drainage system
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 13 - Foundation Inspection
label | REQUIREMENTS / REFERENCE: WCC 1354 Annex 4.2
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Provide notice of completed excavation and compaction of foundations 1 day prior to the commencement of drainage structures and foundations
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 14 - Compaction of Subgrade - Culverts
label | REQUIREMENTS / REFERENCE: WCC 1351 Cl 1.4
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Provide notice to the Principal of an upcoming inspection 1 day prior to the compaction and suitability of subgrade under the culverts
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 15 - Rock Foundation (1)
label | REQUIREMENTS / REFERENCE: WCC 1351 Cl 3.3
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: If rock is encountered at foundation level, provide notice to Principal prior to proceeding, then excavate to a depth requiring by the pipe type and backfill with compacted selected fill (if required)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 16 - Rock Foundation (2)
label | REQUIREMENTS / REFERENCE: WCC 1354 Cl 3.2
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: If rock is encountered at the bottom of excavations for wingwalls and headwalls, provide notice to Principal at completion of excavation and compaction (if required)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 17 - Rock Foundation (3)
label | REQUIREMENTS / REFERENCE: WCC 1354 Cl 3.2
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: For gully pits and sumps, if full depth of excavation is in sound rock, construct a neatly formed pit of the required size and omit the concrete lining except to the wall adjacent and parallel to the road. Provide notice to Principal at completion of excavation and compaction of foundation (if required)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 18 - Inspection of Pipework Installation
label | REQUIREMENTS / REFERENCE: WCC 1352 Annex 4.1
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Provide notice to the Client for an inspection of each section of the installed and jointed pipework prior to the commencement of trench backfilling
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 19 - Installation of Precast Units
label | REQUIREMENTS / REFERENCE: WCC 1354 Cl 1.6
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Provide notice to the Client of the anticipated date of precast pit installation(s) 5 days prior to the anticipated date
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 20 - Backfill of Pipes and Precast Drainage Structures
label | REQUIREMENTS / REFERENCE:
label | • AS/NZS 2566.2
label | • WCC 1354 Cl 3.6
label | ACCEPTANCE CRITERIA:
label | • Compact bedding and backfill as per WCC Specifications and requirements stated in the project Drawings
label | • Provide compaction and moisture test results (if required)
text | INSPECTION:
label | COMMENTS / ATTACHMENTS: Compaction and moisture test results
checkpoint | 21 - Backfilling of In-Situ Drainage Structures
label | REQUIREMENTS / REFERENCE:
label | • WCC 1354 Cl 3.6
label | • WCC 1351 Cl 3.4
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Do not backfill against structures less than 14 days after placing concrete or before the concrete strength is more than 15 MPa. Provide notice of in-situ concrete structure backfill 2 days prior to date of backfill (if required)
text | INSPECTION:
label | COMMENTS / ATTACHMENTS: Concrete test results
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 22 - Compaction Adj. to Culverts or Drainage Structures
label | REQUIREMENTS / REFERENCE: WCC 1351 Annex 4.1
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Prior to proceeding with the entire backfilling process, provide notice of an inspection to the Principal to observe the compaction around culverts to check compliance
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 23 - Compaction of Pipe Drainage Bedding
label | REQUIREMENTS / REFERENCE: WCC 1351 Annex 4.1
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: When required to cementitiously stabilise concrete pipe bedding and haunch zones, provide notice to the Principal of the compaction of drainage bedding prior to proceeding (if required)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 24 - Construction Traffic
label | REQUIREMENTS / REFERENCE: WCC 1351 Cl 3.1
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: If proposing to move heavy construction plant or vehicles over pipe or box culvert structures provide protective measures. Submit certificate of verification of protective measures 5 days prior to installation
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 25 - Completion of Works
label | REQUIREMENTS / REFERENCE: WCC 1351 Cl 3.9
label | ACCEPTANCE CRITERIA:
label | • Inspect drainage structures first upon completion of all drainage structures and prior to commencement of pavement construction above, and again no more than 14 days prior to completion. Verify the works are within the specified tolerances, there are no visual signs of structural failure, and there is no obstruction to the flow of water
label | • On completion of the drainage system, flush all pipes clean from end to end and leave in working order
text | INSPECTION:
label | COMMENTS / ATTACHMENTS:
label | • CCTV / Inspection records (Initial inspection)
label | • CCTV / Inspection records (Final inspection)
checkpoint | 26 - Works As Executed (WAE) Drawings
label | ACCEPTANCE CRITERIA:
label | • Provide Works As Executed (WAE) Drawings and Survey Reports for the completed works
text | INSPECTION:
label | COMMENTS / ATTACHMENTS: WAE Drawings, Survey Report(s)
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature