## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | AXXX - West Dapto - ITC 004 (ITP004) - Clearing and Grubbing, Topsoil Strip | [5 empty] | AXXX - West Dapto - ITC 004 (ITP004) - Clearing and Grubbing, Topsoil Strip
checkpoint | 1 - Preparation Works
label | REQUIREMENTS / REFERENCE: Project Safety Plan, Project Environment Plan
label | ACCEPTANCE CRITERIA:
label | • All site personnel inducted, required SWMS completed and signed, Safety Plan approved
label | • ERSED controls installed on site, air quality visually monitored for dust etc due to construction activities, Environment Plan approved
label | • Contact DBYD and complete excavation permit, extent of works set out with survey pegs
text | INSPECTION:
checkpoint | 2 - Clearing and Grubbing Plan
label | REQUIREMENTS / REFERENCE: 1111 Cl 2.1
label | ACCEPTANCE CRITERIA:
label | • Submit the following, as detailed in WCC 1111 Section 2
label | • HOLD POINT: Submission of Clearing and Grubbing Plan
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 3 - Weed Management Plan
label | REQUIREMENTS / REFERENCE: 1111 Cl 2.1
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submission of Weed Management Plan
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 4 - Clearing Report
label | REQUIREMENTS / REFERENCE: 1111 Cl 2.1
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submission of Clearing Report
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Survey Plan of Clearing Area
label | REQUIREMENTS / REFERENCE: 1111 Cl 2.3
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit a survey plan showing the proposed area for clearing to confirm the clearing perimeters
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 6 - Peg Out of Clearing Area
label | REQUIREMENTS / REFERENCE: 1111 Cl 2.3
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Peg out area for clearing
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 7 - Clearing Method Statement
label | REQUIREMENTS / REFERENCE: 1111 Cl 2.3
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit a method statement for clearing including proposed methods, equipment and materials
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 8 - Method Statement for Work in Exclusion Zones
label | REQUIREMENTS / REFERENCE: 1111 Cl 3.1
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit a method statement for work within exclusion zone and driplines
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 9 - Notice of Protected Trees
label | REQUIREMENTS / REFERENCE: 1111
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Notice of trees to be protected
label | • Display a sign in a prominent position at each entrance to site, warning that trees and other plants are to be protected during the contract works
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 10 - Marking of Trees
label | REQUIREMENTS / REFERENCE: 1111
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Mark all trees documented for preservation or transplanting with ribbon markers
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 11 - Marking of Unsound Trees
label | REQUIREMENTS / REFERENCE: 1111
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Mark any unsound trees in the road reserve, but outside limits of clearing
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 12 - Additional Weed Control
label | REQUIREMENTS / REFERENCE:
label | • 1111 Cl 3.7
label | • 1111 Cl 3.8
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Identify any additional areas that require weed control
label | • Treatment of cleared vegetation as necessary and as per Section 3.7
label | • Re-use materials wherever possible
label | • Walk site after completion of clearing to identify any further trees or stumps that require removal
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 13 - Topsoil Strip
label | REQUIREMENTS / REFERENCE: 0222 Cl 3.4
label | ACCEPTANCE CRITERIA:
label | • If the following are encountered, notify client of as-found site conditions: Bad ground, discrepancy in site conditions, rock, springs and seepages, topsoil more than 100mm deep
label | • Strip topsoil to a maximum depth of 200mm and remove if unsuitable for re-use
label | • Stockpile topsoil intended for re-use as per Specification requirements
text | INSPECTION:
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature