## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | AXXX - West Dapto - ITC 005 (ITP005) - Pre-Commencement | [5 empty] | AXXX - West Dapto - ITC 005 (ITP005) - Pre-Commencement
checkpoint | 1 - Preparation Works
label | REQUIREMENTS / REFERENCE: Project Safety Plan, Project Environment Plan
label | ACCEPTANCE CRITERIA:
label | • All site personnel inducted, required SWMS completed and signed, Safety Plan approved
label | • ERSED controls installed on site, air quality visually monitored for dust etc due to construction activities, Environment Plan approved
label | • Contact DBYD and complete excavation permit, extent of works set out with survey pegs
text | INSPECTION:
checkpoint | 2 - Pre-start Documentation
label | REQUIREMENTS / REFERENCE: Project Specific Specifications
label | ACCEPTANCE CRITERIA:
label | • Submit the following as per the Project Specific Specification:
label | o All security required under the Contract
label | o Evidence of all insurance required to be effected and maintained
label | o Contract Program
label | o Work Health and Safety Management Plan
label | o Construction Environmental Management Plan
label | o Quality Management Plan
label | o Staging Plan
label | o Traffic and Pedestrian Management Plan
label | o Dilapidation Report
text | INSPECTION:
checkpoint | 3 - Site Compound Facility Details
label | REQUIREMENTS / REFERENCE: Project Specific Specifications
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submission of site compound facilities details including location, arrangements and appearance
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 4 - Client Accommodation Details
label | REQUIREMENTS / REFERENCE: Project Specific Specifications
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submission of Client accommodation details including location in relation to dust and noise generating activities, layout of compound, internal layout of buildings, furniture provided, security measures, program for its construction
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Environmental Management Plan
label | REQUIREMENTS / REFERENCE: 0173
label | ACCEPTANCE CRITERIA:
label | • Submit the following as per WCC 0173:
label | o Environmental Management Plan (EMP) (HP)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 6 - Unexpected Finds
label | REQUIREMENTS / REFERENCE: 0173
label | ACCEPTANCE CRITERIA:
label | • Submit the following as per WCC 0173:
label | o Details of any unexpected finds (HP)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 7 - Non-Conforming Items
label | REQUIREMENTS / REFERENCE: 0173
label | ACCEPTANCE CRITERIA:
label | • Submit the following as per WCC 0173:
label | o Details of any non-conforming items (HP)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 8 - Removal or Rectification of Enviro. Issues
label | REQUIREMENTS / REFERENCE: 0173
label | ACCEPTANCE CRITERIA:
label | • Submit the following as per WCC 0173:
label | o Invitation to witness completion of removal or rectification of environmental issues (WP)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 9 - Submission of Control Plans
label | REQUIREMENTS / REFERENCE: 0173
label | ACCEPTANCE CRITERIA:
label | • Submit the following items as per WCC 0173:
label | o Ground contamination control plan
label | o Air quality control plan
label | o Water quality control plan
label | o Noise and vibration control plan
label | o Flora and fauna control plan
label | o Cultural heritage management plan
label | o Weed management control plan
label | o Erosion and sediment control
text | INSPECTION:
checkpoint | 10 - Submit ESCP
label | REQUIREMENTS / REFERENCE: 1102
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit ESCP as detailed in 1102
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 11 - Submit embankment survey
label | REQUIREMENTS / REFERENCE: 1102
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit a survey of embankments
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 12 - Submit section plans
label | REQUIREMENTS / REFERENCE: 1102
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit section plans
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 13 - Initial install of sediment controls
label | REQUIREMENTS / REFERENCE: 1102
label | ACCEPTANCE CRITERIA:
label | • Give inspection notice for:
label | o Initial installation of sediment controls (HP)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 14 - Stockpile protection measures
label | REQUIREMENTS / REFERENCE: 1102
label | ACCEPTANCE CRITERIA:
label | • Give inspection notice for:
label | o Stockpile protection measures in place (WP)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 15 - Site access and exit vehicle decontam.
label | REQUIREMENTS / REFERENCE: 1102
label | ACCEPTANCE CRITERIA:
label | • Give inspection notice for:
label | o Access and exit areas – Decontamination of vehicles (WP)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 16 - Fencing and protection of areas
label | REQUIREMENTS / REFERENCE: 1102
label | ACCEPTANCE CRITERIA:
label | • Give inspection notice for:
label | o Fencing and protection of areas (WP)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 17 - Construction and lining
label | REQUIREMENTS / REFERENCE: 1102
label | ACCEPTANCE CRITERIA:
label | • Give inspection notice for:
label | o Construction and lining (WP)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 18 - Temporary sediment traps
label | REQUIREMENTS / REFERENCE: 1102
label | ACCEPTANCE CRITERIA:
label | • Give inspection notice for:
label | o Temporary sediment traps and batter protection (WP)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 19 - Removal of temporary ERSED controls
label | REQUIREMENTS / REFERENCE: 1102
label | ACCEPTANCE CRITERIA:
label | • Give inspection notice for:
label | o Removal of temporary erosion and sedimentation works (WP)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 20 - Completion of cleaning
label | REQUIREMENTS / REFERENCE: 1102
label | ACCEPTANCE CRITERIA:
label | • Give inspection notice for:
label | o Completion of cleaning (WP)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 21 - Inspection and Test Plans
label | REQUIREMENTS / REFERENCE: Project Specific Specifications
label | ACCEPTANCE CRITERIA:
label | • Submit ITPs two weeks before any work under construction
text | INSPECTION:
checkpoint | 22 - Protection of Surveyor Marks
label | REQUIREMENTS / REFERENCE: 0136
label | ACCEPTANCE CRITERIA:
label | • Provide verification that all permanent survey marks have been identified
label | • Preserve survey infrastructure as needed
label | • WITNESS POINT: Obtain approval and transfer permanent surveyor marks clear of operations
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 23 - Digital Design Model Discrepancies
label | REQUIREMENTS / REFERENCE: 0136
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Check the digital design model and notify Client of discrepancies between the model and the drawings
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 24 - Adjoining Property
label | REQUIREMENTS / REFERENCE: 0136
label | ACCEPTANCE CRITERIA:
label | • Submit to owners and occupants of adjoining property written notice of intention to commence work and an outline description of the type and extent of works
text | INSPECTION:
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature