## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | AXXX - West Dapto - ITC 006 (ITP006) - Open Drains | [5 empty] | AXXX - West Dapto - ITC 006 (ITP006) - Open Drains
checkpoint | 1 - Preparation Works
label | REQUIREMENTS / REFERENCE: Project Safety Plan, Project Environment Plan
label | ACCEPTANCE CRITERIA:
label | • All site personnel inducted, required SWMS completed and signed, Safety Plan approved
label | • ERSED controls installed on site, air quality visually monitored for dust etc due to construction activities, Environment Plan approved
label | • Contact DBYD and complete excavation permit, extent of works set out with survey pegs
text | INSPECTION:
checkpoint | 2 - Road Opening Permit
label | REQUIREMENTS / REFERENCE: WCC 1121 Annex. 4.1
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: 10 days prior to commencement on site, submit to the Principal, a road opening permit
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 3 - Materials
label | REQUIREMENTS / REFERENCE: WCC 1121 Cl 2.5
label | ACCEPTANCE CRITERIA:
label | • Geotextile material conforms to requirements of Project Drawings and Specifications
text | INSPECTION:
label | COMMENTS / ATTACHMENTS: Details of geofabric / geotextile used on site
checkpoint | 4 - Temporary Drainage
label | REQUIREMENTS / REFERENCE: WCC 1121 Cl 1.4
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit details of procedures / devices to maintain effective drainage of the work area during construction, 10 days prior to site commencement
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Open Drain Set-out
label | REQUIREMENTS / REFERENCE: WCC 1121 Annex. 4.1
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: 5 days prior to set-out of the open drain, submit to the Principal details of any changes to the design of the open drain (if required)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 6 - Set-out of Open Drains
label | REQUIREMENTS / REFERENCE: WCC 1121 Cl 3.1
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: 3 days prior to set-out, provide a notice of inspection to the Principal
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 7 - Location of Open Drains
label | REQUIREMENTS / REFERENCE: WCC 1121 Cl 3.2
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: 1 day before setting out, provide notice to the Principal of the location of open drains
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 8 - Excavation of Open Drains
label | REQUIREMENTS / REFERENCE: WCC 1121 Cl 3.2
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Provide notice to the Principal of the grade of the excavated open drain
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 9 - Excavation below natural channel
label | REQUIREMENTS / REFERENCE: WCC 1121 Cl 3.2
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: In the event of overexcavation or excavation below the level of the natural channel, backfill with suitable material and compact. Provide notice of the Principal of backfilling with suitable material (if applicable)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 10 - Surplus Material
label | REQUIREMENTS / REFERENCE: WCC 1121 Cl 3.2
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: In the event of surplus material, place excavated material to form embankments to lower side of drains or remove spoil stockpiles as required. Provide notice to the Principal of backfilling with suitable material (if applicable)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 11 - Table Drains
label | REQUIREMENTS / REFERENCE: WCC 1121 Cl 3.3
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Provide notice to the Principal of the location of table drains, swales and depressed medians (if applicable)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 12 - Compaction
label | REQUIREMENTS / REFERENCE: WCC 1121 Cl 3.2
label | ACCEPTANCE CRITERIA:
label | • Compact the excavated material to no less than 95% for standard compactive effort, to AS 1289.5.4.1
text | INSPECTION:
label | COMMENTS / ATTACHMENTS: Compaction test results
checkpoint | 13 - Completion of Works
label | REQUIREMENTS / REFERENCE: WCC 0257 Cl 3.4
label | ACCEPTANCE CRITERIA:
label | • Spread topsoil, line channel with organic fibre mat or geotextile as per Project Drawings and Specifications
label | • Complete any vegetation within 7 days of the open drain excavation
text | INSPECTION:
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature