## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | AXXX - West Dapto - ITC 008 (ITP008) - Kerbs and Gutters | [5 empty] | AXXX - West Dapto - ITC 008 (ITP008) - Kerbs and Gutters
checkpoint | 1 - Preparation Works
label | REQUIREMENTS / REFERENCE: Project Safety Plan, Project Environment Plan
label | ACCEPTANCE CRITERIA:
label | • All site personnel inducted, required SWMS completed and signed, Safety Plan approved
label | • ERSED controls installed on site, air quality visually monitored for dust etc due to construction activities, Environment Plan approved
label | • Contact DBYD and complete excavation permit, extent of works set out with survey pegs
text | INSPECTION:
checkpoint | 2 - Materials
label | REQUIREMENTS / REFERENCE:
label | • 1122
label | • 0319
label | • WCC 7000 C10
label | ACCEPTANCE CRITERIA:
label | • Confirm concrete mix design is acceptable for use with Client
label | • 20 MPa concrete mix (28 day strength) as per WCC 7000 C10
text | INSPECTION:
checkpoint | 3 - Set-out of Demolition Works
label | REQUIREMENTS / REFERENCE: 1122
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Client inspection of set-out of any sawcutting to existing kerbs and gutters, footpaths, driveways, road pavements
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 4 - Temporary Drainage Arrangements
label | REQUIREMENTS / REFERENCE: 1122
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Details of procedures and / or devices for temporary drainage arrangements while the works are taking place
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Ground Preparation Works
label | REQUIREMENTS / REFERENCE:
label | • 0319
label | • 1122
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Client inspection of prepared foundation / base of future kerb and gutter, shaped and compacted
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 6 - Confirm Driveway Crossovers
label | REQUIREMENTS / REFERENCE: 0319
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Confirm location(s) of any driveway crossovers in kerbs, gutters and channels (if required)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 7 - Reconnect Property Stormwater
label | REQUIREMENTS / REFERENCE: 0319
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Reconnect and extend existing property stormwater outlets through to the new kerb and / or gutter (if required)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 8 - Certification of Completed Formwork
label | REQUIREMENTS / REFERENCE: 0319
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Certification of completed formwork conformance (if required)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 9 - Client Inspection of Formwork
label | REQUIREMENTS / REFERENCE: 0319
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Client inspection of completed formwork
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 10 - Client Inspection of Reinforcement
label | REQUIREMENTS / REFERENCE: 0319
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Client inspection of installed steel reinforcement including cores, fixings and embedded items fixed in place (if required)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 11 - Trial Sections
label | REQUIREMENTS / REFERENCE: 1122
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Construct a 3m trial section to the documented level of finish to show capability of the forming equipment and request Client inspection. Subject to approval, incorporate the trial section into the completed works
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 12 - Concrete Dockets and Records
label | REQUIREMENTS / REFERENCE:
label | • 0319
label | • 1122
label | ACCEPTANCE CRITERIA:
label | • Confirm weather is suitable for pouring concrete
label | • Complete concrete testing and keep pour records, if required
label | • Protect finished concrete and cure as needed
text | INSPECTION:
label | COMMENTS / ATTACHMENTS:
label | • Concrete pour and test records
label | • Concrete docket(s)
checkpoint | 13 - Stripping Formwork and Backfill
label | REQUIREMENTS / REFERENCE: 1122
label | ACCEPTANCE CRITERIA:
label | • Strip kerb and gutter works once concrete has achieved suitable strength
label | • Backfill stripped works as specified in drawings
label | • WITNESS POINT: Client inspection of completed backfill placed behind kerb and gutters
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 14 - Reinstatement of Damages
label | REQUIREMENTS / REFERENCE: 1122
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Reinstate any damage to footpaths, road pavement and services in the event of their damage during the works (if required)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature