## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | AXXX - West Dapto - ITC 009 (ITP009) - Traffic Management | [5 empty] | AXXX - West Dapto - ITC 009 (ITP009) - Traffic Management
checkpoint | 1 - Preparation Works
label | REQUIREMENTS / REFERENCE: Project Safety Plan
label | ACCEPTANCE CRITERIA:
label | • All site personnel inducted (includes environment and cultural)
label | • Required Safe Work Method Statements completed and signed
label | • Subcontractor’s safety plan/procedure approved
text | INSPECTION:
checkpoint | 2 - Environment
label | REQUIREMENTS / REFERENCE: Project Environment Plan
label | ACCEPTANCE CRITERIA:
label | • Traffic requirements in place as per Plan
text | INSPECTION:
checkpoint | 3 - Traffic Management
label | REQUIREMENTS / REFERENCE: 1101 2.1
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submission of Traffic Management Plan (TMP) to the requirements of section 2.1
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 4 - Authority Approvals
label | REQUIREMENTS / REFERENCE: 1101 1.5
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submission of evidence of approvals for temporary traffic arrangements 4 weeks prior to works commencing
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Approval of Speed Zone Changes
label | REQUIREMENTS / REFERENCE: 1101 1.5
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submission of evidence of approvals for changes to speed zoning 5 weeks before implementation
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 6 - Construction of Temporary Pavement
label | REQUIREMENTS / REFERENCE: 1101 4.5
label | ACCEPTANCE CRITERIA:
label | • Permission to construct under traffic: Give 5 days’ notice of before carrying out work.
label | • WITNESS POINT: Notification of completed temporary pavement construction for inspection 3 days before installation of control devices and signs
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 7 - Completed Temporary Roadway
label | REQUIREMENTS / REFERENCE: 1101 4.6
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Notification of completed temporary roadway inclusive of traffic devices 3 days before opening to traffic. Written approval required to open to traffic
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 8 - Traffic Control Signs and Devices
label | REQUIREMENTS / REFERENCE:
label | • 1101 1.6
label | • 1101 4.7
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Notification of completed installation of any of the following:
label | o Signs and devices
label | o Alternative access
label | o Warning devices installation
label | • 1 day before opening to traffic
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 9 - Opening Completed Work
label | REQUIREMENTS / REFERENCE: 1101 4.7
label | ACCEPTANCE CRITERIA:
label | • Provide at least 10 working days’ written notice of the date of opening the Works to traffic. Obtain agreement for the procedure for opening including with the local Police.
label | • HOLD POINT: Notification of reinstatement of affected area by the works 2 days before opening to traffic
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature