## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Villaboard Checklist |  |  |  |  | Yes | Villaboard Checklist | 33ce16cc-9918-4693-98fd-96ce90a74653
checkpoint-status |  |  | checkpoint | Framing set out (i.e. stud and nog spacing) correct
checkpoint-status |  |  | checkpoint | GIB Lining base are secure and flush with each other with no protruding fixings
checkpoint-status |  |  | checkpoint | Gap between Villaboard edges/joints are at 1-2mm maximum
checkpoint-status |  |  | checkpoint | Villaboard must be installed dry
checkpoint-status |  |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status |  |  | checkpoint | Villaboard report sent through to client
checklist-flat |  |  | checklist | Concrete Testing Results |  |  |  |  | Yes | Concrete Testing Results Checklist | ba0bff2c-9138-49a3-9778-632888708b8e
checkpoint-status |  |  | checkpoint | Concrete testing results attached, checked and acceptable
holdpoint |  |  | signoff | Request Documentation / Signoff
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-flat |  |  | checklist | Seratone Checklist |  |  |  |  | Yes | Seratone Checklist | 594e03bf-0282-4e56-9ecb-65204f16b9ae
checkpoint-status |  |  | checkpoint | Panels received free of damage
checkpoint-status |  |  | checkpoint | Edges are well sanded
checkpoint-status |  |  | checkpoint | Aluminium jointer fixings are at 300mm centres
checkpoint-status |  |  | checkpoint | Adhesive applied at 300mm and double-sided tape at 400mm
checkpoint-status |  |  | checkpoint | Panels fitted are firmly installed against the wall
checkpoint-status |  |  | checkpoint | Seratone report sent through to client
checklist-flat |  |  | checklist | Site Concrete Checklist |  |  |  |  | Yes | Site Concrete Checklist | 89f81745-c9a6-4b90-abe9-ba4aab7eac00
checkpoint-status |  |  | checkpoint | Area accessible and substrate acceptable
checkpoint-status |  |  | checkpoint | Concrete specifications checked, correct and delivery docket photographed
checkpoint-status |  |  | checkpoint | Site concrete placed
checkpoint-status |  |  | checkpoint | Concrete placed to the correct height
checkpoint-status |  |  | checkpoint | Site concrete pour completed and finish acceptable
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-flat |  |  | checklist | Precast Panel / Column Placement |  |  |  |  | Yes | Precast Panel / Column Placement Checklist | 371c3e47-ce93-453a-a1bb-5d5a9f40ec81
checkpoint-status |  |  | checkpoint | Precast panel / column received and damage free
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Setout completed and clearly marked (heights and locations) ready for installation
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Installed in correct location with adequate seating
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Adequately braced
checkpoint-status |  |  | checkpoint | Panel / column install complete (checked location, height and level)
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All props removed for respective panels and stacked neatly
boolean | d2626006-dcd4-4ed8-a007-262242c2c355 |  | tickbox | Panel surface checked and all Livefirm responsibilities completed
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-flat |  |  | checklist | GIB Lining Ceiling Checklist |  |  |  |  | Yes | GIB Lining Ceiling Checklist | 4ca27759-5fd1-4afd-a4d4-001f7ac66b8c
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status |  |  | checkpoint | Area ready for GIB install
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Correct lining checked and approved and area specifics checked
checkpoint-status |  |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status |  |  | checkpoint | Sealant applied as per spec
checkpoint-status |  |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status |  |  | checkpoint | GIB Lining Ceiling completed correctly within specified tolerance, checked and approved
checkpoint-status |  |  | checkpoint | GIB Lining Ceiling report sent through to client
checklist-flat |  |  | checklist | Oak Battens |  |  |  |  | Yes | Oak Battens Checklist | 94c72856-9f76-45fc-a259-bcd4e72443cb
checkpoint-status |  |  | checkpoint | Manufacture defects discovered and disclosed before installation.
checkpoint-status |  |  | checkpoint | Oak Battens setup to correct height and locations?
checkpoint-status |  |  | checkpoint | Correct order of patterns for layout of each battens?
checkpoint-status |  |  | checkpoint | Correct spacing between battens in its corresponding area?
checkpoint-status |  |  | checkpoint | Screws are aligned straight, in correct position and all defect free?
checkpoint-status |  |  | checkpoint | General photos and notes
checkpoint-status |  |  | checkpoint | Straight, flush, levelled and plumb within an acceptable tolerance.
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-flat |  |  | checklist | GIB Stopping Checklist |  |  |  |  | Yes | GIB Stopping Checklist | 344d4109-7e1f-4fb1-a3df-a025063423fe
checkpoint-status |  |  | checkpoint | Area ready for GIB stopping
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Correct stopping product and applied correctly
checkpoint-status |  |  | checkpoint | Square stopping, slimlines and joints checked and acceptable
checkpoint-status |  |  | checkpoint | Adequate drying time between applications & no visible bubbling
checkpoint-status |  |  | checkpoint | GIB Stopping completed correctly within specified tolerance, checked and approved
checkpoint-status |  |  | checkpoint | GIB Stopping report sent through to client
checklist-sectioned |  |  | checklist | Allsheets 500 Checklist |  |  |  |  | Yes | Allsheets 500 DPM Checklist | cfbebb6c-0239-4c27-bd5c-b25091ccfddb
checkpoint-group |  |  | section | Substrate
checkpoint-status |  |  | checkpoint | Substrate - An even layer of sand (5mm) to blind all sharp aggregate basecourse materials
label | 8c1eb6a2-8732-4f40-b0f1-a5a7083a78ff |  | note | NOTE: Alternatively apply continuous woven or nonwoven separation fabric over prepared consolidated basecourse, with panels overlapped a minimum 150mm
checkpoint-status |  |  | checkpoint | Photos taken
checkpoint-group |  |  | section | Application
checkpoint-status |  |  | checkpoint | Application - Allow 1mm surplus each way per 1 degree C temperature drop per 10m of membrane
checkpoint-status |  |  | checkpoint | Application - Turn up all edges at vertical faces
checkpoint-status |  |  | checkpoint | Application - Extend a minimum 150mm min past form bulkheads/staged application to provide overlap to subsequent adjacent membrane sections
label | c9b5c7ad-b0c1-4469-87c7-476c979dab06 |  | note | NOTE: If used as ground cover in crawl spaces and sub floor cavities: Loose lay the membrane over the entire area to be covered. Overlaps and joining methods including sealing to piles and other protrusions are as per “Joining Instructions”.
checkpoint-status |  |  | checkpoint | Photos taken
checkpoint-group |  |  | section | Joining
checkpoint-status |  |  | checkpoint | Joining - Laps between Allsheet where jointing is required must be 100mm min lap
checkpoint-status |  |  | checkpoint | Joining - All surfaces must be clean, dry and free from oil, pooled water and grease. Overlap and apply Allco Seem Tape to the entire edge of the sheet of each adjacent membrane section. Apply approximately 1m at a time, ensuring 50% of the Seem Tape width is spanning between each side of the relevant joint being applied to. Pressure seal the joint using a 50mm – 100mm wide rubber hand roller
label | b9acd98e-6083-4bc6-90d6-58cedb2f2b31 |  | note | NOTE: You should form support under the membrane (wooden board) shifted progressively as jointing proceeds. Avoid tape and membrane wrinkles to achieve a smooth and moisture proof seal.
checkpoint-status |  |  | checkpoint | Photos taken
checkpoint-group |  |  | section | Penetration
checkpoint-status |  |  | checkpoint | Penetrations - To avoid penetration or any form of damage to the integrity of the membrane. Penetration of the membrane shall not be allowed except for protrusion of structural elements and permanent utilities. Coat all utilities with an approved wet applied sealant (Cetseal can be used), allow to cure and apply Allco Seem Tape around protrusion at membrane edge and seal with press roller.
label | 5f37c28d-e149-4f24-8535-1372e010a38a |  | note | NOTE: Care shall be taken that the membrane not be damaged by any other means and that the membrane shall be damp proof at the time concrete placement is completed
checkpoint-status |  |  | checkpoint | Photos taken
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-flat |  |  | checklist | Decortech Checklist |  |  |  |  | Yes | Decortech Checklist | 958e999b-e624-481e-bde5-1422b0500c89
checkpoint-status |  |  | checkpoint | Framing set out ie; studs or battens at 600mm ctr max
checkpoint-status |  |  | checkpoint | Correct fixings used. 200mm ctr max. at perimeter, 400mm ctr max through centre of panel
checkpoint-status |  |  | checkpoint | Negative detail between all edges of panels are at 3-5mm
checkpoint-status |  |  | checkpoint | Panels fitted are firmly installed against the wall
checkpoint-status |  |  | checkpoint | All cut edges are to be sanded smooth
checkpoint-status |  |  | checkpoint | All panels secured and flush with each other with no protruding fixings
checkpoint-status |  |  | checkpoint | Decortech report sent through to client
checklist-flat |  |  | checklist | Stair Timber Framing Checklist |  |  |  |  | Yes | Stair Timber Framing Checklist | c34b25ff-3f8a-4167-8683-df5d0da318a3
checkpoint-status |  |  | checkpoint | Correct thickness of plywood
checkpoint-status |  |  | checkpoint | Gaps between plywood sheets correct
checklist-flat |  |  | checklist | GIB Stopping Ceiling Checklist |  |  |  |  | Yes | GIB Stopping Ceiling Checklist | ec67ade6-61f6-4484-8139-2610794ab835
checkpoint-status |  |  | checkpoint | Area ready for GIB stopping
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Correct stopping product and applied correctly
checkpoint-status |  |  | checkpoint | Square stopping, slimlines and joints checked and acceptable
checkpoint-status |  |  | checkpoint | Adequate drying time between applications & no visible bubbling
checkpoint-status |  |  | checkpoint | GIB Stopping Ceiling completed correctly within specified tolerance, checked and approved
checkpoint-status |  |  | checkpoint | GIB Stopping Ceiling report sent through to client
checklist-flat |  |  | checklist | Precast Flooring Placement |  |  |  |  | Yes | Precast Flooring Placement Checklist | dbeccb54-bf9b-477f-91c8-332677c081ae
checkpoint-status |  |  | checkpoint | Precast Flooring received and damage free
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Setout completed and clearly marked (heights and locations) ready for installation
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Installed in correct location with adequate seating
boolean | b6401f74-0a81-4a3e-81a6-e294a7332e01 |  | tickbox | Bearing strip installed correctly as required
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast flooring install complete (checked location, height and level)
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-flat |  |  | checklist | Timber Framing Checklist |  |  |  |  | Yes | Timber Framing Checklist | 51a1ea9a-940f-48f2-a009-4a1daea4895f
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status |  |  | checkpoint | Area ready for Internal Framing install
checkpoint-status |  |  | checkpoint | Dimensions / locations checked and accurate
checkpoint-status |  |  | checkpoint | All frames are square
checkpoint-status |  |  | checkpoint | Frames are straight and level
checkpoint-status |  |  | checkpoint | Fixings are correct
checkpoint-status |  |  | checkpoint | Any bracing requirements installed
checkpoint-status |  |  | checkpoint | Nogs / service nogs installed correctly as per plan
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Timber Framing completed within specified tolerance, checked and approved
checkpoint-status |  |  | checkpoint | Timber Framing report sent through to client
checklist-flat |  |  | checklist | GRC Support Timber Checklist |  |  |  |  | Yes | GRC Support Timber Checklist | 923b6ddc-1cba-4367-bd09-60abe5a9210c
checkpoint-status |  |  | checkpoint | All relevant drawings and revisions numbers checked and attached.
checkpoint-status |  |  | checkpoint | Dimension / Location of framing checked and correct.
checkpoint-status |  |  | checkpoint | Correct solid timber blocking used.
checkpoint-status |  |  | checkpoint | Fixings and bolts checked and correct.
checkpoint-status |  |  | checkpoint | DPC installed, checked and correct as per specifications.
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations.
checkpoint-status |  |  | checkpoint | Report sent through to client.
checklist-flat |  |  | checklist | Sealant |  |  |  |  | Yes | Sealant Checklist | db355f54-21c9-4f2b-81dd-9d11eeaac0d7
checkpoint-status |  |  | checkpoint | Any defects are rectified and disclosed before installation.
checkpoint-status |  |  | checkpoint | Surface properly prepared.
checkpoint-status |  |  | checkpoint | Spacing for sealant is 10mm.
checkpoint-status |  |  | checkpoint | Proper sealant color applied.
checkpoint-status |  |  | checkpoint | Sealant applied with a smooth finish and finishing edges.
checkpoint-status |  |  | checkpoint | No defects are found within the finishing application.
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-sectioned |  |  | checklist | Concrete Pour Checklist |  |  |  |  | Yes | Concrete Pour Checklist | e08b6da3-c532-4823-a331-147e9d4f1980
checkpoint-group |  |  | section | Pour Details
text | 6e9309f8-3cf0-42cb-9465-fbc42bf47c60 | Data not allowed on checkpoint-group. | textbox | Area to be poured
text | 6e7943e1-d69e-4b6d-a9dc-05e1b6b3dcf3 | Data not allowed on checkpoint-group. | textbox | Date of pour
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
text | 35d02338-5ec8-42d3-b6f2-bb57961d5572 |  | textbox | Drawing numbers and revisions
checkpoint-group |  |  | section | Formwork and embedded items
checkpoint-status |  |  | checkpoint | Grids and RLs clearly marked fore reference
checkpoint-status |  |  | checkpoint | Formwork - location, heights, falls and dimensinos checked and accurate
checkpoint-status |  |  | checkpoint | Formwork sufficiently fixed and braced
checkpoint-status |  |  | checkpoint | Any rebates / nibs / cast in items are correctly positioned, sized and appropriately fixed in place.
boolean | e543d088-174c-427c-aec4-d94679a76de2 |  | tickbox | Hold down bolts checked and correct
boolean | c6ebb6f4-427c-44d7-92f8-7083eb5a89a2 |  | tickbox | Precast panel starters checked and correct
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork, etc.)
checkpoint-status |  |  | checkpoint | Any control joints / stop ends installed accurately and correctly braced
checkpoint-status |  |  | checkpoint | DPM & Connection to other waterproofing completed
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Any additional formwork photos and observations
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All formwork elements completed and ready for concrete pour (excess debris removed)
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Concrete ordered - correct mix and strength
text | 8474da70-3ff2-41f1-856e-0cce49197cc3 |  | textbox | Mix
text | a790af78-7b20-4f9a-b241-55fd6a2dcc50 |  | textbox | Strength: |  |  | MPa
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
text | 35cadabe-5c95-4460-83f6-dc380d0d6e26 |  | textbox | Who is placing the concrete
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Height and falls checked / confirmed before placement
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Cover correct to specification
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All concrete checked and correct on arrival (mix and strength)
boolean | 5016577c-6c19-45f5-bc3c-36ea05b47b4d |  | tickbox | All concrete dockets attached
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | General photos and observations of concrete placement attached
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Heights and falls checked / confirmed after placement
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-group |  |  | section | Post Pour Checks / Signoff
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - all final checks and documentation completed and attached
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-flat |  |  | checklist | GIB Lining Checklist |  |  |  |  | Yes | GIB Lining Checklist | ce6ea3c4-19fd-4311-a49f-ef59752343fd
checkpoint-status |  |  | checkpoint | All pre installation checks completed and approval given to line
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
text | 8ab6bf55-c7fd-407c-bc7e-199f90a7f927 |  | textbox | Drawing no. and revision
checkpoint-status |  |  | checkpoint | Correct lining checked and approved and area specifics checked
checkpoint-status |  |  | checkpoint | Substrate accepted and approval given to start gib lining
checkpoint-status |  |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status |  |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | All lining completed correctly within specified tolerance, checked and approved
holdpoint |  |  | signoff | Raise remedial / request signoff
checkpoint-status |  |  | checkpoint | GIB Lining report sent through to client