## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-CIV-General Safety and Guard Fence
ITP Description: |  | General Safety and Guard Fence
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2022-10-12
ITP created by: |  | Romualdo Magpantay
ITP approved for use by: |  | Romualdo Magpantay
Special Notes to ConQA Team : |  | Fitzgerald Road
Inspection & Test Plan - General Safety and Guard Fence
[9 empty] | Revision: | 0
[9 empty] | Date: | 2022-10-12
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | Vic Roads 707 Austroad | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | Vic roads traffic engineering manual Vo.2 MRP-057-C-AUR-DRG-11-ADR-CFN-0155 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | AS1725.1/NIST 2662 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Non Dependent | MRP-057-C-AUR-DRG-60-ADR-CPW-0152 SAST-3281 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Materials
2.1 | Submit materials and components conformance certificates by subcontractor for fence, gates and stock grids(Steel Columns, Cladding, Handrails, Chain Wire Mesh etc | Vic roads 707.03 c,d, g,h & K AS/NZS 4680 AS 1725 Austroad | ● Verify supplied materials and components comply with the Specification ● Submit signed Certificates of Compliance ● Chain wire shall comply with AS 1725 requirements ● Steel posts (minimum yield strength of 195 MPa)to be hot dipped galvanised in accordance with AS/NZS 4680 ●•Timber post and chain Link ●Welded mesh | Document review | Per type | HP | SE/Site Supervisor | Certificate of Compliance
2.2 | Concrete | IFC Drawings AS3972 | 25 MPa concrete to be used as per IFC drawings. All cement to be GP or GB or SR complying with AS3972. | Document Review | Each Mix | HP | SE/Site Supervisor | Certificate of Compliance
2.3 | Check materials upon delivery | Vic roads 707.03 c,d, g,h & K AS/NZS 4680 AS 1725 | ● Components are as per purchase order/s & delivery docket/s ● Free from damages/defects | Measure Visual | Per delivery | IP | Surveyor SE/PE/SPE | This ITP
3 | Pre Installation work
3.1 | Survey Set-out | IFC Drawings | Survey to set out the following but not limited to: existing contours, levels and features, surface pits ● Establish Pegs or equivalent to define the boundary of fencing ● Fences shall be constructed on the boundary of the infrastructure lease or wihin the infrastructure as necessary | Measure Visual | Per Area | IP | Surveyor SE/PE/SPE | This ITP
3.2 | Remove existing fencing (if applicable) | Vic roads 707.07 | ● Backfill and compact all holes left after removal in 150mm max layers to same relative compaction as adjoining ground material. ● Total length of fence removed: | Visual | Per Area | IP | SE/Site Supervisor | This ITP
4 | Construction / Installation Activities
4.1 | Neatly excavate/drill holes for posts | IFC Drawings | All open excavation should be fenced. Follow asset owners guidelines for work around their service. Post holes to correct dia. and to the concrete footing as shown on the appoved drawing see item 4.3. | Visual | Per lot | IP | SE/Site Supervisor | This ITP
4.2 | Ground Conditions | IFC Drawings | All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material. If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required. | Visual | Per lot | IP | SE/Site Supervisor | This ITP
4.3 | Post Foundation (Weld/ Mesh ) | IFC Drawings VicRoads Section 707.04e | Concrete footing shall be set as shown in drawing or to be 600mm depth and 200mm in diameter.Minimum 550mm embedment. Top of concrete crowned to shed water. Concrete posts holes must be filled using an approved 25 MPa ready mixed concrete | Measure | Per lot | IP | SE/Site Supervisor | Post and concrete dockets
4.4 | Post Foundation (Timber post with Chain link- guard Fence) | IFC Drawings VicRoads Section 707.04d Austroad | Concrete footing for end post at 750mm depth and 600mm depth for all posts.Diameter of 250 to be used. Minimum embedment of 300mm. Top of concrete crowned to shed water. Footing to manufactures detals Concrete posts holes must be filled using an approved 25 MPa ready mixed concrete | Measure | Per lot | IP | SE/Site Supervisor | Post and concrete dockets
4.5 | Post Installation | IFC Drawings | Maximum post spacing to be 3330mm for both end panel and intermediate panel. Max. post height 1890mm above ground level. Galvanised weather cap installed on all posts. Posts to be installed vetically within 1 in 50 plumb. Black powder coated post and rails. Wooden post 100mmX200MM guard fence post with two 36X18mm slotted holes X445mm height | Measure | Per lot | IP | SE/Site Supervisor | This ITP
4.6 | Chain Wire Mesh Installation | IFC Drawings VicRoads Section 707.04 | Chain-wire mesh 3.15 heavily galv. wire with nom. 50 pitch (W10Z) to be tightened and fastened to post and line wires (Support cable single 4mm Heilcoil and diagonal bracing cable twin 3.15 twisted) Chain wire to be fastened with 2.5mm dia. galv. tie wire or clips. Spacing to be not more than 400mm intervals on line posts and not more than 500mm intervals on line wires. Weld mesh fence to have balck powder coated finish and /or chain link fence to be black PVC coated with balck powder coated post and rails. | Visual | Per lot | IP | SE/Site Supervisor | This ITP
4.7 | Bracing | IFC Drawings | Tee Clamp T5032 and Cross clamps used on posts. Bracing to be installed on both sides of the fence at the fence corners | Visual | Per lot | IP | SE/Site Supervisor | This ITP
4.8 | Install Gates | IFC Drawings AS 4680 VicRoads Section 707.03(h) AS1742.7 Vic roadsTraffic Engineering manual Vo.2 Victrack Design requirements | Gates shall be standard proprietary manufactured items with galvanized tubular steel frame For VictracK:4200 opening double gates located at private access roas entrance Hinges, catches and other fittings for gates shall be standard proprietary manufactured items fabricated from grade 250/300 structural steel and hot-dipped galvanized - All gates are to be inward opening towards the rail easement. All gates to have signs as listed facing outward and all sign fixing to be vandal proof. | Visual | Per lot | IP | SE/Site Supervisor | This ITP
5 | Vi
5.1 | Fence Height and Track Clearance | IFC Drawings VicRoads Section 707.08 | Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings. Vertical tolerance of ± 20mm from the design line, longitudinal line tolerance of ± 20mm in plan view, tolerance on verticality to be 1 in 50. | Measure | Per lot | IP | SE/Site Supervisor | This ITP
5.2 | As-built Survey | As Built Drawings Asset Change form VicRoads Section 160.A8 | Survey activities undertaken to validate correct construction Attach: -Survey Report -Engineering Asset From | Survey Document Review | Once | IP | Track Surveyor Site/Project Engineer | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /