## res_ITP-CIV Delineation Fence R
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-CIV-General Safety and Guard Fence | itp |  |  |  |  | ITP-CIV-General Safety and Guard Fence Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
note | Document Title: ITP-CIV-General Safety and Guard Fence
note | ITP Description: General Safety and Guard Fence
note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
note | Discipline (e.g. CIV/STR/RAIL): CIV
note | Revision Number: 0
note | Revision Date: 12/10/2022
note | ITP created by: Romualdo Magpantay
note | ITP approved for use by: Romualdo Magpantay
note | 1.1 - Non Dependent
note | Reference Documents:
note | • Vic Roads 707 Austroad
note | 1.2 - Non Dependent
note | Reference Documents:
note | • Vic roads traffic engineering manual Vo.2
note | • MRP-057-C-AUR-DRG-11-ADR-CFN-0155
note | 1.3 - Non Dependent
note | Reference Documents:
note | • AS1725.1/NIST 2662
note | 1.4 - Non Dependent
note | Reference Documents:
note | • MRP-057-C-AUR-DRG-60-ADR-CPW-0152 SAST-3281
section | Materials
checkpoint | 2.1 Submit materials and components conformance certificates by subcontractor for fence, gates and stock grids(Steel Columns, Cladding, Handrails, Chain Wire Mesh etc
note | REFERENCE:
note | Vic roads 707.03 c,d, g,h & K
note | AS/NZS 4680
note | AS 1725
note | Austroad
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Verify supplied materials and components comply with the Specification
note | • Submit signed Certificates of Compliance
note | • Chain wire shall comply with AS 1725 requirements
note | • Steel posts (minimum yield strength of 195 MPa)to be hot dipped galvanised in accordance with AS/NZS 4680
note | • Timber post and chain Link
note | • Welded mesh
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Per type
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/Site Supervisor
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Certificate of Compliance
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.2 Concrete
note | REFERENCE:
note | IFC Drawings
note | AS3972
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: 25 MPa concrete to be used as per IFC drawings. All cement to be GP or GB or SR complying with AS3972.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Mix
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/Site Supervisor
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Certificate of Compliance
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.3 Check materials upon delivery
note | REFERENCE:
note | Vic roads 707.03 c,d, g,h & K
note | AS/NZS 4680
note | AS 1725
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Components are as per purchase order/s & delivery docket/s
note | • Free from damages/defects
note | – – – – – – – – – – – – – – – – –
note | METHOD:
note | Measure
note | Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Per delivery
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | Surveyor
note | SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Pre Installation work
checkpoint | 3.1 Survey Set-out
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Survey to set out the following but not limited to: existing contours, levels and features, surface pits
note | • Establish Pegs or equivalent to define the boundary of fencing
note | • Fences shall be constructed on the boundary of the infrastructure lease or wihin the infrastructure as necessary
note | – – – – – – – – – – – – – – – – –
note | METHOD:
note | Measure
note | Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Per Area
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | Surveyor
note | SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.2 Remove existing fencing (if applicable)
note | REFERENCE: Vic roads 707.07
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Backfill and compact all holes left after removal in 150mm max layers to same relative compaction as adjoining ground material.
note | • Total length of fence removed:
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Per Area
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/Site Supervisor
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Construction / Installation Activities
checkpoint | 4.1 Neatly excavate/drill holes for posts
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | All open excavation should be fenced.
note | Follow asset owners guidelines for work around their service.
note | Post holes to correct dia. and to the concrete footing as shown on the appoved drawing see item 4.3.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Per lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/Site Supervisor
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.2 Ground Conditions
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
note | If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Per lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/Site Supervisor
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.3 Post Foundation (Weld/ Mesh)
note | REFERENCE:
note | IFC Drawings
note | VicRoads Section 707.04e
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Concrete footing shall be set as shown in drawing or to be 600mm depth and 200mm in diameter.Minimum 550mm embedment.
note | Top of concrete crowned to shed water.
note | Concrete posts holes must be filled using an approved 25 MPa ready mixed concrete
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Per lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/Site Supervisor
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Post and concrete dockets
textbox | Date Completed:
checkpoint | 4.4 Post Foundation (Timber post with Chain link- guard Fence)
note | REFERENCE:
note | IFC Drawings
note | VicRoads Section 707.04d
note | Austroad
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Concrete footing for end post at 750mm depth and 600mm depth for all posts.Diameter of 250 to be used. Minimum embedment of 300mm.
note | Top of concrete crowned to shed water.
note | Footing to manufactures detals
note | Concrete posts holes must be filled using an approved 25 MPa ready mixed concrete
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Per lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/Site Supervisor
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Post and concrete dockets
textbox | Date Completed:
checkpoint | 4.5 Post Installation
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Maximum post spacing to be 3330mm for both end panel and intermediate panel.
note | Max. post height 1890mm above ground level.
note | Galvanised weather cap installed on all posts.
note | Posts to be installed vetically within 1 in 50 plumb.
note | Black powder coated post and rails.
note | Wooden post 100mmX200MM guard fence post with two 36X18mm slotted holes X445mm height
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Per lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/Site Supervisor
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.6 Chain Wire Mesh Installation
note | REFERENCE:
note | IFC Drawings
note | VicRoads Section 707.04
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Chain-wire mesh 3.15 heavily galv. wire with nom. 50 pitch (W10Z) to be tightened and fastened to post and line wires (Support cable single 4mm Heilcoil and diagonal bracing cable twin 3.15 twisted)
note | Chain wire to be fastened with 2.5mm dia. galv. tie wire or clips. Spacing to be not more than 400mm intervals on line posts and not more than 500mm intervals on line wires.
note | Weld mesh fence to have balck powder coated finish and /or chain link fence to be black PVC coated with balck powder coated post and rails.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Per lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/Site Supervisor
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.7 Bracing
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Tee Clamp T5032 and Cross clamps used on posts.
note | Bracing to be installed on both sides of the fence at the fence corners
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Per lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/Site Supervisor
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.8 Install Gates
note | REFERENCE:
note | IFC Drawings
note | AS 4680
note | VicRoads Section 707.03(h)
note | AS1742.7
note | Vic roadsTraffic Engineering manual Vo.2
note | Victrack Design requirements
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Gates shall be standard proprietary manufactured items with galvanized tubular steel frame
note | For VictracK:4200 opening double gates located at private access roas entrance
note | Hinges, catches and other fittings for gates shall be standard proprietary manufactured items fabricated from grade 250/300 structural steel and hot-dipped galvanized -
note | All gates are to be inward opening towards the rail easement.
note | All gates to have signs as listed facing outward and all sign fixing to be vandal proof.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Per lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/Site Supervisor
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 5.1 Fence Height and Track Clearance
note | REFERENCE:
note | IFC Drawings
note | VicRoads Section 707.08
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
note | Vertical tolerance of ± 20mm from the design line, longitudinal line tolerance of ± 20mm in plan view, tolerance on verticality to be 1 in 50.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Per lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/Site Supervisor
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.2 As-built Survey
note | REFERENCE:
note | As Built Drawings
note | Asset Change form
note | VicRoads Section 160.A8
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Survey activities undertaken to validate correct construction
note | Attach:
note | – Survey Report
note | – Engineering Asset From
note | – – – – – – – – – – – – – – – – –
note | METHOD:
note | Survey
note | Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | Track Surveyor
note | Site/Project Engineer
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | Metropolitan Roads Program Alliance Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP