## Resources
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Cable Support System |  | Cable Support System | 0230044b-5739-4b65-8cce-566e449e3fe1
| checkpoint | Confirm that the cable support system has been selected as per drawings and specifications
| checkpoint | Cable support system has been selected to correctly hold the required weight
| checkpoint | Each cable support has sufficient room for future expansion
| checkpoint | Cable support system has been correctly installed and is secure in place
| checkpoint | Height of cable support system has been confirmed and installed to that height in all areas
| checkpoint | Cable support system is as per shop drawings and not impacting any other services
| checkpoint | All threaded rods have been cut off to correct size
| checkpoint | All nuts/bolts/channel nuts have been tightened
| checkpoint | Any changes to drawings have been noted on the site as built drawings
| checklist | Pre-start Toolbox Talks |  | Pre-start Toolbox Talks | 08113b8a-6cba-447b-b6b8-23a14d56d3c1
| checkpoint | Pre-start Toolbox Safety meeting completed
ff49b524-6995-5b8d-bfa4-8e5f02aa2646 | textbox | Location:
ef24ace5-415d-558a-85d0-ddf1c4c9d2df | textbox | Date:
160e78cc-a807-5252-8a72-e25ffbf9a962 | textbox | Client:
cf597fa1-960f-5766-9ff1-45eeca8793d5 | textbox | Supervisor:
c52ce046-cc8b-59e0-8a3f-a683cb7938c8 | textbox | Subject:
d76890e5-9d6d-5eb0-a7f4-49319f793054 | textbox | Duration:
a367da39-7292-5d1f-8b52-573854767608 | textbox | Persons present
fb30855c-70b9-5f8b-b1dd-26e88c4f0b8c | textbox | Comments & points raised
| checkpoint | Signed off by Ergo Group Supervisor
| checklist | 8B. Investigation - Witness Statement |  | 8B. Investigation - Witness Statement | 14fec178-3af4-44ba-a9cf-46ae5421e5df
| section | Details
| checkpoint-no-value | Details
b179979e-03cf-56b3-b1d6-157050c55629 | textbox | Name:
cdea9793-5375-5858-be38-a5d21871681e | textbox | Job Title:
0294e5d8-7edb-593c-8393-a700b1f4a426 | textbox | Employer:
67244d15-6ac4-5d08-8032-f171b1762067 | textbox | Supervisor:
22e98108-8cce-5a59-bac1-96f566658412 | textbox | Work Location:
bfa31aa4-32cf-5043-bc02-7f75711f54a2 | textbox | Contact Details:
38e35423-420f-54ad-87de-0ea32686a366 | textbox | Location of Incident:
b22d23e5-25cc-5e91-9309-f9262ebc43d4 | textbox | Date/Time of Incident:
843992a7-c7b5-5aab-b846-8e07b50acc1c | textbox | Interview Time/Date:
bdda74e5-0284-5dff-b54c-15ea008cb967 | textbox | Interview Number:
755084f1-a159-5714-a855-5eb11bd2f7dd | textbox | Please fully describe the work and conditions in progress leading up to the incident.
10983555-6c03-5ed4-acbb-c1dc8d2d831a | textbox | Please fully describe the incident sequence from start to finish.
56c8f2f9-79dc-54d9-88ad-8e02ea3604e7 | textbox | Note anything unusual observed prior to, or during the incident (sights, sounds, smells etc.)
d6211f41-3bac-5d0b-ba61-f8fae4ff6c55 | textbox | What was your role in the incident sequence?
733f4a8a-29e6-5c06-95a2-dba212421c04 | textbox | What conditions influenced the incident (weather, time of day, equipment malfunctions etc.)?
85afce3e-d1df-5f4f-912a-8086cb738bf5 | textbox | How did people influence the incident (actions, emergency response etc.)?
88a3b9a9-1795-5ef0-b2f0-51c97c5dc32f | textbox | What do you think caused the incident?
1c4286a6-74af-5cd5-86c3-eb389f7d47b6 | textbox | How do you think the incident could have been prevented?
592f86ac-1281-5e8c-ae07-10f9db6bacac | textbox | Please list other possible witnesses.
0e8f9f3e-48a9-5c08-aeaa-3b28aaf83786 | textbox | Additional comments/observations.
| checkpoint | Interviewee Details:
1467ccf4-fb4c-5248-b708-7acc2bd6add9 | textbox | Interviewee:
| signoff | Signature:
| checkpoint | Interviewer Details:
40527e59-00c3-583d-ac95-4e16305c2e05 | textbox | Interviewer:
| signoff | Signature:
| checklist | Data cabling and outlets |  | Data cabling and outlets | 15cea317-e0d7-4fa9-893e-b8305bbe71ad
| section | Rough In
| checkpoint | Confirm that the cable support system has been completed as per documentation
| checkpoint | Data cabling has been selected as per drawings and specifications (Cat6/CatA & brand)
| checkpoint | Mechanical protection has been provided to minimise the likelihood of physical damage to cabling
| checkpoint | Cabling has been concealed where possible in ceiling spaces, wall cavities or risers
| checkpoint | All outlets have been wired as per drawings
| checkpoint | All data outlets have been numbered and marked on the site as built drawing
| checkpoint | Height and location have been confirmed for each outlet
| section | Fit Off & Commission
| checkpoint | Equipment/materials have been selected and installed as per drawings/specifications
| checkpoint | Terminations have been checked and all terminations are correct and secure in all outlets
| checkpoint | Outlets have all been secured in place and levelled
| checkpoint | All cabling has been tested using the Fluke data tester
| checkpoint | Each cable has been correctly installed and terminated in the patch panel
| checkpoint | Each outlet has been labelled
| checkpoint | Each outlet marked on the site as built
| checklist | ITP017 Temp DBs |  | ITP017 Temp DBs | 18c8c067-597b-42b7-a28c-27b45b01a65a
| checkpoint | 1 - RCD
| checkpoint | 2 - Date of testing
| checkpoint | 3 - Next test due
| checkpoint | 4 - Results and/or trip current (less 30ma) for earth leakage device
| checkpoint | 5 - Has a new tag been installed on the db - please take a photo
| checkpoint | 6 - Has the front cover been updated
| checkpoint | 7 - Please take a photo of DB - pass once attached
| checkpoint | 8 - Compliance certificate completed and attached
| checkpoint | 9 - License no.
| checklist | Temp Board Install Checklist |  | Temp Board Install Checklist | 1da62304-fbd5-4ff7-a21b-0825a98faf2e
| checkpoint | Are all final circuits protected by an RCD
| checkpoint | Are all DB doors lockable
| checkpoint | Are all DB’s securely fixed in position
| checkpoint | Are all switchboards labelled correctly
| checkpoint | Are all final circuits labelled at board
| checkpoint | Are all live parts at DB inaccessible
| checkpoint | Are socket outlets in DB in good working order
| checkpoint | Are empty glands and holes covered over
| checkpoint | Is switchboard door lockable, fitted with a retaining bar, and unable to be removed without the use of a tool
| checkpoint | Is emergency lighting provided adjacent to switchboard
| checkpoint | CCEW form been completed? (Take photo of each page)
| checklist | ITP016 Earth Grids / Lighting Protection |  | ITP016 Earth Grids / Lighting Protection | 20819c19-0913-4cae-808e-6c4a5a5517a3
| checkpoint | 1 - Refer to drawings to determine size of grid.
| checkpoint | 2 - Check size of cable and earth electrode.
| checkpoint | 3 - Check specification for resistance level.
| checkpoint | 4 - Drive earth electrode into ground.
| checkpoint | 5 - Earth test electrode or grid.
36f8a754-68a7-5df6-a9a1-8822ee148590 | textbox | Earth tester number
| checkpoint | 6 - If insufficient reading, add other electrodes 2 metres apart and link up with initial electrode with earth cable.
| checkpoint | 7 - Terminate cable from first electrode to frame or earth bar and label.
| checkpoint | 8 - Test sheet completed and attached
| checklist | ITP013 Install Distribution Boards -Terminate Cables |  | ITP013 Install Distribution Boards -Terminate Cables | 22cec7c6-969a-494c-8960-a4298b932393
| checkpoint | 1 - Delivery check for damage, paint finish, dimensions and doors against approved shop drawing
| checkpoint | 2 - Locate & fix into position
| checkpoint | 3 - Install submains cabling as appropriate eg. Glands, tray, duct
| checkpoint | 4 - Install lugs and terminate
| checkpoint | 5 - Install sub circuit cabling and terminate. If circuit not complete at the other end, it must not be terminated.
| checkpoint | 6 - Clean & vacuum
| checkpoint | 7 - Record results
| checkpoint | 8 - Organise inspection by inspector. Lodge prescribed / non prescribed (as applicable) certificate of electrical safety (if required).
| checkpoint | 9 - Clearly identify services
| checkpoint | 10 - Energize
| checkpoint | 11 - Check phase rotation
| checkpoint | 12 - Check switchboard as installed matches shop drawing. If necessary modify shop drawing to match installed & return to office
| checkpoint | 13 - Check typed schedule for accuracy and install in schedule holder
| checkpoint | 14 - Clean switchboard cupboard
| checklist | ITP019 Communications Cabinet |  | ITP019 Communications Cabinet | 2e236983-2fd4-4994-b984-4abf24c8fc15
| checkpoint | 1 - Ensure room layout, cabinets and equipment have been approved
| checkpoint | 2 - Confirm that cable support system has been completed as documented
| checkpoint | 3 - Adhere to a single certified system throughout a new building installation
| checkpoint | 4 - Comply with the detailed installation specifications
| checkpoint | 5 - Network cables have been appropriately sized and selected to ensure that they will support currently installed and future equipment
| checkpoint | 6 - Connections have been correctly terminated and insulated to ensure perfect connectivity and protect against faults and interference
| checkpoint | 7 - Sufficient spare cable has been left coiled up outside of the cabinet
| checkpoint | 8 - Check all internal wiring as per panel wiring diagram. Has all equipment including cable managers been installed as per rack layout
| checkpoint | 9 - Has a dedicated power circuit been supplied for the cabinet
| checkpoint | 10 - Is there a steel tray/raceway installed between each cabinet to accommodate linking patch leads
| checkpoint | 11 - All cabling has been tested using the Fluke data tester
| checkpoint | 12 - Undergo certification tests prior to acceptance of work completed
| checkpoint | 13 - Provide copies of certification tests to the Office of IT Services
| checklist | Power cabling and outlets |  | Power cabling and outlets | 30e7a1aa-eb23-4293-b706-93ac6a4e9605
| section | Rough In
| checkpoint | Confirm that the cable support system has been completed as per documentation
| checkpoint | Electrical cables have been appropriately sized and selected to ensure that they will support currently installed and future equipment
| checkpoint | Mechanical protection has been provided to minimise the likelihood of physical damage to cabling
| checkpoint | Cabling has been concealed where possible in ceiling spaces, wall cavities or risers
| checkpoint | All outlets have been wired as per drawings
| checkpoint | All outlets have been marked on the site as built drawing
| checkpoint | Height and location have been confirmed for each outlet
| section | Fit Off & Commission
| checkpoint | Equipment/materials have been selected and installed as per drawings/specifications
| checkpoint | Terminations have been checked and all terminations are correct and secure in all outlets
| checkpoint | Outlets have all been secured in place and levelled
| checkpoint | All cabling has been tested for insulations resistance and continuity
| checkpoint | Each circuit is terminated at the DB and protected by the correct protective device
| checkpoint | Each outlet has been labelled
| checkpoint | Functional test carried out on each outlet
| checkpoint | Each outlet marked on the site as built
| checklist | ITP002 In-Deck/Slab Conduits |  | ITP002 In-Deck/Slab Conduits | 35133b1e-fbd6-4180-b588-f25145447220
| checkpoint | 1 - Confirm that the selected conduit is of adequate size for purpose
| checkpoint | 2 - It has been confirmed that all outlets/fittings in slab have been captured
| checkpoint | 3 - Conduit has been securely fixed
| checkpoint | 4 - Conduit has been securely fixed to the box or volcano
| checkpoint | 5 - Conduit box has temporarily been secured and tied down in place for pour
| checkpoint | 6 - Alternative route has been supplied in case main route is damaged
| checkpoint | 7 - Conduit runs have all been marked on as builts
| checklist | ITP011 Data Installation and Fit Off |  | ITP011 Data Installation and Fit Off | 36b2a954-3f82-4818-b433-fd4640c47647
| checkpoint | 1 - Check drawings for quantity, brand, type and colour
| checkpoint | 2 - Fit off and fix outlets, terminations have been checked and all terminations are correct and secure in all outlets
| checkpoint | 3 - Outlets have all been secured in place and levelled
| checkpoint | 4 - All cabling has been tested using the fluke data tester
| checkpoint | 5 - Each cable has been correctly installed and terminated in the patch panel
| checkpoint | 6 - Cover plates (if required)
| checkpoint | 7 - Install label (if a specified requirement)
| checkpoint | 8 - All outlets & appliances marked on the site as build’s
| checklist | ITP018 Temp Lighting |  | ITP018 Temp Lighting | 49263a72-daff-4b7e-82fe-d63d3e970a8f
| checkpoint | 1 - Determine cable support system ie. Catinary, cable tray, fix to structure, ducting
| checkpoint | 2 - Install cable support system
| checkpoint | 3 - Mechanical protection has been provided to minimise the likelihood of physical damage to cabling
| checkpoint | 4 - Fix cables to support system
| checkpoint | 5 - Temporary construction tape has been installed along cabling
| checkpoint | 6 - Cabling has been concealed where possible in ceiling spaces, wall cavities or risers
| checkpoint | 7 - Fit-off outlets, plug bases etc. (if necessary), each circuit to be fitted off completely & clean up area
| checkpoint | 8 - Location/compliance
| checkpoint | 9 - Fit off light fittings
| checkpoint | 10 - Functional test carried out on each fitting
| checklist | ITP004 Conduit & Cable Tray |  | ITP004 Conduit & Cable Tray | 4f3ebde9-d124-4e3d-a1d6-c7d98ba93cd0
| section | Conduit Installation
| checkpoint | 1 - Coordinate with other services ensure segregation from comms / data services
| checkpoint | 2 - Size and type of conduit
| checkpoint | 3 - Install conduit
| checkpoint | 4 - Fixings
| section | Cable Tray Installation
| checkpoint | 5 - Coordinate with other services
| checkpoint | 6 - Size of cable tray each cable support has sufficient room for future expansion
| checkpoint | 7 - Cable support system has been selected to correctly hold the required weight
| checkpoint | 8 - Install fixings
| checkpoint | 9 - Install cable tray cable support system has been correctly installed and is secure in place
| checkpoint | 10 - Height of cable support system has been confirmed and installed to that height in all areas
| checkpoint | 11 - Cable support system is as per shop drawings and not impacting any other services
| checkpoint | 12 - All threaded rods have been cut off to correct size
| checkpoint | 13 - All nuts/bolts/channel nuts have been tightened
| checkpoint | 14 - Do sketch or mark up drawing for future as builts
| checklist | Test and Tag Register |  | Test and Tag Register | 5a170388-f5cc-45b5-adab-33ce441adcf1
| checkpoint | Test and Tag register completed (upload picture of each page)
| checklist | ITP015 Submains Test Results |  | ITP015 Submains Test Results | 5ebfb36c-2d3a-4aef-ac5d-9e8367b09165
| checkpoint | Submains Test Results - Complete and Test Sheet attached
| checklist | ITP003 Main Switchboard & Termination of Cables |  | ITP003 Main Switchboard & Termination of Cables | 60e1333b-a2e4-47f9-8145-5b5de2b6257a
| checkpoint | 1 - Locate and fix switchboard into position
| checkpoint | 2 - Determine cable sizes for cable glands, mark out gland plate (if not previously determined at planning meeting)
| checkpoint | 3 - Install cable glands and cables
| checkpoint | 4 - Install lugs & terminate
| checkpoint | 5 - Clean and vacuum out board
| checkpoint | 6 - Check all circuits are terminated & safe at the other end or disconnect.
| checkpoint | 7 - Visual inspection
aab05d14-02c8-5ac9-9364-b93c5513c3f8 | textbox | 8 - Test earth continuity and resistance
bbb6fa48-7ee7-552d-9404-7780dfd9c10f | textbox | 9 - Test insulation resistance
fb5f807b-9826-5444-ae0e-8a9695db97cb | textbox | 10 - Test polarity
ce2bc6eb-8ccc-5d86-840e-506271133842 | textbox | 11 - Test phase rotation
| checkpoint | 12 - Lodge prescribed certificate of electrical safety. Organise inspection by inspector.
| checkpoint | 13 - Isolate / lock off / danger tag all outgoing circuits.
| checkpoint | 14 - Ensure all labelling is complete and accurate.
| checkpoint | 15 - Energize
| checkpoint | 16 - Check phase rotation
| checkpoint | 17 - Check switchboard as installed matches shop drawing
| checkpoint | 18 - Modify shop drawing to match existing & return to office
| checkpoint | 19 - Clean switchroom
| checkpoint | 20 - Check if requirement for spare fuse
| checkpoint | 21 - Check requirements for laminated drawing to be installed
| checklist | Emergency Lighting Testing Evidence |  | Emergency Lighting Testing Evidence | 637e25da-a419-420e-8554-1788eec3b5ab
| checkpoint | Emergency Lighting Testing Evidence uploaded
| checklist | 8A. Incident / Accident Register |  | 8A. Incident / Accident Register | 6616aba2-632f-446f-99f5-e48d5ae3a163
| section | Details
| checkpoint-no-value | Details
dabf244f-1b28-5a2d-9e4b-399d5d2be427 | textbox | Client:
1ddc5457-b7ca-590e-acf4-a97e2848b2d1 | textbox | Project:
4c6f1340-071a-5054-9031-8405b4214487 | date | Date:
6024c298-9583-51e0-b241-48a05f20e444 | textbox | Site Address:
9577b72f-9e63-51f7-86e8-e185dad9cd50 | date | Date of Incident:
e563789f-e4ad-5dd5-ad9f-36aed14bf047 | textbox | Time of Incident:
7212644a-7f39-56db-92b1-4606cd5b4632 | textbox | Incident Report No:
ba226d84-938b-5a11-8f77-ae1322015003 | textbox | Workers Name:
3662b5d0-4767-5fb7-a6dc-c90517e1311f | textbox | Supervisor Name:
ce54a187-8610-5b5a-8904-5d96ff50cefc | textbox | Location:
caf4c90c-8909-5b5e-a0d6-12c89c137e06 | dropdown | Outcome - 1st Aid: (FAT), Medical: (MTI), Lost Time: (LTI), Near Miss: (NM), Report Only: (REP) | 1st Aid: (FAT), Medical: (MTI), Lost Time: (LTI), Near Miss: (NM), Report Only: (REP)
cc33c01d-0cb5-5792-82f2-53a2e61a7d06 | dropdown | Outcome - Return to Work: (RTW), Doctor: (Doc), Hospital: (Hosp), Snt Home: (SH), Report Only: (Rep) | Return to Work: (RTW), Doctor: (Doc), Hospital: (Hosp), Snt Home: (SH), Report Only: (Rep)
0f64f120-9dbb-5faa-85ad-2aabd4d88c4d | textbox | Days Lost (If LTI):
| checklist | ITP010 Lighting Installation and Fit Off |  | ITP010 Lighting Installation and Fit Off | 70c99d66-34e2-4091-a217-f80e20b81c16
| checkpoint | 1 - Check drawings for quantity, brand, type and colour
| checkpoint | 2 - Each circuit is terminated at the db and protected by the correct protective device
| checkpoint | 3 - Location/compliance wet areas, hazards etc. Mounting heights,
| checkpoint | 4 - Fit off and fix switches, where multi gang switches with multi circuits are involved use shrouds on each switch. Each circuit must be fitted off completely.
| checkpoint | 5 - Fit off final light fittings
| checkpoint | 6 - Functional test carried out on each outlet
| checkpoint | 7 - Cover plates (if required)
| checkpoint | 8 - Install label (if a specified requirement)
| checkpoint | 9 - All lights and switches marked on the site as build’s
| checklist | ITP001 Underground Conduits |  | ITP001 Underground Conduits | 73095a92-d572-42b0-b6c4-7eaefd3870a3
| section | Preparation
| checkpoint | 1 - Determine origin & destination
| checkpoint | 2 - Confirm area of work is accessible & acceptable to commence
7d8ab980-c03d-5fde-afdc-bad10ee0ba61 | textbox | 3 - Drawing & revision number
| checkpoint | 4 - Check clear of other services N.B. the clearance for gas pipes is 300mm & other services 100mm
| checkpoint | 5 - Check cable size to verify conduit size & determining size of trench
| checkpoint | 6 - Organise barricades, webbing, plates, warning lights if applicable prior to excavation
| checkpoint | 7 - Determine spoil removal, back fill material, compaction, cable marking & protection & re-instatement requirements
| section | Installation
| checkpoint | 8 - Mark out trench route arrange saw cutting if required
| checkpoint | 9 - Excavate trench & install barricades as required check depth, taking into account final ground levels
| checkpoint | 10 - Determine which way cable will be installed and lay couplings in no friction direction, install conduit, glue
| checkpoint | 11 - Install draw wire if required
| checkpoint | 12 - Inspect trench by supply authority if applicable
| checkpoint | 13 - Inspect & back fill trench
| checkpoint | 14 - Re-instate & clean area
| checkpoint | 15 - Install direction marker if applicable
| checkpoint | 16 - Do sketch or mark up drg for future as builts
| checklist | ITP005 Mains, Submains Cable in Conduits or on Trays |  | ITP005 Mains, Submains Cable in Conduits or on Trays | 81b349f8-0e5f-4de6-8b77-a8db4dc34335
| checkpoint | 1 - Measure cable runs with appropriate accurate measuring instrument eg tape measure, wheel
| checkpoint | 2 - Check cable sizes. Resistance of protective earth conductor shall be low enough to permit passage of current necessary to operate protective device.
| checkpoint | 3 - Confirm length of cable
| checkpoint | 4 - Install cable in applicable method eg. Cable stands, electric winch, pulleys etc. Any cable not terminated immediately must have the ends taped covering the bare copper.
| checkpoint | 5 - Tri-foil (refer to details on back for all options) cables and tie cables to support system
| checkpoint | 6 - Check requirements for cable identification and install
| checklist | Temporary DB Monthly Testing |  | Temporary DB Monthly Testing | 89749468-342b-450d-b019-732cb146682a
| checkpoint | Operating time of RCD’s (note trip times in comments)
| checkpoint | RCD Push button Operation
| checkpoint | General condition of DB (must include a photo)
| checkpoint | Photo of completed tag on DB
| checklist | ITP014 Distribution Board Test Results |  | ITP014 Distribution Board Test Results | aade797d-71d9-424d-a9a5-2f869e7d208a
| checkpoint | Distribution Board Test Results - Complete and Test Sheet attached
| checklist | Toolbox Safety Talks Meeting Minutes |  | Toolbox Safety Talks Meeting Minutes | b38fdf83-af9f-48ed-9275-82d18793a638
| checkpoint | Toolbox Safety meeting completed
2a89c104-f7e9-5149-b1b3-f0b716afab44 | textbox | Location:
418dc8ac-d145-5638-871a-fc7587bb5e0e | textbox | Date:
358f1937-df0b-587e-8f48-8070e79972a9 | textbox | Client:
8b0f244c-659e-5be6-8e40-18518758e711 | textbox | Supervisor:
9c7f2b34-9642-5c10-86f0-fc6cc8aa28cc | textbox | Subject:
9fae3c6d-f41a-57a3-bc49-cd8c33425315 | textbox | Duration:
d87e0f1f-3abf-5db1-ab36-aaab268d4663 | textbox | Persons present
22d0c969-9512-5e57-8214-1e6d63a88dd7 | textbox | Comments & points raised
| checkpoint | Signed off by Ergo Group Supervisor
| checklist | ITP008 Data Wiring Rough In |  | ITP008 Data Wiring Rough In | b8ddaad5-340a-4f90-899f-7935748b24b2
| checkpoint | 1 - Refer to drawing to determine cable support route and check separation from power services
| checkpoint | 2 - Determine cable type
| checkpoint | 3 - Determine cable support system ie. Catinary, cable tray, fix to structure, ducting
| checkpoint | 4 - Install cable support system
| checkpoint | 5 - Install and identify cables.
| checkpoint | 6 - Mechanical protection has been provided to minimise the likelihood of physical damage to cabling
| checkpoint | 7 - Fix cables to support system
| checkpoint | 8 - Cabling has been concealed where possible in ceiling spaces, wall cavities or risers
| checkpoint | 9 - All outlets have been wired as per drawings
| checkpoint | 10 - All outlets have been marked on the site as built drawing
| checkpoint | 11 - Height and location have been confirmed for each outlet
| checklist | ITP007 Lighting Wiring Rough In |  | ITP007 Lighting Wiring Rough In | ba650ae9-8e30-4c26-9807-ae7488632f53
| checkpoint | 1 - Refer to drawing to determine cable support route and check separation from data/comms services
| checkpoint | 2 - Determine cable size
| checkpoint | 3 - Cable sizes max length
| checkpoint | 4 - Determine cable support system ie. Catinary, cable tray, fix to structure, ducting
| checkpoint | 5 - Install cable support system
| checkpoint | 6 - Check cable size/type/colour
| checkpoint | 7 - Install and identify cables. Any cable not terminated immediately must have the ends taped covering the bare copper.
| checkpoint | 8 - Mechanical protection has been provided to minimise the likelihood of physical damage to cabling
| checkpoint | 9 - Fix cables to support system
| checkpoint | 10 - Cabling has been concealed where possible in ceiling spaces, wall cavities or risers
| checkpoint | 11 - Fit-off outlets, plug bases etc. (if necessary), each circuit to be fitted off completely & clean up area
| checkpoint | 12 - All lighting points and switches have been wired as per drawings
| checkpoint | 13 - All lighting points and switches have been marked on the site as built drawing
| checkpoint | 14 - Height and location have been confirmed for each lighting points and switches
| checklist | Site Variations |  | Site Variations | c50cdd59-c9fb-47d0-8a4e-0d93f0ddb7ee
| section | Contract Variation/Site Instruction Request
| checkpoint | Contract Variation/SI Request
ecf8f05e-c5b5-5af4-9ecb-d8f1d49cb3bd | textbox | Company:
b2b1de8c-d9e2-5e02-b680-f0077a2354c1 | textbox | Address:
c9492efc-22c2-5f8b-85ac-1ab2ffb25916 | textbox | Project Name:
eb41256b-3ed9-59c3-ac76-02eb5f00d905 | textbox | Representative:
95ca27fc-d07a-5656-ae0a-b76d2527a0c1 | textbox | Variation date:
| section | Scope of Works
| checkpoint-no-value | Scope of Works:
a75068a4-feb5-52b9-a08b-c74c89b5b670 | textbox
| checkpoint-no-value | DATE (1)
49333b66-ab7d-51d2-b37a-6125b9bb03a6 | textbox
7a167e21-2eca-5154-9577-dbf9378b9732 | textbox | LABOUR
9126fb06-56eb-5310-b5b2-f99426037ea8 | textbox | HRS
546b3d24-e7ae-5f76-8489-dfd33dcf9362 | textbox | MATERIALS
f4bf1c68-8a26-567b-964b-f5738092bd3b | textbox | QTY
| checkpoint-no-value | DATE (2)
da00de81-b275-5622-aa32-94dbfc5c5947 | textbox
08de56e6-7c91-5d8a-af05-36a6bc8d8bf3 | textbox | LABOUR
6a5d302b-6328-595d-a2ce-17fb77b339fa | textbox | HRS
24e779c1-a155-53fd-b34a-1746a9d590b7 | textbox | MATERIALS
f151df19-364c-5b01-b152-9032adc10980 | textbox | QTY
| checkpoint-no-value | DATE (3)
f8521350-3f48-54d2-9449-03c93755bfa9 | textbox
f53ebcb0-0bed-53ee-a66a-67bc0d27042a | textbox | LABOUR
b9fa1578-b6e4-5f57-af73-c3278e1663c5 | textbox | HRS
d95787fa-d8e8-5a86-bffb-841091e72621 | textbox | MATERIALS
9b6d8df1-717c-54d2-92ea-0f803fe126f7 | textbox | QTY
| checkpoint-no-value | DATE (4)
0db5a785-d34c-572f-a190-5671f1f735c3 | textbox
ecc5b394-3a91-5c28-93cb-44c5972f5ac2 | textbox | LABOUR
947f1e8b-4b81-5a6c-81d2-ad7cc0d31975 | textbox | HRS
b94d599b-e580-57f7-8d81-f3b03565075b | textbox | MATERIALS
645b19f2-da0d-55dc-8982-789eed24a7ee | textbox | QTY
| checkpoint-no-value | DATE (5)
816181e8-b5eb-532f-9dce-63adb6d96e85 | textbox
f9bbd5ec-413c-5752-9f4f-8913ec93b66b | textbox | LABOUR
104c05bb-3252-5c01-a483-71b3e929a57f | textbox | HRS
c19269fc-ffc4-5704-bf25-597dd93c77e3 | textbox | MATERIALS
717d66db-7736-5905-ade9-d0cb47bb2198 | textbox | QTY
| checkpoint-no-value | DATE (6)
2a964e1b-574b-5e21-ab7d-442bb2366d32 | textbox
dd6f33cd-d599-583c-8c94-90acb6d1b7b5 | textbox | LABOUR
294ab235-963c-5244-9d95-1a8ecb8f4912 | textbox | HRS
0692d18d-9154-5917-9375-4f90230a23d8 | textbox | MATERIALS
55b0882f-82bf-53ad-bec1-59d46766397a | textbox | QTY
| checkpoint-no-value | DATE (7)
9d43961a-204f-5d4e-8981-469705956567 | textbox
8dd24b1f-d741-56f6-8c7b-80f73d618181 | textbox | LABOUR
43e34995-8e5e-5122-a567-ba5d075f3e2e | textbox | HRS
4e5c4516-c107-50ce-88c1-abcb6ade2a46 | textbox | MATERIALS
92f6a681-06c2-55ed-b27d-e5ce31b7ad2d | textbox | QTY
| checkpoint-no-value | DATE (8)
b9d00bae-685e-5092-98a7-b134a8229c8e | textbox
30b594e8-b495-5fea-90c7-98cc0c96ddee | textbox | LABOUR
211a6e97-3816-5a43-973d-f8d3030e02f1 | textbox | HRS
ac9d7b59-d371-51b9-beb2-f529688d0006 | textbox | MATERIALS
3b6236d6-e303-5838-b72c-6c4d1f6b6f9c | textbox | QTY
| checkpoint-no-value | DATE (9)
4677e410-6ed2-5d91-8811-06c598b5e1a0 | textbox
c0ccf001-aed9-50a2-96ba-abe1e848908d | textbox | LABOUR
e8660633-5619-59d7-9898-c3cce51987ee | textbox | HRS
c4cdde0a-e0fe-5ff4-bdc6-3c085ec448dc | textbox | MATERIALS
aa00fc54-558a-568b-988e-a599707b8461 | textbox | QTY
| checkpoint-no-value | DATE (10)
9eca556c-db25-55b2-9139-accaaf45de26 | textbox
bcb5c246-bc33-584b-8265-8bc35ef541e9 | textbox | LABOUR
13310c12-65ed-5c10-b6b8-6b88acc2cfc7 | textbox | HRS
34a6f7dc-d662-564f-83f2-4f288384a031 | textbox | MATERIALS
5e75926a-09d6-5a9a-99a9-ac2b4a1eae76 | textbox | QTY
| checkpoint-no-value | DATE (11)
42c6f1e3-5667-5571-accc-101e0aed3ec5 | textbox
7df04fa9-1506-5cb7-9d66-ac3d4161fe96 | textbox | LABOUR
01234db3-3a80-5ecb-81d9-a0ca3052641f | textbox | HRS
dfb121cb-a87f-5541-967d-a1d5e6f377de | textbox | MATERIALS
ffb08200-77ce-5f8a-a60e-f3c332be919d | textbox | QTY
| section | The above Variation is accepted by:
| checkpoint | Client Representative
| signoff | Add Signature
| checkpoint | Ergo Representative
| signoff | Add Signature
| checklist | ITP020 Main Switchboard & Termination of Cables |  | ITP020 Main Switchboard & Termination of Cables | dce30815-cbac-4ce8-a9cf-6cd673b4f6eb
| section | Preparation
| checkpoint | Locate & fix switchboard into position - check for clearances fix correctly
| checkpoint | Determine cable sizes for cable glands & mark out gland plate (check cable O.D's for cable size glands)
3afdd7a6-5ba2-5368-9bfa-933f8fe8d071 | button | Install cable glands & cables | Yes, No, N/A
830d2e03-c5a4-50ff-95c2-217ab6601b6e | button | Install lugs & terminate | Yes, No, N/A
| checkpoint | Clean & vacuum out board - please take a photo
| checkpoint | Check all circuits are terminated & safe at the other end or disconnect
| checkpoint | Final visual inspection of board - please take a photo
| section | Installation
| checkpoint | Test earth continuity & resistance
2dff3383-807a-590a-af7c-82cf599ca37d | button | Test insulation resistance | Yes, No, N/A
ad2e95cc-2edb-54e3-a655-104f12eacc37 | button | Test polarity | Yes, No, N/A
893d5c72-83e6-507d-9752-0bc8f34288dc | button | Test phase rotation | Yes, No, N/A
| checkpoint | Attach prescribed certificate of electrical safety. Organise inspection by inspector (Add photo or attached certification
| checkpoint | Isolate / lock off/ dange tag all outgoing circuits - please take a photo
c9001b54-ac07-56c9-912b-82dc3ec4130a | button | Ensure labelling is complete & accurate | Yes, No, N/A
| checkpoint | Energise system
e71875ed-e39a-5c17-a469-b36ae8232080 | button | Check phase rotation | Yes, No, N/A
4ebb1246-a118-593f-a0a6-adc3a5b99155 | button | Check switchboard as installed as per drawings | Yes, No, N/A
61129063-c385-552b-93ed-37aef4aa3b9e | textbox | Drawing & revision number(s)
| checkpoint | Ensure any modifications to shop drawings are matched to existing & returned to office / attach drawings
| checkpoint | Ensure switch room is left clean - please take a photo
| checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
| checklist | Lighting cabling and outlets |  | Lighting cabling and outlets | ebedf870-860a-46c5-957a-4413b81a5e62
| section | Rough In
| checkpoint | Confirm that the cable support system has been completed as per documentation
| checkpoint | Electrical cables have been appropriately sized and selected to ensure that they will support currently installed and future equipment
| checkpoint | Mechanical protection has been provided to minimise the likelihood of physical damage to cabling
| checkpoint | Cabling has been concealed where possible in ceiling spaces, wall cavities or risers
| checkpoint | All lights have been wired as per drawings
| checkpoint | All lights and switches have been marked on the site as built drawing
| checkpoint | Height and location have been confirmed for each switch
| checkpoint | Lighting control system has been confirmed (DALI/240v)
| checkpoint | Ceiling supports have been installed where required (ceiling fans/pendants)
| section | Fit Off & Commission
| checkpoint | Equipment/materials have been selected and installed as per drawings/specifications
| checkpoint | Terminations have been checked and all terminations are correct and secure in all outlets
| checkpoint | Switches have all been secured in place and levelled
| checkpoint | All lights are sitting flush and/or been levelled
| checkpoint | All cabling has been tested for insulations resistance and continuity
| checkpoint | Each circuit is terminated at the DB and protected by the correct protective device
| checkpoint | Each switch has been labelled
| checkpoint | Functional test carried out on each switch and light
| checkpoint | Each circuit has been marked on the site as built
| checklist | Electrical Installation Testing |  | Electrical Installation Testing | f0a31951-ba3b-4597-9955-ba9d358f38cd
| section | Test Point/ Circuit Number
| checkpoint | Main earth tested
9d6c9fee-7fa3-5a60-b4ee-7a147a672a1e | textbox | Conductor Sizes (mm²) Actives/Earths
b2104591-3d44-534b-a811-a8bf4e85fbb8 | textbox | MCB (Rating & Type)
| section | Continuity
| checkpoint | Continuity tested
52257cca-a18d-5dc8-b27d-df487aaa126b | textbox | Active Conductor (Rph)
dc41095d-088a-5c2b-80fb-bef183acef45 | textbox | Earth Conductor (Re)
| section | IR
| checkpoint | IR tested
ad330d9a-c85e-5de2-88c0-af879dfc4a8c | textbox | Insulation Resistance (MΩ)
| section | CCC
| checkpoint | Correct Circuit Connections
| section | Polarity
| checkpoint | Polarity tested
| section | Fault Loop Impedance
| checkpoint | Measured Loop Value R
| checkpoint | Maximum Permitted Loop Value
| section | RCD
| checkpoint | RCD tested
| checklist | ITP009 Power Installation and Fit Off |  | ITP009 Power Installation and Fit Off | f11d7213-a2d9-44df-ae82-e1a41b48d5a8
| checkpoint | 1 - Check drawings for quantity, brand, type and colour
| checkpoint | 2 - Each circuit is terminated at the db and protected by the correct protective device
| checkpoint | 3 - Location/compliance wet areas, hazards etc. Mounting heights,
| checkpoint | 4 - Fit off and fix switches, where multi gang switches with multi circuits are involved use shrouds on each switch. Each circuit must be fitted off completely.
| checkpoint | 5 - Fit off and fix gpo’s, where a gpo is located within 150mm of a metal stud, use shroud. Each circuit must be fitted off completely.
| checkpoint | 6 - Fit off final appliances
| checkpoint | 7 - Functional test carried out on each outlet
| checkpoint | 8 - Cover plates (if required)
| checkpoint | 9 - Install label (if a specified requirement)
| checkpoint | 10 - All outlets & appliances marked on the site as build’s
| checklist | ITP0012 Exit & Emergency Light Installation |  | ITP0012 Exit & Emergency Light Installation | f646c053-ee24-468b-9152-f34b64fbe1df
| checkpoint | 1 - Delivery check for damage and correct quantities
| checkpoint | 2 - Locations coordinate with other services
| checkpoint | 3 - Marking out (if required) - refer to reflected ceiling plan for locations
| checkpoint | 4 - Plug in or fit off light fit-off data cable if applicable
| checkpoint | 5 - Number and install light fitting and as built drawing
| checkpoint | 6 - Install lamp & diffuser and clean fitting
| checkpoint | 7 - Mark up lighting drawing, data loop included, numbering all exit and emergency lights (if applicable)
| checkpoint | 8 - Complete log book and record results if applicable
| checklist | Install Distribution Boards - Terminate Cables |  | Install Distribution Boards -Terminate Cables ITP006 | f90c8a2b-e4b9-48fa-b761-5f09b53a9622
| checkpoint | Setout & alignment as per drawing (include revision below)
62938eee-e776-5138-b9f4-6f659b9e4c7e | textbox | Drawing & revision number(s)
| checkpoint | Check delivery of distribution board - Check for damage (paint finish, dimensions & door against drawing) - Please take a photo
| checkpoint | Locate & fix into position
| checkpoint | Install sub mains cabling as appropriate (glands, tray & duct)
| checkpoint | Install lugs & terminate
| checkpoint | Install sub circuit & terminate (if circuit not complete at the other end, it must not be terminated)
| checkpoint | Clean & vacuum area - please take a photo
dda2648f-8494-54d4-905f-df3ab48ec56a | textbox | Record results
| checkpoint | Clearly identify services
| checkpoint | Energise system
| checkpoint | Check phase rotation
| checkpoint | Check switchboard as installed as per drawings
| checkpoint | Check typed schedule for accuracy & install
| checkpoint | Ensure switchboard cupboard & area is left clean - Please take a photo
| checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
| checklist | ITP006 Power Wiring Rough In |  | ITP006 Power Wiring Rough In | fdc68cc3-9563-45b3-aabf-cab7e6e85af2
| checkpoint | 1 - Refer to drawing to determine cable support route and check separation from data/comms services
| checkpoint | 2 - Determine cable size
| checkpoint | 3 - Cable sizes max length
| checkpoint | 4 - Determine cable support system ie. Catinary, cable tray, fix to structure, ducting
| checkpoint | 5 - Install cable support system
| checkpoint | 6 - Check cable size/type, black sheath for power, white sheath for light: 4mm to be used for runs over 90 metres (unless specified differently)
| checkpoint | 7 - Install and identify cables. Any cable not terminated immediately must have the ends taped covering the bare copper.
| checkpoint | 8 - Mechanical protection has been provided to minimise the likelihood of physical damage to cabling
| checkpoint | 9 - Fix cables to support system
| checkpoint | 10 - Cabling has been concealed where possible in ceiling spaces, wall cavities or risers
| checkpoint | 11 - Fit-off outlets, plug bases etc. (if necessary), each circuit to be fitted off completely & clean up area
| checkpoint | 12 - All outlets have been wired as per drawings
| checkpoint | 13 - All outlets have been marked on the site as built drawing
| checkpoint | 14 - Height and location have been confirmed for each outlet