## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-001 - Clearing & Grubbing | itp |  |  |  |  | ITP-001 - Clearing & Grubbing
section | 1 - Preliminary Works
checkpoint | 1.1 - Check current drawings are used on site for works
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS,
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Excavation Permit issued
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Excavation Permit #
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.4 - Flora & Fauna
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: A qualified Ecologist is or trained wildlife handler to be present during removal of native vegetation; has provided advice on alternative fauna habitat sites if applicable and be present on the site during any relocation works if required.
label | REFERENCE DOCUMENTS: Construction Environmental Management Plan Appendix 2
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.5 - Permit to distrurb flora & fauna
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: VicRoads has already obtained permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works.
label | REFERENCE DOCUMENTS: Condition Plans endorsement
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
section | 2 - Clear & Grub
checkpoint | 2.1 - Define work area
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site.
label | REFERENCE DOCUMENTS: 201.1
label | INSPECTION/TEST METHOD: Inspect
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Cultural Heritage and Areas of Significance
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
label | ○ Works are to be suspended immediately and Cultural Heritage representatives (BLCAC) are to be notified, if any items of significance are discovered or identified during construction.
label | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
label | REFERENCE DOCUMENTS: CHMP
label | INSPECTION/TEST METHOD: Inspect
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Joint Inspection to Mark vegetation or habitat to be removed
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the project Arborist and project Ecologist
label | REFERENCE DOCUMENTS: Drawings CEMP Tree Management Plan 176.I1
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Felling of Trees
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: Trees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared
label | REFERENCE DOCUMENTS: 201.04
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.5 - Backfill holes
label | FREQUENCY: After clearing
label | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material and compacted
label | REFERENCE DOCUMENTS: 201.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.6 - Dispose of Trees and vegetation
label | FREQUENCY: After clearing
label | ACCEPTANCE CRITERIA: Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works.
label | ○ Noxious weeds shall not be mulched.
label | REFERENCE DOCUMENTS: 201.07
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.7 - Dispose of concrete, bituminous and other recyclable materials.
label | FREQUENCY: After clearing
label | ACCEPTANCE CRITERIA: Salvaged concrete, bituminous materials over 50mm and other recyclable materials have been sent to approved recycling establishments.
label | REFERENCE DOCUMENTS: 201.07
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.8 - Stripping of topsoil
label | FREQUENCY: Prior and after commencement of any ground disturbing activities
label | ACCEPTANCE CRITERIA: Topsoil shall be stripped for the full width of the formation.Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil, and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
label | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.204.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.9 - Removal of abandoned services
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Pits which are no longer required shall be removed or broken back to a depth not less than 0.3 m below the finished surface of the subgrade. Remaining pipe openings shall be sealed with concrete. Any remnants of pits shall be backfilled with material and compacted to a density ratio of not less than 95%. The calculation of density ratio shall be based on Standard compactive effort.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.10 - Clearing of Trees and Vegetation
label | FREQUENCY: During clearin works
label | ACCEPTANCE CRITERIA: Clearing work shall not be undertake outside of the specified limits of work.
label | ○ Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.04
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.11 - Grubbing of vegetation
label | FREQUENCY: Prior and after commencement of any ground disturbing activities
label | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment. In areas to be covered by embankments, to a depth of not less than 0.3 m below the stripped surface or not less than 0.6 m below the finished surface of the subgrade, whichever is the lesser treatment.
label | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material
label | REFERENCE DOCUMENTS: CEMP VicRoads Spec. Cl.201.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
checklist | ITP-003 - Earthworks Foundation | itp |  |  |  |  | ITP-003 - Earthworks Foundation
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: All personnel on site have completed site specific induction
label | REFERENCE DOCUMENTS: Induction Register
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS,
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Excavation Permit issued
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Excavation Permit No.
label | IP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
checkpoint | 1.4 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.5 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: All environmental measures and site controls to be implemented as per current CEMP and CHMP. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: IFC Drawings CEMP, CHMP
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.6 - Verification of Site Clearing
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.05, ITP-001
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.7 - Placing Fill
label | FREQUENCY: Prior to Commencing Fill
label | ACCEPTANCE CRITERIA: Placing fill shall not commence on the prepared areas until the area has been reviewed by the Superintendent
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(b)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.8 - Rock Subgrade
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | ○ Details of any necessary amendments to the sub surface drainage design including trasverse subsurface drainage at the interfaces shall be submitted to the Superintendent for review.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.9 - Ground Water
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: The Superintendent shall be notified where groundwater or seepage is encountered and the proposed action to be taken, shall be submitted for review. Any necessary approvals from relevant authorities for treatment and disposal of this groundwater shall also be submitted .
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(h)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.10 - Unsuitable Material
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, actions shall be:
label | a) excavate the unsuitable material and backfill with 20mm Class 3 Crushed rock and compacted to min 98% Standard MDD to the approval of Superintendent
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Survey set-out
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. Survey activities undertaken to ensure and validate that all Works meet level and location requirements. Verification of conformity with latest IFC drawings.
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Survey records & pegs on the ground
label | SCP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.2 - Placement of Geotextiles
label | FREQUENCY: On cut surfaces
label | ACCEPTANCE CRITERIA: Geotextiles / fabrics placed as per manufacturers specification
label | REFERENCE DOCUMENTS: Drawings, Manufactuer specification
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: This ITP Signed off
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
checklist | ITP-011 - Bored Piling | itp |  |  |  |  | ITP-011 - Bored Piling
section | 1.0 - Design and Submissions
checkpoint | 1.1 - Check for correct documetation
label | FREQUENCY: Before commencement of activity
label | ACCEPTANCE CRITERIA: Check correct documentation is being utilized (latest drawing revision) and IFC/ Proof Engineering
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Current revision of drawing
label | RECORD OF CONFORMITY: Current revision of drawing
label | HP*
label | RESPONSIBILITY: Project Engineer, Site Engineer
date | Date Completed:
checkpoint | 1.2 - Approval of Mix Design
label | FREQUENCY: No less than 4 weeks prior to commencement of activity
label | ACCEPTANCE CRITERIA: Mix design reviewed and approved by superintendent.
label | REFERENCE DOCUMENTS: Cl 610.07(b
label | INSPECTION/TEST METHOD: Approval
label | RECORD OF CONFORMITY: VicRoads letter of approval
label | AP
label | RESPONSIBILITY: Superintendent
date | Date Completed:
checkpoint | 1.3 - Approval of Quality Procedure
label | FREQUENCY: No less than 4 weeks prior to commencement of activity
label | ACCEPTANCE CRITERIA: Proposed materials and pile construction procedures reviewed by the superintendent
label | REFERENCE DOCUMENTS: Cl 606.03(a)
label | INSPECTION/TEST METHOD: Approval
label | RECORD OF CONFORMITY: VicRoads letter of approval
label | HP
label | RESPONSIBILITY: Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Ensure Traffic, Safety, Quality and Environmental management measures are in place
label | FREQUENCY: Prior to commencement of activity. EMP at least 2 weeks prior
label | ACCEPTANCE CRITERIA: Safety plan, traffic management plan and environmental management plan
label | REFERENCE DOCUMENTS: PSP, TMP & EMP
label | INSPECTION/TEST METHOD: Ensure all measures in place as per plan
label | RECORD OF CONFORMITY: Inspection
label | HP
label | RESPONSIBILITY: Site Engineer, Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Certification of approved Hot Dip Galvanising
label | FREQUENCY: Prior to Epoxy coating
label | ACCEPTANCE CRITERIA: Galvanising treatment in accordance with appropriate Standard documents and Design specification 200 microns
label | REFERENCE DOCUMENTS: Drawings AS/NZ4680
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Manufacturers certificate
label | HP*
label | RESPONSIBILITY: Project Manager, Site Engineer
date | Date Completed:
checkpoint | 1.6 - Certification of approved Epoxy coating
label | FREQUENCY: Prior to arrival on site
label | ACCEPTANCE CRITERIA: Epoxy treatment in accordance with appropriate Standard documents and Design specification
label | ○ 2 x Base Coat GFX @ 250 microns
label | ○ 1 x Top Coat Polyurethane, 100 microns
label | REFERENCE DOCUMENTS: Drawings AS2312
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Manufacturers certificate
label | HP*
label | RESPONSIBILITY: Project Manager, Site Engineer
date | Date Completed:
section | 2.0 - Bored Piling
checkpoint | 2.1 - Survey and setout
label | FREQUENCY: Each Pile
label | ACCEPTANCE CRITERIA: Survey and confirm position and depth as per drawing
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Survey
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer, Geotechnical Engineer
date | Date Completed:
checkpoint | 2.2 - Excavation Levels
label | FREQUENCY: Each Pile
label | ACCEPTANCE CRITERIA: Check the excavation levels and base are acceptable and conform to the drawing prior to commencement of piling works.
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Drilling check sheet
label | HP
label | RESPONSIBILITY: Site Engineer, Geotechnical Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Inspection of Pile Excavation
label | FREQUENCY: Each Pile
label | ACCEPTANCE CRITERIA: First 3 piles to be inspected by Geotechnical Engineer to check dimensions and toe level are correct and within tolerance. Correct Toe level. Material encountered consistent with design.
label | REFERENCE DOCUMENTS: Drawings Cl 606.06
label | INSPECTION/TEST METHOD: Inspection / Test Method
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Site Engineer, Geotechnical Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Bore Logs
label | FREQUENCY: Each Pile
label | ACCEPTANCE CRITERIA: All bore logs and pile installation records to be sent to and reviewed by designer
label | REFERENCE DOCUMENTS: Bore logs
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Drilling check sheet
label | HP
label | RESPONSIBILITY: Site Engineer, Geotechnical Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Spacers installed on Reinforcement Cage
label | FREQUENCY: Each Pile
label | ACCEPTANCE CRITERIA: Spacers/supports to be placed along steel reinforcement at a maximum 2m intervals
label | REFERENCE DOCUMENTS: Cl 611.10
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Site Engineer, Superintendent
date | Date Completed:
checkpoint | 2.6 - Inspection of column and cage height and centre
label | FREQUENCY: Each Pile
label | ACCEPTANCE CRITERIA: Ensure heights, centre and spacing of reinforcement cage and column are in accordance with drawings and within tolerance
label | REFERENCE DOCUMENTS: Drawings Cl 606.08
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer, Superintendent
date | Date Completed:
section | 3.0 - Placing and Finishing Concrete
checkpoint | 3.1 - Quality Checks
label | FREQUENCY: Prior to each concrete pour
label | ACCEPTANCE CRITERIA: Relevant ITPs and Quality Control checklists completed and reviewed
label | REFERENCE DOCUMENTS: Cl 610.18
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Site Engineer, Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Carry out sampling of concrete
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16 Slump: As per VR450/50 mix 675mm (+/- 125mm), (550mm - 800mm)
label | REFERENCE DOCUMENTS: Cl 610.16 Table 610.161
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.3 - Record location of each batch
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Batch location recorded
label | REFERENCE DOCUMENTS: Cl 610.15
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Checklist
label | IP
label | RESPONSIBILITY: Tester
date | Date Completed:
checkpoint | 3.4 - 7 Day concrete test result
label | FREQUENCY: Each sample
label | ACCEPTANCE CRITERIA: Concrete cyclinder test smples: 7 day concrete strength achieved of 35MPa
label | REFERENCE DOCUMENTS: Cl 610.05
label | INSPECTION/TEST METHOD: Test Report
label | RECORD OF CONFORMITY: This ITP Signed off
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.5 - 28 Day concrete test result
label | FREQUENCY: Each sample
label | ACCEPTANCE CRITERIA: Concrete cyclinder test smples: 7 day concrete strength achieved of 50MPa
label | REFERENCE DOCUMENTS: Cl 610.05
label | INSPECTION/TEST METHOD: Test Report
label | RECORD OF CONFORMITY: This ITP Signed off
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.6 - Tolerance Check and As Built Survey
label | FREQUENCY: Each Pile
label | ACCEPTANCE CRITERIA: Check tolerances and survey pile positions. Mark all details correctly on as-builts. Pile head position and verticality
label | REFERENCE DOCUMENTS: Cl 605
label | INSPECTION/TEST METHOD: Survey
label | RECORD OF CONFORMITY: Survey report
label | WP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: